## Problem Actions
Business Platform | Product portfolio | Incident | Action Open Date | Title | Action | Action categorization | Action Owner | Action updates | DevOps / Product Team | Tactical/Strategic | ETA | Action closed date | Status | Risk ID | Backlog ID | Back log Status | Problem Manager | Current day | Ageing | Aging Bucket | Action Closed month | Action closed year | Over Due Range
Customer Channels | Customer Engagement | 90716711 | 2025-10-04 | Connectivity issues with Ignite Travel Bureau Stores | Define the financial impact of this issue, given that all PEDs were offline. We have visibility of the number of failed card transactions during the affected period and can use the Average Transaction Value (ATV) to estimate the potential revenue loss. Additionally, gather data on customer complaints to assess the broader impact. | Impact analysis | Valliammai, Chris , Daniel |  | Travel Money | Tactical | 16/04/25 |  | Open |  |  |  | Naveen | 2025-02-10 | 175 | >60 | January | 1900 | 90+ Days
Customer Channels | Customer Engagement | 90716711 | 2025-10-04 | Connectivity issues with Ignite Travel Bureau Stores | Create a comms template for travel bureaus similar to the one we have for have one for Worldline credit card issues. | Business & IT Communication | Valliammai, Chris , Daniel |  | Travel Money | Tactical | 17/04/25 |  | Open |  |  |  | Naveen | 2025-02-10 | 175 | >60 | January | 1900 | 90+ Days
Customer Channels | Customer Engagement | 90716711 | 2025-10-04 | Connectivity issues with Ignite Travel Bureau Stores | MIM communications were delayed due to uncertainty over which portfolio takes ownership of Travel Bureaus. Further discussion is needed with product owners and leadership to clarify ownership, as this currently sits with Customer Engagement. The agreed distribution list should also be provided for comms. | Supplier and support involvement | Priyabrata S , Valliammai |  | Travel Money | Tactical | 24/04/25 |  | Open |  |  |  | Naveen | 2025-02-10 | 175 | >60 | January | 1900 | 90+ Days
Customer Channels | Customer Engagement | 90716711 | 2025-10-04 | Connectivity issues with Ignite Travel Bureau Stores | Review and propose internal alerting via the network for issues relating to Travel Bureau connectivity to PED's | Problem identification & Alerting | Nick Baldwin |  | Network | Tactical | 24/04/25 |  | Open |  |  |  | Naveen | 2025-02-10 | 175 | >60 | January | 1900 | 90+ Days
Customer Channels | Customer Engagement | 90716711 | 2025-10-04 | Connectivity issues with Ignite Travel Bureau Stores | Ask Verifone whether they have alerting in place for this type of issue, and if so, whether their alerts were triggered. Could communication with Customer have been improved in that case? Additionally, what is their formal communication process, and who is included in their agreed distribution list? | Problem identification & Alerting | James Baxter |  | Travel Money | Tactical | 24/04/25 |  | Open |  |  |  | Naveen | 2025-02-10 | 175 | >60 | January | 1900 | 90+ Days
Customer Channels | Customer Engagement | 90716711 | 2025-10-04 | Connectivity issues with Ignite Travel Bureau Stores | Root cause and resolution details pending from Verifone, we will also ascertain what are their SLA's with regards to root cause | Root cause | James Baxter |  | Travel Money | Tactical | 24/04/25 |  | Open |  |  |  | Naveen | 2025-02-10 | 175 | >60 | January | 1900 | 90+ Days
C&H and Intl | C&H and Intl Supply Chain | 90693741 | 2025-01-04 | Ecom orders not dropping in at Donington, Ollerton, Thorncliffe DC's for delivery date 30/03 | Analyse Oracle DB timezone setting within JDA (WMS). | Solution & Recovery | Kunal Chickar, Jishin Jacob | WMS and Oracle DBA team to collaborate and analyze the feasibility to save the time stamp received from OMS and not to change it again to BST. | WMS and DBA team |  | 15/04/25 |  | Open |  |  |  | Pavithra | 2025-02-10 | 184 | >60 | January | 1900 | 90+ Days
Customer Channels | Service Experience | 90693741 | 2025-01-04 | Ecom orders not dropping in at Donington, Ollerton, Thorncliffe DC's for delivery date 30/03 | Review the SFI interface (Std fulfilment interface) between OMS and Mulesoft/WMS to pre-empt future issues | Problem avoidance | Andrei / Suresh | Based on the analysis, decisions can be made to remove the shipment date or to remove the time from the delivery date as only the date is relevant, however action requires deeper analysis. | OMS |  | 15/04/25 |  | Open |  |  |  | Pavithra | 2025-02-10 | 184 | >60 | January | 1900 | 90+ Days
C&H and Intl | C&H and Intl Supply Chain | 90693741 | 2025-01-04 | Ecom orders not dropping in at Donington, Ollerton, Thorncliffe DC's for delivery date 30/03 | Explore the feasibility to set-up an alert to notify the drop in order volume for a specific delivery date. | Problem identification & Alerting | Kunal Chickar/ WMS Team |  | WMs |  | 15/04/25 |  | Open |  |  |  | Pavithra | 2025-02-10 | 184 | >60 | January | 1900 | 90+ Days
C&H and Intl | C&H and Intl Supply Chain | 90693741 | 2025-01-04 | Ecom orders not dropping in at Donington, Ollerton, Thorncliffe DC's for delivery date 30/03 | Ensure we do not have the same issue during the next clock change | Problem avoidance | OMS/WMS team | There will be an action added as part of the clock change readiness for both OMS and WMS to validate all the cut-off time and Lead time before the clock change and necessary actions will be taken before the clock change. | OMS; WMS |  | NA | 2025-01-04 | Closed |  |  |  | Pavithra | 2025-02-10 | 184 | >60 | April | 2025 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90693741 | 2025-01-04 | Ecom orders not dropping in at Donington, Ollerton, Thorncliffe DC's for delivery date 30/03 | Ensure MIM is engaged on a timely manner as soon as DC's see a significant impact. | Issue handling/Management | Service Leads- CD | It has been agreed to loop in MIM as soon as we see a significant increase in impact. | Service Leads- CD |  | NA | 2025-01-04 | Closed |  |  |  | Pavithra | 2025-02-10 | 184 | >60 | April | 2025 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90693741 | 2025-01-04 | Ecom orders not dropping in at Donington, Ollerton, Thorncliffe DC's for delivery date 30/03 | Before moving the proposition, an assessment needs to be performed on the impact- by comparing the lost sales due to prop move vs avoiding CFR. | Solution & Recovery | Service Leads- CD |  | Service Leads- CD |  | NA | 2025-01-04 | Closed |  |  |  | Pavithra | 2025-02-10 | 184 | >60 | April | 2025 | #VALUE!
Customer Channels | Service Experience | 90693741 | 2025-01-04 | Ecom orders not dropping in at Donington, Ollerton, Thorncliffe DC's for delivery date 30/03 | OMS to update their runbook with the recovery steps taken during the incident for future reference. | Solution & Recovery | Vipin -OMS |  | OMS |  | 15/04/25 |  | Open |  |  |  | Pavithra | 2025-02-10 | 184 | >60 | January | 1900 | 90+ Days
C&H and Intl | C&H and Intl Supply Chain | 90693741 | 2025-01-04 | Ecom orders not dropping in at Donington, Ollerton, Thorncliffe DC's for delivery date 30/03 | Perform an end-to-end impact assessment and ensure we have right actions captured to mitigate the overall impact before resolving the incident | Impact analysis | MIM and WMS | During the incident, the first priority was to mitigate the impact for orders with the delivery date of 30/03. However, we failed to analyze and track the future orders that were impacted due to the same scenario. This is a lesson learnt, during any recurrence of such incidents in future, this actions will be addressed before setting the incident to resolved. | MIM and WMS |  | NA | 2025-01-04 | Closed |  |  |  | Pavithra | 2025-02-10 | 184 | >60 | April | 2025 | #VALUE!
GTS | Operations | 90698496 | 2025-09-04 | Microsoft central outage impacting multiple services hosted within Northern Europe | Define and document clear expectations for the information Microsoft should provide when joining a major incident call. Engage vendor management to ensure these expectations are communicated, agreed upon, and consistently met. | Supplier and support involvement | Rehan Siddiqui |  | MIM |  | 15/04/25 |  | Open |  |  |  | Gokul | 2025-02-10 | 176 | >60 | January | 1900 | 90+ Days
Customer Channels | Platform & Store Ops | 90698496 | 2025-09-04 | Microsoft central outage impacting multiple services hosted within Northern Europe | As there is currently no disaster recovery (DR) solution in place for the Scan & Shop mobile application, an accepted risk should be formally raised to document this gap. | Solution & Recovery | Ezhilarasi Baghavan | 15/04: Ezhil is OOO until 22nd, hence reached out to the product owner Lauren, if a risk has been raised and we need to check with Priyabrata (OOO - 15/04) | Store Product |  | 22/04/25 |  | Open |  |  |  | Gokul | 2025-02-10 | 176 | >60 | January | 1900 | 90+ Days
GTS | Operations | 90698496 | 2025-09-04 | Microsoft central outage impacting multiple services hosted within Northern Europe | Request and obtain the full Root Cause Analysis (RCA) statement from Microsoft. | Root cause | Rehan Siddiqui | 15/04: Awaiting root cause from Microsoft | MIM |  | 18/04/25 |  | Open |  |  |  | Gokul | 2025-02-10 | 176 | >60 | January | 1900 | 90+ Days
GTS | ETP- Cloud operations / Frameworks | 90698496 | 2025-09-04 | Microsoft central outage impacting multiple services hosted within Northern Europe | Review the current alerting configuration for VMs, which is set to trigger only after five minutes of consistent unresponsiveness, to ensure earlier detection of issues related to service impact. | Problem identification & Alerting | Emmanuel George | 15/04: Team is still reviewing on it | Cloud Operations |  | 18/04/25 |  | Open |  |  |  | Gokul | 2025-02-10 | 176 | >60 | January | 1900 | 90+ Days
Customer Channels | Selling Experience | 90698496 | 2025-09-04 | Microsoft central outage impacting multiple services hosted within Northern Europe | WCS database failover currently takes approximately four minutes. Review the feasibility of implementing an active-active solution to reduce or eliminate service disruption. | Problem avoidance | Charly Webster | 17/04/2025 This is being worked on by the WCS team and we will come back before the ETA. | Head of Engineering |  | 2025-05-06 |  | Open |  |  |  | Gokul | 2025-02-10 | 176 | >60 | January | 1900 | 90+ Days
Customer Channels | Selling Experience | 90698496 | 2025-09-04 | Microsoft central outage impacting multiple services hosted within Northern Europe | The WCS database disaster recovery (DR) test has not been conducted. A DR test plan should be developed and scheduled as a priority. | Problem avoidance | Charly Webster | 17/04/2025 This is being worked on by the WCS team and we will come back before the ETA. | Head of Engineering |  | 2025-05-06 |  | Open |  |  |  | Gokul | 2025-02-10 | 176 | >60 | January | 1900 | 90+ Days
Data | Digital & Data | 90702108 | 2025-08-04 | Power BI Reports inaccessible due to Central Microsoft issue | Detailed root cause and information regarding the delayed resolution are yet to be shared by Microsoft | Solution & Recovery | Supriyo Pal Barrett, Timothy Ramya Vadivel | Power BI is part of the O365 bundle (SaaS) and needs clarification from Microsoft vendor. | Microsoft Vendor |  | 18/04/25 |  | Open |  |  |  | Balaji | 2025-02-10 | 177 | >60 | January | 1900 | 90+ Days
Data | Digital & Data | 90702108 | 2025-08-04 | Power BI Reports inaccessible due to Central Microsoft issue | Microsoft Vendor needs to clarify if Power BI Uptime is dependent on Availability Zone's Uptime. | Problem identification & Alerting | Supriyo PalBarrett, Timothy | Power BI is part of the O365 bundle (SaaS) and needs clarification from Microsoft vendor. | Microsoft Vendor |  | 18/04/25 |  | Open |  |  |  | Balaji | 2025-02-10 | 177 | >60 | January | 1900 | 90+ Days
Data | Digital & Data | 90702108 | 2025-08-04 | Power BI Reports inaccessible due to Central Microsoft issue | It was confirmed that the issue was identified only after the colleagues reported and there is no proactive monitoring to check the reports availability in the Power BI tool we need to Implement of Proactive monitoring after discussion with Vendor. | Problem identification & Alerting | Supriyo Pal | It was confirmed at this given point of time we do not have a monitoring to check the connectivity between Power BI application and the Data Source. Need suggestions from the Microsoft Vendor. | Microsoft Vendor |  | 18/04/25 |  | Open |  |  |  | Balaji | 2025-02-10 | 177 | >60 | January | 1900 | 90+ Days
GTS | Digital Workplace Services | 90702108 | 2025-08-04 | Power BI Reports inaccessible due to Central Microsoft issue | As a proactive Impact assessment measure for future incidents, we are reaching out to all service leads to understand the potential impact on their operations if Power BI is unavailable. | Impact analysis | All Service Leads and Rehan | Rehan to send mail to all service leads to have the clarity on potential business impact | Service Leads |  | 18/04/25 |  | Open |  |  |  | Balaji | 2025-02-10 | 177 | >60 | January | 1900 | 90+ Days
GTS | Digital Workplace Services | 90702108 | 2025-08-04 | Power BI Reports inaccessible due to Central Microsoft issue | To understand the delay in supplier engagement we have reached out to Ramya Vadivel - Microsoft Customer success account manager | Supplier and support involvement | Siddiqui, Rehan | Rehan to send mail to Ramya to understand the gap. | MIM |  | 18/04/25 |  | Open |  |  |  | Balaji | 2025-02-10 | 177 | >60 | January | 1900 | 90+ Days
Data | Digital & Data | 90702108 | 2025-08-04 | Power BI Reports inaccessible due to Central Microsoft issue | Risk #1584970835 - review must be initiated to realign the risk level based on recent findings | Impact analysis | Barrett, Timothy | The Risk review discussion must be initiated with Andrew Neilson | Customer |  | 18/04/25 |  | Open |  |  |  | Balaji | 2025-02-10 | 177 | >60 | January | 1900 | 90+ Days
GTS | Digital Workplace Services | 90702108 | 2025-08-04 | Power BI Reports inaccessible due to Central Microsoft issue | Vendor management team to Clarify the agreed Turnaround time for sharing the Root Cause and engagement in Incident Call as per contract. | Supplier and support involvement | Arun Narayanan | We will discuss this with the vendor management team to identify any deviations from the contractual obligations. | Vendor Management |  | 18/04/25 |  | Open |  |  |  | Balaji | 2025-02-10 | 177 | >60 | January | 1900 | 90+ Days
GTS | Digital Workplace Services | 90702108 | 2025-08-04 | Power BI Reports inaccessible due to Central Microsoft issue | Vendor management team to review and discuss with Microsoft Vendor on the Process alignment to publish the Root Cause. | Supplier and support involvement | Arun Narayanan | Vendor Management will discuss and evaluate the feasibility of aligning the vendor to the Customer process if any deviations are identified. | Vendor Management |  | 18/04/25 |  | Open |  |  |  | Balaji | 2025-02-10 | 177 | >60 | January | 1900 | 90+ Days
Customer Channels | Customer Engagement | 90704278 | 2025-03-04 | Search Services performance impacting search results & PLPs | To create an alert for top categories that return zero search results, it is essential to collaborate with the Apps team. This collaboration will help identify the most frequently used categories and any specific categories of interest. Please update the Search service runbook to include the procedure to be followed when this alert is triggered, as well as the recovery steps. | Problem identification & Alerting | Toyin Butler | Results in search and there are certain categories that should never return 0. So that's something that we are going to implement | Engineering Manager (Search & Sort) |  | 17/04/25 |  | Open |  |  |  | Gokul | 2025-02-10 | 182 | >60 | January | 1900 | 90+ Days
Customer Channels | Customer Engagement | 90704278 | 2025-03-04 | Search Services performance impacting search results & PLPs | A feature is needed in Merch Hub to indicate the rule audit changes captured in the Search Service. This information should also be accessible in New Relic or a similar APM tool to help narrow down the changes effectively. | Problem identification & Alerting | Jack Reeves | Currently there is no functionality available to have a historical log of changes in the merchandising hub when changes are made. | Product Manager (Search & Sort) |  | 18/04/25 |  | Open |  |  |  | Gokul | 2025-02-10 | 182 | >60 | January | 1900 | 90+ Days
Customer Channels | Customer Engagement | 90704278 | 2025-03-04 | Search Services performance impacting search results & PLPs | To enhance customer experience, it is essential to establish alert conditions for instances where PLP items yield zero results from the Search Response API. This process should ensure traceability of search requests, allowing for seamless data flow from Mobile Apps to Elastic and the accurate transfer of relevant data back to the users. | Problem identification & Alerting | Matthew Magee | Matt will assess the feasibility of implementing customer experience alerts. Rob can help on the Front end experience on how to define result responses and contract | Android App |  | 17/04/25 |  | Open |  |  |  | Gokul | 2025-02-10 | 182 | >60 | January | 1900 | 90+ Days
Customer Channels | Customer Engagement | 90704278 | 2025-03-04 | Search Services performance impacting search results & PLPs | Consider implementing an enhanced debugging approach for search requests originating from various channels, particularly those that follow specific category patterns or involve a limited number of requests. This strategy will facilitate quicker issue identification for teams, streamlining the troubleshooting process. | Problem identification & Alerting | Robert Haley |  | Staff Manager (Search & Sort) |  | 17/04/25 |  | Open |  |  |  | Gokul | 2025-02-10 | 182 | >60 | January | 1900 | 90+ Days
Customer Channels | Customer Engagement | 90704278 | 2025-03-04 | Search Services performance impacting search results & PLPs | Amending the existing runbook on the contacts, procedures for clearing the web, SRP. This update aims to eliminate any confusion regarding which cache needs to be cleared to restore customer experience effective. | Solution & Recovery | Toyin Butler |  | Engineering Manager (Search & Sort) |  | 17/04/25 |  | Open |  |  |  | Gokul | 2025-02-10 | 182 | >60 | January | 1900 | 90+ Days
Customer Channels | Customer Engagement | 90704278 | 2025-03-04 | Search Services performance impacting search results & PLPs | Amending the existing runbook on the contacts, procedures for clearing the web, SRP. This update aims to eliminate any confusion regarding which cache needs to be cleared to restore customer experience effective. | Impact analysis | Priyabrata Sahu | Informational, no actions required. The team was on the incident bridge to investigate the cause of the initial service recovery, which was unusual, since the services restored themselves. Despite this, communication remained a high priority. | Service Lead |  | NA | 2025-03-04 | Closed |  |  |  | Gokul | 2025-02-10 | 182 | >60 | April | 2025 | #VALUE!
Customer Channels | Customer Engagement | 90704278 | 2025-03-04 | Search Services performance impacting search results & PLPs | Conduct a refresher training with Merch Hub users on global rules. Looking at today's incident it was clear that making changes to global rules can damage website availability, customer experience | Problem avoidance | Sneha Das |  | Senior Product Manager (Search & Sort) |  | 16/04/25 |  | Open |  |  |  | Gokul | 2025-02-10 | 182 | >60 | January | 1900 | 90+ Days
Customer Channels | Customer Engagement | 90704278 | 2025-03-04 | Search Services performance impacting search results & PLPs | Implement a feature that notifies users when they are making, modifying, or adding changes to global rules. This UI alert should include a warning message outlining the potential implications of the changes on the website | Problem avoidance | Holly Morris |  | Associate Product Manager (Search & Sort) |  | 16/04/25 |  | Open |  |  |  | Gokul | 2025-02-10 | 182 | >60 | January | 1900 | 90+ Days
Customer Channels | Customer Engagement | 90704278 | 2025-03-04 | Search Services performance impacting search results & PLPs | Global rule changes should implement a structured role-based (access control authorization) workflow to effectively manage any amendments. This approach will enhance the strategic understanding of any gaps that may exist. | Permanent Fix | Sneha Das | All global rule functions had been migrated from BR to Merch Hub as-it-is. What is the purpose of using global rule functions and impact to wider website? | Senior Product Manager (Search & Sort) |  | 18/04/25 |  | Open |  |  |  | Gokul | 2025-02-10 | 182 | >60 | January | 1900 | 90+ Days
Customer Channels | Customer Engagement | 90704278 | 2025-03-04 | Search Services performance impacting search results & PLPs | Conduct a discovery workshop focused on the upcoming Product Launch and the features of Campaign Launch within Merch Hub. We will explore how to optimize product data usage for enhanced control and effectiveness. | Permanent Fix | Holly Morris | Discussion with Business Stakeholders (Charlotte, Himanshu) on use cases of new product launch | Associate Product Manager (Search & Sort) |  | 18/04/25 |  | Open |  |  |  | Gokul | 2025-02-10 | 182 | >60 | January | 1900 | 90+ Days
Customer Channels | Customer Engagement | 90704278 | 2025-03-04 | Search Services performance impacting search results & PLPs | It is essential to evaluate all current features of MerchHub, many of which are derived from Bloomreach. These features pose significant risks to the business, affect customer experience, and influence trade, particularly in cases like the Global rule. Additionally, it is crucial to map out user actions within the Hub to understand any broader implications that may arise. | Permanent Fix | Sneha Das |  | Senior Product Manager (Search & Sort) |  | 23/04/25 |  | Open |  |  |  | Gokul | 2025-02-10 | 182 | >60 | January | 1900 | 90+ Days
Customer Channels | Customer Engagement | 90704278 | 2025-03-04 | Search Services performance impacting search results & PLPs | Address the fuzzy search behavior which was returning incorrect/unrelated search results during the incident | Problem avoidance | Robert Haley |  | Staff Manager (Search & Sort) |  | 16/04/25 |  | Open |  |  |  | Gokul | 2025-02-10 | 182 | >60 | January | 1900 | 90+ Days
Customer Channels | Selling Experience | 90685299 | 26/03/25 | Customers unable to place orders across UK & IE website. | Rigor In Operations - Team Refresh session to be done ( Not to be overconfident & complacent) | Problem avoidance | Sumitro Chakravarty | Follow-up has been send, we are awaiting feedback on the latest update. | .com |  | 2025-03-04 |  | Open |  |  |  | Balaji | 2025-02-10 | 190 | >60 | January | 1900 | 90+ Days
Customer Channels | Selling Experience | 90685299 | 26/03/25 | Customers unable to place orders across UK & IE website. | Multiple tasks not getting clubbed together by the same person performing the change - GTM Change, Deployment, DB Checks. | Problem avoidance | Sumitro Chakravarty | Follow-up has been send, we are awaiting feedback on the latest update. | .com |  | 2025-03-04 |  | Open |  |  |  | Balaji | 2025-02-10 | 190 | >60 | January | 1900 | 90+ Days
Customer Channels | Selling Experience | 90685299 | 26/03/25 | Customers unable to place orders across UK & IE website. | Carry out the GTM at around 10:30 PM UK time the previous night so that the person doing the release can check that traffic is 100% on the correct hall. To be added to the deployment plan Note: Ensure that a single hall can handle the traffic before carrying out the GTM | Problem avoidance | Karuppasamy, Ramachandran | Follow-up has been send, we are awaiting feedback on the latest update. | .com |  | 2025-01-04 |  | Open |  |  |  | Balaji | 2025-02-10 | 190 | >60 | January | 1900 | 90+ Days
Customer Channels | Selling Experience | 90685299 | 26/03/25 | Customers unable to place orders across UK & IE website. | DBA will check the traffic in the database to ensure that no hit is coming from the hall/origin where the deployment will happen. Add this step to the deployment plan | Problem avoidance | Gaikwad, VivekanandaKaruppasamy, Ramachandran | Follow-up has been send, we are awaiting feedback on the latest update. | .com |  | 2025-01-04 |  | Open |  |  |  | Balaji | 2025-02-10 | 190 | >60 | January | 1900 | 90+ Days
Customer Channels | Selling Experience | 90685299 | 26/03/25 | Customers unable to place orders across UK & IE website. | Review whether an alert can be triggered if the GTM has not worked as expected | Problem identification & Alerting | Karuppasamy, Ramachandran | Follow-up has been send, we are awaiting feedback on the latest update. | .com |  | 2025-01-04 |  | Open |  |  |  | Balaji | 2025-02-10 | 190 | >60 | January | 1900 | 90+ Days
Customer Channels | Selling Experience | 90685299 | 26/03/25 | Customers unable to place orders across UK & IE website. | Review whether it is possible to simplify the GTM (i.e. review number of properties, currently 7, can any of them be combined) | Problem avoidance | Pandi, Thirumal | Follow-up has been send, we are awaiting feedback on the latest update. | .com |  | 2025-01-04 |  | Open |  |  |  | Balaji | 2025-02-10 | 190 | >60 | January | 1900 | 90+ Days
Customer Channels | Selling Experience | 90685299 | 26/03/25 | Customers unable to place orders across UK & IE website. | Check absolute numbers for GTM (visual confirmation). Create New Relic widget to show %age of traffic on each hall | Problem identification & Alerting | Karuppasamy, Ramachandran | Follow-up has been send, we are awaiting feedback on the latest update. | .com |  | 2025-01-04 |  | Open |  |  |  | Balaji | 2025-02-10 | 190 | >60 | January | 1900 | 90+ Days
Customer Channels | Selling Experience | 90685299 | 26/03/25 | Customers unable to place orders across UK & IE website. | Review with David Raine whether or not the GTM process can be automated | Solution & Recovery | Sumitro Chakravarty Raine, David | Follow-up has been send, we are awaiting feedback on the latest update. | .com |  | 2025-01-04 |  | Open |  |  |  | Balaji | 2025-02-10 | 190 | >60 | January | 1900 | 90+ Days
Customer Channels | Selling Experience | 90678495 | 21/03/25 | Incorrect promo code badge appearing across PLP's, SRP's & PDP's for UK | Guidelines to create promotions fresh rather cloning pervious templates and SOP was updated with checklist and peer review guidelines. | Problem avoidance | Natarajan, Srinivasan | Promotions fresh has been completed | .com |  | NA | 28/03/25 | Closed |  |  |  |  | 2025-02-10 | 195 | >60 | March | 2025 | #VALUE!
Customer Channels | Selling Experience | 90678495 | 21/03/25 | Incorrect promo code badge appearing across PLP's, SRP's & PDP's for UK | Configured alert to detect improper combinations e.g. system coded combined with sparks segment. | Problem identification & Alerting | Dhanaseelan Mahalingam; Revathi Gopalakrishnan | Alert has been configured | .com |  | NA | 28/03/25 | Closed |  |  |  |  | 2025-02-10 | 195 | >60 | March | 2025 | #VALUE!
Business Process Services | Business Process Services | 90678495 | 21/03/25 | Incorrect promo code badge appearing across PLP's, SRP's & PDP's for UK | Business ops team to include checks for appropriate badges while performing site walk (Sanity checks) | Problem avoidance | Natarajan, Srinivasan | Checks has been included, awaiting calrity on what checks has been included. | .com |  | 28/03/25 |  | Open |  |  |  |  | 2025-02-10 | 195 | >60 | January | 1900 | 90+ Days
Customer Channels | Selling Experience | 90678495 | 21/03/25 | Incorrect promo code badge appearing across PLP's, SRP's & PDP's for UK | Exploring the feasibility of decoupling promotion displays form the main product assembly process | Problem avoidance | Chitluri, Kesava Manikanta | We are not doing any development work in PA as its legacy API and consumers will use Federation to get similar functionality in future. | .com |  | 31/03/25 |  | Open |  |  |  |  | 2025-02-10 | 195 | >60 | January | 1900 | 90+ Days
Customer Channels | Selling Experience | 9065926 | 13/03/25 | Customers unable to update profiles and navigate basket pages in mobile apps (iOS & Android) | Until E2E test script is fixed, all production changes will be manually reviewed and released with caution. This action should have a date as well | Problem avoidance | Oladoja, Tawfiq | 13/03: Dave to create a meeting with Order fulfilment team to review their Deployment processes. | Basket Pages |  | 18/04/25 |  | Open |  |  |  | Kavitha | 2025-02-10 | 203 | >60 | January | 1900 | 90+ Days
Customer Channels | Selling Experience | 9065926 | 13/03/25 | Customers unable to update profiles and navigate basket pages in mobile apps (iOS & Android) | An evaluation of the change management process for standard pipelines, focusing on integration with Remedy, is essential for optimizing workflow and ensuring seamless operations. | Impact analysis | Webster, Charly/ Priyabrata Sahu | 13/03: This is for service management to work with platform, on brightcloud integrating with Remedy for automated change requests 16/04/2025 We have a PR open for both Remedy workflow for zero approval and deployment markets. The platform team are stopping us from merging both currently and will come back with estimates next week on when we can merge in the deployment-markers repository once they have integrated the zero trust workflow for Remedy. | Basket Pages |  | 30/04/25 |  | Open |  |  |  | Kavitha | 2025-02-10 | 203 | >60 | January | 1900 | 90+ Days
Customer Channels | Selling Experience | 9065926 | 13/03/25 | Customers unable to update profiles and navigate basket pages in mobile apps (iOS & Android) | Assess the alerts to determine if the price domain requires earlier notifications. | Problem avoidance | Oladoja, Tawfiq | 13/03: Yet to start | Price Domain |  | 18/04/25 |  | Open |  |  |  | Kavitha | 2025-02-10 | 203 | >60 | January | 1900 | 90+ Days
Customer Channels | Selling Experience | 9065926 | 13/03/25 | Customers unable to update profiles and navigate basket pages in mobile apps (iOS & Android) | Incorporate the allowed_uri in Terraform with the updated endpoint_uri, and verify that the Smoke Test passes successfully. | Problem avoidance | Problem avoidance | 13/03: The change to Incorporate the allowed_uri in Terraform with the updated endpoint_uri has been implemented | Basket Pages |  | NA | 2025-03-13 | Closed |  |  |  | Kavitha | 2025-02-10 | 203 | >60 | March | 2025 | #VALUE!
Customer Channels | Selling Experience | 9065926 | 13/03/25 | Customers unable to update profiles and navigate basket pages in mobile apps (iOS & Android) | Enhance the Smoke Test to identify issues when modifying the endpoint URI. | Problem avoidance | Oladoja, Tawfiq | 13/03: There are43 parts to the action out of which 2 are done and 2 are inprogress Part 1 - add create quote request which does not use a cached quote. (DONE) Part 2 - make price talk to price-enquiry via the custom DNS. (DONE) Part 3 - add post deployment smoke tests for dev and prod (IN PROGRESS) Part 4 - ensure we are using slotted deployment for dev, (NOT STARTED) | Basket Pages |  | 15/05/25 |  | Open |  |  |  | Kavitha | 2025-02-10 | 203 | >60 | January | 1900 | 90+ Days
GTS | Enterprise Integration | 90641785 | 18/03/25 | Delay in sales data availability on the Retail Dashboard | Review and refine the testing scenario, ensure we cover all the aspects during testing. | Problem identification & Alerting | Vijendra Rao, Swathika | 18/03; Due to inadequate testing, we were not able to identify the subscription changes in the lower environment due to the time of testing. It has been agreed to include more testing scenarios and to have extended hypercare to capture all the observations with the message flow across all the interfaces. | Cloud integration frame work |  | NA | 2025-03-18 | Closed |  |  |  | Kavitha | 2025-02-10 | 198 | >60 | March | 2025 | #VALUE!
GTS | Enterprise Integration | 90641785 | 18/03/25 | Delay in sales data availability on the Retail Dashboard | Amend the alert configurations within MQ to trigger the alerts to the appropriate product teams for efficient issue identification and recovery | Problem identification & Alerting | Subramanian, Rajasekar | 18/03: Alerting set-up has been reviewed, for any future reoccurrence of the issue, alerts are expected to be triggered to the right audience. | Messaging Team |  | NA | 2025-03-18 | Closed |  |  |  | Kavitha | 2025-02-10 | 198 | >60 | March | 2025 | #VALUE!
GTS | Enterprise Integration | 90641785 | 18/03/25 | Delay in sales data availability on the Retail Dashboard | Ensure code comparison is performed before any deployment. | Problem avoidance | Vijendra Rao, Swathika | 18/03: Going forward for any version upgrades/changes via Github, a code comparison will be performed between the Production version and the intended version to ensure the right code deployment. This step will be added as part of the implementation plan. SOP are updated to include the code comparison step on the implementation plan for any version upgrade/code changes. | Cloud integration frame work |  | NA | 2025-03-18 | Closed |  |  |  | Kavitha | 2025-02-10 | 198 | >60 | March | 2025 | #VALUE!
GTS | Enterprise Integration | 90641785 | 18/03/25 | Delay in sales data availability on the Retail Dashboard | Enable access restrictions to Master branch, so that any changes to the Master branch is being performed only by the right team. | Problem avoidance | Subramanian, Rajasekar | 18/03:All the admin dev access has been revoked, keeping the permissions limited to the senior SME's for any code changes to be performed on the MQ gateway and repository through proper approval process. | Cloud integration frame work |  | NA | 2025-03-18 | Closed |  |  |  | Kavitha | 2025-02-10 | 198 | >60 | March | 2025 | #VALUE!
Enterprise Integration | Enterprise Integration | 90641785 | 18/03/25 | Delay in sales data availability on the Retail Dashboard | Review all the changes made to the Master branch within the Github and ensure all changes go through proper approval process. | Problem avoidance | Pandurangan, Saranya | 18/03: Action item Completed. Going forward any changes to the Master branch will be committed only after the proper approval from the cloud frameworks team. | Messaging Team |  | NA | 2025-03-18 | Closed |  |  |  | Kavitha | 2025-02-10 | 198 | >60 | March | 2025 | #VALUE!
Foods | Foods Supply Chain | 90617876 | 28/02/25 | Delay in Foods NDC allocations impacting picking operations at the sites | Apply restriction Relex UI to stop erroneous updates on the ''corrective forecast for total figures field' | Problem identification & Alerting | Gagandeep Singh | 15/04: We have received a confirmation that the threshold to invoke contingency plan has been agreed with Relex. The threshold metrics are mentioned in the below update. 28/02: The threshold has been being agreed and is under business review and once it formalised it will be monitored, and the alerts will be configured Below are the threshold levels that as been agreed upon, Variance in both Day-1 and Day-7 order volumes exceeds 25 Variance in either Day-1 or Day-7 exceeds 50%. | Relex/ Ganadeep |  | NA | 2025-04-15 | Closed |  |  |  | Kavitha | 2025-02-10 | 216 | >60 | April | 2025 | #VALUE!
Foods | Foods Supply Chain | 90617876 | 28/02/25 | Delay in Foods NDC allocations impacting picking operations at the sites | Configure automated alerts to notify an over allocation volume with Relex for proactive issue identification | Problem avoidance | Gagandeep Singh | 28/02: will be prioritize once the cutover tech is complete FOATR-27355 has been raised to track | Relex/ Ganadeep |  | NA | 2025-02-28 | Closed |  |  |  | Kavitha | 2025-02-10 | 216 | >60 | February | 2025 | #VALUE!
Customer Channels | Selling Experience | 90669693 | 24/03/25 | Goodwill voucher of $100 auto applied for international orders from US site | Promotion Go Live Testing Process Review | Problem avoidance | Srinivasan Natarajan, Vineetha.Sreejith | 09/04 - Follow-up has been made, yet to receive an update 24/03 - Review and ensure we have a comprehensive testing strategy Develop test cases for wider use cases | .com |  | 30/04/25 |  | Open |  |  |  | Pavithra | 2025-02-10 | 192 | >60 | January | 1900 | 90+ Days
Customer Channels | Selling Experience | 90669693 | 24/03/25 | Goodwill voucher of $100 auto applied for international orders from US site | Identifying threshold for international orders and setup order tracking alerts for early warning. | Problem identification & Alerting | Chokkanathan Ramanathan, Ranjan Prusty | 09/04 - Threashold has been Identified - the daily International order count threshold as 2500 and teams have Implemented order tracking alerts in Dynatrace system. Scheduled this order monitor to run every 10 minutes once and trigger the alert to support team if the order threshold has breached. 24/03 -Spikes Can we do it per product level? | .com |  | NA | 2025-04-09 | Closed |  |  |  | Pavithra | 2025-02-10 | 192 | >60 | April | 2025 | #VALUE!
Customer Channels | Selling Experience | 90669693 | 24/03/25 | Goodwill voucher of $100 auto applied for international orders from US site | Daily report for Promotions live on the site? | Problem identification & Alerting | Vineetha.Sreejith | 09/04 - Follow-up has been made, yet to receive an update 24/03 -Make sure that is action is realistic and easy to do implementation. Maybe focus on Goodwill to start with? | .com |  | 2025-01-04 |  | Open |  |  |  | Pavithra | 2025-02-10 | 192 | >60 | January | 1900 | 90+ Days
Customer Channels | Selling Experience | 90669693 | 24/03/25 | Goodwill voucher of $100 auto applied for international orders from US site | Document standard recovery procedure across all systems. | Solution & Recovery | Chokkanathan Ramanathan | 09/04 - It is still pending to include OMS and WMS recovery procedures in the document, we will consolidate and update asap. 24/03 -Steps to consolidate and reconciliation data across application (Global-e, OMS & WMS) | .com |  | 14/04/25 |  | Open |  |  |  | Pavithra | 2025-02-10 | 192 | >60 | January | 1900 | 90+ Days
Group Platforms | Finance | 90661983 | 23/03/25 | Multiple wine products scanning at incorrect prices across Scotland, Wales and Ireland stores | Explore the feasibility of configuring a technical or quality-of-life change within SAP that either couples or auto-converts unit of measure updates or provides a notification when a corresponding change is not made accurately. | Problem avoidance | Chadalawada, Balakrishna | During the PIR, the SAP architect confirmed that deploying systemic restrictions within the SAP standard code is not feasible. As a result, validation will remain a manual process. To mitigate risks, we have agreed on the actions outlined above to ensure changes are made accurately and that any errors can be identified and corrected before impacting stores. | SAP Architect |  | NA | 2025-03-23 | Closed |  |  |  | Saloni | 2025-02-10 | 193 | >60 | March | 2025 | #VALUE!
Customer Channels | Service Experience | 90661983 | 23/03/25 | Multiple wine products scanning at incorrect prices across Scotland, Wales and Ireland stores | Align on the impact framework to streamline incident categorization, considering that the illegal trading scenario was mitigated by advising stores to stop selling the affected wine products | Impact analysis | Valliammai Ramasamy | Valli will discuss with Rich to determine the appropriate categorization of incidents involving illegal trading scenarios. | Service Lead |  | 31/03/25 |  | Open |  |  |  | Saloni | 2025-02-10 | 193 | >60 | January | 1900 | 90+ Days
Customer Channels | Service Experience | 90661983 | 23/03/25 | Multiple wine products scanning at incorrect prices across Scotland, Wales and Ireland stores | Explore options for allowing store colleagues to edit the Lowest Available Allowable (LALO) price on the tills during an illegal trading scenario to prevent trading impact. | Problem avoidance | Balaguru Subramaian | Teams will assess the feasibility of creating a central configuration that enables stores to temporarily adjust prices in such scenarios. Once the issue is resolved, this configuration will be disabled to prevent any unauthorised price overrides in POS. | POS |  | 31/03/25 |  | Open |  |  |  | Saloni | 2025-02-10 | 193 | >60 | January | 1900 | 90+ Days
GTS | Enterprise Integration | 90661983 | 23/03/25 | Multiple wine products scanning at incorrect prices across Scotland, Wales and Ireland stores | Explore option to validate the changes in SAP within Enterprise Services for additional checks before the overnight batch kicks in. | Solution & Recovery | Rajasekar Subramaniam | Feasibility being explored | Enterprise Services |  | 31/03/25 |  | Open |  |  |  | Saloni | 2025-02-10 | 193 | >60 | January | 1900 | 90+ Days
Business Process Services | Business Process Services | 90661983 | 23/03/25 | Multiple wine products scanning at incorrect prices across Scotland, Wales and Ireland stores | Introduce a peer review process for master data changes to ensure their accuracy before being sent to downstream systems, particularly POS. | Solution & Recovery | Lily Aravind | Once changes are made in SAP master data, a report will be extracted on the same day before the SAP cutoff at 16:30 to validate the modifications. Any anomalies identified will be corrected in collaboration with the SAP team before the cut off. If discrepancies are detected after the data has been sent to downstream systems, reactive recovery will be initiated through the major incident management process, involving POS, FMD, and other downstream systems to implement manual corrections. POS has an existing capability to adjust prices before stores opens. | BPS |  | NA | 2025-03-23 | Closed |  |  |  | Saloni | 2025-02-10 | 193 | >60 | March | 2025 | #VALUE!
Business Process Services | Business Process Services | 90661983 | 23/03/25 | Multiple wine products scanning at incorrect prices across Scotland, Wales and Ireland stores | Additional associate training / best practice sessions will be conducted by the Subject Matter Expert to ensure all associates are familiar with executing this update | Solution & Recovery | Jaturson Yogendran | In Progress | BPS |  | 31/03/25 |  | Open |  |  |  | Saloni | 2025-02-10 | 193 | >60 | January | 1900 | 90+ Days
Business Process Services | Business Process Services | 90661983 | 23/03/25 | Multiple wine products scanning at incorrect prices across Scotland, Wales and Ireland stores | Standard Operating Procedure (SOP) document will be created by 31st March for this new request, including highlighting all necessary checks and corresponding updates [content unit update (unit a -> unit b) and net content value (value a -> value b)]. | Problem avoidance | Jaturson Yogendran | The SOP creation is in progress. | BPS |  | 31/03/25 |  | Open |  |  |  | Saloni | 2025-02-10 | 193 | >60 | January | 1900 | 90+ Days
Data | Digital & Data | 90652016 | 20/03/25 | Data Replication delay between EDW Prod and DR databases | Establish a clear understanding of the business impact when there is a replication lag between EDW-PROD and DR. | Impact analysis | Timothy Barrett | A repository will be created to document the list of impacted reports during an EDW-DR-PROD vs. DR replication issue scenario. | Data Ops |  | 28/03/25 |  | Open |  |  |  | Saloni | 2025-02-10 | 196 | >60 | January | 1900 | 90+ Days
GTS | ETP-On premise services | 90652016 | 20/03/25 | Data Replication delay between EDW Prod and DR databases | Plan the reintegration of the passive server into the cluster by reinstalling the firmware and executing the commands suggested by IBM to validate if the issue persists. | Solution & Recovery | Rajendra Jadhav | The change is currently being planned via the change management process, with the implementation plan already being validated. Approvals are being secured from the finance business and relevant portfolio teams. | Linux |  | 28/03/25 |  | Open |  |  |  | Saloni | 2025-02-10 | 196 | >60 | January | 1900 | 90+ Days
GTS | ETP-On premise services | 90652016 | 20/03/25 | Data Replication delay between EDW Prod and DR databases | Include additional post checks/ hypercare after an upgrade to identify potential errors - explore observability to eliminate manual monitoring | Problem identification & Alerting | Sathish Selvapillai | Product teams to incorporate additional checkpoints to validate the progress of replication and engage MIM in case of any issues. | Linux |  | 28/03/25 |  | Open |  |  |  | Saloni | 2025-02-10 | 196 | >60 | January | 1900 | 90+ Days
GTS | ETP-On premise services | 90652016 | 20/03/25 | Data Replication delay between EDW Prod and DR databases | Determine the root cause of the issue with the EDW DR passive server - hlxp0ed027 | Root cause | Sathish Selvapillai | The below actions are being performed to identify the root cause: Review of the configurations between active servers and passive server. Selvapillai, Sathish to update the output. Two cases have been raised with HP and IBM. While we work on adjusting the HP contract for additional support, IBM has recommended reinstalling the firmware, executing specific commands, and reintroducing the server into the cluster to verify if the issue persists. There is a plan to execute this activity through a planned change after agreeing with the Finance business as it incurs an outage to the database | Linux |  | 28/03/25 |  | Open |  |  |  | Saloni | 2025-02-10 | 196 | >60 | January | 1900 | 90+ Days
Data | Digital & Data | 90653767 | 18/03/25 | Colleagues unable to access scheduled/canned reports on SAP Business Objects Universe | Data platform team to review the process for housekeeping the storage accounts | Problem avoidance | Bijal Patel | 02/04 - The team was advised to raise a change with clear instructions after identifying the stale IP's working with Cloud Ops team, hence closing this action. 18/03 - Data platform & Cloud Ops to work together and identify the stale IPs/private endpoints and then proceed with change process for the deletion of those entries | Data Platform |  | NA | 2025-02-04 | Closed |  |  |  | Gokul | 2025-02-10 | 198 | >60 | April | 2025 | #VALUE!
GTS | ETP- Connectivity,service & solution | 90653767 | 18/03/25 | Colleagues unable to access scheduled/canned reports on SAP Business Objects Universe | Refrain from doing changes in system configuration (addition, modification, or removal) with work orders | Problem avoidance | Balaji Srinivasan | 15/04 - Network cloud ops team advised that if the addition requests for DNS goes via change it would be delayed for the approval and it has to be conveyed to a wider business community. 09/04 - Scheduled a call with Network cloud ops and change management team on 15/04 01/04 - Network cloud ops team is working with Change team on the addressing all the system configuration. 18/03 - System configuration changes are to be made with change requests only by both Network cloud ops. Team to work with change management and agree on the process | Network |  | 18/04/25 |  | Open |  |  |  | Gokul | 2025-02-10 | 198 | >60 | January | 1900 | 90+ Days
Foods | Foods Supply Chain | 90664966 | 20/03/25 | Food RDC's unable to receive stock for 17 suppliers | Thirumoorthi, Sathish to collaborate with FITS support team and provide a full timeline of the incident | Issue handling/Management | Sathish Thirumoorthi | Provided. | FITS |  |  | 25/03/25 | Closed |  |  |  | Rehan | 2025-02-10 | 196 | >60 | March | 2025 | 90+ Days
Foods | Foods Supply Chain | 90664966 | 20/03/25 | Food RDC's unable to receive stock for 17 suppliers | Speak to Maddox, Daniel so that he can contact a supplier with the relationship with True Commerce and ask for: A better explanation of the cause including description of their change, find out about how effectively the change was tested and if the change was/can be communicated to key stakeholders going forward. | Root cause | Lisy Eucharista | 26/03: Root cause: An update was made to the TrueCommerce communications portal to OpenText. The intent of this change was to further refine file routing processes. As a result, once the change was applied, it inadvertently led to file duplication. This led to the same instance of a messages being transmitted to OpenText. True Commerce Change Process - Supplier will be notified on the changes if there is an outage associated. There were no comms for this particular change to suppliers as no outage involved in True Commerce RCA - Its in progress and will receive a copy from suppliers once its shared in (ETA - 28th Mar) | Service Lead |  | 25/03/25 | 26/03/25 | Closed |  |  |  | Rehan | 2025-02-10 | 196 | >60 | March | 2025 | 90+ Days
Foods | Foods Supply Chain | 90664966 | 20/03/25 | Food RDC's unable to receive stock for 17 suppliers | If Dan Maddox cannot get a further or better reply then we can raise a risk to highlight risks with the lack of process with EDI suppliers making changes which Customer/GIST are unaware of. | Problem avoidance | Lisy Eucharista, Sathish Thirumoorthi | 26/03: True Commerce Change Process - Supplier will be notified on the changes if there is an outage associated. There were no comms for this particular change to suppliers as no outage involved in True Commerce RCA - Its in progress and will receive a copy from suppliers once its shared in (ETA - 28th Mar) | Service Lead |  | 25/03/25 | 26/03/25 | Closed |  |  |  | Rehan | 2025-02-10 | 196 | >60 | March | 2025 | 90+ Days
Customer Channels | Selling Experience | 90664432 | 20/03/25 | Customers on Ireland site redirecting to UK site | Synthetic alert for IE homepage | Problem identification & Alerting | Sulthan Manthiri | 25/03: Sultan created a script for IE home page and it is completed | Senior Engineering |  | 25/03/25 | 25/03/25 | Closed |  |  |  | Naveen | 2025-02-10 | 196 | >60 | March | 2025 | 90+ Days
Customer Channels | Selling Experience | 90664432 | 20/03/25 | Customers on Ireland site redirecting to UK site | Improve Deployment time for Onyx pipeline | Solution & Recovery | Luke Sparkes/Stuart Brown | 4/4 : Discussed with Hisham and sent an email to Luke and Stuart for further discussions 26/03 - Discussions with Stuart who confirmed that it needs to be discussed with Selling Experience | Head of SW Engineering |  | 2025-11-04 |  | Open |  |  |  | Naveen | 2025-02-10 | 196 | >60 | January | 1900 | 90+ Days
Customer Channels | Selling Experience | 90664432 | 20/03/25 | Customers on Ireland site redirecting to UK site | P1 break glass route to production so changes specific to restoration of service take priority | Solution & Recovery | Luke Sparkes/Stuart Brown | 4/4 : Discussed with Hisham and sent an email to Luke and Stuart for further discussions 26/03 - Discussed with Stuart who updated that people need to click a "skip" button and he will raise a ticket for documentation | Head of SW Engineering |  | 2025-11-04 |  | Open |  |  |  | Naveen | 2025-02-10 | 196 | >60 | January | 1900 | 90+ Days
Customer Channels | Selling Experience | 90664432 | 20/03/25 | Customers on Ireland site redirecting to UK site | IE Should be considered in all testing requirements . Review existing tests | Problem avoidance | Luke Sparkes/Tim Morgan | 4/4 : To send an email to Luke and Tim based on discussion with Hisham | Head of SW Engineering |  | 2025-11-04 |  | Open |  |  |  | Naveen | 2025-02-10 | 196 | >60 | January | 1900 | 90+ Days
Customer Channels | Selling Experience | 90664432 | 20/03/25 | Customers on Ireland site redirecting to UK site | All the product teams to review and familiarize themselves with the severity and risk matrix | Problem avoidance | All product teams | 4/4: Action for awareness to product teams . Discussed with Hisham to close this | Selling Experience |  | 2025-11-04 | 2025-04-04 | closed |  |  |  | Naveen | 2025-02-10 | 196 | >60 | April | 2025 | 90+ Days
Customer Channels | Selling Experience | 90664432 | 20/03/25 | Customers on Ireland site redirecting to UK site | Review force cache control headers | Solution & Recovery | David Raine | 25/03- David is OOO and back in April | Akamai |  | 2025-11-04 |  | Open |  |  |  | Naveen | 2025-02-10 | 196 | >60 | January | 1900 | 90+ Days
Customer Channels | Selling Experience | 90664432 | 20/03/25 | Customers on Ireland site redirecting to UK site | Review standard operating procedure for holding pages | Issue handling/Management | Jack Tye/Hisham | 4/4: discussed with Hisham who confirmed to discuss with Jack on the SOP review 25/03 - Discussed with Jack who confirmed to wait for Hisham who is OOO. Discussion to happen in 1st week of April | Business ops |  | 2025-11-04 |  | Open |  |  |  | Naveen | 2025-02-10 | 196 | >60 | January | 1900 | 90+ Days
Customer Channels | Selling Experience | 90664432 | 20/03/25 | Customers on Ireland site redirecting to UK site | Create/improve impact metrix to see if we can identify the precise impact | Problem identification & Alerting | Dervla Richardson/David Raine | x | Akamai |  | 30/04/25 |  | Open |  |  |  | Naveen | 2025-02-10 | 196 | >60 | January | 1900 | 90+ Days
Customer Channels | Selling Experience | 90659216 | 13/03/25 | Customers unable to access Basket Page | Enhance the Smoke Test to identify issues when modifying the endpoint URI. | Problem Avoidance | Oladoja, Tawfiq | 25-03-2025 - Part 1 - add create quote request which does not use a cached quote. (DONE) Part 2 - make price talk to price-enquiry via the custom DNS. (DONE) Part 3 - add post deployment smoke tests for dev and prod (IN PROGRESS) Part 4 - ensure we are using slotted deployment for dev, (NOT STARTED) 24-03-2025 - The action is In progress, Follow-up sent to Priyabrata, Awaiting confirmation on closure | Onyx basket team |  | 15/05/25 |  | Open |  |  |  | Balaji | 2025-02-10 | 203 | >60 | January | 1900 | 90+ Days
Customer Channels | Selling Experience | 90659216 | 13/03/25 | Customers unable to access Basket Page | Incorporate the allowed_uri in Terraform with the updated endpoint_uri, and verify that the Smoke Test passes successfully. | Problem Avoidance | Oladoja, Tawfiq | 25-03-2025 - PR is finished, waiting for the deployment to complete. 24-03-2025 - The action is In progress, Follow-up sent to Priyabrata, Awaiting confirmation on closure.Refined and pending post smoke test completion 17-04-2025 PR is finished, waiting for the deployment to complete. DONE | Onyx basket team |  | 18/04/25 |  | Open |  |  |  | Balaji | 2025-02-10 | 203 | >60 | January | 1900 | 90+ Days
Customer Channels | Selling Experience | 90659216 | 13/03/25 | Customers unable to access Basket Page | Assess the alerts to determine if the price domain requires earlier notifications. | Problem Avoidance | Oladoja, Tawfiq | 25-03-2025 - Spike for the alert has been created and Awaiting the team member to be alerted. 24-03-2025 - The action is In progress, Follow-up sent to Priyabrata, Awaiting confirmation on closure.Refined and pending post smoke test completion | Onyx basket team |  | 15/05/25 |  | Open |  |  |  | Balaji | 2025-02-10 | 203 | >60 | January | 1900 | 90+ Days
Customer Channels | Selling Experience | 90659216 | 13/03/25 | Customers unable to access Basket Page | An evaluation of the change management process for standard pipelines, focusing on integration with Remedy, is essential for optimizing workflow and ensuring seamless operations. | Impact analysis | Webster, Charly/ Priyabrata Sahu | 24-03-2025 - The action is In progress, Follow-up sent to Priyabrata, Awaiting confirmation on closure 16/04/2025 We have a PR open for both Remedy workflow for zero approval and deployment markets. The platform team are stopping us from merging both currently and will come back with estimates next week on when we can merge in the deployment-markers repository once they have integrated the zero trust workflow for Remedy. | Onyx basket team |  | 30/04/25 |  | Open |  |  |  | Balaji | 2025-02-10 | 203 | >60 | January | 1900 | 90+ Days
Customer Channels | Selling Experience | 90659216 | 13/03/25 | Customers unable to access Basket Page | Until E2E test script is fixed, all production changes will be manually reviewed and released with caution. This action should have a date as well | Problem Avoidance | Oladoja, Tawfiq | 24-03-2025 - The action is In progress, Follow-up sent to Priyabrata, Awaiting confirmation on closure 17-04-2025 Partially DONE and in review now, we have adopted release process in price-enquiry successfully and are now testing it for few weeks to see if it works for our team | Onyx basket team |  | 30/05/25 |  | Open |  |  |  | Balaji | 2025-02-10 | 203 | >60 | January | 1900 | 90+ Days
Customer Channels | Platform & Store Ops | 90636458 | 2025-07-03 | Delay in sending order payment messages from POS Beanstore to Sterling and CSSM | Explore options to systematically correct the corrupted stock in CSSM. | Solution & Recovery | Akash Arjunan | To minimize manual intervention in stock correction, the teams will explore the feasibility of implementing a systemic solution to automatically correct the corrupted stock positions, reducing the risk of manual errors | CSSM |  | 21/03/25 |  | Open |  |  |  | Saloni | 2025-02-10 | 209 | >60 | January | 1900 | 90+ Days
Customer Channels | Platform & Store Ops | 90636458 | 2025-07-03 | Delay in sending order payment messages from POS Beanstore to Sterling and CSSM | Perform non prod level testing of the query created within CSSM to manually update stock positions. | Solution & Recovery | Akash Arjunan | Since this was a new scenario in CSSM, the query for manually updating stock positions was created but not tested in a lower environment. To mitigate the risk of further impact, it was agreed with Retail Ops to send the mandated counts to stores on 03/03. The query will now be tested in a lower environment to ensure readiness in case the issue arises. | CSSM |  | 21/03/25 |  | Open |  |  |  | Saloni | 2025-02-10 | 209 | >60 | January | 1900 | 90+ Days
Customer Channels | Service Experience | 90636458 | 2025-07-03 | Delay in sending order payment messages from POS Beanstore to Sterling and CSSM | Revisit the Sterling time threshold increase process to ensure no approval is required to reduce customer impact | Solution & Recovery | Vipin Kumar | After discussions with the Sterling team, and the dot-com service manager, it has been agreed that no further approval will be necessary to increase the threshold time once an alert is triggered or if there is an impact to 100 customer orders due to delayed payment messages. | Sterling Support |  | NA | 2025-11-03 | Closed |  |  |  | Saloni | 2025-02-10 | 209 | >60 | March | 2025 | #VALUE!
Customer Channels | Service Experience | 90636458 | 2025-07-03 | Delay in sending order payment messages from POS Beanstore to Sterling and CSSM | Enhance the incident handling efficiency within Enterprise Middleware team to reduce recovery/issue identification time | Issue handling/Management | Mukundan Rajagopalan | The team has been asked to review their call rota and designate a technical SME to ensure a quicker and more efficient response to such investigations. | Enterprise Middleware Team |  | NA | 2025-11-03 | Closed |  |  |  | Saloni | 2025-02-10 | 209 | >60 | March | 2025 | #VALUE!
GTS | Enterprise Integration | 90636458 | 2025-07-03 | Delay in sending order payment messages from POS Beanstore to Sterling and CSSM | Review the overall process in SAGG to identify any access issues or technical challenges encountered during the incident in providing the store, UPC, quantity information to CSSM for impact assessment. | Impact analysis | Sivasubramani Pappusamy | During the incident, there was a significant delay from the SAGG team in providing the relevant information to CSSM for impact assessment. To address this, a comprehensive analysis will be conducted to identify the technical challenges or issues faced by the relevant associate. Based on the findings, a plan will be developed to improve the process and ensure timely information is provided, reducing the time required for impact assessment. | Enterprise Integration |  | 21/03/25 |  | Open |  |  |  | Saloni | 2025-02-10 | 209 | >60 | January | 1900 | 90+ Days
Customer Channels | Service Experience | 90636458 | 2025-07-03 | Delay in sending order payment messages from POS Beanstore to Sterling and CSSM | Revisit the refund process for customer order cancellations. | Solution & Recovery | Randhawa, DinoGrigg, Thomas | Currently, the contact center is responsible for reaching out to customers and processing refunds. However, further discussions between the POS and Sterling teams will take place to explore a more system-driven approach to streamline the refund process. | Service Experience |  | 21/03/25 |  | Open |  |  |  | Saloni | 2025-02-10 | 209 | >60 | January | 1900 | 90+ Days
Customer Channels | Service Experience | 90636458 | 2025-07-03 | Delay in sending order payment messages from POS Beanstore to Sterling and CSSM | Amend the 3hr time threshold to 6hr within Sterling to reduce the impact on order cancellation count - Agree with Customer POs by assessing any cascading effect before deploying in prod. | Solution & Recovery | Vipin Kumar | The current time threshold in Sterling for customer orders, from placement to payment, is set at three hours. The product team will work with the product owner to extend this to six hours, allowing more time for issue investigations and reducing order cancellations. Implementing this change requires a release process, and a detailed assessment will be conducted to identify any potential cascading effects before deployment to production. | Sterling Support |  | 21/03/25 |  | Open |  |  |  | Saloni | 2025-02-10 | 209 | >60 | January | 1900 | 90+ Days
Customer Channels | Platform & Store Ops | 90636458 | 2025-07-03 | Delay in sending order payment messages from POS Beanstore to Sterling and CSSM | Explore options to gather store, UPC, quantity information from POS in a timely manner to reduce the time taken for impact assessment in CSSM. | Impact analysis | Sivasurath, Seevaratam Chelliah, Velrajan | Currently being explored | CSSM |  | 21/03/25 |  | Open |  |  |  | Saloni | 2025-02-10 | 209 | >60 | January | 1900 | 90+ Days
Customer Channels | Service Experience | 90636458 | 2025-07-03 | Delay in sending order payment messages from POS Beanstore to Sterling and CSSM | Explore options to automate the reset process for POS channels that enter a retry state. | Solution & Recovery | Balaguru Subramanian | During the issue, the impacted POS sender channel required manual intervention for reset, which delayed the recovery process. To mitigate future impact and expedite resolution, we are exploring automation options to reset channels automatically when they enter a retry state. | POS |  | 21/03/25 |  | Open |  |  |  | Saloni | 2025-02-10 | 209 | >60 | January | 1900 | 90+ Days
Customer Channels | Service Experience | 90636458 | 2025-07-03 | Delay in sending order payment messages from POS Beanstore to Sterling and CSSM | Configure a queue depth alert within the POS system to effectively monitor message backlogs in the queues. Additionally, update the Standard Operating Procedure (SOP) to include a step for validating external sender channels during incident triage. | Problem identification & Alerting | Balaguru Subramanian | While there were previous alerts in the POS system, they did not provide sufficient insight for effective issue identification. To address this, a queue depth alert will be configured to detect message backlogs more accurately. The SOP will also be updated to incorporate a step for proactively validating external sender channels, ensuring quicker identification and resolution of potential issues. | POS |  | 21/03/25 |  | Open |  |  |  | Saloni | 2025-02-10 | 209 | >60 | January | 1900 | 90+ Days
Customer Channels | Service Experience | 90636458 | 2025-07-03 | Delay in sending order payment messages from POS Beanstore to Sterling and CSSM | Perform a full analysis of the logs within POS and the MQ environment to determine the root cause of the issue. | Root cause | Sivasubramani Pappusamy/ Balaguru Subramanian | Initial investigations indicate a communication error on one of the POS BeanStore nodes. Additionally, as an MQ upgrade took place in the morning, followed by another deployment within the MQ landscape for a separate issue, further investigation is underway. A follow-up call is scheduled to finalize the root cause statement for this incident. | POS |  | 21/03/25 |  | Open |  |  |  | Saloni | 2025-02-10 | 209 | >60 | January | 1900 | 90+ Days
GTS | ETP- Cloud operations / Frameworks | 90634845 | 2025-12-03 | SAP POSDTA application was inaccessible | Review the security housekeeping process for deleting VNet peers or performing any activities on production subscriptions within Azure network layer. | Problem avoidance | Vidhya B | The VNet peer was deleted in production without a change record. The team has been advised to strictly follow the change management process for all production activities to ensure proper tracking and compliance | Cloud Platform |  | NA | 2025-12-03 | Closed |  |  |  | Saloni | 2025-02-10 | 204 | >60 | March | 2025 | #VALUE!
GTS | ETP- Cloud operations / Frameworks | 90634845 | 2025-12-03 | SAP POSDTA application was inaccessible | Review the overall VNet peering configuration to ensure it is managed as code within source control. | Problem avoidance | Vidhya B | The cloud team has confirmed that VNet peering for internal Customer subscriptions are already configured as code. However, for SAP’s subscription, authorization constraints exist. The team will explore options to extend this approach to third-party subscriptions. | Cloud Platform |  | 21/03/25 |  | Open |  |  |  | Saloni | 2025-02-10 | 204 | >60 | January | 1900 | 90+ Days
Group Platforms | Finance | 90634845 | 2025-12-03 | SAP POSDTA application was inaccessible | Collaborate with the SAP vendor to procure Firefighter Azure PIM privileges by creating an AD account for a designated Customer account (ideally a service account - Y account). This will enable faster recovery in reinstating VNet peers in case of accidental deletion. | Solution & Recovery | Vidhya B/ Gopi Kishan | Discussions are underway with SAP to secure these privileges, ensuring quicker resolution and minimizing downtime during recovery. | Cloud Platform/ SAP |  | 28/03/25 |  | Open |  |  |  | Saloni | 2025-02-10 | 204 | >60 | January | 1900 | 90+ Days
GTS | ETP- Cloud operations / Frameworks | 90634845 | 2025-12-03 | SAP POSDTA application was inaccessible | Implement a locking mechanism within the Azure network layer to prevent inadvertent deletion of active VNet peers or subscriptions. | Permanent Fix | Vidhya B | The cloud team is in the process of configuring this mechanism to ensure that active VNets and subscriptions cannot be deleted in error. | Cloud Platform |  | 21/03/25 |  | Open |  |  |  | Saloni | 2025-02-10 | 204 | >60 | January | 1900 | 90+ Days
GTS | ETP- Cloud operations / Frameworks | 90634845 | 2025-12-03 | SAP POSDTA application was inaccessible | Document all third-party subscriptions where access is unavailable to verify the status of underlying VNet peers, preventing inadvertent deletions within the Azure network layer. | Impact analysis | Vidhya B/ Fastin Xavier | The cloud team will identify all third-party SaaS subscriptions and their respective owners to ensure a thorough impact assessment before proceeding with any security cleanup activities. | Cloud Platform/ Networks |  | 21/03/25 |  | Open |  |  |  | Saloni | 2025-02-10 | 204 | >60 | January | 1900 | 90+ Days
GTS | ETP- Cloud operations / Frameworks | 90634845 | 2025-12-03 | SAP POSDTA application was inaccessible | Conduct a detailed review of the Azure subscription decommissioning process to prevent ad-hoc deletion of stale VNet peers. Identify owners for all subscriptions, particularly third-party ones, to enable thorough impact assessments before any deletions. | Problem avoidance | Vidhya B | As per the existing process, VNet peers should be deleted when a subscription is decommissioned. However, in this case, the Customer Cloud team lacked access to assess the impact due to the SaaS nature of the subscription. Going forward, we will streamline owner consultations during cleanup activities to ensure proper impact assessment and mitigate the risk of inadvertent deletions. | Cloud Platform |  | 21/03/25 |  | Open |  |  |  | Saloni | 2025-02-10 | 204 | >60 | January | 1900 | 90+ Days
Foods | Foods Supply Chain | 90610998 | 2025-11-03 | Inflated Allocations for Thatcham (Foods) RDC impacting stock deliveries to stores | There was a gap in communicating the issue on 17/02 to the wider business stakeholders. Therefore, a defined communication process needs to be established through the service leads to ensure stakeholders are informed in cases where MIM is not involved or when the issue impacts a single store, even if the overall impact is minimal. | Business & IT Communication | Lisy Eucharista/ Valliammai Ramasamy | 15/04: For future incidents involving limited number of stores which does not warrant MIM involvement, it has been agreed with Retail to provide regular updates in the Retail & Foods Service Connect until the issue is resolved. 01/04 - Lisy to speak with Dinesh. The service leads, in collaboration with the service management team, will identify a structured approach for communication. This will require product teams to inform service leads of any issues where MIM is not involved, so that stakeholders are kept updated at regular intervals throughout the resolution and recovery process. | Food/stores |  | NA | 15/04/25 | Closed |  |  |  | Saloni | 2025-02-10 | 205 | >60 | April | 2025 | #VALUE!
Foods | Foods Supply Chain | 90610998 | 2025-11-03 | Inflated Allocations for Thatcham (Foods) RDC impacting stock deliveries to stores | Analyze the behavior in RELEX to ensure it is not accepting negative stock-in-transit values, which have resulted in over-allocations. | Permanent Fix | Matt White | In Quantum, negative stock-in-transit values were adjusted to zero, ensuring that appropriate allocations were generated for the stores. An EPIC has been raised with RELX, and they are actively working to identify why negative values are being considered and to determine a potential solution. FOATR-27334 is created for this | Food |  | 21/03/25 | 2025-01-04 | closed |  |  |  | Saloni | 2025-02-10 | 205 | >60 | April | 2025 | 90+ Days
Customer Channels | Platform & Store Ops | 90610998 | 2025-11-03 | Inflated Allocations for Thatcham (Foods) RDC impacting stock deliveries to stores | Assess the feasibility of adopting an alternative approach in CSSM to recover the stock position, rather than nullifying adjustments. | Solution & Recovery | Nancy Ledsome, Akash Arjunan | Currently, positive stock adjustments are nullified by reversing them through the creation of additional events with random data to correct the stock position. The teams are now exploring a more efficient and technically optimized approach, while also evaluating the cascading impact on other downstream systems. | CSSM |  | 21/03/25 |  | Open |  |  |  | Saloni | 2025-02-10 | 205 | >60 | January | 1900 | 90+ Days
Foods | Foods Supply Chain | 90610998 | 2025-11-03 | Inflated Allocations for Thatcham (Foods) RDC impacting stock deliveries to stores | Advise GIST to follow the change management process to ensure Customer stakeholders are informed of any capability or smoke tests for new functionalities. | Issue handling/Management | James Sherman | James from GIST has confirmed that Customer will be notified of any changes in their environment, including smoke tests. Additionally, an informational change will be recorded in the MNS BMC Helix system for tracking. | GIST |  | NA | 2025-11-03 | Closed |  |  |  | Saloni | 2025-02-10 | 205 | >60 | March | 2025 | #VALUE!
Foods | Foods Supply Chain | 90610998 | 2025-11-03 | Inflated Allocations for Thatcham (Foods) RDC impacting stock deliveries to stores | Assess the overall observability within GIST to identify significant volumes of stock adjustment messages or inflated allocations at the store level. | Problem identification & Alerting | James Sherman | 15/04 - In this incident, the smoke test performed by GIST was not communicated to Customer which had actually caused the inflated order volume for stores. However, technically there is no scope of configuring an alert within GIST based on the amount of increased volume of stock adjustment messages as these are not supposed to be sent to stores. Going forward, communication for any smoke tests will be provided to Customer and the DWS change will not be attempted in future which eliminates the scope of issue recurrence. In addition, there are predefined threshold configured within GIST to identify a spike in volume of stock adjustment messages. We are currently working with GIST to analyze their monitoring mechanisms and identify areas for improvement, aiming to enhance proactive detection of such issues in the future | GIST |  | NA | 15/04/25 | Closed |  |  |  | Saloni | 2025-02-10 | 205 | >60 | April | 2025 | #VALUE!
GTS | Digital Workplace Services | 90633315 | 2025-05-03 | Foods Buyers were unable to access RDA (Reference Data Approval) application | Duane’s team is developing an automation system to detect when a primary owner of a Y account is disabled. The system will automatically assign the secondary owner and maintain a Distribution List (DL) for tracking. Estimated Completion :A few months. | Problem avoidance | Duane Bergh | 09/04 - This action will be further tracked via a backlog - https://jira-marksandspencer-app.atlassian.net/jira/software/projects/WPS/boards/529 05/03 - Duane to provide some form of log number so that this can be closed fro the PIR and tracked by the product team. | Product owner - AD |  | NA | 2024-09-04 | Closed |  | https://jira-marksandspencer-app.atlassian.net/jira/software/projects/WPS/boards/529 |  | Pavithra | 2025-02-10 | 211 | >60 | April | 2024 | #VALUE!
GTS | Digital Workplace Services | 90633315 | 2025-05-03 | Foods Buyers were unable to access RDA (Reference Data Approval) application | Leads will be notified to ensure that Y account disablement is only approved by: Account owners and their Customer counterpart owners | Problem avoidance | Kaleeswaran, PushpaSubramaniyan, Sushmitha | The AD team’s approval process will be revised to ensure that only team managers can authorise account disablement tasks. | DWS Team (As part of Red Audit team) |  | NA | 2025-05-03 | Closed |  |  |  | Pavithra | 2025-02-10 | 211 | >60 | March | 2025 | #VALUE!
Foods | Foods Supply Chain | 90633315 | 2025-05-03 | Foods Buyers were unable to access RDA (Reference Data Approval) application | Obtain or create a formal design for the Food Buyers Application and ensure a dedicated support team is in place who understands the system’s requirements and the necessary accounts. | Problem identification & Alerting | Sasirekha (Foods) | 15/04: Pilot went live on for CRD on 8th April. Further rollouts are being planned in May. 09/04 - Sasi rekha and Uma from the team are working on enhancing the document . ETA: 15/04 01/04: RDA is being replaced by CRD and the service design document is being done for this. Sasirekha will check again for the RDA documemt | Foods |  | 18/04/25 |  | Open |  |  |  | Pavithra | 2025-02-10 | 211 | >60 | January | 1900 | 90+ Days
Group Platforms | HR | 90622655 | 2025-03-03 | Issues with external recruitment page on the Customer career site | Revisit the post checks procedures/timings to verify the features after a patching activity to ensure enough buffer time for the product teams to resolve an issue to avoid business impact | Problem avoidance | Mudassar Kazmi | 19/03: Mudassar has agreed with the offshore team to perform the basic sanity testing immediately after the release around 1 AM and complete the rest of the functional testing with business and product owners at 8 AM. 03/03: Patch was released by 21:00, however the sanity testing was performed by 08:00 next day only. Therefore, we have agreed to perform the post implementation checks after an activity by securing relevant access to test the functionality to allow enough time for triage if an issue occurs. | Service Lead |  | NA | 19/03/25 | Closed |  |  |  | Gokul | 2025-02-10 | 213 | >60 | March | 2025 | #VALUE!
Group Platforms | HR | 90622655 | 2025-03-03 | Issues with external recruitment page on the Customer career site | Raise a risk to highlight the testing inefficiencies, due to the difference in configuration between the production and SIT environment across all the third party connections | Problem identification & Alerting | Mudassar Kazmi | 19/03: Mudassar has created the risk 1871406093 and agreed with the product teams to discuss on next step for creating third party connections. 03/03: SIT environment didn't have the third party connections (thirty three), due to which the issue was not identified in the testing phase. | Service Lead |  | NA | 19/03/25 | Closed |  |  |  | Gokul | 2025-02-10 | 213 | >60 | March | 2025 | #VALUE!
Group Platforms | HR | 90622655 | 2025-03-03 | Issues with external recruitment page on the Customer career site | Record the 24/7 support contacts across all the 3rd party vendors including the Customer managed vendors | Supplier and support involvement | Mudassar Kazmi | 14/04: Call with Alex has been postponed to 17/04. 31/03: Mudassar has gathered the details for all the 3rd parties vendors. Alex and Kirsten are out of office until 07/04 28/03: Call was postponed due to Oracle breach issue. 19/03: Mudassar has gathered the 24/7 contact details for most of the 3rd parties vendors, has a call with the product owners by 27th March 03/03: Initially, there were challenges in involving the vendor ThirtyThree in the call. Since it was a Saturday, the product teams were unable to reach the right contact. | Service Lead |  | 18/04/25 |  | Open |  |  |  | Gokul | 2025-02-10 | 213 | >60 | January | 1900 | 90+ Days
Group Platforms | HR | 90622655 | 2025-03-03 | Issues with external recruitment page on the Customer career site | Review the DL's for the communication, if required separate DLs to be created with respect to impacted modules. | Business & IT Communication | Mudassar Kazmi | 14/04: Call with Alex has been postponed to 17/04. 31/03: Mudassar has gathered all the business contacts for required for communication across all modules. Alex and Kirsten are out of office until 07/04 28/03: Call was postponed due to Oracle breach issue. 19/03: Mudassar is working with product team to identify the required DL's, has a call with the product owners by 27th March 03/03: Currently there are no separate DL's for individual HR modules and comms were sent to individual email addresses during the issue. Service lead will be collating the individual details to be incorporated into a DL for future comms. | Service Lead |  | 18/04/25 |  | Open |  |  |  | Gokul | 2025-02-10 | 213 | >60 | January | 1900 | 90+ Days
Group Platforms | HR | 90622655 | 2025-03-03 | Issues with external recruitment page on the Customer career site | Review the release notes thoroughly and to involve vendor for any clarifications before the deployment | Problem avoidance | Mudassar Kazmi | 19/03: Mudassar has agreed with the team to ensure they review the release notes thoroughly. 03/03: As part of the Oracle 25A patch, a URL structure change introduced by Oracle which resulted in issues while redirecting to the Thirty Three connection. Since, no customizations were made to the Oracle product, the product team overlooked the relevant release notes | Service Lead |  | NA | 18/03/25 | Closed |  |  |  | Gokul | 2025-02-10 | 213 | >60 | March | 2025 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90647077 | 13/03/25 | Carrier label printing failures at Ollerton DC impacting packing & despatch operations | Implementation of Dynatrace for enhanced log capturing in Mule Engine. | Problem Identification & Alerting | Pappusamy, Sivasubrmani | This must be implemented to ensure that we have necessary logs and artifacts to determine the Actual Root cause for the Mule Engine Going to hung State | Integration Services |  | NA | 2025-08-03 | Closed |  |  |  | Balaji | 2025-02-10 | 203 | >60 | March | 2025 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90647077 | 13/03/25 | Carrier label printing failures at Ollerton DC impacting packing & despatch operations | Mule Alert refresher training for team members along with SOP creation that contains detailed information on Alert Impact and recovery steps. | Problem Avoidance | Pappusamy, Sivasubrmani | Reoccurring session for training team members on Alert handling has been scheduled and this is a continuous effort to ensure the tickets are addressed appropriately | Integration Services |  | NA | 18/03/25 | Closed |  |  |  | Balaji | 2025-02-10 | 203 | >60 | March | 2025 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90647077 | 13/03/25 | Carrier label printing failures at Ollerton DC impacting packing & despatch operations | Process Gap - where the team members are not aware of the escalation process and Support model must be addressed. | Problem Avoidance | Davies, Mark | Mark Davies has explained and shared the Service design document to Ops to follow the escalation process. | Service Lead |  | NA | 2025-08-04 | closed |  |  |  | Balaji | 2025-02-10 | 203 | >60 | April | 2025 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90647077 | 13/03/25 | Carrier label printing failures at Ollerton DC impacting packing & despatch operations | Upgrading to Mule 4.6 is proposed as a fix and this already being the pipeline, the team will also have to confirm if they are going to fix issue in the existing version or the version post the upgrade using the Dynatrace. | Permanent fix | Pappusamy, Sivasubrmani | 08/04 - This activity is being performed via a change - CRQ000000222082 and it is expected to be completed by End of April. Since teams are already on it, executing the CR, this action is being closed. 03/25-It was confirmed that Implementation of script to automatically restart the Mule Engine when gone to hung state will be part of the deployment along with other fixes including auto restart, G1 NGEN memory increase and OJDBC Driver upgrade. | Integration Services |  | 2025-01-05 |  | Open |  |  |  | Balaji | 2025-02-10 | 203 | >60 | January | 1900 | 90+ Days
C&H and Intl | C&H and Intl Supply Chain | 90647077 | 13/03/25 | Carrier label printing failures at Ollerton DC impacting packing & despatch operations | Feasibility to Leveridge WMS health check emails for better monitoring by tools or manually, this needs to be checked and implemented. | Problem Identification & Alerting | Babu, Mohan | 1. Queue threshold alert enabled already, 2. Alert will be generated if any error in run task (printing instruction) These are the maximum check can be enabled in healthchecks. The issue on that day was, run task was completing success, no queue depth threshold, but only label printing didnot happen. Mule is having alerting for their jvm task hung error which they need to act upon rightly.13-03-25: They are Hourly Health check alerts; The team is working to check the feasibility to Reduce the Health check alert time Span. and increase the effectiveness and utilization of the alert they will also explore the option for integration with existing monitoring systems. | WMS |  | NA | 2025-08-04 | Closed |  |  |  | Balaji | 2025-02-10 | 203 | >60 | April | 2025 | #VALUE!
Customer Channels | Selling Experience | 90643228 | 2025-03-03 | Drop in products on the Customer Ireland website | Conduct a review and cleanup of all categories marked as "off-sale" | Permanent fix | Busines Content Team Khanna, Himanshu to identify the owner | The team is trying to fix the issue, if they confirm the fix cannot be identified and addressed then a risk will be raised. | .com |  | 25/04/25 |  | Open |  |  |  | Balaji | 2025-02-10 | 213 | >60 | January | 1900 | 90+ Days
Customer Channels | Selling Experience | 90643228 | 2025-03-03 | Drop in products on the Customer Ireland website | Investigate the current alerting and propose next steps. Setup a meeting with the relevant teams. | Problem Identification & Alerting | Khalid, HishamKasmani, Aadil & Product Teams | The teams are yet to share the findings after the meeting | .com |  | 25/04/25 |  | Open |  |  |  | Balaji | 2025-02-10 | 213 | >60 | January | 1900 | 90+ Days
Customer Channels | Selling Experience | 90643228 | 2025-03-03 | Drop in products on the Customer Ireland website | Implement monitoring to detect drops in category-product mappings based on outcome of action 2 | Problem Identification & Alerting | Owners to be identified from action 2 | Owner yet to be identified | .com |  | 25/04/25 |  | Open |  |  |  | Balaji | 2025-02-10 | 213 | >60 | January | 1900 | 90+ Days
Customer Channels | Selling Experience | 90643228 | 2025-03-03 | Drop in products on the Customer Ireland website | Define SOPs: Establish clear guidelines for handling data filtering requests. for handling filtering requests without impacting live products | Problem Avoidance | SHIKOTARA, JIGNESH & All Data handling product teams | Jignesh: Data handling is managed by PIM only and mentioned SOP following. 1). For any data problem with reference to live categories, connect to the PIM team via DL "GRP - DL-TCS-MnS.com STEP Support". 2). Category re-triggered from PIM after required correction, Navigation doing post verification. -> To avoid such problems, the content team needs to make sure while product to category mapping that category status should not be off-sale/deleted. -> Should commence cleanup and verification activity at PIM end to avoid such mistakes. | .com |  | 25/04/25 |  | Open |  |  |  | Balaji | 2025-02-10 | 213 | >60 | January | 1900 | 90+ Days
Customer Channels | Selling Experience | 90643228 | 2025-03-03 | Drop in products on the Customer Ireland website | Appropriate testing and impact analysis before implementing changes | Problem Avoidance | SHIKOTARA, JIGNESH & All Data handling product teams | Jignesh: Data handling is managed by PIM only and mentioned SOP following. 1). For any data problem with reference to live categories, connect to the PIM team via DL "GRP - DL-TCS-MnS.com STEP Support". 2). Category re-triggered from PIM after required correction, Navigation doing post verification. -> To avoid such problems, the content team needs to make sure while product to category mapping that category status should not be off-sale/deleted. -> Should commence cleanup and verification activity at PIM end to avoid such mistakes. | .com |  | 25/04/25 |  | Open |  |  |  | Balaji | 2025-02-10 | 213 | >60 | January | 1900 | 90+ Days
Customer Channels | Selling Experience | 90643228 | 2025-03-03 | Drop in products on the Customer Ireland website | Change control and clear approvals before implementing changes. | Problem Avoidance | SHIKOTARA, JIGNESH & All product teams | Jignesh:-> As per standard practise we are following defined procedures only, like: Implementation -> PR Review - CAB Approval -> Deployment -> Post Verification. | .com |  | 25/04/25 |  | Open |  |  |  | Balaji | 2025-02-10 | 213 | >60 | January | 1900 | 90+ Days
Customer Channels | Selling Experience | 90643228 | 2025-03-03 | Drop in products on the Customer Ireland website | Map data flow: create a visual representation of data pipeline for better troubleshooting. | Solution & Recovery | Khalid, Hisham; Kasmani, Aadil & Product Teams |  | .com |  | 25/04/25 |  | Open |  |  |  | Balaji | 2025-02-10 | 213 | >60 | January | 1900 | 90+ Days
C&H and Intl | C&H and Intl Supply Chain | 90633159 | 2025-07-03 | Carrier label printing failure at Castle Donington impacting packing operations | Check that all existing carrier ranges have the correct names and will be picked up by our monitor. | Problem Avoidance | Sorted | Completed | Sorted |  | NA | 2025-07-03 | Closed |  |  |  | Rehan | 2025-02-10 | 209 | >60 | March | 2025 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90633159 | 2025-07-03 | Carrier label printing failure at Castle Donington impacting packing operations | Review the other carriers that are used and check if the range can potentially run out for these other carriers? | Problem Avoidance | Sorted | Completed. The other carrier where the range has to manually set up is Anpost. Other carriers have cyclical range creation and these are ranges are created in an automated way. | Sorted |  | NA | 2025-07-03 | Closed |  |  |  | Rehan | 2025-02-10 | 209 | >60 | March | 2025 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90633159 | 2025-07-03 | Carrier label printing failure at Castle Donington impacting packing operations | Have Sorted got alerting for the other carriers if the range runs low? | Problem Avoidance | Sorted | Completed. Range depletion alerting is in place for Anpost and the naming convention checked to ensure t meets the correct format, | Sorted |  | NA | 2025-07-03 | Closed |  |  |  | Rehan | 2025-02-10 | 209 | >60 | March | 2025 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90633159 | 2025-07-03 | Carrier label printing failure at Castle Donington impacting packing operations | If the issue happens again with any carrier, is there an option to switch to the next carrier, even if the price is higher? What process needs to be put in place and how? | Problem Avoidance | Jackie Martin | Update: 10/04: There is an update as we had a discussion between Customer and Sorted about a playbook for the Sorted Support team. Basically, the initiative is agreed and we just need to get the process documented. Let me write an email so that you and Donington have a statement of the agreed plan of action. Tom Prince advises this is possible. We don't have Customer carrier team support team out of hours after 2200. Therefore a SOP be written for Sort out of hours support so they can switch carriers. Sorted and Customer carrier team to agree. | Product Manager |  | 17/04/25 |  | Open |  |  |  | Rehan | 2025-02-10 | 209 | >60 | January | 1900 | 90+ Days
Customer Channels | Selling Experience | 90632370 | 2025-04-03 | Drop in orders on the Customer website | Follow up RCA and preventative measures with Secure Auth | Root Cause | Priyabrata Sahu | Updated on the SA case, awaiting their response. Also requested product team to follow up with SA on their weekly catch up - https://support.secureauth.com/hc/en-us/requests/152167?page=1 4th March. Root cause shared. COMPLETE | .com | 2025-06-03 | NA | 2025-06-03 | Closed |  |  |  | Balaji | 2025-02-10 | 212 | >60 | March | 2025 | #VALUE!
Customer Channels | Selling Experience | 90632370 | 2025-04-03 | Drop in orders on the Customer website | Awareness of 'no change' days | Problem Avoidance | Simon Attard | Although SA is a SaaS provider, we will share details of business 'no change' days . Contractually they do not have to honour this but will see if they will try and take account of them. Simon will discuss this with them in more detail | .com |  | 25/04/25 |  | Open |  |  |  | Balaji | 2025-02-10 | 212 | >60 | January | 1900 | 90+ Days
Customer Channels | Selling Experience | 90633124 | 2025-04-03 | Multiple order management services encountering Intermittent timeout errors | Firewall Rule to allow URL category-based traffic resolution | Permanent Fix | Fastin Xavier | Completed, Firewall rule was updated to use URL category for resolving the endpoints. | .com |  | 25/04/25 |  | Open |  |  |  | Balaji | 2025-02-10 | 212 | >60 | January | 1900 | 90+ Days
Customer Channels | Selling Experience | 90633124 | 2025-04-03 | Multiple order management services encountering Intermittent timeout errors | Firewall rule updates in DR | Permanent Fix | Fastin Xavier, Abhishek Kumar | Planned | .com |  | 25/04/25 |  | Open |  |  |  | Balaji | 2025-02-10 | 212 | >60 | January | 1900 | 90+ Days
Customer Channels | Selling Experience | 90633124 | 2025-04-03 | Multiple order management services encountering Intermittent timeout errors | APM dashboard to track OMS outbound calls | Problem identification & Alerting | Vipin Kumar | Requires Dynatrace APM to be set up. Work will start this quarter, but full setup might not be in place until Q1. | .com | 30/05/25 | 30/05/25 |  | Open |  |  |  | Balaji | 2025-02-10 | 212 | >60 | January | 1900 | 90+ Days
Customer Channels | Selling Experience | 90633124 | 2025-04-03 | Multiple order management services encountering Intermittent timeout errors | Alerts for error rate increase for OMS outbound API calls | Problem identification & Alerting | Vipin Kumar | Dependency on action 4 | .com | 30/05/25 | 30/05/25 |  | Open |  |  |  | Balaji | 2025-02-10 | 212 | >60 | January | 1900 | 90+ Days
Customer Channels | Selling Experience | 90633124 | 2025-04-03 | Multiple order management services encountering Intermittent timeout errors | Tactical alert based on error logs in OMS | Problem identification & Alerting | Vipin Kumar | Done | .com | 28/02/25 | NA | 2025-07-03 | Closed |  |  |  | Balaji | 2025-02-10 | 212 | >60 | March | 2025 | #VALUE!
Customer Channels | Selling Experience | 90633124 | 2025-04-03 | Multiple order management services encountering Intermittent timeout errors | Socket timeout error still present in OMS logs | Problem identification & Alerting | Vipin Kumar | Check and confirm that the underlying firewall issue is 100% resolved, as some errors are still visible in logs. Vipin updated that this is unrelated. Action completed. | .com | 2025-04-05 | NA | 2025-07-03 | Closed |  |  |  | Balaji | 2025-02-10 | 212 | >60 | March | 2025 | #VALUE!
Customer Channels | Selling Experience | 90633124 | 2025-04-03 | Multiple order management services encountering Intermittent timeout errors | Analyse future Apigee release notes and notify impacted teams | Problem avoidance | Saurabh, Mani | Future action to be taken up based on Apigee change comms | .com |  | 25/04/25 |  | Open |  |  |  | Balaji | 2025-02-10 | 212 | >60 | January | 1900 | 90+ Days
Customer Channels | Selling Experience | 90633124 | 2025-04-03 | Multiple order management services encountering Intermittent timeout errors | CMWA observability | Problem identification & Alerting | Rotheram , EmmaPaul, Tarun | Completed 07/03 - Alerts configured | .com | 2025-07-03 | NA | 2025-07-03 | Closed |  |  |  | Balaji | 2025-02-10 | 212 | >60 | March | 2025 | #VALUE!
Customer Channels | Selling Experience | 90633124 | 2025-04-03 | Multiple order management services encountering Intermittent timeout errors | Add logging and Dynatrace transaction ID propagation in Apigee in the AS and OMS proxies and Akamai | Problem identification & Alerting | Paul, TarunKumar, Vipin | This will speed up problem identification | .com |  | 25/04/25 |  | Open |  |  |  | Balaji | 2025-02-10 | 212 | >60 | January | 1900 | 90+ Days
Customer Channels | Selling Experience | 90633124 | 2025-04-03 | Multiple order management services encountering Intermittent timeout errors | Add logging and Dynatrace transaction ID propagation in Apigee in the Carrier Gateway proxy and Akamai | Solution & Recovery | Mehta, Vijesh |  | .com |  | 25/04/25 |  | Open |  |  |  | Balaji | 2025-02-10 | 212 | >60 | January | 1900 | 90+ Days
Customer Channels | Selling Experience | 90633124 | 2025-04-03 | Multiple order management services encountering Intermittent timeout errors | Review fallback solution in OMS when AS is unavailable for both Item Capping & C&H. Need to have a view of current day stock at least. | Problem avoidance | Kumar, VipinXavier, FastinMandal, MrinmoyPaul, TarunLincy, Rajula | Fall back solution to prevent the OOS and false calendar experience << UPDATE (Vipin) - Had a call within Product team and a design is agreed for fall back. Development Task will be raised and taken to PM by Vasupalli, Raja Chaitanya>> | .com |  | 25/04/25 |  | Open |  |  |  | Balaji | 2025-02-10 | 212 | >60 | January | 1900 | 90+ Days
Customer Channels | Selling Experience | 90633124 | 2025-04-03 | Multiple order management services encountering Intermittent timeout errors | Review all outbound API calls from OMS Cluster (OMS & API Namespace) and associated firewall rules (and make sure they are URL based, not IP based) | Problem avoidance | Kumar, VipinXavier, FastinMandal, MrinmoyPaul, TarunLincy, Rajula | Collaboration between teams will be held to decide the plan of action and dates will be updated. | .com |  | 25/04/25 |  | Open |  |  |  | Balaji | 2025-02-10 | 212 | >60 | January | 1900 | 90+ Days
Foods | Foods Supply Chain | 90624297 | 2025-04-03 | Delay in processing Relex batch impacting NDC Allocations, Foods Supplier orders | The initial impact assessment did not account for the impact on reports such as OTS, Flic, and others. It is necessary to revise the contingency process and formally document the requirement to highlight the impact on these reports | Impact analysis | Tamilenbakumar | 15/04: Tamil confirmed that the SOP has been updated with reporting impact. 01/04: Continuing to work on SOPs 19/03 - Tamil says that the SOP's will be amending to consider reporting impact by 31/03 | Relex |  | NA | 15/04/25 | Closed |  |  |  | Naveen | 2025-02-10 | 212 | >60 | April | 2025 | #VALUE!
Foods | Foods Supply Chain | 90624297 | 2025-04-03 | Delay in processing Relex batch impacting NDC Allocations, Foods Supplier orders | In the PIR Relex advised that they realised the impact of the issue quite late in the day after the issue started, which resulted in a delay of communicating possible impacts to Customer. Relex are working on playbooks with different scenarios including prioritisation of actions to include communication. | Supplier and support involvement | Michael Shotbolt(Relex) | 19/03: The root issue was traced to a network switch where one port/cable combination experienced a partial failure, leading to increased error rates. While Relex is designed to automatically failover in cases of complete cable failure (an industry-standard practice already in use at RELEX), this partial failure did not meet the criteria to trigger automatic failover. As a result, some network traffic was disrupted. Relex has implemented enhancements to monitoring as recommended by their vendor which ensures quick detection and have quick response to similar issues in future without introducing unnecessary complexity or risk to network. | Relex |  | NA | 20/03/25 | Closed |  |  |  | Naveen | 2025-02-10 | 212 | >60 | March | 2025 | #VALUE!
Foods | Foods Supply Chain | 90624297 | 2025-04-03 | Delay in processing Relex batch impacting NDC Allocations, Foods Supplier orders | It is essential that when we initiate the batch process again, we commence from the very beginning rather than from any subsequent point. Failing to do so may result in incomplete data being displayed in the user interface, along with calculations that have not been executed. Ensure that the Standard Operating Procedure (SOP) is updated accordingly. | Solution & Recovery | Gagandeep Singh | 01/04: gagan is saying that it is not possible to restart the batch from the beginning without incurring impact. Best practice from Relex is to start from point of failure, the SOP has been updated and engineers have recorded the learnings. 19/03 - Ankush from Relex Support will follow up and get an update | Relex |  | 26/03/25 | 2025-01-04 | closed |  |  |  | Naveen | 2025-02-10 | 212 | >60 | April | 2025 | 90+ Days
Foods | Foods Supply Chain | 90624297 | 2025-04-03 | Delay in processing Relex batch impacting NDC Allocations, Foods Supplier orders | Update the SOP with the two step process to cancel the nightly run. One of the steps is to cancel the Connect job. Relex should cancel the connect job alongside the planned jobs in the Nightly run otherwise the nightly job doesn't stop immediately, and we don't know at which point the data stops to be able to perform a better clean up job. | Solution & Recovery | Gagandeep Singh | 01/04: This has now been updated in the SOP. 19/03 - Ankush from Relex Support will follow up and get an update | Relex |  | 26/03/25 | 2025-01-04 | closed |  |  |  | Naveen | 2025-02-10 | 212 | >60 | April | 2025 | 90+ Days
Foods | Foods Supply Chain | 90527201 | 21/01/25 | Over Allocations in Relex impacting Foods NDC operations | Explore possibilities to have a timely decision in invoking contingency by setting a threshold | Solution & Recovery | Matt White | 01/04: An agreement has been proposed and agreed upon. We have added a ten minute wait time to allow the analysis to take place by Relex. Relex also have the pre-approved conditions. 19/03: Agreement for NDC alloc to be done and Mat will follow up with Dan to provide update 04/03 : Agreement for NDC alloc to be done and Mat will follow up with Dan to provide update 20/02: Initial session happened on agreeing to contingency and required check points. Further follow-ups to be done with Matt Update 04/02: We have agreed on checkpints at which we would invoke contingency. Matt is putting together a proposal to the business. As Product teams are dependent on business to take a decision to invoke contingency, Matt to have a discussion with business to define thresholds that will help Product teams and business to take a decision to invoke contingency in a timely manner. | Business ops |  | NA | 2025-01-04 | closed |  |  |  | Naveen | 2025-02-10 | 254 | >60 | April | 2025 | #VALUE!
Foods | Foods Supply Chain | 90527201 | 21/01/25 | Over Allocations in Relex impacting Foods NDC operations | Explore options to have additional alerting to detect any huge variance in data updates made by business colleagues in Relex UI | Problem identification & Alerting | Matt White | EPIC ID : FOATR-21976. Lisy is in dicussion with product manager to prioritize this delivery 20/02 - Lisy to share the EPIC ID with Naveen. Also Lisy to discuss with Magda to prioritize this as this issue is a recurring one 04/02: This is a long term action with multiple elements. EPIC ID/JIRA required - Lisy to get from Magda, then we can close. Although alerting is already in place within RELEX to identify variances in allocations and decide on contingency planning, the teams are further exploring options to configure an alert within the RELEX UI to detect any errors made during manual updates by business colleagues. | Relex |  | NA | 20/02/25 | Closed |  |  |  | Naveen | 2025-02-10 | 254 | >60 | February | 2025 | #VALUE!
Foods | Foods Supply Chain | 90527201 | 21/01/25 | Over Allocations in Relex impacting Foods NDC operations | Explore options to have additional validations in Relex UI | Problem avoidance | Relex | 05/02: FOATR-16449 & FOATR-21976 epics / features for improving the data validations to avoid operation issues and UX/UI - PIR improvments 04/02: This is a long term action with multiple elements. EPIC ID/JIRA required - Lisy to get from Magda, then we can close. As business make changes in the Relex UI and there are no additional validations done by business or Relex , Relex to introduce a process to perform additional validations by Relex/business to avoid allocation issues | Relex |  | NA | 2025-05-02 | Closed |  |  |  | Naveen | 2025-02-10 | 254 | >60 | February | 2025 | #VALUE!
Foods | Foods Supply Chain | 90527201 | 21/01/25 | Over Allocations in Relex impacting Foods NDC operations | Explore options to establish a process/SOP while updating the safety stock inputs in Relex UI[A mass update done by Supply chain colleagues for Ambient products which increased the safety stock inputs] | Problem avoidance | John Christopher | 05/02: FOATR-16449 & FOATR-21976 epics / feautes for improving the data validations to avoid operation issues and UX/UI - PIR improvments 04/02: This is a long term action with multiple elements. EPIC ID/JIRA required - Lisy to get from Magda, then we can close. A training/ workshop will be conducted by the business teams to do future updates in a controlled manner. SOP is documented as well. | Business ops |  | NA | 2025-05-02 | Closed |  |  |  | Naveen | 2025-02-10 | 254 | >60 | February | 2025 | #REF!
Foods | Foods Supply Chain | 90503293 | 16/01/25 | Relex performance issue impacting the Overnight critical batches | During the major incident, there were unexpected delays in receiving technical support from Relex. To address this , review and streamline the support and engagement process from Relex during major incidents to ensure swift recovery and timely updates. | Supplier and support involvement | Matt White | 04/03 - There is a discussion planned in Apr on mitigating the risk of one Relex single point of failure 20/02 - Matt unavailable , Lisy to follow-up with him 04/02: Matt is in talks with Relex about their support process and finding wider SME's - or provide more control to Customer. 30/01 - Emailed Matt to get an update from him 24/01 - Contacted Matt via teams to get an update from him. No response yet 16/01 Relex Engineer was unable to provide the expected L2 technical support during the call. Relex to review the engagement during a major incident and agree on a process to provide resources with technical expertise. This action will be led by Matt in collaboration with Rich to ensure appropriate support is in place, improving RELX’s engagement during future incidents. | Relex |  | 29/04/25 |  | Open |  |  |  | Naveen | 2025-02-10 | 259 | >60 | January | 1900 | #REF!
Foods | Foods Supply Chain | 90503293 | 16/01/25 | Relex performance issue impacting the Overnight critical batches | Assess and explore alternative workarounds to enable faster recovery and minimize the impact on the RELEX overnight batch during an infrastructure issue. | Solution & Recovery | Michael Shotbolt(Relex) | 19/03 - The reason automated recovery was not invoked was because there was a partial cable failure. Monitoring has been enhanced to trigger in the case of a partial failure. 13/03 - No update received yet , mailed Michael and Tommi on this request 04/03 - Michael to share the update by today. 20/02 - Lisy also followed-up , no response from Relex. Lisy to escalate the issue to Matt and have a call. 24/01/25 - Received the RCA document from Relex team .Still awaiting further details on why the automated failover did not happen. 16/01/25 - Relex are exploring an automated recovery process to ensure that , in the event of any issue in a specific environment , services can fail over to a functional environment. This will help prevent delays to the RELEX nightly batch. | Relex |  | NA | 19/03/25 | Closed |  |  |  | Naveen | 2025-02-10 | 259 | >60 | March | 2025 | #REF!
Foods | Foods Supply Chain | 90503293 | 16/01/25 | Relex performance issue impacting the Overnight critical batches | Develop a plan to grant additional access for sending business communications to the product teams - TPM/TEM during major incidents, ensuring timely and efficient communication to avoid delays | Business & IT Communication | Tamilenbakumar | 29/01 - Tamil confirmed with Lisy that access is not needed to TEM's/TPM's as of now to the mailbox. As Shubankar already has access as Offshore service lead , no further action needed on this line item 24/01- Followed up with Tamil and as Lisy was on leave , no further updates were provided. Tamil to discuss with Lisy and update 16/01/25- A work order has been raised to grant access to additional team members, ensuring such delays are avoided in the future - Shubhankar De, Andrew Goslin. Bhuvana S | Foods |  | NA | 29/01/25 | Closed |  |  |  | Naveen | 2025-02-10 | 259 | >60 | 29/01/25 | #VALUE! | #REF!
Foods | Foods Supply Chain | 90503293 | 16/01/25 | Relex performance issue impacting the Overnight critical batches | Identify whether an alert is configured for the faulty network switch port and to understand what actions had been taken in response to the issue. | Problem identification & Alerting | Michael Shotbolt(Relex) | 31/01/25- Relex confirmed to close this action item as alerting is in place 24/01/25 - Received the RCA document from Relex team and alerting is in place to help identify these issues. Still awaiting further details on why the automated failover did not happen. 16/01/25 - RELEX confirmed that no alerts were configured for the network switch issue. Hence, RELEX is exploring options to enhance their alerting mechanisms for hardware-related issues. | Relex |  | NA | 31/01/25 | Closed |  |  |  | Naveen | 2025-02-10 | 259 | >60 | January | 2025 | #VALUE!
Customer Channels | Selling Experience | 90474650 | 2025-02-27 | Customers encountering "Sorry, Something Went Wrong" errors on Customer.com website | Explore changes to store the Auth Session into Browser Session Storage to reduce the number of requests and therefore reduce error rate. | Solution & Recovery | Prince Kumar | 17/04: They conducted a spike and concluded that it is neither feasible nor secure to proceed with this approach. Instead, they are working on implementing server-side sessions, which will also reduce the overall number of requests and, consequently, the error rate. This is still a work in progress as it's a large piece of work. Once completed, the apps will need to adopt this capability. 27/02: A github ticket https://github.com/DigitalInnovation/onyx/issues/24711 has been raised, however, PM will follow up with Prince on 28/02 to get the latest progress | Onyx Web Platform Team |  | 2025-01-05 |  | Open |  |  |  | Saloni | 2025-02-10 | 217 | >60 | January | 1900 | 90+ Days
Customer Channels | Selling Experience | 90474650 | 2025-02-27 | Customers encountering "Sorry, Something Went Wrong" errors on Customer.com website | Implement Onyx Auth Error Page so that control of the errors and monitoring of it remains within the teams control | Problem identification & Alerting | Prince Kumar | 17/04: This is not needed as we have implemented the error state to be returned to the consuming apps, where they have more control on how they want to react to the errors. The action can be closed. Here is the tracking ticket addressing the PIR for the incident - https://github.com/DigitalInnovation/onyx/issues/24928 27/02: A github ticket https://github.com/DigitalInnovation/onyx/issues/24711 has been raised, however, PM will follow up with Prince on 28/02 to get the latest progress | Onyx Web Platform Team |  |  | 17/04/25 | Closed |  |  |  | Saloni | 2025-02-10 | 217 | >60 | April | 2025 | 90+ Days
Customer Channels | Selling Experience | 90474650 | 2025-02-27 | Customers encountering "Sorry, Something Went Wrong" errors on Customer.com website | Rever the AuthSession provider changes which were implemented during the incident but did not yield for any improvements | Solution & Recovery | Prince Kumar | 27/02 : The change was reverted on 13/01 | Onyx Web Platform Team |  | NA | 27/02/25 | Closed |  |  |  | Saloni | 2025-02-10 | 217 | >60 | February | 2025 | #VALUE!
Customer Channels | Selling Experience | 90474650 | 2025-02-27 | Customers encountering "Sorry, Something Went Wrong" errors on Customer.com website | Identify a long term fix for the logic issue within Next Auth to avoid errors on the website | Permanent Fix | Prince Kumar | 27/02: The suggestion is to upgrade the Next Auth version and a github ticket github.com/DigitalInnovation/onyx/issues/24928 has been raised for it. | Onyx Web Platform Team |  | NA | 2025-03-03 | Closed |  | github.com/DigitalInnovation/onyx/issues/24928 |  | Saloni | 2025-02-10 | 217 | >60 | March | 2025 | #VALUE!
Customer Channels | Selling Experience | 90618941 | 20/02/25 | Customers were unable to check out on International Sites from 5:29 to 6:24 | International Support Team to post all Sev1 and Sev2 incidents in the incident channel. | Issue handling/Management | Ramanathan, Chokkanathan ; Khalid, Hisham | 20-03-2025 - Tapas Rajan Prusty confirmed that this action item can be closed as the team agreed to Post in Teams Incident channel for all Sev 1 and Sev 2s 04-03-2025 - Follow up email sent to Hisham and Chokkanathan, awaiting feedback on all action items | .com |  | 25/02/25 | 20/03/25 | Closed |  |  |  | Balaji | 2025-02-10 | 224 | >60 | March | 2025 | 90+ Days
Customer Channels | Selling Experience | 90618941 | 20/02/25 | Customers were unable to check out on International Sites from 5:29 to 6:24 | International Support Team to engage on-call service lead out of office hours. | Issue handling/Management | Ramanathan, Chokkanathan; Khalid, Hisham | 20-03-2025 - Tapas Rajan Prusty confirmed that this action item can be closed as the team is aware on how to engage the oncall Service lead during Out of office hours 04-03-2025 - Follow up email sent to Hisham and Chokkanathan, awaiting feedback on all action items | .com |  | 25/02/25 | 20/03/25 | Closed |  |  |  | Balaji | 2025-02-10 | 224 | >60 | March | 2025 | 90+ Days
Customer Channels | Selling Experience | 90618941 | 20/02/25 | Customers were unable to check out on International Sites from 5:29 to 6:24 | Follow up RCA and preventative measures with SFCC | Root Cause | Ramanathan, Chokkanathan | RCA: The Technology team and third-party vendor determined the initial root cause of the incident was a software bug that caused the load balancer to reboot. Typically, the pair of load balancers remain in sync to allow a graceful failover. In this case, there was a subset of VIP pools that were not configured the same way on the passive load balancer. The third-party vendor identified a further bug that was deemed to be the cause of the load balancers not remaining in sync. The Technology team further addressed this issue by executing a change to sync the passive load balancer after the disruption. The Technology team also implemented alternate telemetry to identify when load balancers are out of sync. Preventative action: To maintain the performance level that our customers expect from Salesforce and to prevent this defect from recurring, our focus is on continuous improvement. The Technology team has identified and is implementing the following actions: Complete: ● Collaborated with the third-party vendor: The Technology team investigated the impacted load balancer to identify the full root cause of this incident with the vendor. In Progress: ● Adding additional monitoring: The Technology team is implementing a configuration drift monitoring system between active/passive load balancers. ● Creating a remediation plan while the bug still exists: The Technology team is investigating a remediation plan for load balancers containing the identified bug. 04-03-2025 - Follow up email sent to Hisham and Chokkanathan, awaiting feedback on all action items | .com |  | 2025-06-03 | 20/02/25 | Closed |  |  |  | Balaji | 2025-02-10 | 224 | >60 | February | 2025 | 90+ Days
Customer Channels | Selling Experience | 90618941 | 20/02/25 | Customers were unable to check out on International Sites from 5:29 to 6:24 | SFCC service disruption alert timing to be reviewed. | Problem Identification & Alerting | Ramanathan, Chokkanathan | 20-03-2025 - Tapas Rajan Prusty confirmed that Enhanced Monitoring has been set up, a configuration drift monitoring system has been implemented to continuously track and maintain synchronization between active and passive load balancers. 04-03-2025 - Follow up email sent to Hisham and Chokkanathan, awaiting feedback on all action items | .com |  | 25/04/25 |  | Open |  |  |  | Balaji | 2025-02-10 | 224 | >60 | January | 1900 | 90+ Days
Customer Channels | Service Experience | 90594365 | 2025-02-14 | Some Flowers and hampers products were not available for next day delivery | Checkpoint for SOD status validation | Permanent Fix | Tarun/Meena | 11/04: The validation steps have been added in to the job 14/02: Availabilty service is going to add a step in the midnight automated job, as a checkpoint for SOD processing status. Based on status it will enable the execution for the automated job | Availability Services Support |  | NA | 2025-11-04 | Closed | NA | NA | NA | Kavitha | 2025-02-10 | 230 | >60 | April | 2025 | #VALUE!
Customer Channels | Service Experience | 90594365 | 2025-02-14 | Some Flowers and hampers products were not available for next day delivery | Discuss with Supplier to agree on time frame for SOD process to avoid any conflict in future. | Problem avoidance | Laming. Mark | 09/02: Issue was taken up with supplier to streamline and ensure time consistency of 02:00 AM was followed moving forward to avoid such issue or supplier will call out if there was any deviation | Ops-Hub |  | NA | 14/02/25 | Closed | NA | NA | NA | Kavitha | 2025-02-10 | 230 | >60 | February | 2025 | #VALUE!
Customer Channels | Service Experience | 90594365 | 2025-02-14 | Some Flowers and hampers products were not available for next day delivery | Reschedule automate job to 12:00 AM instead of 01:00 AM | Problem avoidance | Paul, Tarun | 09/02: Workaround automated job (pre) was rescheduled to execute at 12:00 AM, this is evaluated based on the SOD processing timeframe from past dates | Availability Services Support |  | NA | 14/02/25 | Closed | NA | NA | NA | Kavitha | 2025-02-10 | 230 | >60 | February | 2025 | #VALUE!
GTS | ETP-On premise services | 90591874 | 13/02/25 | Missing files after HNAS to Pure Storage migration | Carry out full housekeeping of the Citrix user profiles. We have been advised that the final number of colleagues using Citrix after the housekeeping should be approx. 300. | Problem avoidance | Kaluva, Sailesh Arumugam, Hariharasudhan | 10/04: Followed up with Sailesh and awaiting an update 12/03 Followed up with Sailesh and awaiting an update | Storage |  | 17/04/25 |  | Open |  |  |  | Rehan | 2025-02-10 | 231 | >60 | January | 1900 | 90+ Days
GTS | ETP-On premise services | 90591874 | 13/02/25 | Missing files after HNAS to Pure Storage migration | The final EVS migration needs to be planned in detail - Full review to be conducted on the final migration - Sign off by Golder, Elizabeth Change and MIM | Problem avoidance | Kaluva, SaileshArumugam, Hariharasudhan | 10/04: Followed up with Sailesh and awaiting an update 12/03 Followed up with Sailesh and awaiting an update | Storage |  | 17/04/25 |  | Open |  |  |  | Rehan | 2025-02-10 | 231 | >60 | January | 1900 | 90+ Days
GTS | ETP-On premise services | 90591874 | 13/02/25 | Missing files after HNAS to Pure Storage migration | Comms for the final migration to be fully planned and users identified - all approvals to be taken through every relevant service lead | Business & IT Communication | Arumugam, Hariharasudhan | 10/04: Followed up with Sailesh and awaiting an update | Storage |  | 17/04/25 |  | Open |  |  |  | Rehan | 2025-02-10 | 231 | >60 | January | 1900 | 90+ Days
Customer Channels | Selling Experience | 90594352 | 2025-02-13 | Gifting and Entertainment Hampers & Wine products availability | Create a Detailed SOP | Problem avoidance | Kamalakaran, TamilSelvan (Sterling Support) | Step by Step SOP has been created and an awareness was conducted across the support associates. | OMS |  | NA | 14/02/25 | Closed | NA | NA | NA | Pavithra | 2025-02-10 | 231 | >60 | February | 2025 | #VALUE!
Customer Channels | Selling Experience | 90594352 | 2025-02-13 | Gifting and Entertainment Hampers & Wine products availability | Ensure we have the right alerting in place | Problem identification & Alerting | Kamalakaran, TamilSelvan (Sterling Support) | Team will be evaluating and configured alert to keep track of the issue and mitigate. | OMS |  | NA | 14/02/25 | Closed | NA | NA | NA | Pavithra | 2025-02-10 | 231 | >60 | February | 2025 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90599097 | 2025-02-12 | Castle Donington DC colleagues were unable to scan SYW (Shop your way) orders | Change management to review the existing product-4-wall process and risk categorizations along with the product team | Problem avoidance | Mookandi, Valli, Somasundaram, Priyadharshini, Poikaikumaran, Nirmal | 09/04 - Donington team to measure the Risk/ Impact level in detail and send the changes for CAB Approvals. - This is the agreed approach going forward. 26/02 - A Formal email has been sent by Nirmal to take all the changes in PRod for Donnington DC will be taken to Cab and not via product 4-wall. Once it has been agreed by all the CD stakeholders and change management - this action can we closed. 12/02 - Nirmal has advised to remove the product4 wall templates/process for CD changes considering the criticality and sensitivity. Once a formal email is triggered by the CD team, all changes within Donington environment will undergo e-cab and Cab for the right risk and impact assessments. | Change Management and CD tech team |  | NA | 2025-09-04 | Closed | NA | NA | NA | Pavithra | 2025-02-10 | 232 | >60 | April | 2025 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90599097 | 2025-02-12 | Castle Donington DC colleagues were unable to scan SYW (Shop your way) orders | Ensure we have a stringent Maker checker process followed during any change implementation | Problem avoidance | WMS Team/ Chichkar, Kunal | 12/02 - It has been agreed to follow the make checker process effectively and also going forward, for any changes in WMS database Commit action will be carried out as a separate step on the implementation plan rather executing them using scripts | WMS CD tech team |  | NA | 2025-12-02 | Closed | NA | NA | NA | Pavithra | 2025-02-10 | 232 | >60 | February | 2025 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90599097 | 2025-02-12 | Castle Donington DC colleagues were unable to scan SYW (Shop your way) orders | Explore the feasibility to automate the scripts wherever possible. | Problem avoidance | Chichkar, Kunal | 09/04- The shell script has been enabled to create/perform the database changes going forward rather than manually running through sql developer. This will prevent any manual errors. 12/02 - WMS Tech engineer will explore the CI/CD pipeline options to check if they can automate the changes on the database | WMS CD tech team |  | NA | 2025-09-04 | Closed | NA | NA | NA | Pavithra | 2025-02-10 | 232 | >60 | April | 2025 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90599097 | 2025-02-12 | Castle Donington DC colleagues were unable to scan SYW (Shop your way) orders | Ensure to MIM is engaged on a timely manner | Issue handling/Management | Srinivasan, Murali/Vasan, Pragadeesh | 12/02 - Any operational impact to Donington is a straightforward sev1., but in this case MIM was not engaged on time and there were issues with the communications sent out. It has now been agreed to engage MIM as soon as they observe disruption in service within Donnington and comms will be reviewed on the bridge call before being published. | Service Leads - CD |  | NA | 2025-12-02 | Closed | NA | NA | NA | Pavithra | 2025-02-10 | 232 | >60 | February | 2025 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90599097 | 2025-02-12 | Castle Donington DC colleagues were unable to scan SYW (Shop your way) orders | Improvise the Impact assessment process | Issue handling/Management | Srinivasan, Murali/Vasan, Pragadeesh | 12/02 - During the incident, it was challenging to derive the full impact (no.of failed orders) as it required site ops involvement to provide the impact details. Tech team has identified a seamless way to communicate to the site OPS for a quick impact details. Once we got the impact from site ops, it can further be tracked via the existing powerBI dashboards | Service Leads - CD |  | NA | 2025-12-02 | Closed | NA | NA | NA | Pavithra | 2025-02-10 | 232 | >60 | February | 2025 | #VALUE!
Foods | Foods Supply Chain | 90591809 | 2025-11-02 | Increase in supplier orders volume for Foods chilled & ambient lines | Implement a housekeeping job that clears down existing files. | Problem avoidance | Ponnusamy, Puviyarasu | 01/04: Housekeeping job created 19/03 : ETA for prod deployment is now 28th Mar due to the other business priority work. 04/03 : ETA for prod deployment is now 20th Mar due to the other business priority work. 20/02 : ASO is working on the implementation and ETA provided is in 1st week of March. Next follow-up on 10th March | ASO TPM |  | 28/03/25 | 2025-01-04 | Closed |  |  |  | Rehan | 2025-02-10 | 233 | >60 | April | 2025 | 90+ Days
GTS | Operations | 90591809 | 2025-11-02 | Increase in supplier orders volume for Foods chilled & ambient lines | Rehan to organise a call with Maluroutu, Dinesh White, Matt Eucharista, LisyChristopher, John to discuss how Foods MIM calls should be run in future as there is feedback from technical teams that they should be allowed to work on the investigation without the added distraction of being part of a MIM call. | Issue handling/Management | Siddiqui, Rehan | This has been completed and we have agreed that the call wil be held on one bridge in a structured manner allowing everyone to complete their tasks including MIM communications which priority will be given to. | Service Management |  | NA | 2025-12-03 | Closed |  |  |  | Rehan | 2025-02-10 | 233 | >60 | March | 2025 | #VALUE!
Foods | Foods Supply Chain | 90591809 | 2025-11-02 | Increase in supplier orders volume for Foods chilled & ambient lines | Change the documented test plan to delete the SAND file after testing - this has been documented and the team has been appraised | Problem avoidance | Ponnusamy, Puviyarasu |  | ASO TPM |  | NA | 2025-11-02 | Closed |  |  |  | Rehan | 2025-02-10 | 233 | >60 | February | 2025 | #VALUE!
Customer Channels | Selling Experience | 90590123 | 2025-10-02 | Significant drop in orders on website and various Store impacts | Holding Page - There was discussion about whether or not to put up a partial holding page (i.e. allow browse but not basket and checkout) but that holding page was not Production ready at the time of the incident. (it is now). | Issue handling/Management | Tim Morgan & David Raine | 10/03: Elaine confirmed that this action is complete. 10/02: 1. Review holding page experience and see whether we need a range of different holding pages. Product team to discuss with Himanshu Khanna from the business to understand the business requirement – Tim 2. Need ability to throttle traffic back to the website via the holding pages. Tim Morgan to hold a retro about holding page control and involved David Raine 3. Need to confirm who is accountable for the holding pages and ‘owns’ them - Tim | Head of SW Engineering |  | NA | 2025-10-03 | Closed |  |  |  | Gokul | 2025-02-10 | 234 | >60 | March | 2025 | #VALUE!
Customer Channels | Selling Experience | 90590123 | 2025-10-02 | Significant drop in orders on website and various Store impacts | The App drop lock | Issue handling/Management | Tim Morgan | 04/04: Tim confirmed that the scope is reviewed 24/03: We are waiting for further updates from Tim on the App drop lock. 12/03: App Lock Review meeting scheduled for Tuesday 18th March at 14:00. 10/02: The App drop lock experience is not ideal which means that the preference is to leave it off when the holding page is put up. Agreed that this should be coupled with holding page actions. It should be possible to control the drop lock independently, but it should hit the same end points. Tim to review scope | Head of SW Engineering |  | NA | 2025-04-04 | Closed |  |  |  | Gokul | 2025-02-10 | 234 | >60 | April | 2025 | #VALUE!
Customer Channels | Selling Experience | 90590123 | 2025-10-02 | Significant drop in orders on website and various Store impacts | Communication with Stakeholders | Business & IT Communication | Elaine Hawthorn | 04/04: Elaine confirmed that this will be part of the PIR review/revamp which is in progress. 12/03: Elaine updated that reviewing the comm framework is still being worked upon. 10/02: Need to communicate better with Senior Business Stakeholders such as Simon Wood, Stephen Langford. Elaine to agree the communication framework with Himanshu and then document the process for communication with both Senior Business and Senior Technical Stakeholders | Service Lead |  | NA | 2025-04-04 | Closed |  |  |  | Gokul | 2025-02-10 | 234 | >60 | April | 2025 | #VALUE!
Customer Channels | Selling Experience | 90590123 | 2025-10-02 | Significant drop in orders on website and various Store impacts | Apigee | Problem avoidance | Tim Morgan & Steve Warren | 15/04: Elaine confirmed that Apigee rate limit was reviewed and action is complete 04/04: Apigee Rate Limit discussion rescheduled for Monday 7th April @ 09:30 GMT. 24/03: We are waiting for further updates from Tim on the Apigee 12/03: Apigee rate limit meeting scheduled for Tuesday 18th March at 14:30. 10/02: No clear owner of Rate Limits (RL). Need to have standards regarding what the RLs should be, so that individual Product teams understand how to set them (rather than just setting a very high number). Note: The RLs should not be owned by the Apigee team. Steve will review governance standards for RLs. Tim will consider whether or not we need to implement circuit breakers. | Head of SW Engineering | 45761 | NA | 15/04/25 | Closed |  |  |  | Gokul | 2025-02-10 | 234 | >60 | April | 2025 | #VALUE!
Customer Channels | Selling Experience | 90590123 | 2025-10-02 | Significant drop in orders on website and various Store impacts | Change Process | Issue handling/Management | Steve Warren | 15/04: Steve is stil reviewing the change process 04/04: Change process is still being reviewed 12/03: Elaine updated that reviewing the change process is still being worked upon. 10/02:There was a lack of visibility of the change carried out by the Browse team which triggered the incident. Steve will review the Change model (i.e. educate teams regarding when they need to tell people about their changes and also how they inform). Not necessary to bring all changes to CAB but need some sort of communication with regard to potentially impactful changes. Tim suggested the use of a deployment checklist e.g. what systems impacted by change. It was thought that Dynatrace might be able to help with this. | Senior Hd of SW Engineering |  | 18/04/25 |  | Open |  |  |  | Gokul | 2025-02-10 | 234 | >60 | January | 1900 | 90+ Days
Customer Channels | Selling Experience | 90590123 | 2025-10-02 | Significant drop in orders on website and various Store impacts | Traffic Modelling | Problem identification & Alerting | Peter Mouland | 12/03: Elaine confirmed that the traffic modelling is done. 10/02: David suggested using traffic modelling i.e. if we traffic model and see a spike then, we should look at it and determine whether or not it will cause an impact. Peter advised that he will look into this for the Browse team | SW Engineering Manager |  | NA | 2025-12-03 | Closed |  |  |  | Gokul | 2025-02-10 | 234 | >60 | March | 2025 | #VALUE!
Customer Channels | Selling Experience | 90590123 | 2025-10-02 | Significant drop in orders on website and various Store impacts | Architecture | Problem avoidance | Peter Mouland | 12/03: Elaine confirmed that the architecture has been reviewed. 10/02: There was a concern that the solution that the Browse team had deployed had been built a long time ago and that there was no ownership of this. It was suggested that Kevin Magrane should review the architecture and design. Peter to discuss it with Kevin | SW Engineering Manager |  | NA | 2025-12-03 | Closed |  |  |  | Gokul | 2025-02-10 | 234 | >60 | March | 2025 | #VALUE!
Customer Channels | Selling Experience | 90590123 | 2025-10-02 | Significant drop in orders on website and various Store impacts | Alerting - Teams were not aware of the significant increase in traffic. Agreed that alerting should be added to highlight significant changes to load profile. | Problem identification & Alerting | Prince Kumar & David Raine | 12/03: Elaine confirmed that the reversion of changes has been completed. 10/02: 1. Prince agreed to put this alerting in for Onyx Auth 2. David agreed to put the alerting in for the re-instatement of the WAF security change 7.03 - complete | Akamai |  | NA | 2025-12-03 | Closed |  |  |  | Gokul | 2025-02-10 | 234 | >60 | March | 2025 | #VALUE!
Customer Channels | Selling Experience | 90590123 | 2025-10-02 | Significant drop in orders on website and various Store impacts | Reversion of changes - Agreed to revert the Browse change which caused the incident plus revert the WAF related Security change that was carried out as part of the incident triage to try and restore service. | Solution & Recovery | David Raine | 1. Auth roll out in Browse reversion completed on 10th February 16:05 2. Reversion to v703 of WAF config completed on 11th Feb | Akamai |  | NA | 2025-10-03 | Closed |  |  |  | Gokul | 2025-02-10 | 234 | >60 | March | 2025 | #VALUE!
Customer Channels | ETP- Connectivity,service & solution | 90575084 | 18/02/25 | Convenience stores experiencing network performance issues | Share update on the SSL key exchange test and DSL test performed by Vodafone | Problem Identification & Alerting | Nick Baldwin | The SSL-key exchange tests were traced by Vodafone in the core network and by TCS at the DC and store From this trace the packet loss can be seen to be occurring between the store and the LNS_PE | Vodafone |  | NA | 28/02/25 | Closed |  |  |  | Balaji | 2025-02-10 | 226 | >60 | February | 2025 | #VALUE!
Customer Channels | ETP- Connectivity,service & solution | 90575084 | 18/02/25 | Convenience stores experiencing network performance issues | The root cause identification is pending with Vodafone, once its identified the Fix will be identified. | Solution & Recovery | Nick Baldwin | 10/04: We are converting these stores to SD WAN stores from MPLS. The root cause has not been determined and therefore we need to remove all these stores from legacy infrastructure at the Vodafone end. Action can be closed and this will be tracked under the project - managed by Paul Joesph. Rik Vodafone, is still working on Root cause analysis and Fix is yet to be Identified. | Vodafone |  | 17/04/25 | 2025-10-04 | Open |  |  |  | Balaji | 2025-02-10 | 226 | >60 | April | 2025 | 90+ Days
Customer Channels | ETP- Connectivity,service & solution | 90575084 | 18/02/25 | Convenience stores experiencing network performance issues | Once fix is Identified Fix Implementation timeline will be shared. | Permanent fix | Nick Baldwin | 10/04: We are converting these stores to SD WAN stores from MPLS. The root cause has not been determined and therefore we need to remove all these stores from legacy infrastructure at the Vodafone end. Action can be closed and this will be tracked under the project - managed by Paul Joesph. Vodafone, is still working on Root cause analysis and once determined it will fix will be determined | Vodafone |  | 17/04/25 | 2025-10-04 | Open |  |  |  | Balaji | 2025-02-10 | 226 | >60 | April | 2025 | 90+ Days
Customer Channels | ETP- Connectivity,service & solution | 90575084 | 18/02/25 | Convenience stores experiencing network performance issues | Problem Root cause investigation is with Vodafone (Vendor) | Root Cause | Nick Baldwin | 10/04: We are converting these stores to SD WAN stores from MPLS. The root cause has not been determined and therefore we need to remove all these stores from legacy infrastructure at the Vodafone end. Action can be closed and this will be tracked under the project - managed by Paul Joesph. Vodafone, is still working on Root cause analysis and once determined it will fix will be determined | Vodafone |  | 17/04/25 | 2025-10-04 | Open |  |  |  | Balaji | 2025-02-10 | 226 | >60 | April | 2025 | 90+ Days
Customer Channels | Platform & Store Ops | DN Ref:128197457 | 2025-02-03 | Connectivity issues between Apigee and Retail AKS cluster impacting Digital Café kiosks and in-store applications | Review and enable additional logging for applications using api calls via Apigee, to backtrack the error logs from the application to apigee. | Problem identification & Alerting | Ravindran, Rohith/Ahamed, Anees | Collect app - the additional logging will be enable via the backlog "https://jira-marksandspencer-app.atlassian.net/browse/CSA-285" - Action is closed Intelligent waste - https://jira-marksandspencer-app.atlassian.net/browse/FSO-969 | Retail product team |  | NA |  | Closed | NA | Collect app: https://jira-marksandspencer-app.atlassian.net/browse/CSA-285 Intelligent waste - https://jira-marksandspencer-app.atlassian.net/browse/FSO-969 | In-progress | Pavithra | 2025-02-10 | 241 | >60 | January | 1900 | #REF!
GTS | Enterprise Integration | DN Ref:128197457 | 2025-02-03 | Connectivity issues between Apigee and Retail AKS cluster impacting Digital Café kiosks and in-store applications | Raise a ticket with Apigee to review and understand the timeout error received during the incident. | Root cause | Mani Saurabh | 20/02 - Apigee has confirmed no major/central issue observed within apigee, seems like the issue appears to be from the target end, however due to adequte logs from the application end, we are unable to drill down to the root cause. 14/02 - Appigee has confirmed no central issues from their end. However, their message processor logs will be checked to validate the reason for the timeout errors 03/01- Apigee Support case #57096228 is raised - | Apigee Team |  | NA | 20/02/24 | Closed | NA | NA | NA | Pavithra | 2025-02-10 | 241 | >60 | February | 2024 | #REF!
GTS | ETP- Cloud operations / Frameworks | DN Ref:128197457 | 2025-02-03 | Connectivity issues between Apigee and Retail AKS cluster impacting Digital Café kiosks and in-store applications | Raise a case with Microsoft - to ensure there was no connectivity issue between apigee and AKS cluster services during the incident. | Root cause | Emmanuel George | 26/02 - Microsoft have confirmed no central outage/issue at their end , no SNAT connectivity issue.exhaustion. Thus the root cause remains inconclusive. 14/02 - No Central issue observed in Microsoft - However logs have been shared for further checks. 03/02 - MS case raised 2502030030008927 | Cloud Platform |  | NA | 20/02/25 | Closed | NA | NA | NA | Pavithra | 2025-02-10 | 241 | >60 | February | 2025 | #REF!
Customer Channels | Service Experience | DN Ref:128197457 | 2025-02-03 | Connectivity issues between Apigee and Retail AKS cluster impacting Digital Café kiosks and in-store applications | Review the Dynatrace logging for VOD (Vision on Demand) | Issue handling/Management | Dhiraj Shaw | 09/04 - Dynatrace alerting has been reviewed and tweaks have been made to fit the purpose 12/02-Though VOD, had the additional logging for the between the application to apigee, whilst backtracking the api calls from the application layers via Dynatrace we could see discrepancies with the logging. Product teams will review the existing logging set-up to ensure it fits the purpose. | POS Team |  | NA | 2025-09-04 | closed | NA | NA | NA | Pavithra | 2025-02-10 | 241 | >60 | April | 2025 | #REF!
Customer Channels | Customer Engagement | 90565151 | 2025-03-02 | Increase in Generic Error Pages & Decline in orders on Customer.com Website | Secure Auth improvement on Alerting/error metrics | Problem identification & Alerting | Simon Attard | 20/03: Action is still in progress 11/02: An updated was expected today ,however the owner of the actions in OOO and will be back on 24/02. 03/02: From the RCA provided by SecureAuth it appears they were unaware of any issue until it was raised with them via the ticket. Have they improved/added additional alerting to be aware of any issue on their side earlier? | Identity Team | Tactical | 28/03/25 |  | Open |  |  |  | Kavitha | 2025-02-10 | 241 | >60 | January | 1900 | 90+ Days
Customer Channels | Customer Engagement | 90565151 | 2025-03-02 | Increase in Generic Error Pages & Decline in orders on Customer.com Website | Check with Secure Auth whether it would be feasible to have a mechanism to force cache purge for an error being cached scenario | Problem avoidance | Simon Attard | 17/03: Feasibility of having cache purge was explored and confirmed to be closed 11/02: An updated was expected today ,however the owner of the actions in OOO and will be back on 24/02. 03/02:Enable some mechanism like automated cache refreshing/ forced cache purge if something like this goes wrong instead of waiting for 20 minutes. | Identity Team | Tactical | NA | 17/03/25 | Closed |  |  |  | Kavitha | 2025-02-10 | 241 | >60 | March | 2025 | #VALUE!
Customer Channels | Customer Engagement | 90565151 | 2025-03-02 | Increase in Generic Error Pages & Decline in orders on Customer.com Website | Confirming with Secure Auth whether a fix for this could have been deployed sooner than 24 hours | Problem avoidance | Simon Attard | 20/03: Action is still in progress 11/02: An updated was expected today ,however the owner of the actions in OOO and will be back on 24/02. 03/02:The issue could have reoccurred at any point between 27th–28th (As fix was applied on 28th). If the cause was known earlier, would it have been possible for Secure Auth to safely deploy sooner? And reduce the risk of a reoccurrence. | Identity Team | Tactical | 28/03/25 |  | Open |  |  |  | Kavitha | 2025-02-10 | 241 | >60 | January | 1900 | 90+ Days
Customer Channels | Customer Engagement | 90565151 | 2025-03-02 | Increase in Generic Error Pages & Decline in orders on Customer.com Website | Reduce Threshold time of alert | Problem identification & Alerting | Simon Attard | 17/03: The alerting threshold has been reduced 11/02: An updated was expected today ,however the owner of the actions in OOO and will be back on 24/02. 03/02: Reduce the threshold time / use anomaly-based alerts for any sudden spikes instead of fixed time thresholds to get earlier visibility of impacting issues | Identity Team | Tactical | NA | 17/03/25 | Closed |  |  |  | Kavitha | 2025-02-10 | 241 | >60 | March | 2025 | #VALUE!
Customer Channels | Customer Engagement | 90565151 | 2025-03-02 | Increase in Generic Error Pages & Decline in orders on Customer.com Website | Explore whether we can raise a ticket with vendor at an earlier time even if internal investigation isn’t fully complete | Supplier and support involvement | Simon Attard | 03/02 – The Aim of this action is to give earlier visibility of the issue to the vendor so they can check earlier whether there is any issue on their end.Identity team have discussed this action and will start to raise a ticket with secure Auth earlier going forward.. | Identity Team | Stragetic | NA | 2025-03-02 | Closed |  |  |  | Kavitha | 2025-02-10 | 241 | >60 | February | 2025 | #VALUE!
Customer Channels | Service Experience | TBC | 29/01/25 | Contact Center colleagues encountered intermittent performance degradation while handling emails | Improved Volume / Performance testing. | Problem avoidance | TTEC Jesse Beatty/Chris McGrath | 10/4: Emailed Simon at TTEC again for a material update 26/03: Emailed Simon for a more material update 12/03: Simon from TTEC advised: this remains the subject of ongoing collaboration between TTEC & Google. There are several actions underway and a full update will be provided to Customer on planned next steps by Friday of this week. Once this has been shared and actions agreed then we will be in a better position to provide you with a material update. Update 12/03 - Rehan has written to the relevant engineers at vendor TTEC for an update and await a response. TTEC to follow-up with Ujet/Google to ensure that Google/Ujet evidence Volume / Performance testing has been completed against clear targets with upper bounds. For example, the team can prove the platform can handle X throughput with Y performance. Platform has a performance ceiling of X. Customer throughput requirement are under that ceiling. | TCS Product Owner |  | 17/04/25 |  | Open |  |  |  | Rehan | 2025-02-10 | 246 | >60 | January | 1900 | #REF!
Customer Channels | Service Experience | TBC | 29/01/25 | Contact Center colleagues encountered intermittent performance degradation while handling emails | Improve Service Support model. | Problem avoidance | TTEC Simon Taylor/Chris McGrath | 10/4: Emailed Simon at TTEC again for a material update 26/03: Emailed Simon for a more material update 12/03: Simon from TTEC advised: this remains the subject of ongoing collaboration between TTEC & Google. There are several actions underway and a full update will be provided to Customer on planned next steps by Friday of this week. Once this has been shared and actions agreed then we will be in a better position to provide you with a material update. Update 12/03 - Rehan has written to the relevant engineers at vendor TTEC for an update and await a response. Initiate Continuous Service Improvement Plan to identify gaps and improvement actions with the current TTEC/Google/Uject model. | TCS Product Owner |  | 17/04/25 |  | Open |  |  |  | Rehan | 2025-02-10 | 246 | >60 | January | 1900 | #REF!
Customer Channels | Service Experience | TBC | 29/01/25 | Contact Center colleagues encountered intermittent performance degradation while handling emails | Improve monitoring and reporting. | Problem avoidance | TTEC Jesse Beatty/Chris McGrath | 10/4: Emailed Simon at TTEC again for a material update 26/03: Emailed Simon for a more material update 12/03: Simon from TTEC advised: this remains the subject of ongoing collaboration between TTEC & Google. There are several actions underway and a full update will be provided to Customer on planned next steps by Friday of this week. Once this has been shared and actions agreed then we will be in a better position to provide you with a material update. Update 12/03 - Rehan has written to the relevant engineers at vendor TTEC for an update and await a response. Liaise with Google to request additional (client-side) monitoring and reporting. | TCS Product Owner |  | 17/04/25 |  | Open |  |  |  | Rehan | 2025-02-10 | 246 | >60 | January | 1900 | #REF!
C&H and Intl | C&H and Intl Supply Chain | 90538790 | 2025-01-27 | Hand Held Terminal connectivity issues | Determination of Final Root Cause | Root Cause | paul.wallis@gxo.com | 26/03 - Statement from Richard Burrows suggesting closure - Given the business impact to Customer was minimal I’d suggest drawing this one to a close. I’d only really want to follow up if this was part of a wider period of ongoing disruption, but if it’s an isolated incident as it appears to be, then probably not much point. I suspect the impact to GXO of a central network issue will likely be considerably greater than the impact to Customer outlined below, so I’d work on the basis it’s being followed up by GXO internally Root cause - no further details will be provided: The issue was triggered by packet loss on the Virgin Media links at our Node4 DC. This issue was resolved with manual intervention due to the connected hardware going into a hung state. No further preventative action is possible in this specific scenario. 14-03-2025 - Node 4 have confirmed the issue was there end and a restart was required, however the details of the Root cause is unknown at this given point of time. 04-03-2025 - Follow up email sent to Paul looping Vivek, awaiting feedback on all action items The initial root cause was confirmed to be the network disturbance in the WAN due to which the Firewall blocked traffic. However, we do not have clarity if the issue was with the last mile Provider or the ISP. We also need to know what kind of disturbance created this service disruption. | GXO |  | NA | 26/03/25 | Closed |  |  |  | Balaji | 2025-02-10 | 248 | >60 | March | 2025 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90538790 | 2025-01-27 | Hand Held Terminal connectivity issues | Configure Proactive and enhanced observability/alerts to identify firewall issues within GXO landscape. | Problem identification & Alerting | paul.wallis@gxo.com | 26/03 - Statement from Richard Burrows suggesting closure - Given the business impact to Customer was minimal I’d suggest drawing this one to a close. I’d only really want to follow up if this was part of a wider period of ongoing disruption, but if it’s an isolated incident as it appears to be, then probably not much point. I suspect the impact to GXO of a central network issue will likely be considerably greater than the impact to Customer outlined below, so I’d work on the basis it’s being followed up by GXO internally. Update provided: There is monitoring on this solution, which assisted with the investigation. 14-03-2025 - As it is a 3rd party managed DC (Node 4) it took longer time to investigate than it would take for GXO to investigate. Details of the alert enhancement is yet to be shared. 04-03-2025 - Follow up email sent to Paul looping Vivek, awaiting feedback on all action items Paul from the GXO confirmed that there was no proactive monitoring. The GXO team is working with its Networking team to implement effective proactive monitoring | GXO |  | NA | 26/03/25 | Closed |  |  |  | Balaji | 2025-02-10 | 248 | >60 | March | 2025 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90538790 | 2025-01-27 | Hand Held Terminal connectivity issues | Investigate the cause of the network failover failure and evaluate the feasibility of a rapid failover to mitigate impact. Additionally, identify the quickest restoration process to minimize downtime in case of recurrence. | Solution & Recovery | paul.wallis@gxo.com | 26/03 - Statement from Richard Burrows suggesting closure - Given the business impact to Customer was minimal I’d suggest drawing this one to a close. I’d only really want to follow up if this was part of a wider period of ongoing disruption, but if it’s an isolated incident as it appears to be, then probably not much point. I suspect the impact to GXO of a central network issue will likely be considerably greater than the impact to Customer outlined below, so I’d work on the basis it’s being followed up by GXO internally 04-03-2025 - Follow up email sent to Paul looping Vivek, awaiting feedback on all action items The GXO team is working with its Networking team to gather information. | GXO |  | NA | 26/03/25 | Closed |  |  |  | Balaji | 2025-02-10 | 248 | >60 | March | 2025 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90538790 | 2025-01-27 | Hand Held Terminal connectivity issues | Investigate and implement other preventative actions to avoid recurrence. | Problem avoidance | paul.wallis@gxo.com | 04-03-2025 - Follow up email sent to Paul looping Vivek, awaiting feedback on all action items The GXO team is working with its Networking team to gather information. | GXO |  | NA | 26/03/25 | Closed |  |  |  | Balaji | 2025-02-10 | 248 | >60 | March | 2025 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90538790 | 2025-01-27 | Hand Held Terminal connectivity issues | GXO to assess whether there was a delay in engaging their ISP and identify necessary actions to prevent such delays in the future. | Supplier and support involvement | paul.wallis@gxo.com | There was not a delay in engaging, it is driven by 3rd party Node 4. 04-03-2025 - Follow up email sent to Paul looping Vivek, awaiting feedback on all action items Paul will share the feedback after consultation with GXO stakeholders. | GXO |  | NA | 2025-04-03 | Closed |  |  |  | Balaji | 2025-02-10 | 248 | >60 | March | 2025 | #VALUE!
Customer Channels | Customer Engagement | 90548919 | 27/01/25 | Customers unable to sign up in Mobile Apps | Review and enhance alerts configurations (including E2E tests alerts, customer journey user errors) | Problem identification & Alerting | Simon Attard | 27/01: A JIRA back log has been rasied to configure the alert | Identity Team | Tactical | NA | 27/01/25 | Closed |  |  |  | Kavitha | 2025-02-10 | 248 | >60 | January | 2025 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90538790 | 2025-01-27 | Hand Held Terminal connectivity issues | Assess the financial Impact | Issue handling/Management | paul.wallis@gxo.com | Paul confirmed that the financial Impact was £1,134 between 6:00 AM to 8:39 AM, as the working hours would start only at 6:00 AM. The approach used to determine the financial impact was also shared. | GXO |  | NA | 28/01/25 | Closed |  |  |  | Balaji | 2025-02-10 | 248 | >60 | January | 2025 | #VALUE!
Customer Channels | Customer Engagement | 90548919 | 27/01/25 | Customers unable to sign up in Mobile Apps | Enforce change control for any Production deployments | Problem avoidance | Ben Philip | 17/03:We are awaiting further updates from Sandhya on the CAB process 25/02: Follewed up with Priyabharath who is cordinating with CE colleagues for updates and awaiting response 27/01:Ben Phillips to advice on the change control process with all microservices changes | Identity Team | Tactical | 28/03/25 |  | Open |  |  |  | Kavitha | 2025-02-10 | 248 | >60 | January | 1900 | 90+ Days
Foods | Foods Supply Chain | 90537221 | 23/01/25 | Delay in Foods NDC allocations impacting operations | Liaise with business to take decision on any volume cap is required or provide required communication to DC and Ops whenever a stock intake activity is planned | Business & IT Communication | Valliammai Ramasamy/Lisy | 23/01: This action is valid until the stock activity process continues to remain the same. In addition, discussions are underway to perform the stock intake activity in smaller batches. | Relex/CSSM | Stragetic | NA | 31/01/25 | Closed |  |  |  | Kavitha | 2025-02-10 | 252 | >60 | January | 2025 | #VALUE!
Customer Channels | Platform & Store Ops | 90537221 | 23/01/25 | Delay in Foods NDC allocations impacting operations | Investigate further and confirm whether the stock intake and the resulting negative stock are within the expected limits. | Root Cause | Valliammai Ramasamy | 25/02: The extracts were generated for comparsion, considering how the reports generated we are unable to have like to like comparision to conclude that negative stocks are with in the thershold, hence closing this actions as we are unable to investigate further 05/02: Valli is still laising with Beam to extract the in required format for comparision 23/01: Compare the previous year's stock value and this year;s value and advise further | CSSM | Tactical | NA | 25/02/25 | Closed |  |  |  | Kavitha | 2025-02-10 | 252 | >60 | February | 2025 | #VALUE!
Foods | Foods Supply Chain | 90537221 | 23/01/25 | Delay in Foods NDC allocations impacting operations | How do we handle the impact to DC if the same scenario reoccurs? | Solution & Recovery | Matt/ Relex | 23/01: Tech to liaise with Business to align the DC to handle the capacity or add a constraint in Relex to handle the volume. These are the only two viable options to be considered by business. However, we have workaround of invoking contingency after securing business approval | Relex | Stragetic | NA | 31/01/25 | Closed |  |  |  | Kavitha | 2025-02-10 | 252 | >60 | January | 2025 | #VALUE!
Foods | Foods Supply Chain | 90537221 | 23/01/25 | Delay in Foods NDC allocations impacting operations | The stock intake activity is a usual activity. Why did it suddenly impact the NDC allocation volume? | Root Cause | Matt/Tamil | 23/01: We always had negative stocks, (drop in stock value). The only difference is the way in which Quantum and Relex handle stock and generate orders. | Relex | Tactical | NA | 31/01/25 | Closed |  |  |  | Kavitha | 2025-02-10 | 252 | >60 | January | 2025 | #VALUE!
Foods | Foods Supply Chain | 90537221 | 23/01/25 | Delay in Foods NDC allocations impacting operations | What caused the increase in NDC allocation volume? | Root Cause | Matt/Tamil | 23/01: A drop of 2M Ambient stock volume was observed in Relex resulting in generation of additional volume for Bradford and Milton Keynes NDCs after the stock take activity performed on 12/01. The stock loss is part of the stock take activity, and it is expected to change the stock position in the CSSM and downstream systems. | Relex | Tactical | NA | 31/01/25 | Closed |  |  |  | Kavitha | 2025-02-10 | 252 | >60 | January | 2025 | #VALUE!
GTS | Operations | 90531649 | 17/01/25 | Gift Card and Scan Tower operations impacted at X-Dock DCs (Gift Card, Westfield & Hydepark) | Document all the troubleshooting steps and actions taken during a major incident | Issue handling/Management | MIM/All | 17/01 - It has been agreed to document all the troubleshooting steps/actions taken during any triage. | MIM/All |  | NA |  | Closed | NA | NA | NA | Pavithra | 2025-02-10 | 258 | >60 | January | 1900 | #VALUE!
GTS | ETP- Connectivity,service & solution | 90531649 | 17/01/25 | Gift Card and Scan Tower operations impacted at X-Dock DCs (Gift Card, Westfield & Hydepark) | Perform an end-to-end validation, post any recovery actions on production | Problem avoidance | Ganesh Athivilli | 17/01 - During the incident, though the removal of IP from the routing table resolved one of the issues, it created another new incident. Therefore, every recovery action/troubleshooting step will be validated E2E, impacts assessed before we perform any changes in production. All the recovery actions related to a major incident will only be performed on a MIM call. | NOC |  | NA |  | Closed | NA | NA | NA | Pavithra | 2025-02-10 | 258 | >60 | January | 1900 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90531649 | 17/01/25 | Gift Card and Scan Tower operations impacted at X-Dock DCs (Gift Card, Westfield & Hydepark) | Review the alerts within Apigee/Scan towers | Problem identification & Alerting | Karthick GC/Deepika Velumani/WMS | 20/02 - Alerting has been there and the severity has been reviewed to address such issue on a timely basis 17/01 - Though we had the errors observed within Apigee since the IP removal, we need to understand the alert handling process within WMS. | WMS |  | NA | 20/02/25 | Closed | NA | NA | NA | Pavithra | 2025-02-10 | 258 | >60 | February | 2025 | #VALUE!
GTS | ETP- Connectivity,service & solution | 90531649 | 17/01/25 | Gift Card and Scan Tower operations impacted at X-Dock DCs (Gift Card, Westfield & Hydepark) | Explore the feasibility on alerting for routing issues within switches. | Problem identification & Alerting | Lokesh puruthosaman | 17/01 - This option, is not feasible with the current network setup. However, trace routes can help us identify issues within the routing mechanism. | NOC |  | NA |  | Closed | NA | NA | NA | Pavithra | 2025-02-10 | 258 | >60 | January | 1900 | #VALUE!
GTS | ETP-On premise services | 90527210 | 16/01/25 | Intermittent label printing issue at Ollerton DC on 07/01 | Confirm with Redhat if the issue was caused due to the bug in the kernel 7.9 version. | Root cause | Harish Kumar | Awaiting further updates from Redhat | Linux Team |  | 2025-04-03 |  | Open | NA | NA | NA | Saloni | 2025-02-10 | 259 | >60 | January | 1900 | 90+ Days
GTS | ETP-On premise services | 90527210 | 16/01/25 | Intermittent label printing issue at Ollerton DC on 07/01 | Review the alerting configuration to detect Linux cluster connectivity issues and enable proactive recovery of services before DCs report the issue. | Problem identification & Alerting | Harish kumar | 27/02: Proactive alerts are configured across all DCs which will report in case if there are any connection drops within the clusters. On the day of the issue, alerts were configured across all DCs to detect intermittent drops in the Linux clusters. A further review is planned to ensure the alerts are functioning as expected. | Linux Team |  | NA | 27/02/25 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 259 | >60 | February | 2025 | #VALUE!
GTS | ETP-On premise services | 90527210 | 16/01/25 | Intermittent label printing issue at Ollerton DC on 07/01 | Assess whether the patches were tested effectively before deployment in the production environment. | Problem avoidance | Harish Kumar | 27/02: Linux team have confirmed that there were no gaps in lower region testing., same version was applied in CATE and no issues reported. The patch was tested in the lower environment in early December, and thorough checks were performed across both the infrastructure and application layers, with no issues identified. As there is no configurational difference between the production and pre-production environments, and until the root cause is established, it has been concluded that there were no gaps in the testing process. | Linux Team |  | NA | 27/02/25 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 259 | >60 | February | 2025 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90527210 | 16/01/25 | Intermittent label printing issue at Ollerton DC on 07/01 | Devise a plan to revert the patches across Ollerton, Welham, Outlet, and CrossDock DCs to prevent further impact from the RedHat bug. | Problem avoidance | Nandakumar Sivalingam | 18/02: All redhat patches reverted by 1st week of Feb in the impacted DCs Red Hat has confirmed that a new version containing a fix for the existing bug will be released in March 2025. Consequently, the C&H Supply Chain team will coordinate with the business and DC Operations to secure a planned outage, ensuring the patch reversion is carried out in a controlled and systematic manner. | C&H Service Lead |  | NA | 18/02/25 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 259 | >60 | February | 2025 | #VALUE!
GTS | ETP-On premise services | 90527210 | 16/01/25 | Intermittent label printing issue at Ollerton DC on 07/01 | Review and enhance alerting on the Linux clusters to enable the proactive identification of restarts and ensure timely engagement of downstream teams (MQ, Mule, and application teams) to perform technical checks and mitigate any impact. | Problem identification & Alerting | Harish kumar/Jafar | 27/02: Alerting for cluster resource failure is in place - the Linux team will hereby publish it to wider audience if they come across similar issues Due to the existing Red Hat bug, which poses a risk of automatic cluster restarts and potential impact on DC operations, it has been agreed to review the alerting mechanisms to ensure proactive engagement of application teams for additional checks and to involve MIM if required. | Linux Team |  | NA | 27/02/25 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 259 | >60 | February | 2025 | #VALUE!
GTS | ETP-On premise services | 90527210 | 16/01/25 | Intermittent label printing issue at Ollerton DC on 07/01 | Enhance the post-checks across the application and infrastructure layers following any network activity to ensure comprehensive validation and timely issue identification. | Problem avoidance | All | It was agreed during the call that, although relevant checks were performed, a further review of the post-implementation checklist is necessary across all layers to ensure potential issues are identified promptly and business impact is minimised. | Linux Team/WMS |  | NA | 19/02/25 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 259 | >60 | February | 2025 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90527210 | 16/01/25 | Intermittent label printing issue at Ollerton DC on 07/01 | Explore options to configure alerts within the WMS layer to identify intermittent issues impacting DC operations. | Problem identification & Alerting | Nandakumar Sivalingam | An hourly report is generated within the WMS landscape that highlights drops in label printing counts. However, as carrier label printing is a real-time, DC-oriented function, it is not feasible to configure alerts for intermittent scenarios. | C&H Service Lead |  | NA | 19/02/25 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 259 | >60 | February | 2025 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90528545 | 15/01/25 | Stores unable to book in some parcels shipped from Ollerton DC | Conduct a workshop with DC colleagues to ensure orders are systemically shipped and identify any other potential challenges causing delays in the shipment process. | Problem Avoidance | Davies, Mark | 29/01: Mark confirmed that a workshop was conducted with experienced colleagues of Thorncliffe to teach/enforce the correct process to the Ollerton colleagues as part of the standard order management within WMS last week and appropriate SOPS were updated within Ollerton. Hence, closing the action. 15/01: The service lead will collaborate with site operations to ensure orders are being shipped systemically, preventing further “Awaiting Dispatch” scenarios. | Service Lead |  | NA | 29/01/25 | Closed | NA | NA | NA | Gokul | 2025-02-10 | 260 | >60 | January | 2025 | #VALUE!
Customer Channels | Service Experience | 90528545 | 15/01/25 | Stores unable to book in some parcels shipped from Ollerton DC | Streamline the process within Ops to ensure that any issues follow a structured process for timely identification, investigation, and recovery. | Problem Identification & Alerting | Crowe, Andrew | 19/02: As this group chat is helping in addressing daily operational issues and addressing those scenarios. Also, WMS and Store Ops Service Leads are working on SOP for the same. Hence, closing this action. 11/02: There is an existing active group chat "Awaiting Dispatch process alignment OMS > WMS" across all DC's, WMS and OMS teams. Regularly this is being monitored and actions assigned to specific owners by Andrew. But, we need to check if the actions are being done. 04/02: Have followed up on the action with Andrew 29/01: Have checked with Andrew on the status of the structured process 15/01: A clear, structured process will be defined to ensure that when issues arise, they are identified promptly, and the necessary technical investigations and recovery actions are initiated without delays | OMS |  | NA | 19/02/25 | Closed | NA | NA | NA | Gokul | 2025-02-10 | 260 | >60 | February | 2025 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90528545 | 15/01/25 | Stores unable to book in some parcels shipped from Ollerton DC | Continue investigation into potential scenarios causing ASN failures from WMS to OMS. | Root Cause | Velumani, Deepika; Kumar, Vipin | 19/02: No more scenarios in the last 1 week, hence closed 11/02: All newly identified scenarios have been fixed and there is an existing group chat "Awaiting Dispatch process alignment OMS > WMS" across all DC's, WMS and OMS teams. For 1 more week, scenarios will be monitored and in case there are none. This action will be set to closed. 03/02: Vipin updated that OMS has already provided all failures with reasons to WMS to work on fixes, awaiting further updates from Deepika. 29/01: Have followed up with Deepika and Vipin on the status of the action. 15/01: A thorough investigation will be conducted to identify any additional scenarios or defects contributing to the ASN failure, and to determine appropriate fixes. | WMS/OMS |  | NA | 19/02/25 | Closed | NA | NA | NA | Gokul | 2025-02-10 | 260 | >60 | February | 2025 | #VALUE!
Customer Channels | Platform & Store Ops | 90528545 | 15/01/25 | Stores unable to book in some parcels shipped from Ollerton DC | Explore the feasibility of assigning a location for parcels in store through the unexpected parcel function. | Solution & Recovery | Ramasamy, Valliammai/ Vipin Kumar | 31/03: Anu and Vipin are in discussion on the best approach for addressing the action 18/03: Valli is in discussion with Anu and Vipin on raising the backlog 05/03: Valli agreed to check the backlog creation from the TPM of the team which owns the device for parcel scanning and providing location 26/02: Awaiting for backlog from Vipin. 13/02: Valli & Vipin, agreed in the call that Digital Ops team need to address it. Vipin to raise a backlog. 11/02: Vipin suggested it to be raised by Valli to the product manager. Have scheduled a call by 13/02 to discuss further on it. 03/02: Valli updated based on her discussion with collect app team that unexpected parcels can never be assigned with location as per .com+ application on it. Hence, discussing with OMS team to understand further on it. 15/01: During the issue, stores were advised to follow the unexpected parcel scenario, but no location was assigned, making it difficult for store colleagues to locate the parcels. Valli to coordinate this action with the relevant team. | Service Lead |  | 2025-03-04 |  | Open | NA | NA | NA | Gokul | 2025-02-10 | 260 | >60 | January | 1900 | 90+ Days
C&H and Intl | C&H and Intl Supply Chain | 90528545 | 15/01/25 | Stores unable to book in some parcels shipped from Ollerton DC | Establish an effective and stringent process to handle the Awaiting Dispatch scenarios on a daily basis to prevent impact to the stores. | Solution & Recovery | Sivalingam, Nandakumar Ramasamy, Valliammai | 10/03: Deepika confirmed that the actions have been automated to create incidents. 26/02: We spoke to Nirmal and ensured that the product teams are documenting the process and working to make it automated with help of Kunal and Ivan. 14/02: Valli confirmed that to streamline the process, this needs to be discussed with WMS team and Nanda and documented. 11/02: Have scheduled a call by 13/02 to discuss further on it. 03/02: Have reached out to Valli and Nanda to understand the status of the action. Note: There is an existing group chat "Awaiting Dispatch process alignment OMS > WMS" across all DC's, WMS and OMS teams. This group chat is to address the daily ASN failures with the corresponding owners. 15/01: While there is an existing Teams chat including relevant stakeholders from WMS, OMS, RetailOps, and DotcomOps for addressing daily issues with the Awaiting Dispatch scenario, a more structured process needs to be implemented. This will ensure that daily issues highlighted by DCs or stores are resolved in a timely manner, avoiding future major incidents and minimising impact to store operations and customer experience. | Service Lead |  | NA | 2025-10-03 | Closed | NA | NA | NA | Gokul | 2025-02-10 | 260 | >60 | March | 2025 | #VALUE!
Customer Channels | Service Experience | 90528545 | 15/01/25 | Stores unable to book in some parcels shipped from Ollerton DC | Extract daily reports from the store Honeywells or the collection database to identify unexpected parcels across stores for proactive identification and determination of the next course of action. | Problem Identification & Alerting | David Gillard | 27/02: Backlog CRSO-265 is raised in Jira cloud 18/02: Anu Narayanan and Valli updated that this action is being addressed as part of Jira CRSO-1439 (Collect Parcel Scanning App - Unexpected Parcels) and a new epic will be created by prioritisation in jira cloud. 11/02: Vipin advised that the Retail Ops team would have better visibility on the stats of the "unexpected parcels" error and can fetch a report regularly and identify them. Have scheduled a call by 13/02 to discuss further on it. 04/02: David updated that "Collection DB maynot have this data as store will not be able to book the parcel in. Retail apps may have some reporting, but it would likely only show you the total volume of unexpected error events on a given day for a store, not the specific parcels. I think the most likely source for any proactive reporting would be the order management system". But upon checking with Tamil/OMS team, as this status appears in honeywells when store colleague scans the parcel, only honeywell teams should be able to fetch them. 15/01:By tracking the unexpected parcel volume at stores, we can proactively identify any underlying defects causing issues. This will enable timely actions to be taken, helping to prevent further impact to store operations and improving issue resolution efficiency. | Product Manager |  | NA | 27/02/25 | Closed | NA | CRSO 265 | NA | Gokul | 2025-02-10 | 260 | >60 | February | 2025 | #VALUE!
Customer Channels | Service Experience | 90528545 | 15/01/25 | Stores unable to book in some parcels shipped from Ollerton DC | Improve the automated regression tests around the WMS system to make sure that future changes don't introduce defects to these interface | Problem Avoidance | Velumani, Deepika;Kumar, Vipin | 11/02: Deepika confirmed that the scenarios have been added to the WMS regression test packs. 29/01:Vipin updated that the action lies with WMS to action and nothing from OMS as these interfaces are already part of OMS regression suite. Have followed up with Deepika on the status of the action. 15/01: The OMS team is actively working on automating regression tests, including the interfaces to and from OMS, to ensure that any changes do not introduce new defects. Additionally, the WMS team will assess the feasibility of implementing automated regression testing within the WMS environment to further enhance system stability. | WMS/OMS |  | NA | 2025-11-02 | closed | NA | NA | NA | Gokul | 2025-02-10 | 260 | >60 | February | 2025 | #VALUE!
Customer Channels | Platform & Store Ops | 90474650 | 2025-10-01 | Customers encountering "Sorry, Something Went Wrong" errors on Customer.com website | Explore changes to store the Auth Session into Browser Session Storage to reduce the number of requests and therefore reduce error rate. | Problem avoidance | Onyx Web Platform Team | 10/01:The changes to store the Auth Session into Browser Session. Storage to reduce the number of requests and therefore reduce error rate. Is tracked under the GITHUB ticket-24791 | Onyx Web Platform Team | Stragetic | NA | 2025-10-01 | Closed |  |  |  | Saloni | 2025-02-10 | 265 | >60 | January | 2025 | #VALUE!
Customer Channels | Platform & Store Ops | 90474650 | 2025-10-01 | Customers encountering "Sorry, Something Went Wrong" errors on Customer.com website | Implement Onyx Auth Error Page so that control of the errors and monitoring of it remains within the teams contro | Solution & Recovery | Onyx Web Platform Team | 10/01: The error control monitoring will be implemented and is tracked under GITHUB ticket -24711 | Onyx Web Platform Team | Stragetic | NA | 2025-10-01 | Closed |  |  |  | Saloni | 2025-02-10 | 265 | >60 | January | 2025 | #VALUE!
Customer Channels | Platform & Store Ops | 90474650 | 2025-10-01 | Customers encountering "Sorry, Something Went Wrong" errors on Customer.com website | Revert the AuthSessionProvider changes which were made during the incident but did not show any improvement | Solution & Recovery | Onyx Web Platform Team | 10/01: The change performed during the incident has been reverted | Onyx Web Platform Team | Stragetic | NA | 2025-10-01 | Closed |  |  |  | Saloni | 2025-02-10 | 265 | >60 | January | 2025 | #VALUE!
Customer Channels | Platform & Store Ops | 90474650 | 2025-10-01 | Customers encountering "Sorry, Something Went Wrong" errors on Customer.com website | Long term fix for the issue to aid the customer when they encounter the something went wrong error page | Permanent Fix | Onyx Web Platform Team | 10/01: The long term fix is being tracked under the GITHUB ticket -24928 | Onyx Web Platform Team | Stragetic | NA | 2025-10-01 | Closed |  |  |  | Saloni | 2025-02-10 | 265 | >60 | January | 2025 | #VALUE!
Customer Channels | Selling Experience | 90519981 | 2025-10-01 | Digital Cafes unable to serve customers due to an error on the kiosks | Agree with Counter Solution on a more defined and strict change management process to prevent similar issues in the future. | Problem avoidance | Avalon Smith/ CS | 10/01 - Counter Solutions have committed to a stricter adherence to the agreed process. Moving forward, CS will require a formal sign-off email from Customer before proceeding with any changes. If the sign-off is not received, the changes will not be implemented and will need to be rescheduled. Additionally, Customer will be required to review and validate all key elements, including 3-day parts - AM breakfast menus, PM lunch menus, and PM afternoon menus, and provide written sign-off via email to the Counter Solutions Project Services Team. These steps have been agreed upon by all relevant stakeholders, with new milestone dates established for the phase change final cut-off and the phase change final sign-off. | Digitial café product Team |  | NA | 29/01/24 | Closed | NA | NA | NA | Pavithra | 2025-02-10 | 265 | >60 | January | 2024 | #VALUE!
Customer Channels | Selling Experience | 90519981 | 2025-10-01 | Digital Cafes unable to serve customers due to an error on the kiosks | Ensure that the lead times for the menu phases (a.m. breakfast, p.m. lunch, and p.m. afternoon) are considered during the testing of any changes | Problem avoidance | Counter solutions/Digital café product team | 10/01 - As the menus operate in three distinct phases—AM morning, PM lunch, and PM afternoon—it has been agreed that the lead times for each phase will be factored into the testing process to ensure that changes function correctly across all menu periods | Digitial café product Team |  | NA | 29/01/24 | Closed | NA | NA | NA | Pavithra | 2025-02-10 | 265 | >60 | January | 2024 | #VALUE!
Customer Channels | Selling Experience | 90519981 | 2025-10-01 | Digital Cafes unable to serve customers due to an error on the kiosks | Establish an escalation process within DN, particularly for out-of-office hours. | Supplier and support involvement | Laura Whittle | 10/01 - A dedicated point of contact has been identified to provide support during out-of-office hours. The service lead and product teams have been informed to contact this individual for assistance during future incidents. | Service Lead |  | NA | 29/01/24 | Closed | NA | NA | NA | Pavithra | 2025-02-10 | 265 | >60 | January | 2024 | #VALUE!
Customer Channels | Selling Experience | 90519981 | 2025-10-01 | Digital Cafes unable to serve customers due to an error on the kiosks | Evaluate the feasibility of configuring an alert within Counter Solutions to proactively detect issues before stores report them. | Problem identification & Alerting | DN/CS | 18/02 - The required additonal alerting has been put in place and we believe this should help us proactively identify the issue before impacting the stores. 10/01- CounterSolutions will explore options to implement an alerting mechanism to identify system issues in a timely manner. | Counter Solutions |  | NA | 20/01/25 | Closed | NA | NA | NA | Pavithra | 2025-02-10 | 265 | >60 | January | 2025 | #VALUE!
Foods | Foods Supply Chain | 90501176 | 2025-09-01 | Understated frozen allocations impacting Bedworth site operations | Develop an SOP for invoking the contingency plan for frozen allocations. | Solution & Recovery | Tamilenbakumar K | 29/01:SOP has been created to handle the contigency allocation for Frozen, This can be closed. 26/01: Have checked with Tamil on the status of the action. 09/01: The teams are actively working to document the necessary steps to ensure the contingency plan can be executed promptly, minimizing delays in incident recovery. | FOAL |  | NA | 29/01/25 | Closed | NA | NA | N/A | Gokul | 2025-02-10 | 266 | >60 | January | 2025 | #VALUE!
Foods | Foods Supply Chain | 90501176 | 2025-09-01 | Understated frozen allocations impacting Bedworth site operations | Configure alerts to identify over- or under-allocations for frozen products. | Problem identification & Alerting | Gurwinder Singh | 04/02: We have now added reporting which allows us to check high and low allocations for frozen. 26/01: Have checked with Tamil on the status of the action. 09/01:Teams to review the existing alerting for frozen products | Relex |  | NA | 2025-04-02 | Closed |  |  |  | Gokul | 2025-02-10 | 266 | >60 | February | 2025 | #VALUE!
Foods | Foods Supply Chain | 90501176 | 2025-09-01 | Understated frozen allocations impacting Bedworth site operations | Constraint functionality to be implemented for Frozen | Permanent Fix | Gurwinder Singh | 04/02: backlog ID. FOATR-23206 26/01: Have checked with Tamil on the status of the action. 09/01:It is already being worked upon with a backlog. Relex to share the backlog id | Relex |  | NA | 2025-04-02 | Closed |  | FOATR-23206 |  | Gokul | 2025-02-10 | 266 | >60 | February | 2025 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90523891 | 2025-08-01 | Clustering issues at Ollerton DC after Linux OS patching | The issue at Ollerton DC was first reported at 2:00 PM, but the MIM was not engaged until 4:30 PM. Investigate the reasons for the delay in MIM engagement. | Issue handling/Management | Girichandramohan, Karthick | After the completion of the activity, post-checks by the technical teams did not identify any issues in WMS. Since the site was clustering the previous day’s orders, the issue was not observed or highlighted until 2:00 PM. Once the issue was reported, the WMS team began performing initial recovery actions as part of their SOP, which contributed to the delay in informing the MIM. It has now been agreed that MIM will be informed promptly as soon as any site identifies and highlights any impact. | WMS |  | NA | 2025-07-01 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 267 | >60 | January | 2025 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90523891 | 2025-08-01 | Clustering issues at Ollerton DC after Linux OS patching | Review the IODM/ implementation plan to include additional validation steps especially on the job release process whilst planning changes. Review the escalation metrics to ensure that the change is completed within the agreed time window. | Solution & Recovery | Girichandramohan, Karthick ; Selvaraj, Jeevanandhan | 27/02: A workshop was conducted to adhere to the process of mentioning job folder names in the change along with user held jobs to ensure errorneous jobs are not being triggered. Also, an action was performed to disable all user held jobs from schedulling to avoid this issue in future, It has been agreed that the job folder name will be mentioned in the implementation plan, however, application team to effectively indicate the user held jobs should not be released after the activity. The escalation matrix will be reviewed to engage relevant SMEs for faster recovery and avoid delays in handing over to site operations. | WMS and Infra |  | NA | 27/02/25 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 267 | >60 | February | 2025 | #VALUE!
GTS | Operations | 90523891 | 2025-08-01 | Clustering issues at Ollerton DC after Linux OS patching | Enhance PCM SOP to include additional validation step whilst releasing job folders during an activity | Solution & Recovery | Priya, karthika | It has been agreed that PCM will review the jobs in user held status before releasing a job folder during an activity. | PCM |  | NA | 2025-07-01 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 267 | >60 | January | 2025 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90523891 | 2025-08-01 | Clustering issues at Ollerton DC after Linux OS patching | Disable the scheduling of User held jobs in WMS within Control-M to prevent them from being released during an activity. | Permanent Fix | Girichandramohan, Karthick | 26/02: All thr 150 jobs have been disabled from being scheduled to avoid incorrect scheduling after any activity. There are ~150 jobs across 10 DCs which have been kept in prolonged user held status. This will ensure that these jobs are not inadvertently triggered or impacted during the change | WMS |  | NA | 26/02/25 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 267 | >60 | February | 2025 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90523891 | 2025-08-01 | Clustering issues at Ollerton DC after Linux OS patching | Propose a solution to ensure that, for any future jobs requiring prolonged User held status, they are disabled in Control-M to prevent inadvertent job releases | Permanent Fix | Girichandramohan, Karthick | It has been agreed to disable any newly created jobs in Control-M requiring prolonged user-held status during maintenance or change activities. The SOP will be updated in accordance with the process. | WMS |  | NA | 2025-07-01 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 267 | >60 | January | 2025 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90523891 | 2025-08-01 | Clustering issues at Ollerton DC after Linux OS patching | Determine the root cause of the generation of multiple list IDs and assess whether the inadvertent release of the order priority assignment job led to a cascading impact, resulting in the creation of multiple list IDs. | Root Cause | Girichandramohan, Karthick | 20/03: Though the control jobs were disabled , Multiple list id were created due to older Move task data. In future, SOP were updated to clear the cache or older move task data before disabling the Control M Job The architects are being involved to identify the cause behind the multiple list id generation. | WMS |  | NA | 20/03/25 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 267 | >60 | March | 2025 | #VALUE!
GTS | ETP-On premise services | 90523891 | 2025-08-01 | Clustering issues at Ollerton DC after Linux OS patching | Develop a comprehensive checklist across both the infrastructure and application layers to be followed diligently post-change completion. | Solution & Recovery | Selvaraj, Jeevanandhan | 20/03: Application end checklist ready and shared. This action towards infra to submit their checklist. Please change the owner accordingly This checklist ensures that both infrastructure and application layers are thoroughly validated, focusing on connectivity, system health, and critical site operations to minimize any impact on site performance. Also, this should be documented as part of the change implementation. | WMS and Infra |  | 2025-03-03 |  | Open | NA | NA | NA | Saloni | 2025-02-10 | 267 | >60 | January | 1900 | 90+ Days
GTS | ETP-On premise services | 90523891 | 2025-08-01 | Clustering issues at Ollerton DC after Linux OS patching | Extract a list of all jobs held in User held status for prolonged durations in Control M which requires additional actions during activities across the products/applications. | Problem Avoidance | Malaiyandi, Sathya | Control M team will coordinate with the product teams to highlight the user held jobs and agree on a process to disable them to avoid manual errors during any job release process after an activity | Control M\SMT |  | NA | 20/03/25 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 267 | >60 | March | 2025 | #VALUE!
GTS | ETP-On premise services | 90523891 | 2025-08-01 | Clustering issues at Ollerton DC after Linux OS patching | Assess the feasibility of enhancing IGNIO tool to automatically release jobs after checking for user-held jobs to avoid manual interventions | Problem Avoidance | Malaiyandi, Sathya | The option to enhance Ignio is currently being explored. Note: Ignio automation is enabled for standalone server for patching activity. A separate activity is ongoing to allow the automation option for clustered servers - awaiting a backlog id. | Control M\SMT |  | 2025-10-04 |  | Open | NA | NA | NA | Saloni | 2025-02-10 | 267 | >60 | January | 1900 | 90+ Days
C&H and Intl | C&H and Intl Supply Chain | 90484323 | 19/12/24 | Stores receiving C&C parcels for future collection dates causing capacity constraint | Implement appropriate monitoring to ensure that the hold rule is actually working for Ollerton and Thorncliffe in the most efficient manner for stores - once the permanent solution is in place, review the monitoring and ensure it remains fit for purpose.` | Problem identification & Alerting | Sukaityte, Ugne; Girichandramohan, Karthick | Its been a month since the solution was amended in production with appropriate dashboard monitoring 06-Feb-2025 - Karthik is OOO, reached out to Ugne for update. 13-Jan-2025 - Reminder Initiated regarding the action Item to Karthik. 06-Jan-2025 - Followed up with Girichandramohan, Karthick and awaiting response 19-Dec-2024 - GC will liaise with the WMS architects to configure the appropriate alerting & monitoring mechanisms. | WMS TPM |  | NA | 25/02/25 | Closed |  |  |  | Balaji | 2025-02-10 | 287 | >60 | February | 2025 | #VALUE!
Customer Channels | Customer Engagement | 90484323 | 19/12/24 | Stores receiving C&C parcels for future collection dates causing capacity constraint | We were notified of the issue far too late when the stores were already struggling to cope. During the incident it was challenging to appreciate the impact in terms of how many parcels were sent out, how many awaiting collection, how many have been collected etc and how many collection point each store had, what was their cap. We need a front end dashboard to provide this information. | Impact analysis | Valliammai Ramasamy | Completed - 02-02-2025 - JIRA Backlog https://jira-marksandspencer-app.atlassian.net/browse/JDATE-92 Backlog created. 13-Jan-2025 - followed up with Valli, she advised that a front end dashboard has to be build and the Product team will be working on it, Once the Backlog ID is created it will be shared. PM has already requested to expedited as it is already 4 weeks. 19-Dec-2024 - This is in progress by navigating multiple application database | Retail Service Lead |  | NA | 2025-02-02 | Closed |  |  |  | Balaji | 2025-02-10 | 287 | >60 | February | 2025 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90484323 | 19/12/24 | Stores receiving C&C parcels for future collection dates causing capacity constraint | Review the delivery date -2 for bank holidays, and other retail events to ensure it remain fit for purpose or amend if required. | Solution & Recovery | Coy, Martin; Vasan, Pragadeesh | Completed - 02-Jan-2025 - This delivery date -2 is implemented in production during Dec'24 and the solution is working as expected. 19-Dec-2024 - This will be planned after the Golden Quarter to mitigate store impact for next year | WMS TPM |  | NA | 2025-02-01 | Closed |  |  |  | Balaji | 2025-02-10 | 287 | >60 | January | 2025 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90484323 | 19/12/24 | Stores receiving C&C parcels for future collection dates causing capacity constraint | Implement appropriate monitoring to ensure that the hold rule is actually working for all CD in the most efficient manner for stores - once the permanent solution is in place, review the monitoring and ensure it remains fit for purpose.` | Problem identification & Alerting | Pragadesh vasan | Permanent Solution: 25-02-2025 [JDATE-5] Ship by date calculation logic change for DRL - Small store hold - Jira 06-Feb-2025 - Reached out to Pragedeesh to confirmed if the final solution is finetuned as per the previous update. 02-Jan-2025 - It’s been a month since the solution was amended in production with appropriate dashboard monitoring. Permanent solution is yet to be fine-tuned along with Architects, WMS and OMS teams to develop a solution. 19-Dec-2024 - Praga will liaise with the WMS architects to configure the appropriate alerting & monitoring mechanisms. | WMS TPM |  | NA | 25/02/25 | Closed |  |  |  | Balaji | 2025-02-10 | 287 | >60 | February | 2025 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90484323 | 19/12/24 | Stores receiving C&C parcels for future collection dates causing capacity constraint | How can we fix the issue permanently so that the lead time for delivery is much more realistic and manageable? | Permanent Fix | Kunal Chickar | Permanent Solution: 25-02-2025 [JDATE-5] Ship by date calculation logic change for DRL - Small store hold - Jira 06-Feb-2025 - Kunal confirmed that the solution roll-out will only be a part of the next quarter and the solution details is yet to be shared. They are yet to create a change request. 09-Jan-2025 - The permanent solution is agreed and will be implemented in coming quarters. The details on the actual fix is yet to be shared. 19-Dec-2024 - Kunal has agreed to arrange and lead the discussion with architects to come to a proposal | WMS Devops |  | NA | 25/02/25 | Closed |  |  |  | Balaji | 2025-02-10 | 287 | >60 | February | 2025 | #VALUE!
GTS | ETP- Connectivity,service & solution | 90281344 | 18/12/24 | Central network connectivity issue impacting various services | Investigate the latency issues during inter-site transfers between the Stockley Park and Swindon data centers, as well as between the Stockley Park and Swindon firewalls with Vodafone. | Solution & Recovery | Kamalakkanan Kaniappan | 13/03 - This action now depends on the SP exit and will be tracked under that project as by July SP will not exisit so we need to make sure there is no latency between SW and Prologis Park. During the incident, it was noted that while the inter-site links were not over-utilized, there were signs of latency for traffic between the data centers. The network team worked with Vodafone to investigate, but no issues were identified. A long-term action has been agreed upon with Vodafone to review the architecture, and this will be tracked as part of the Stockley Park exit plan. Requires a backlog id. | Network |  | NA | 13/03/25 | Closed |  |  |  | Saloni | 2025-02-10 | 288 | >60 | March | 2025 | #VALUE!
GTS | ETP- Connectivity,service & solution | 90281344 | 18/12/24 | Central network connectivity issue impacting various services | Conduct a comprehensive review of the monitoring setup for the Stockley Park firewall. Streamline the identification of usual and unusual metrics and implement appropriate alert configurations to ensure timely detection and response | Problem identification & Alerting | Kamalakkaanan Kaniappan | 10/04: Spoke with Kamal and he will look at the trends that have emerged by early next week. 13/03 - kamal has advised that the network team need more time to establish a trend/pattern as the estate is currently undergoing significant change. Kamal has asked for a couple more weeks to establish a trend benchmark upon which alerts can be configured The Dynatrace rollout was conducted in phases, starting on the 18/09 and completed by the 20/09. It was expected that the gradual increase in the number of sessions on the firewall would lead to a CPU spike. However, this was not identified prior to the incident. Therefore, the network team will baseline CPU utilisation on the firewalls and configure alerts to proactively identify any potential issues. | Network |  | 17/04/25 |  | Open |  |  |  | Saloni | 2025-02-10 | 288 | >60 | January | 1900 | 90+ Days
Customer Channels | Service Experience | 90281344 | 18/12/24 | Central network connectivity issue impacting various services | Streamline the process to align architectural design with the implementation plan, minimizing conflicts. Incorporate network checks as part of the process to validate application functionality and ensure it aligns with the planned architecture. | Problem avoidance | Shikhar Khanna/ Lokesh Purushothaman | 31/03 - Kamal has advised that the Customer archtechtural review design team will take care of this | Network/ Retail TEM |  | NA | 13/03/25 | Closed |  |  |  | Saloni | 2025-02-10 | 288 | >60 | March | 2025 | #VALUE!
GTS | ETP- Connectivity,service & solution | 90281344 | 18/12/24 | Central network connectivity issue impacting various services | Regarding the C&H Bradford carrier label printing issue, when cloud connect traffic was enabled through Swindon, it was expected that the carrier gateway traffic would automatically fail over to Swindon. Further investigations need to be conducted to determine why this automatic failover did not occur as anticipated | Solution & Recovery | Kamalakannan Kanniappan | 13/03 - This action now depends on the SP exit and will be tracked under that project as by July SP will not exisit - when we do the cloud failover testing we should make sure it works between SW and Prologis Park. Action to be passed to Rajesh Srinnivasan for SP exit. | Network |  | NA | 13/03/25 | Closed |  |  |  | Saloni | 2025-02-10 | 288 | >60 | March | 2025 | #VALUE!
Customer Channels | Service Experience | 90281344 | 18/12/24 | Central network connectivity issue impacting various services | Determine whether a rollback plan was in place for the Dynatrace installation to address potential issues during the scenario. | Solution & Recovery | Shikhar Khanna | Although a rollback plan was in place for the Dynatrace installation, the change was not initially identified as the cause of the incident. As a result, no decision was made to execute the reversion. | Retail TEM |  | NA | 18/12/24 | CLosed |  |  |  | Saloni | 2025-02-10 | 288 | >60 | December | 2024 | #VALUE!
GTS | Operations | 90281344 | 18/12/24 | Central network connectivity issue impacting various services | Extract a report detailing all changes "completed" within the 48 hours and "in progress" changes within the estate preceding an incident | Problem identification & Alerting | Dinesh Malaroutu | This is an established process within the Service Management team to provide a report of all changes to the relevant product team for thorough review and to rule out any potential causes. The importance of adhering to this process has been reiterated to all team members, as it aids in identifying the root cause of incidents and facilitates faster recovery. | SM lead |  | NA | 18/12/24 | CLosed |  |  |  | Saloni | 2025-02-10 | 288 | >60 | December | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90281344 | 18/12/24 | Central network connectivity issue impacting various services | During the incident, the recovery was delayed at Donginton as one individual CDIT colleague had to manually go around rebooting PAC Benches and clearing caches. To prevent such delays in the future, an on-site rota should be published to ensure the CDIT team is available for immediate response during major incidents requiring on-site support. | Issue handling/Management | Murali Srinivasan | A constructive onsite rota has been published for CDIT support to provide appropiate support during major incidents | C&H Service Lead |  | NA | 18/12/24 | Closed |  |  |  | Saloni | 2025-02-10 | 288 | >60 | December | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 90281344 | 18/12/24 | Central network connectivity issue impacting various services | There was latency at the pack benches in Donington after the internet traffic was switched to Swindon, while cloud connect traffic remained at Stockley Park. This latency occurred because the internet traffic needed to traverse the Swindon and Stockley Park firewall through the intersite link to access the internet, increasing the number of sessions and overall bandwidth utilisation. The next step is to identify and analyse bandwidth utilization on the intersite link to validate this finding. | Solution & Recovery | Kamalakannan Kanniappan | 13/03 - This action now depends on the SP exit and will be tracked under that project as by July SP will not exisit - when we do the cloud failover testing we should make sure it works between SW and Prologis Park. Action to be passed to Rajesh Srinnivasan for SP exit. To begin after GQ as product teams are engaged in remediating the security risk within the FGT infrastructure across the estate | Network |  | NA | 13/03/25 | Closed |  |  |  | Saloni | 2025-02-10 | 288 | >60 | March | 2025 | #VALUE!
GTS | ETP- Connectivity,service & solution | 90281344 | 18/12/24 | Central network connectivity issue impacting various services | Identify the root cause of the issue with the three PSO pack benches not functioning when the Internet and Cloud Connect were switched to Swindon. | Solution & Recovery | Kamalakannan Kanniappan | It has been confirmed that enabling traffic through Swindon is not feasible, as it requires a full traffic failover, which is not desirable during the Golden Quarter. Consequently, this action has been closed. | Network |  | NA | 18/12/24 | Closed |  |  |  | Saloni | 2025-02-10 | 288 | >60 | December | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90281344 | 18/12/24 | Central network connectivity issue impacting various services | During the issue, most pack benches were operational after the internet and Cloud Connect traffic were switched to Swindon. However, three PSO pack benches required a manual workaround, necessitating the provision of a direct URL for access. To understand why this workaround was needed, identify the differences between the standard Pack benches and the PSO pack benches at Donington. This comparison will help clarify the specific requirements or configurations that led to the need for manual intervention. | Solution & Recovery | Kapil Shinde | [JDATE-91] PIR Action - Central network connectivity issue impacting various services - has been raised for this action. | Architect (WMS) |  | NA | 21/02/25 | Closed |  |  |  | Saloni | 2025-02-10 | 288 | >60 | February | 2025 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90281344 | 18/12/24 | Central network connectivity issue impacting various services | There is an existing architectural diagram for the Blue Yonder JDA application used in the pack benches at Donington. Review the existing architecture diagram and update it to include all relevant infrastructure elements, including network components, to support efficient troubleshooting in future instances | Solution & Recovery | Pragadesh vasan | [JDATE-91] PIR Action - Central network connectivity issue impacting various services - has been raised for this action. | CD TPM |  | NA | 21/02/25 | Closed |  |  |  | Saloni | 2025-02-10 | 288 | >60 | February | 2025 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90281344 | 18/12/24 | Central network connectivity issue impacting various services | The WMS team reported observing network timeouts that contributed to the latency at the pack benches. To validate this, review the Dynatrace logs in the WMS, which indicate network timeout errors, to confirm the cause of the latency. | Problem identification & Alerting | Kapil Shinde | [JDATE-91] PIR Action - Central network connectivity issue impacting various services - has been raised for this action. | Architect (WMS) |  | NA | 21/02/25 | Closed |  |  |  | Saloni | 2025-02-10 | 288 | >60 | February | 2025 | #VALUE!
GTS | ETP- Connectivity,service & solution | 90435629 | 2024-10-12 | Castle Donington - Users unable to access internet/ applications through 'SALINA' network | As part of a work around a policy was applied to route the traffic to London 5 (Primary) and Manchester 1 (Secondary) Data Centre to restore services on 22/11. We need to move everyone back to the dynamic policy and off the work around. | Solution & Recovery | Kamal | 13/03 - Completed 27/02 - I have spoke with kamal and he has advised that this has not been done and he is targeting netweek to do this under a focussed change. | Network |  | NA | 13/03/25 | Closed |  |  |  | Rehan | 2025-02-10 | 296 | >60 | March | 2025 | #REF!
Foods | Foods Supply Chain | 90450816/90457701/90458656 | 2024-09-12 | Delay in supplier orders and NDC allocations issues in Relex on 28/11,01/12,02/12 | Review and enhance the testing scopes by incorporating relevant scenarios for any changes to existing weekly jobs or the introduction of new jobs in the environment and align with the nightly run to prevent any unexpected impacts on the overnight batch processing. | Problem identification & Alerting | Anshuman Pani | 20/02: Anshuman provided the below EPIC ID FOATR-6136 - Overall test automation epic. Test scope optimisation will be added to this epic. FOATR-17065 - Epic for observability dashboard. 05/02:Followed up with Anushman and requested Lisy assistance get the latest on the action 20/01/25: Followed up, awaiting further updates 23/12/24: The action will be picked up after GQ 17/12/24: Update requested. As it was confirmed that the issue on 1st December was caused by the recalculation of demand forecast data for purged records, which was not accounted for during the job configuration. As a result, it has been agreed to conduct thorough testing of any weekly job execution to assess its impact on the nightly run before deploying it into production. | Relex | Tactical | NA | 20/02/25 | Closed |  |  |  | Kavitha | 2025-02-10 | 297 | >60 | February | 2025 | #VALUE!
Foods | Foods Supply Chain | 90450816/90457701/90458656 | 2024-09-12 | Delay in supplier orders and NDC allocations issues in Relex on 28/11,01/12,02/12 | Enhance observability within the RELEX job to enable identification of the root cause behind an overrunning or stuck job. | Problem identification & Alerting | Anshuman Pani | 20/02: Anshuman provided the EPIC ID FOATR-26670 - permanent fix for INC000090457701 based on which we will be resolving the actions 05/02:Followed up with Anushman and requested Lisy assistance get the latest on the action 20/01/25: Followed up, awaiting further updates 23/12/24: The action will be picked up after GQ 17/12/24: Update requested. This needs collaboration with Relex SAAS | Relex | Tactical | NA | 20/02/25 | closed |  |  |  | Kavitha | 2025-02-10 | 297 | >60 | February | 2025 | #VALUE!
Foods | Foods Supply Chain | 90450816/90457701/90458656 | 2024-09-12 | Delay in supplier orders and NDC allocations issues in Relex on 28/11,01/12,02/12 | As the RELEX purge job is scheduled to be executed by the end of January 2025, it has been agreed to implement an extended hypercare period to prevent any impact on the overnight batches | Problem identification & Alerting | Doris (Relex Dev Ops) | 04/02: The scheduling of the purge job has been set to run every 61 days 20/01/25: Followed up, awaiting further updates Being planned for Jan | Relex | Tactical | NA | 2025-04-02 | Closed |  |  |  | Kavitha | 2025-02-10 | 297 | >60 | February | 2025 | #VALUE!
Foods | Foods Supply Chain | 90450816/90457701/90458656 | 2024-09-12 | Delay in supplier orders and NDC allocations issues in Relex on 28/11,01/12,02/12 | Implement a fix to update the configuration of the purge job, ensuring that demand forecasts are not generated for purged records in Relex. | Permanent Fix | Anshuman Pani | 04/02: The issue has been documented so that when the purge job runs support can take the necessary actions to prevent the recalculations 20/01/25: Followed up, awaiting further updates 23/12/24: The action will be picked up after GQ 17/12/24: Update requested. A JIRA is being created to prevent the recalculation of the demand forecast data in Relex affecting the nightly run | Relex | Strategic | NA | 2025-04-02 | Closed |  |  |  | Kavitha | 2025-02-10 | 297 | >60 | February | 2025 | #VALUE!
Foods | Foods Supply Chain | 90450816/90457701/90458656 | 2024-09-12 | Delay in supplier orders and NDC allocations issues in Relex on 28/11,01/12,02/12 | To align the allocation volume, a streamlined process will be introduced and agreed upon with the Flow Planning team in accordance with the weekly DFS run. | Problem avoidance | Christopher John | 05/02 : FOATR-21975 is the epic / feature for Changes to DFS logic to improve performance for Peak 2025. Can be closed 04/02: This is part of the DFS Logic review. Lisy to check with Chris on the latest update or backlog to track 23/12/24: The action will be picked up after GQ 17/12/24: Update requested. The process will also address the allocation volume by aligning the DFS runs, scheduled every Sunday, with any necessary user updates in Relics. This will help ensure efficient management of allocation data and minimise potential impacts. | Foods Business | Strategic | NA | 2025-05-02 | Closed |  |  |  | Kavitha | 2025-02-10 | 297 | >60 | February | 2025 | #VALUE!
Foods | Foods Supply Chain | 90450816/90457701/90458656 | 2024-09-12 | Delay in supplier orders and NDC allocations issues in Relex on 28/11,01/12,02/12 | Explore the feasibility of configuring an alert to detect increases in data volume before the weekly batches initiate and the nightly run begins. | Problem identification & Alerting | Anshuman Pani | 04/02: Over allcoation and underallocatin alerts are already in place 20/01/25: Followed up, awaiting further updates 23/12/24: The action will be picked up after GQ 17/12/24: Update requested. In Progress. | Relex | Tactical | NA | 2025-04-02 | Closed |  |  |  | Kavitha | 2025-02-10 | 297 | >60 | February | 2025 | #VALUE!
Foods | Foods Supply Chain | 90450816/90457701/90458656 | 2024-09-12 | Delay in supplier orders and NDC allocations issues in Relex on 28/11,01/12,02/12 | As part of daily monitoring, if an increase in records or order & allocation volume is detected, explore the feasibility of automatically holding the batch before it is sent to WMS. This hold should be systemically implemented either in RELEX or ASO to minimise potential impacts to supplier ordering and NDC allocations. | Solution & Recovery | Anshuman Pani | 04/02: Having discussed with Matt White and Lisy, they are happy with current manual intervention of holding te job after the situation has been analysed. Automation will be discussed going forward but for now the action can be closed. 20/01/25: Followed up, awaiting further updates 23/12/24: The action will be picked up after GQ 17/12/24: Update requested. This will be included in the automation backlog - awaiting backlog id | Relex | Tactical | NA | 2025-04-02 | Closed |  |  |  | Kavitha | 2025-02-10 | 297 | >60 | February | 2025 | #VALUE!
Foods | Foods Supply Chain | 90450816/90457701/90458656 | 2024-09-12 | Delay in supplier orders and NDC allocations issues in Relex on 28/11,01/12,02/12 | Assess and implement options to maintain and improve batch performance while accommodating additional capabilities within Relex. | Permanent Fix | Anshuman Pani | 04/02: This is about ongoing batch performance improvements and tuning so rather than have one action, multiple actions and tuning will be done over time. 20/01/25: Followed up, awaiting further updates 23/12/24: The action will be picked up after GQ 09/12: The introduction of additional capabilities within Relex has led to continuous delays in receiving order files, posing a potential risk to the critical Foods Final Order and NDC Foods Final Order KPIs - awaiting a plan from Relex. | Relex | Strategic | NA | 2025-04-02 | Closed |  |  |  | Kavitha | 2025-02-10 | 297 | >60 | February | 2025 | #VALUE!
Customer Channels | Service Experience | 90463097 | 2024-06-12 | Digital Receipts sent to customers for historical transactions | Review the communication process followed by the team before performing any action in production. | Business & IT Communication | Shikhar Khanna | 06/12: There was no communication prior to reprocessing the failed messages from the DROS queues to assess the potential impact or agree on a way forward. Going forward, it has been agreed to initially liaise with the service lead in similar scenarios. Necessary actions will be determined in collaboration with the service lead and relevant stakeholders to ensure a clear and informed approach is taken. | DROS |  | NA | 2024-06-12 | Closed |  |  |  | Saloni | 2025-02-10 | 300 | >60 | December | 2024 | #VALUE!
Customer Channels | Service Experience | 90463097 | 2024-06-12 | Digital Receipts sent to customers for historical transactions | It was confirmed that no alerts were configured for the DROS queues to detect a pile up of messages, which led to the teams being unaware of the 33K historic transactions residing in the queue. To address this, it has been agreed to define thresholds for queue depth and message age. Relevant alerts will be configured on both queues to enable proactive identification of potential issues, ensuring timely actions are taken to mitigate any impact on customers. | Problem identification & Alerting | Sipra Sahoo | 18/12: Alerts for queue depth and message volume has been set up across both the queues to identify any pile ups in future. 06/12: There are existing alerts are configured to identify issues between POS and DROS. Product teams are now in process of determining the threshold based on which an alert will be configured by 20th December. | DROS |  | NA | 18/12/24 | Closed |  |  |  | Saloni | 2025-02-10 | 300 | >60 | December | 2024 | #VALUE!
Customer Channels | Service Experience | 90463097 | 2024-06-12 | Digital Receipts sent to customers for historical transactions | As the root cause of the historic 33k messages residing in the non-retry queue from previous years could not be conclusively determined, further investigations were not feasible. It has been agreed to implement a housekeeping process for the DROS queues, archiving unnecessary messages on a daily or weekly basis to prevent similar issues in the future. | Problem avoidance | Sipra Sahoo | 18/12: A manual housekeeping activity has been enabled for the Golden Quarter, automation options are being explored under a backlog RSS-3282 : Housekeeping of queues 06/12: A backlog is being raised to configure the housekeeping after Golden Quarter | DROS |  | NA | 18/12/24 | Closed |  | RSS-3282 |  | Saloni | 2025-02-10 | 300 | >60 | December | 2024 | #VALUE!
Customer Channels | Service Experience | 90463097 | 2024-06-12 | Digital Receipts sent to customers for historical transactions | Since DROS currently lacks the capability for selective message processing, it has been agreed to conduct a detailed analysis of options to enable selective message processing. | Permanent Fix | Shikhar Khanna | 18/12: RSS-3284 has been raised to enable the selective message processing option in DROS 06/12: This enhancement aims to mitigate the risks associated with bulk message processing, to ensure only the required messages are processed based on time and date excluding the historical messages resulting in confusion among customers | DROS |  | NA | 18/12/24 | Closed |  | RSS-3284 |  | Saloni | 2025-02-10 | 300 | >60 | December | 2024 | #VALUE!
Customer Channels | Service Experience | 90463097 | 2024-06-12 | Digital Receipts sent to customers for historical transactions | Investigate the root cause of the API issue within the Yocuda infrastructure, review the recovery actions performed by Yocuda, and assess the mitigations they have implemented to prevent similar scenarios in the future. | Root cause | Shikhar Khanna | 07/01: Please find below the root cause and preventive actions from Yocuda: Root cause: At 18:50 a node failed within one of the internal databases of the Yocuda platform. An automated graceful failover to a replicated node did not occur as the failure was not detected. Yocuda performed a manual failover and the issue was resolved at 19:59. Preventive Actions: The failure detection mechanism has since been enhanced. If this scenario reoccurs then no manual intervention will be required and no outage will occur. The unusual cause of this issue meant that the Yocuda API responded with "422 Store not found" for all incoming receipts. If this scenario did reoccur in the future then it (and any other internal errors) will now respond with "500 Internal Server Error" 18/12: A call has been scheduled with Yocuda to discuss on the root cause of the issue. 06/12: The team are collaborating with Yocuda to understand the cause and resolution details. ETA: 19/12 | DROS |  | NA | 2025-07-01 | Closed |  |  |  | Saloni | 2025-02-10 | 300 | >60 | January | 2025 | #VALUE!
GTS | ETP-On premise services | 90465705 | 2024-12-05 | Demand Notifications & Order Fulfilment messages not processing from Castle Donington WMS into OMS | Identify the root cause and a permanent fix for the uninterruptable processes on the virtual machines. | Root cause | Pappusamy, Sivasubrmani. Selvapillai, Sathish, Rajasekaran Subramaniyum | The root cause was attributed to uninterruptable sleep processes within the mule application resulting in no messages processing from mule to WMS. However, the actual reason for the uninterruptable process during the incident is yet to be determined. A high priority case was raised with Redhat for investigations, and they identified that the blocking sessions due to uninterruptable process had resulted with high load to the systems. To determine the reason behind the uninterruptable process Redhat requires additional logs on the VMCore (VM snapshots) to identify the Mutex owner of the blocking sessions. An action has been agreed to capture the VM snapshots before performing the VM (virtual Machine) restart during the issue reoccurrence, to help determine the root cause and a permanent fix | Mule and Linux | NA | NA | 2024-09-12 | Closed | NA | NA | NA | Pavithra | 2024-12-16 | 11 | 0-30 | December | 2024 | #VALUE!
GTS | ETP-On premise services | 90465705 | 2024-12-05 | Demand Notifications & Order Fulfilment messages not processing from Castle Donington WMS into OMS | Configure the relevant alerts for the system load average component within the virtual machine's | Problem identification & Alerting | Sathish Selvapillai | Alerts are configured for the system load average for all the CD servers. A Sev 3 alert when the average is greater than 20%, Sev 2 for 40% threshold and for 60% sev1 alerts will be triggered. | Linux | NA | NA | 2024-09-12 | Closed | NA | NA | NA | Pavithra | 2024-12-16 | 11 | 0-30 | December | 2024 | #VALUE!
GTS | Enterprise Integration | 90465705 | 2024-12-05 | Demand Notifications & Order Fulfilment messages not processing from Castle Donington WMS into OMS | Review the alerting threshold within mule services | Problem identification & Alerting | Rajasekaran Subramaniyum | 20/12 - The aging for the DN&OF flows were setup as 900 Secs and Email alert setup done for 300 Secs 05/12 - Though there were relevant alerts within mule for message pileups, a potential impact to site operations was already highlighted in parallel. Thus, it has been agreed to review the alerting threshold and it will be amended as required. | Mule Team |  | NA | 20/12/2024 | Closed | NA | NA | NA | Pavithra | 2024-12-16 | 11 | 0-30 | 20/12/2024 | #VALUE! | 0-10 Days
GTS | ETP-On premise services | 90465705 | 2024-12-05 | Demand Notifications & Order Fulfilment messages not processing from Castle Donington WMS into OMS | Perform a complete review on the file systems related to the inbound flows to WMS. | Problem avoidance | Selvapillai, Sathish, Jafar | During the incident - All other VM's were analysed and no abnormalities were observed. System load alerts are now configured to capture the issue proactively on all the CD servers. | Linux team |  | NA | 2024-05-12 | Closed | NA | NA | NA | Pavithra | 2024-12-16 | 11 | 0-30 | December | 2024 | #VALUE!
GTS | Enterprise Integration | 90465705 | 2024-12-05 | Demand Notifications & Order Fulfilment messages not processing from Castle Donington WMS into OMS | Review the high availability / DR architectural design for all the critical services like Mule, MQ etc. | Solution & Recovery | Rajasekaran Subramaniyum/ WMS Architect | 20/12 - PR# PBI000000070934 has been raised for the review and analysis. This will be picked up along with Q4 PIanning. 05/12 - This action will be reviewed post the golden quarter with all the relevant architect's | Mule Team/ WMS |  | NA | 20/12/2024 | Closed | NA | NA | NA | Pavithra | 2024-12-16 | 11 | 0-30 | 20/12/2024 | #VALUE! | Not Over Due
C&H and Intl | C&H and Intl Supply Chain | 90465705 | 2024-12-05 | Demand Notifications & Order Fulfilment messages not processing from Castle Donington WMS into OMS | Assess the overall impact to site operations before securing an outage. | Impact analysis | Service Leads - CD | It has been agreed within the teams to perform a quick E2E impact assessment before proceeding with the site outages. | Service Leads |  | NA | 2024-05-12 | Closed | NA | NA | NA | Pavithra | 2024-12-16 | 11 | 0-30 | December | 2024 | #VALUE!
GTS | Enterprise Integration | 90465705 | 2024-12-05 | Demand Notifications & Order Fulfilment messages not processing from Castle Donington WMS into OMS | Enhance the existing SOP's for Mule service restart - Capture the estimated duration to perform the implementation steps including the pre-requisites. | Solution & Recovery | Rajasekaran Subramaniyum | 20/12 - The SOP has been updated with the timelines 05/12 - While securing the site outage for the second time for the VM restart, the estimated ETA for the activity was 30 mins however it took around 45 mins for a full restart. | Mule Team |  | NA | 20/12/2024 | Closed | NA | NA | NA | Pavithra | 2024-12-16 | 11 | 0-30 | 20/12/2024 | #VALUE! | 0-10 Days
C&H and Intl | C&H and Intl Supply Chain | 90465705 | 2024-12-05 | Demand Notifications & Order Fulfilment messages not processing from Castle Donington WMS into OMS | Ensure we include the Fake DRL process in the existing SOP's for future references | Solution & Recovery | Kunal/WMS | 20/12 - The SOP has been updated with the right steps on Fake DRL | WMS |  | NA | 20/12/24 | Closed | NA | NA | NA | Pavithra | 2024-12-16 | 11 | 0-30 | December | 2024 | 0-10 Days
GTS | Enterprise Integration | 90465705 | 2024-12-05 | Demand Notifications & Order Fulfilment messages not processing from Castle Donington WMS into OMS | Enhancements/improvement to be made on the manual processes involved during the mule/VM and other processes restarts involved in the recovery | Solution & Recovery | Rajasekaran Subramaniyum/ Jafar | 20/12 -The cluster script to stop the mule instances along with the Linux server reboot has been created and is updated in the SOP | Mule and Linux |  | NA | 20/12/2024 | Closed | NA | NA | NA | Pavithra | 2024-12-16 | 11 | 0-30 | 20/12/2024 | #VALUE! | 0-10 Days
GTS | Operations | 90465705 | 2024-12-05 | Demand Notifications & Order Fulfilment messages not processing from Castle Donington WMS into OMS | Capture and update the detailed impact statement in the loop during the incidents | Issue handling/Management | MIM/ Service Leads. | All the Service Leads/Product owners are requested to update the Loop with the business impact due to the incident. Also, it is a MIM's responsibility to keep the loop updated with the impact and timelines. The same has been cascaded to the entire team. | MIM and Service Leads | NA | NA | 2024-06-12 | Closed | NA | NA | NA | Pavithra | 2024-12-16 | 11 | 0-30 | December | 2024 | #VALUE!
Foods | Foods Supply Chain | 90453291 | 2024-04-12 | High number of Open POs in Relex impacting Foods Store Stock Availability | To deploy Open po changes to reduce the STOCK-IN-TRANSIT visibility to 3 days instead of 7 days - Jira | Problem avoidance | Nikki/Relex | With the Jira backlog to deploy Open PO changes to reduce the STOCK-IN-TRANSIT visibility to 3 days instead of 7 days | Relex |  | NA | 29/01/25 | Closed | NA | FOATRC-24 |  | Gokul | 2025-02-10 | 302 | >60 | January | 2025 | #VALUE!
GTS | ETP- Connectivity,service & solution | 90451656 | 2024-02-12 | Store tills were offline across the estate | Create a plan to decommission the virtual F5 servers in SP to mitigate the risk of further memory leaks due to the known bug in F5. | Solution & Recovery | Kamal/Janani | 13/03 - Action now invalid as POS has moved into the cloud 05/03: Janani updated that "VM based F5 build is completed at Swindon and prologis and she also updated that the progress of service cutover would be known by April Mid" 27/02: Awaiting update from Janani on the latest plan for the decommissioning of the virtual F5 server in SP. 30/01: Have understood from Kamal & Janani that this would be done as part of SP Exit by end of Feb and server would be decommissioned in June 10/12: We need to remove the relevant server after peak and release the F5 instance so that we have more memory. 02/12: It has been confirmed that retrieving the 4GB of memory from the virtual servers should prevent any further memory leaks to the F5. Discussions with the Stockley Park exit team have been initiated, and the tentative ETA for releasing the 4GB of memory is December 2024. | Network |  | NA | 13/03/25 | Closed |  |  |  | Gokul | 2025-02-10 | 304 | >60 | March | 2025 | #VALUE!
GTS | ETP- Connectivity,service & solution | 90451656 | 2024-02-12 | Store tills were offline across the estate | Review and enhance the alerting mechanisms within the network layer to proactively detect memory leaks on the Stockley Park F5 load balancer. | Problem identification & Alerting | Kamal | 10/12: Complete as alerting is in place and checked. An existing alert is in place to detect memory leaks on the Stockley Park F5, and this alert was successfully triggered on the day of the incident to identify the issue. It has been noted that the memory utilization of the Stockley Park F5 device is already at 96%. To address this, there is a plan to decommission the virtual F5 servers, as most of the services load-balanced through them have already been decommissioned. This decommissioning will release 4GB of memory back to the device. Additionally, as part of future enhancements, the Beanstore application will be migrated to virtual F5s to eliminate dependency on the current F5 and mitigate risks associated with similar scenarios. The problematic F5 device will ultimately be decommissioned and replaced with an alternative solution as part of the Stockley Park exit strategy. | Network |  | NA | 2024-10-12 | Closed |  |  |  | Gokul | 2025-02-10 | 304 | >60 | December | 2024 | #VALUE!
Customer Channels | Service Experience | 90451656 | 2024-02-12 | Store tills were offline across the estate | Assess the feasibility of enhancing the alerting capabilities within the POS systems to enable proactive incident notification. | Problem identification & Alerting | Balaguru | 16/12 - Bala confirmed that the polling frequency was reduced on the day of the issue (28/11) 02/12 - The POS system currently has an alerting mechanism that polls every five minutes to monitor system status. During the incident, this alert was triggered at 7:31 AM. To improve the efficiency of problem identification, it has been agreed to reduce the polling frequency to three minutes. | POS |  | NA | 16/12/24 | Closed |  |  |  | Gokul | 2025-02-10 | 304 | >60 | December | 2024 | #VALUE!
Customer Channels | Selling Experience | 90451656 | 2024-02-12 | Store tills were offline across the estate | Review the business communication to ensure all relevant impact statements and instructions for the stores are accurately updated and sent in a timely manner | Business & IT Communication | Laura Whittle | We have streamlined the communication process to include the additional impact of Scan & Shop. It has been highlighted that if the issue recurs, Scan & Shop should be shut down, as it is not feasible to process a refund of a purchase made through S&S on the tills. This information has been communicated to the Retail Ops team and will now be managed in a shared location for easy access during an incident. | Service Lead |  | NA | 2024-02-12 | Closed |  |  |  | Gokul | 2025-02-10 | 304 | >60 | December | 2024 | #VALUE!
Customer Channels | Selling Experience | 90451656 | 2024-02-12 | Store tills were offline across the estate | During the incident, the SCO tills were also impacted, but there was a gap in notifying the DN team. A process needs to be established to promptly inform the DN team of any issues with the SCO tills, particularly during tills offline scenario | Issue handling/Management | Laura Whittle | 29/01: Laura confirmed that a process has been put on place to ensure the Scot team are aware. 02/12: Laura will collaborate with the Service Desk team to streamline a process, document, or SOP for liaising with the DN team during tills offline scenario. | Service Lead |  | NA | 29/01/25 | closed | NA | NA | NA | Gokul | 2025-02-10 | 304 | >60 | January | 2025 | #VALUE!
Customer Channels | Platform & Store Ops | 90435749 | 27/11/24 | CSSM Foods Stock Data Corruption | How often do null transactions appear and what is the root cause of it? | Permanent Fix | Anees Ahmed | 08/01 - Backlog raised for further tracking - https://jira-marksandspencer-app.atlassian.net/projects/FSO/versions/10107/tab/release-report-all-issues 31/12 - Have requested for a reference backlog ID which has been raised to support this acitivity. 20/12. Accuracy checker App part is addressed. This is the key issue. The other contributor for the null issue is being analyzed. It was discussed with PIR team, that we will get more insights on the other contributors when we release an updated version of one of our apps in the New year. ETA: 16/01/2025 27/11 - We believe that the null value may be related to accuracy checker and simple counts. Aneesh will work on identifying the root cause. For accuracy checker we have a fix deployed for 5 stores and this is being monitored. once proven to be successful it will be implemented for other stores. Also, other contributors for null transactions are being analyzed further. | CSSM |  | NA | 2024-08-01 | Closed |  | https://jira-marksandspencer-app.atlassian.net/projects/FSO/versions/10107/tab/release-report-all-issues |  | Pavithra | 2025-02-10 | 309 | >60 | January | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 90435749 | 27/11/24 | CSSM Foods Stock Data Corruption | Feasibility to systemically reverse the query/transactions to its original value during any re-occurrences. | Solution & Recovery | Shanmuga Priya/CSSM | 31/12- Solution is in place to support the null value scenario. Thus this action no longer requries tracking. 27/11 - This option is being explored; however it has been de-prioritized as we are already working on the automation for the null value correction, Which is expected to prevent any re-occurrences. | CSSM |  | NA | 31/12/24 | Closed |  |  |  | Pavithra | 2025-02-10 | 309 | >60 | December | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 90435749 | 27/11/24 | CSSM Foods Stock Data Corruption | To Eliminate the manual correction of stock in CSSM, we propose a store procedure that will update the stock (automation). This will trigger when the particular scenario occurs, the procedure applies. | Solution & Recovery | Srinivasulu Gunapati | 31/12 - This action has been completed - A Store procedure has been deployed and it is in use by the prod and support teams 23/12 - Development and QA completed. Planned Go Live date is Dec 5th - awaiting confirmation from the product team 27/11 - A plan is being devised in this sprint to automate the stock correction during the null value scenario. Once we have the plan, testing needs to be carried out prior to deployment. | CSSM |  | NA | 31/12/24 | Closed |  |  |  | Pavithra | 2025-02-10 | 309 | >60 | December | 2024 | #VALUE!
GTS | ETP-On premise services | 90435749 | 27/11/24 | CSSM Foods Stock Data Corruption | Replication was significantly long. A log has been raised with Microsoft to identify the latency between databases | Solution & Recovery | Ragupathi Selvam | Microsoft team has recommended to avoid bulk operation query for Insert, update or delete transaction. However, for workloads with large transactions performance can only be improved by splitting the bulk transaction into small chunks. | DBA Team |  | NA | 27/11/24 | Closed |  |  |  | Pavithra | 2025-02-10 | 309 | >60 | November | 2024 | #VALUE!
GTS | ETP-On premise services | 90435749 | 27/11/24 | CSSM Foods Stock Data Corruption | Microsoft to advise how we can have better visibility of contentions/locks/waits during replication so we can manage better | Solution & Recovery | Ragupathi Selvam | Microsoft has recommended to execute a command "sql scout log" - on both publisher and the subscriber to capture additional logs to effectively identify contentions/locks/waits etc. during the issue reoccurrence | DBA Team |  | NA | 27/11/24 | Closed |  |  |  | Pavithra | 2025-02-10 | 309 | >60 | November | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 90435749 | 27/11/24 | CSSM Foods Stock Data Corruption | Review existing process and suggest improvements including SME’s for additional validations (peer to peer review) if the issue was to occur again | Problem avoidance | shanmugapriya thangavel/ CSSM | 06/12 - The ROTA for the Oncall SME has been published within the team for a peer review whenever required. 27/11 - Though we are working on the automation, in the interim if the issue re-occurs, an enhanced process will be in place where a Senior SME to be made as a On-call to guide the OPS team during any manual intervention on the DB/any critical step. A plan will be devised scenario based, as to when to call the oncall and when not to call them based on the criticality and a ROTA will be made for the oncall SME's. | CSSM |  | NA | 2024-06-12 | Closed |  |  |  | Pavithra | 2025-02-10 | 309 | >60 | December | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 90435749 | 27/11/24 | CSSM Foods Stock Data Corruption | Identify all manual workaround in the CSSM environments and then work through to automate and improve. | Problem avoidance | Baxi Kaustubh Sinha/ Ravikumar S | JIRA Ticket - https://jira.marksandspencer.app/browse/CSSM-13203 has been raised to identify all the manual workarounds in place. And possible automation and improvements will be made based on the criticality | CSSM |  | NA | 2024-06-12 | Closed |  | https://jira.marksandspencer.app/browse/CSSM-13203 |  | Pavithra | 2025-02-10 | 309 | >60 | December | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 90435749 | 27/11/24 | CSSM Foods Stock Data Corruption | Enhance the existing alerting with a feasibility to alert the team when all the stock data in the DB has gone null | Problem identification & Alerting | shanmugapriya thangavel | 31/12 - This action will be picked-up part of Sprint1 Ops automation - ETA - Sprint1 starts from 15th to 29th Jan - further will be tracked via backlog: https://jira.marksandspencer.app/browse/CSSM-13372 27/12: This option will also be explored via a backlog. | CSSM |  | NA | 31/12/24 | Closed |  |  |  | Pavithra | 2025-02-10 | 309 | >60 | December | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 90435749 | 27/11/24 | CSSM Foods Stock Data Corruption | Ensure we engage MIM in a timely manner | Issue handling/Management | Vijay arunprasath and CSSM Team | Though the manual error was identified at 04:00 MIM was not invoked, and correction was done internally. Once stores reported discrepancy with stock data MIM was invoked. Therefore, it has been agreed to invoke MIM during the initial stage which would have prevented the wider impact. | CSSM |  | NA | 27/11/24 | Closed |  |  |  | Pavithra | 2025-02-10 | 309 | >60 | November | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 90435749 | 27/11/24 | CSSM Foods Stock Data Corruption | Enhance the existing Standard operating procedures (SOP) with the entire steps, queries used for complete recovery. | Issue handling/Management | Ravikumar S/ CSSM TPM | The existing SOP will be enhanced with below details: A straightforward query to derive the impacted UPC's - This is being worked via backlog - CSSM-13218 Complete steps/ queries on the recovery involving all aspects such as Sale, Stock, deliveries, counts, negative values etc. - being worked upon via backlog CSSM-13337 Development completion: Dec 10th, QA completion: Dec 24th .Steps to handle the data replication scenario as recommended by MS (action. No: 4) - COMPLETED The query review process before the implementation into prod (i.e) involve the Key SME's before executing the step. - COMPLETED | CSSM |  | NA | 31/12/24 | Closed |  | CSSM-13218/ CSSM-13337 |  | Pavithra | 2025-02-10 | 309 | >60 | December | 2024 | #VALUE!
GTS | Operations | 90435749 | 27/11/24 | CSSM Foods Stock Data Corruption | Identify all manual workaround in the Tech environments and then work through to automate and improve. | Problem avoidance | Sathish Sheshiah | 09/04 - This action istill being worked upon by the Head of ops 26/02 - Sathish is yet to finalize the list of exisiting maunal activities across the estate 15/01 - A list has been finalized, yet needs a review with the product owners - Sathish is working on this action 08/01 - Follow-up made with the problem Owner- Waiting updates 31/12 - This action is being worked upon - an initial list of manual activities are being collated. However, it will take time to completed as it needs consolidation of data across various portfolio's | Ops Manager |  | 15/04/25 |  | Open | NA | NA | NA | Pavithra | 2025-02-10 | 309 | >60 | January | 1900 | 90+ Days
Foods | Foods Supply Chain | 90437625 | 27/11/24 | Delay in Relex overnight batch impacting supplier orders and allocations | Assess the feasibility of automating the manual step in the product assortment process within the Relex environment. | Permanent Fix | Matt White/Tamilenbakumar | 10/12 - Tamil advised that this has been completed and Matt also reconfirmed, hence closing the action. 27/11 - The RELEX DevOps team has identified a solution to automate the product assortment process across both environments. Testing is currently underway, with a plan to deploy in production on 28/11. Additional checks will be conducted to validate the success of the automation. In parallel, the FOAL team will align to validate the changes deployed by RELEX, followed by hypercare support until the completion of the critical batches. | Foods business |  | NA | 2024-10-12 | Closed |  |  |  | Gokul | 2025-02-10 | 309 | >60 | December | 2024 | #VALUE!
Foods | Foods Supply Chain | 90437625 | 27/11/24 | Delay in Relex overnight batch impacting supplier orders and allocations | While implementing the contingency plan for the NDC allocations for Bradford and Milton Keynes, investigate the cause of Cross-Dock orders being incorrectly sent as Direct Store orders to the DCs. | Solution & Recovery | Puviyarasu | 10/12: FOATR-26507 is available, but until it is done, when contigency will be invoked the cross-dock flag will be manually addressed. 27/11: It was confirmed that the Cross-Dock flag was missing in the NDC contingency plan, which caused Cross-dock orders to be sent as Direct Store orders. This was the first time the contingency plan for Relex lines was used, and there is a backlog raised to correct the flag in the contingency file. FOATR-26507 | ASO TPM |  | NA | 2024-10-12 | Closed |  | FOATR-26507 |  | Gokul | 2025-02-10 | 309 | >60 | December | 2024 | #VALUE!
Foods | Foods Supply Chain | 90437625 | 27/11/24 | Delay in Relex overnight batch impacting supplier orders and allocations | Review and update the SOP to include validation of standard metrics eg: order flag checks in the contingency allocation file before applying it to production. | Solution & Recovery | Chandrapandian M/Tamil | 29/01: This has been added into SOP and also Permananent fix deployed on 15th Jan to address missing x-Dock indicator.•[FOATR-26507] - i3405_contingency_file export contains empty Cross Dock field. 17/12: Update requested to Tamil 10/12: Tamil to review the basic attributes to be verified when we use the contigency file and add these checks to the SOP. Tamil to provide new JIRA log | Foods product team |  | NA | 29/01/25 | Closed | NA | FOATR-26507 | closed | Gokul | 2025-02-10 | 309 | >60 | January | 2025 | #VALUE!
Foods | Foods Supply Chain | 90437625 | 27/11/24 | Delay in Relex overnight batch impacting supplier orders and allocations | Review and update the SOP for generating the 28-day order plan to ensure it includes a step for addressing vehicle load build purchase orders as part of the supplier order generation process. | Solution & Recovery | Tamilenbakumar | 10/12: tamil advised this has been completed. | Foods product team |  | NA | 2024-10-12 | Closed |  |  |  | Gokul | 2025-02-10 | 309 | >60 | December | 2024 | #VALUE!
Foods | Foods Supply Chain | 90437625 | 27/11/24 | Delay in Relex overnight batch impacting supplier orders and allocations | A product backlog item has been raised to address the issue with the NDC allocation contingency file, ensuring that the Cross-dock orders flag is updated in the contingency allocation file.. | Solution & Recovery | Matt White | 10/12: Although a backlog FOATR-26507 has been raised, an agreement has been made with Relex to prioritise resolving the contingency allocation file issue. Matt will coordinate with Callum to expedite the process of implementing the fix. | Foods business |  | NA | 13/12/24 | Closed |  | FOATR-26507 |  | Gokul | 2025-02-10 | 309 | >60 | December | 2024 | #VALUE!
Foods | Foods Supply Chain | 90437625 | 27/11/24 | Delay in Relex overnight batch impacting supplier orders and allocations | Review the service design document and the chronology of events from the identification of the issue within RELEX to the notification of the FOAL team and MIM engagement. Identify any gaps and implement measures to ensure timely issue identification and reduce recovery time. | Issue handling/Management | Anshuman Pani, Saloni, Bhuvana, Prathiba Sudheendra | Update 10/12: The relevant teams have been spoken to and engagement processes and timescales have been confirmed, however the note needs to be added that every incident is different and timescales may vary. | Foods product team |  | NA | 2024-10-12 | Closed |  |  |  | Gokul | 2025-02-10 | 309 | >60 | December | 2024 | #VALUE!
Foods | Foods Supply Chain | 90437625 | 27/11/24 | Delay in Relex overnight batch impacting supplier orders and allocations | Review the change management agreement between Relex and Customer to ensure that all production changes are properly captured within the central change management process. | Issue handling/Management | Matt White/Priyadharshini S | 10/12: Matt confirmed that the Accenture team are already part of the change management process and all changes will be advised. Although the change that caused the issue was raised as part of the Customer change management process, Relex confirmed that the hotfixes planned for deployment on 28/11 lacked a change reference. It was reiterated to Relex that all production changes, performed outside of an incident, must adhere to the central change management process. This will be reviewed to ensure clarity and avoid any confusion between the teams. | Foods business |  | NA | 2024-10-12 | Closed |  |  |  | Gokul | 2025-02-10 | 309 | >60 | December | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90430167 | 25/11/24 | WMS – JDA dispatcher application inaccessible at Outlet DC | Paul Wallis site manager to config GXO support teams response times | Issue handling/Management | Paul Wallis/ Sivalingam Nandhakumar | 18/12: Paul has advised that the complete time lines has been that is related to incident. | GXO | Strategic | NA | 18/12/24 | Closed |  |  |  | Kavitha | 2025-02-10 | 311 | >60 | December | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90430167 | 25/11/24 | WMS – JDA dispatcher application inaccessible at Outlet DC | GXO reviewing and streamlining the incident process for better response times and will feedback with their process. In the meantime there will be a special Teams channel for site bypassing the GXO service desk which should be ready by 26/11 for better traction | Issue handling/Management | Will Davison/Sivalingam Nandhakumar | 18/12: Comms were issued to site 26/11 to advise of a ‘Peak’ expedited route to engage our MIM team via a hidden telephony IVR option. This has been in place since 27/11 and will run until 08/01. We will then review whether this be kept. | GXO | Strategic | NA | 18/12/24 | CLosed |  |  |  | Kavitha | 2025-02-10 | 311 | >60 | December | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 90430167 | 25/11/24 | WMS – JDA dispatcher application inaccessible at Outlet DC | We need a SOP between Customer and GXO to agree recovery actions if the IPSEC tunnel was to encounter a further issue. | Solution & Recovery | Mustafa Muzamil/Karthick GC | 10/12: We will stick to the BAU process - GXO will check their side and they are free to bounce the tunnel. If they cannot resolve the issue they will come to Customer D7T. | Network | Tactical | NA | 2024-10-12 | Closed |  |  |  | Kavitha | 2025-02-10 | 311 | >60 | December | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 90430167 | 25/11/24 | WMS – JDA dispatcher application inaccessible at Outlet DC | If the issue is to reoccur the plan is to get a packet capture and soft reset the IPSEC tunnel from Customer or GXO who ever gets there first | Solution & Recovery | Mustafa, Muzamil and Dawid Jeruzal (GXO) | 10/12: We will stick to the BAU process - GXO will check their side and they are free to bounce the tunnel. If they cannot resolve the issue they will come to Customer D7T. | Network | Tactical | NA | 2024-10-12 | Closed |  |  |  | Kavitha | 2025-02-10 | 311 | >60 | December | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 90430167 | 25/11/24 | WMS – JDA dispatcher application inaccessible at Outlet DC | Review all network settings on both sides of the IPSEC tunnel to make sure they match expectations. | Problem identification & Alerting | Mustafa, Muzamil and Dawid Jeruzal (GXO) | 10/12 Review completed. | Network | Tactical | NA | 2024-10-12 | Closed |  |  |  | Kavitha | 2025-02-10 | 311 | >60 | December | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90430167 | 25/11/24 | WMS – JDA dispatcher application inaccessible at Outlet DC | GXO have a monitoring platform (Solar Winds which will be configured to alert stakeholders at Customer and GXO if connectivity to Customer JDA is unavailable. Sivalingam, Nandakumar to provide the names where the alert needs to go to. Mustafa, Muzamil to provide all relevant network config details | Problem identification & Alerting | Sivalingam, Nandakumar/Dawid Jeruzal (GXO) | 26/11: The IP details that needs configured for alerting has been shared with GXO. | GXO | Tactical | NA | 26/11/24 | CLosed |  |  |  | Kavitha | 2025-02-10 | 311 | >60 | November | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 90430167 | 25/11/24 | WMS – JDA dispatcher application inaccessible at Outlet DC | To mitigate the bugs, a firmware upgrade is required. We need from NOC a full report on the current version, the description of the bug how it manifests itself and the planned recovery action whether it be an upgrade etc | Permanent Fix | Santhosh Velmurugam | 10/04: Fortinet are asking us to go for 7.4.7 and there is a testing plan in place for this. There are some issues with this version, we have selected Bangalore sourcing office for this - testing will take two weeks 13/03 - We are waiting for another version release from Fortinet as 7.4.6 also has issues as found when it was tested in WS, ETA Q1 30/01: This DC tunnel link terminated on SW DP firewall (2600F), currently running with 7.4.4 and targeted the bug fix in 7.4.6 and its aimed to pushed into production with in Q4 10/12: Kamal advsies that this will not be happening untIl after peak. | Network | Strategic | 24/04/25 |  | Open |  |  |  | Kavitha | 2025-02-10 | 311 | >60 | January | 1900 | 90+ Days
C&H and Intl | C&H and Intl Supply Chain | 90428181 | 21/11/24 | Ollerton DC was unable to print labels between 22:35 and 00:33 | Alert handling and MIM engagement -There were no challenges with the alerts however there was a delay in MIM engagement, and no notifications were posted on the support channel. | Problem identification & Alerting | Karthick GC | 21/11 - WMS team has been informed to immediately post a notification on the teams support channel and to callout MIM as soon as the DC reports the issue. | WMS Team |  | NA | 22/11/24 | Closed | NA | NA | NA | Pavithra | 2025-02-10 | 315 | >60 | November | 2024 | #VALUE!
GTS | ETP-On premise services | 90428181 | 21/11/24 | Ollerton DC was unable to print labels between 22:35 and 00:34 | Replace the faulty storage controller of the problematic esxi host. | Solution & Recovery | Santhanam, Dinesh BabuBalasubramanian, DharmarajKumar, HarishSelvapillai, SathishSadiq, Jafar | 03/03 - the 3 remaning VM's has been miigrated to a healthy ESXI host. We do not see any risk now wih the VM's - The faulty HW has been replaced by the prodcut teams and the post checks looks healthy and Good. 26/02/ - A Follow-up has been made, awaiting update from the Problem owner. 23/01- Except 3, all other VM's were migrated from problematic ESXi host to another ESXi host. For those remaining 3 VM's, Dinesh is already chasing the respective stakeholders to get an outage window. 15/01 - Follow-up has been done with the problem owner - They were waiting for the PEak to get over to perfoem this actions, now that the GQ is done- will get their plan forward 20/12 - out of 12 VM's 3 have been moved and Wintel team is checking with the appropriate application teams for the most suitable window to move the remaining 9 VM's - as this action may require an outage 26/11- Techinical Teams were engaged in a discussion with the Application team regarding the vMotion plan for the virtual machine hosted on the faulty controller, ESXP8095 and they are currently awaiting an update from the Application team to determine an appropriate window for the migration. Once this schedule is confirmed,they will proceed with the migration and notify the vendor to replace the defective component on the host. 21/11 - This action needs more planning as it requires an outage. Infra teams will collaborate to devise a plan to replace the faulty hardware, following the required validations on the impacts and risks behind it. | Linux and Wintel |  | NA | 2025-03-03 | Closed | NA | NA | NA | Pavithra | 2025-02-10 | 315 | >60 | March | 2025 | #VALUE!
GTS | ETP-On premise services | 90428181 | 21/11/24 | Ollerton DC was unable to print labels between 22:35 and 00:34 | Review all the servers in the clusters across the estate and increase the default totem Value to 30 sec as per the recommendations from Redhat. | Problem avoidance | Kumar, Harish | 26/02 - Considering the downtime required, this task of increasing totem value of clusters in WMS DC's will be addressed as part of the OS patching of the servers which is scheduled to start from March 2025 after the release of new Kernel version by Red-Hat. 29/01 - Since this is a central activity,Linux team will review the action internally to explore the feasbility of implementing it 15/01 - Follow-up has been done with the problem owner - awaiting update 21/11- A review of all the servers in the estate will be performed and a list of servers which require a change in totem value will be finalized. However, this action will be planned after golden quarter as it involves an outage | Linux |  | NA | 26/02/25 | Closed | NA | NA | NA | Pavithra | 2025-02-10 | 315 | >60 | February | 2025 | #VALUE!
GTS | Enterprise Integration | 90428181 | 21/11/24 | Ollerton DC was unable to print labels between 22:35 and 00:34 | Review the high availability configurations within the clusters to prevent such unplanned outages during a reboot | Root cause | Pappusamy, Sivasubrmani | 20/12 - SOP updated with the below details: 1.Team should always login with cluster name 2.Check whether all anchors are generated under Apps. 3.If the flows are not started properly, then go for a graceful mule restart 4.Check both Active and passive servers for cluster file system PR#PBI000000070918 raised to test the mule server failover testing post PEAK. 27/11- Mule team has confirmed no issues with the High availability. During the incident, due to the communication issue the DR failover had an issue as the mule flows were interrupted.Also If Mule engineer was aware of the Passive server, a mule restart could have been performed to restore the servicces in the passive node. However, we will get the high availability tested post the GQ via a PR record 21/11 -The services were failed over to the passive mule server hlxp00dc163, however the application functionality was not restored. Further checks will be carried out between Mule and Linux support to ascertain the root cause behind it. Also, their SOP's will be reviewed. | Mule- Middleware |  | NA | 20/12/24 | Closed | NA | NA | NA | Pavithra | 2025-02-10 | 315 | >60 | December | 2024 | #VALUE!
GTS | ETP-On premise services | 90428181 | 21/11/24 | Ollerton DC was unable to print labels between 22:35 and 00:34 | Work with Redhat to clear the pending events generated with the cluster services during the hardware fault. | Solution & Recovery | Kumar, HarishSelvapillai, Sathish | 15/01 - This action will be addressed as a BAU - Does not need further tracking- Also it has been confirmed that these are not critical events and will not impact any operations 31/12 - Follow-up has been done with the problem owner - awaiting update 20/12 - Sathish Sevapillai is yet to respond on this action 21/11 - It has been agreed to undergo a review with Redhat before clearing the pending events on the other 7 servers. Note: There will be no impact due to the existing pending events. | Linux |  | NA | 15/01/25 | Closed | NA | NA | NA | Pavithra | 2025-02-10 | 315 | >60 | January | 2025 | #VALUE!
Customer Channels | Selling Experience | 90423246 | 20/11/24 | Messages from PIM failing in Product Domain API | Automated test PoC in PIM | Problem Avoidance | Adrian Carvalho | 19/02: This was planned in Jan and it will be done as part of cloud migration in June with the [PIM-116] Automated Test PoC - Jira 10/02: Scheduled a call with Adrian and Ayan on 19/2 to discuss on the open actions. 05/02: Have mailed Adrian for the latest update on this action. 23/01: Hisham has sent a followup mail to action owners | PIM |  | NA | 19/02/25 | Closed | NA | NA | NA | Gokul | 2025-02-10 | 316 | >60 | February | 2025 | #VALUE!
Customer Channels | Selling Experience | 90423246 | 20/11/24 | Messages from PIM failing in Product Domain API | Improved data contract from PIM to Product API | Problem Avoidance | Adrian /Jitendra Tripathy | 26/02: Jitendra updated that the backlog PD-586 has been created to improve the data contract from PIM to Product API. 19/02: Jitendra will check with Adrian and update further on the alerting. However, we can setup alert for failing and he will check and revert on it 10/02: Scheduled a call with Adrian and Ayan on 19/2 to discuss on the open actions. 05/02: Have mailed Adrian for the latest update on this action. 23/01: Hisham has sent a followup mail to action owners | PIM |  | NA | 26/02/25 | Closed | NA | PD-586 | NA | Gokul | 2025-02-10 | 316 | >60 | February | 2025 | #VALUE!
Customer Channels | Selling Experience | 90423246 | 20/11/24 | Messages from PIM failing in Product Domain API | Improved alerting in Product API | Problem identification & Alerting | Luke Sparkes/Jitendra Tripathy | 26/02: Jitendra confirmed that the required alerting has been setup. 19/02: Jitendra will check with Adrian and update further on the alerting. However, we can setup alert for failing and he will check and revert on it 10/02: Scheduled a call with Adrian and Ayan on 19/2 to discuss on the open actions. 05/02: Have mailed Adrian for the latest update on this action. 23/01: Hisham has sent a followup mail to action owners | PIM |  | NA | 26/02/25 | Closed | NA | NA | NA | Gokul | 2025-02-10 | 316 | >60 | February | 2025 | #VALUE!
Customer Channels | Selling Experience | 90423246 | 20/11/24 | Messages from PIM failing in Product Domain API | Update IM QuickStart Guide to include severity change | Business & IT Communication | Adrian / Hisham | 17/12: Adrian shared the confluence page where the Guide has been updated https://confluence.marksandspencer.app/display/PI/Incident+Quickstart+Guide, so that this action can be closed. 02/12: As agreed with Steve Warren, guideline for the teams. There is guidance on raising incidents on the D&T sharepoint site - https://mnscorp.sharepoint.com/sites/ServiceManagement2/SitePages/Incident-Management.aspx. This includes guidance on severity that should be used to classify if something is an incident. Where something is an incident or a potential incident, I'd say it should be logged in the Incident Channel and a Remedy ticket raised. Where something is an issue, an remedy ticket should be created (see guidance on the sharepoint site). In a perfect world, teams should then pick this issue up and handle it as a BAU activity, within a defined SLA. Note: if someone isn't sure if something is an incident, they should raise it as an incident regardless...better to flag a non-issue than not flag an actual issue. | Service Lead |  | NA | 17/12/24 | Closed | NA | NA | NA | Gokul | 2025-02-10 | 316 | >60 | December | 2024 | #VALUE!
C&H and Intl | C&H commercial Trading | 90423246 | 20/11/24 | Messages from PIM failing in Product Domain API | Test Scenarios covering all product states | Problem Avoidance | Wasim Qureshi | NA/11: Fromprogress | Product Manager |  | NA | 20/11/24 | Closed | NA | NA | NA | Gokul | 2025-02-10 | 316 | >60 | November | 2024 | #VALUE!
Customer Channels | Selling Experience | 90423246 | 20/11/24 | Messages from PIM failing in Product Domain API | Identification of Necessary Mandatory Patches | Problem Avoidance | STIBO / Adrian | 17/12 - Adrian updated that Stibo have responded that we need to upgrade to version mp5. As they have not provided hotfixes to our current version, we will need to upgrade STEP. This will be achieved as part of the Version Upgrade project, going live in June. [PI-7252] Version Upgrade Deployment - Jira App | PIM |  | NA | 17/12/24 | Closed | NA | PI-7252 |  | Gokul | 2025-02-10 | 316 | >60 | December | 2024 | #VALUE!
C&H and Intl | C&H commercial Trading | 90423246 | 20/11/24 | Messages from PIM failing in Product Domain API | Request Stibo to test all components involved in outbounds when enabling in-memory cache | Supplier and support involvement | STIBO / Adrian / Wasim | 17/12 - Adrian updated that this has been completed as part of the issue identification. | Product Manager |  | NA | 17/12/24 | Closed | NA | NA | NA | Gokul | 2025-02-10 | 316 | >60 | December | 2024 | #VALUE!
C&H and Intl | C&H commercial Trading | 90423246 | 2024-11-20 | Messages from PIM failing in Product Domain API | Multiple logs raised for the same Brands buyer approval issue inspite of the comms, this could have been avoided. To review and agree process with Business team | Issue handling/Management | Brands / Deepali | 17/12 - Deepali confirmed that it has been agreed with business to raise only 1 log during an incident | Service Lead |  | NA | 17/12/24 | Closed | NA | NA | NA | Gokul | 45932 | 316 | >60 | December | 2024 | #VALUE!
C&H and Intl | C&H commercial Trading | 90423246 | 20/11/24 | Messages from PIM failing in Product Domain API | To check feasibility of set up alert when user get “submission error – the transaction has been rolled back”i.e. unable to submit for buyer approval | Problem identification & Alerting | Wasim Qureshi | 07/01 - Elaine updated that Wasim appraised her that "there is no update as of yet, however we are planning for a version upgrade this quarter so will look to bring this functionality in as part of that process". Hence, closing the action 30/12 - Followed up with Wasim and no response yet 25/12 - Wasim is OOO with no specific return date 23/12 - Followed up with Wasim and no response yet 17/12 - Wasim is OOO until 19/12 | Product Manager |  | NA | 2025-07-01 | Closed | NA | NA | NA | Gokul | 2025-02-10 | 316 | >60 | January | 2025 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90422069 | 18/11/24 | Welham DC - WMS JDA Application unavailable | It was identified that residual issues were reported by the site because an application restart was not performed after the database restart. To prevent recurrence, the application restart action will be added to the existing SOPs for both the product and infrastructure layers. | Solution & Recovery | Karthick GC | It has been confirmed that the step to restart the application stack has been updated in the existing SOP. | TPM |  | NA | 18/11/24 | Closed |  |  |  | Saloni | 2025-02-10 | 318 | >60 | November | 2024 | #VALUE!
GTS | Operations | 90422069 | 18/11/24 | Welham DC - WMS JDA Application unavailable | Review the alert handling SOP within PCM to ensure that incidents raised from the Netcool dashboard include timely callouts to the relevant product teams. | Issue handling/Management | Karthika Priya | 07/01: The SOP is created and cascaded to the Datacentre and Network teams 18/12: It has been agreed to pass on a sev 1 alert/ incident within 5mins and for sev2 within 10mins for DC and network towers. Agreement being made with product teams. 05/12: The SOP has been created, a call is scheduled with Raj K to review the SOP before closing this actions 19/11: It has been agreed to create an SOP with detailed timelines and actions followed by peer review with the leads. | PCM |  | NA | 2025-07-01 | Closed |  |  |  | Saloni | 2025-02-10 | 318 | >60 | January | 2025 | #VALUE!
GTS | ETP-On premise services | 90422069 | 18/11/24 | Welham DC - WMS JDA Application unavailable | Configure an alert based on the VM event logs and route it to the VMware team for early detection of the issue. | Problem identification & Alerting | DineshBabu Sathanam | 06/01: The event based alerting is now created in the VMWare layer. 18/12: A sev3 case has been raised with VMware and work is in progress to configure alerts 12/12: Product teams have encountered an issue after reviewing the VMware logs, since its a manual creation of an Event in VMware - need Vendor interventio, therefore, a case has been raised with VMware, awaiting updates. 05/12: Dinesh has advised that no work has been done on it as of now, teams will be working on configuring the alert by next week. ETA: 11/12 18/11: Wintel team will collaborate with Linux team to configure the alert in Netcool | Vmware |  | NA | 2025-06-01 | Closed |  |  |  | Saloni | 2025-02-10 | 318 | >60 | January | 2025 | #VALUE!
GTS | ETP-On premise services | 90422069 | 18/11/24 | Welham DC - WMS JDA Application unavailable | A workshop will be conducted with the database and Linux teams to enhance the effectiveness of alert handling for timely action and reducing incident recovery times | Problem identification & Alerting | Harish Kumar/ Jishin Jacob | The workshop was conducted to reiterate the team to handle alerts efficiently and inform relevant stakeholder and engage MIM | Linux/ Oracle |  | NA | 18/11/24 | Closed |  |  |  | Saloni | 2025-02-10 | 318 | >60 | November | 2024 | #VALUE!
Customer Channels | Customer Engagement | 90405232 | 18/11/24 | Sign in Pages not loading on Mobile Apps | During the incident there was an issue with agreeing the correct severity. Action to clarify the position of severity for this type of incident going forward | Issue handling/Management | Hisham Khalid | 02/12: As agreed with Steve Warren, guideline for the teams. There is guidance on raising incidents on the D&T sharepoint site - https://mnscorp.sharepoint.com/sites/ServiceManagement2/SitePages/Incident-Management.aspx. This includes guidance on severity that should be used to classify if something is an incident. Where something is an incident or a potential incident, I'd say it should be logged in the Incident Channel and a Remedy ticket raised. Where something is an issue, an remedy ticket should be created (see guidance on the sharepoint site). In a perfect world, teams should then pick this issue up and handle it as a BAU activity, within a defined SLA. Note: if someone isn't sure if something is an incident, they should raise it as an incident regardless...better to flag a non-issue than not flag an actual issue. 27/11: Inprogress | Service Management | Strategic | NA | 2024-03-12 | Closed |  |  |  | Kavitha | 2025-02-10 | 318 | >60 | December | 2024 | #VALUE!
Customer Channels | Selling Experience | 90405232 | 18/11/24 | Sign in Pages not loading on Mobile Apps | Update Secure Auth runbook to include a link to the CIAM Akamai dashboard for triaging acceptance test failure | Solution & Recovery | Identity Team | 16/01: Secure Auth runbook to include a link to the CIAM Akamai dashboard for triaging acceptance test failure has been updated 27/11: Inprogress | Identity Team | Tactical | NA | 16/01/25 | Closed |  |  |  | Kavitha | 2025-02-10 | 318 | >60 | January | 2025 | #VALUE!
Customer Channels | Selling Experience | 90405232 | 18/11/24 | Sign in Pages not loading on Mobile Apps | Explore whether it would be possible to alert on | Problem identification & Alerting | Mobile Apps Team | 16/01: Alerts have been confirgured 27/11: Backlog Mobile-1929 has been raised to review the alerts | Mobile Apps Team | Tactical | NA | 16/01/25 | Closed |  | Mobile-1929 |  | Kavitha | 2025-02-10 | 318 | >60 | January | 2025 | #VALUE!
Customer Channels | Customer Engagement | 90405232 | 18/11/24 | Sign in Pages not loading on Mobile Apps | Secure Auth Action to improve role back time | Problem Avoidance | Simon Attard | 16/01: canary metric has been implemented 27/11:Add a Canary metric to monitor the error rate for each individual path, allow Secure Auth to roll back the deployment if issues arise that affect endpoints with lower traffic. (Pending completion) | Secure Auth - 3rd Party |  | NA | 16/01/25 | Closed |  |  | NA | Kavitha | 2025-02-10 | 318 | >60 | January | 2025 | #VALUE!
Customer Channels | Selling Experience | 90405232 | 18/11/24 | Sign in Pages not loading on Mobile Apps | Review alert sensitivity and why no alert for 5xx errors went off | Problem identification & Alerting | Identity Team | 16/01: The alerting has been implemented 27/11: Backlog CIAM-1244 has been raised to review the alerts | Identity Team |  | NA | 16/01/24 | closed |  | CIAM-1244 |  | Kavitha | 2025-02-10 | 318 | >60 | January | 2024 | #VALUE!
GTS | ETP-On premise services | 90422175 | 18/11/24 | Carrier label printing issues at Ollerton DC on 14/11 | Review the SOP for the Linux environment to triage incidents related to print function errors, ensuring a systematic approach for quick diagnosis and resolution. | Solution & Recovery | Harish Kumar | 28/11: A workshop was conducted to reiterate the prioritisation of critical actions whilst triaging an incident. 18/11: During the issue, while it was clear that the entire carrier label printing operation was impacted, the Linux team conducted additional investigations as per the existing, which slightly delayed the incident recovery. As a result, it has been agreed to review the SOP to ensure that critical actions are clearly identified and prioritised whilst triaging a major incident. | Linux | Y | Na | 28/11/24 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 318 | >60 | November | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90422175 | 18/11/24 | Carrier label printing issues at Ollerton DC on 14/11 | Review the SOP to clearly define actions that must be taken when a print spooler alert is triggered due to more than 350 print jobs in the queue to mitigate any potential impact. | Solution & Recovery | Nandhakumar Saravanan | 28/11: The SOP has been reviewed by the SMEs. 18/11: We already have an existing SOP for clearing the print queues in such situations. However, it has been agreed to conduct a further review of this SOP to ensure that WMS engineers analyse the print jobs before requesting the Linux team to clear the queue. This additional step will help prevent any disruption to ongoing site operations. | WMS | Y | NA | 28/11/24 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 318 | >60 | November | 2024 | #VALUE!
GTS | ETP-On premise services | 90422175 | 18/11/24 | Carrier label printing issues at Ollerton DC on 14/11 | It has been concluded that an existing email alert is configured for the printspooler in the foods warehouses to notify if there are more than 350 print jobs in the queue. Therefore, it has been agreed to extend this alert to cover all warehouses. Additionally, the alert will be integrated with Remedy to enable proactive notification and timely mitigation of any issues. | Problem identification & Alerting | Harish Kumar, Saravanan, Nandhakumar | 28/11:The print spooler email alert configuration is completed for all the sites and remedy integration is completed to trigger an alert to WMS team upon breaching the threshold 18/11: It has been confirmed that the print spooler alert will be configured across all sites by next week. ETA: 22/11. Linux team will own the alert configuration, followed by WMS team owning the remedy intergration | Linux/WMS | Y | NA | 28/11/24 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 318 | >60 | November | 2024 | #VALUE!
GTS | ETP-On premise services | 90422175 | 18/11/24 | Carrier label printing issues at Ollerton DC on 14/11 | To prevent future disruptions to print functionality, we have identified two options for configuring a retry policy on the print queues: Retry Mechanism with Timeout: Configure the print queue to automatically retry failed print jobs for up to 5 minutes. If the job is still not processed successfully within this timeframe, it will be automatically deleted from the queue. Error Handling Policy: Implement an error policy on the print queue to ensure that a failed print job does not disrupt the queue. This will prevent job pileups and ensure the continuous flow of print tasks. | Permanent Fix | Jafar Sadiq | 30/01: Jafar is on annual leave, followed up with Jeeva and awaiting updates. As these changes involve modifications to the print queue configurations, it has been agreed to implement them after the golden quarter to avoid impacting peak operations. | Linux Support | N | 20/01/25 |  | Open | NA | NA | NA | Saloni | 2025-02-10 | 318 | >60 | January | 1900 | 90+ Days
C&H and Intl | C&H and Intl Supply Chain | 90422175 | 18/11/24 | Carrier label printing issues at Ollerton DC on 14/11 | Analyse Nature of Print Jobs: The WMS team will analyze the nature of the print jobs being sent to the affected printer to understand their origin and content. | Root cause | Jakkula, SaiPrasad | 28/11: The printer is an inbound printer used to print inbound tag labels and the print tasks sent to the printer were all valid ones from Tech side , it has been confirmed by the site that the printer had hardware issue and the printer was not closed properly whilst replacing the label film. WO raised to replace the faulty hardwre with Donington hardware support. 18/11: WMS team will perform a thorough analysis to identify the nature of the print jobs being sent to this printer. | WMS | Y | NA | 28/11/24 | CLosed | NA | NA | NA | Saloni | 2025-02-10 | 318 | >60 | November | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90422175 | 18/11/24 | Carrier label printing issues at Ollerton DC on 14/11 | Investigate Printer Status and Print Job Spike: Determine why the affected printer PZ5INB001 is marked as paused in the web interface and identify the root cause of the gradual increase in print jobs being sent to this printer. | Root cause | Ugne Sukaityte | 28/11: Ugne had managed to locate printer physically, confirmed user error when replacing label film as the printer was not fully closed to be able to print. Ops team monitored for couple days and it has been agreed to replace the printer as seems like it is problematic for users to do replacement. Ops raised BAU work order for hardware replacement - no software issues. 18/11: This action requires collaboration with site ops. | WMS | Y | NA | 28/11/24 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 318 | >60 | November | 2024 | #VALUE!
Customer Channels | Selling Experience | 90401735 | 18/11/24 | Ireland home page unavailable from some customers | Identify a correct process of escalating incidents and engaging the right people | Issue handling/Management | Hisham Khalid | 02/12: As agreed with Steve Warren, guideline for the teams. There is guidance on raising incidents on the D&T sharepoint site - https://mnscorp.sharepoint.com/sites/ServiceManagement2/SitePages/Incident-Management.aspx. This includes guidance on severity that should be used to classify if something is an incident. Where something is an incident or a potential incident, I'd say it should be logged in the Incident Channel and a Remedy ticket raised. Where something is an issue, an remedy ticket should be created (see guidance on the sharepoint site). In a perfect world, teams should then pick this issue up and handle it as a BAU activity, within a defined SLA. Note: if someone isn't sure if something is an incident, they should raise it as an incident regardless...better to flag a non-issue than not flag an actual issue. 28/11: Ideally it should be Tech Ops channel and that has the information of the on call service manager. Once confirmed as a Sev1 or 2 needs to move to Incident Channel but this requires a further discussion with Steve Warren. ETA: 05/12 02/12: As agreed with Steve Warren, guideline for the teams. There is guidance on raising incidents on the D&T sharepoint site - https://mnscorp.sharepoint.com/sites/ServiceManagement2/SitePages/Incident-Management.aspx. This includes guidance on severity that should be used to classify if something is an incident. Where something is an incident or a potential incident, I'd say it should be logged in the Incident Channel and a Remedy ticket raised. Where something is an issue, an remedy ticket should be created (see guidance on the sharepoint site). In a perfect world, teams should then pick this issue up and handle it as a BAU activity, within a defined SLA. Note: if someone isn't sure if something is an incident, they should raise it as an incident regardless...better to flag a non-issue than not flag an actual issue. | Service Manager | Y | NA | 2024-03-12 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 318 | >60 | December | 2024 | #VALUE!
Customer Channels | Selling Experience | 90401735 | 18/11/24 | Ireland home page unavailable from some customers | Investigate long term fix for the problematic header causing similar incidents | Permanent Fix | Nigel Magnay | 05/12: Nigel confirmed that he has passed it over to web platform - https://github.com/vercel/next.js/issues/52515 has been raised to traack it. 28/11: Nigel confirmed that work is in progress to identify a more simpler way to manage the cache through the IE homepage. This is already exisitng for UK site, being worked upon for IE under a JIRA. Awaiting the backlog id 21/11: Follow up to be done with Nigel on the course of actions or if it requires a backlog as the intermin caching fix is already considered | Software Dev Manager | N | NA | 2024-05-12 | CLosed | NA | https://github.com/vercel/next.js/issues/52515 | NA | Saloni | 2025-02-10 | 318 | >60 | December | 2024 | #VALUE!
Customer Channels | Selling Experience | 90401735 | 18/11/24 | Ireland home page unavailable from some customers | Update/add caching section to the Onyx repo in GitHub | Problem avoidance | Nigel Magnay | 28/11: Nigel has confirmed that the intermin fix to get Akamai to strip out the header that causes a problem works as expected. However, there is a separate action to identify a more simpler way to manage the cache through the IE homepage. This is already exisitng for UK site, being worked upon for IE under a JIRA. 21/11: Nigel is performing some tests in the lower environment to conclude successful caching | Software Dev Manager | Y | NA | 28/11/24 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 318 | >60 | November | 2024 | #VALUE!
Customer Channels | Selling Experience | 90401735 | 18/11/24 | Ireland home page unavailable from some customers | There was no significant order drop but it would be good to understand if there was any financial impact | Impact analysis | Jack Tye, Himanshu Khanna | 28/11: Jack Tye has confirmed that there is no financial impact due to this incident as customers would have just navigated to the PLPs 21/11: Himanshu and Jack are liasing with Business ops to identify the financial impact | Ops Manager | Y | NA | 28/11/24 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 318 | >60 | November | 2024 | #VALUE!
Customer Channels | Selling Experience | 90401735 | 18/11/24 | Ireland home page unavailable from some customers | No Alerting triggered for this incident – Action on Homepage team to ensure adequate alerting set up and working in case of future occurrence | Problem identification & Alerting | Syed Ibrahim | 08/11: The alerting has been configured | Product Manager | Y | NA | 2024-08-11 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 318 | >60 | November | 2024 | #VALUE!
GTS | Enterprise Integration | 90420458 | 14/11/24 | CD packing impacted due to Mule issue | An alert to be configured once the nproc value reaches 75% of its threshold | Problem identification & Alerting | Sivasubramani Pappusamy | Alert has been configured | Integration Services |  | NA | 14/11/24 | Closed |  |  |  | Naveen | 2025-02-10 | 322 | >60 | November | 2024 | #VALUE!
GTS | Enterprise Integration | 90420458 | 14/11/24 | CD packing impacted due to Mule issue | Workaround: To restart the Mule service during shift change with relevant approvals | Issue handling/Management | Sivasubramani Pappusamy | If the issue is identified through alert / monitoring the above workaround needs to be done until the permanent fix is applied 09/12 - Issues have not recurred and hence under monitoring 20/12- Issue still under monitoring and to be kept open till the deployment of change on Jan 14 16/01- Change deployment successful. | Integration Services |  | NA | 16/01/25 | Closed |  |  |  | Naveen | 2025-02-10 | 322 | >60 | January | 2025 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90420458 | 14/11/24 | CD packing impacted due to Mule issue | Temporary Fix: Based on IBM recommendation the nproc value to be increased to 8192 from 4096 | Problem avoidance | Martin Coy | It involves MQ/Mule refresh which requires a planned outage at the site, we are currently awaiting approval from the Site Ops to plan the activity 09/12 - Martin did not agree for a downtime during the peak. Next follow-up only during the new year , possibly deploy on 14th Jan 19/12 - CRQ212681 raised for the same for implementation on Jan 14th 10/01 - Change is on track for implementation on 14th Jan. Awaiting change completion 16/01- Change implemented successfully. | Service Lead |  | NA | 16/01/25 | Closed |  |  |  | Naveen | 2025-02-10 | 322 | >60 | January | 2025 | #VALUE!
GTS | Enterprise Integration | 90420458 | 14/11/24 | CD packing impacted due to Mule issue | Mule team is working on a code fix to handle the MQ resources unavailable scenario. | Permanent Fix | Sivasubramani Pappusamy | 02/12 - currently in development 09/12 - Currently testing is ongoing and ETA for completion is on 13th Dec 18/12 - No ETA received on the completion. Following up with team 19/12 - Change CRQ212681 raised to implement the property change and code fix on Jan 14th 10/01 - Change is on track for implementation on 14th Jan. Awaiting change completion 16/01- Change implemented successfully. | Integration Services |  | NA | 16/01/25 | Closed |  |  |  | Naveen | 2025-02-10 | 322 | >60 | January | 2025 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90392152 | 2024-12-11 | Castle Donington DC unable to pick orders due to controller fault issue | Do we have any alerting in place to detect the backlog of pending events within SSI? | Problem identification & Alerting | SSI | 13/11 - As per the contractual agreement with SSI, they are not expected to communicate to Customer on the alerts received. However, SSI confirmed they had the right alerting in place and were able to recover the services quickly once they were engaged. As we are moving away from the SSI contract this action cannot be taken further. | SSI Vendor |  | NA | 2024-12-11 | Closed | NA | NA | NA | Pavithra | 2025-02-10 | 324 | >60 | November | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90392152 | 2024-12-11 | Castle Donington DC unable to pick orders due to controller fault issue | Investigate the possibility of placing CCTV at key points of the automation | Problem identification & Alerting | Site OPS/ Webber, Dominic | 20/12 - It has been concluded that getting a New CCTV near the conveyor is not feasible as it involves costs and bugetting - Also seems like we have one CCTV at the other side of the conveyor which should cover the entire view. During the incident, the CCTV was in a different direction this not capturing the right image. It has now been adjusted as requried. 16/12 - Webber is still discussing with an approach for the CCTV installation. 27/11- Follow-up has been done, awaiting response Dominic webber 13/11 - To observe and record potential issues for further root cause investigations | CD site operations | N | NA | 20/12/24 | Closed | NA | NA | NA | Pavithra | 2025-02-10 | 324 | >60 | December | 2024 | #VALUE!
GTS | ETP-On premise services | 90404927 | 2024-12-11 | Store colleagues unable to access Foods CSSM application functionalities | Microsoft to investigate if there are any SQL server related errors. | Root cause | JACOB KUZHIVELI JACOB, JISHIN | 20/11: Microsoft updated that they could not find any abnormalities reported and on analyzing the system health extended events, they could see a session ID which executes some select query has consumed 95% of CPU for 250 Milliseconds, however it has not been logged and any other detail about the query, so we cannot determine what was the query, who triggered it and from where it was coming from, other than this there could not find any other abnormalities reported. So, if the issue reoccurs then during the issue time MS has suggested to execute a SQL_LogScout tool to generate further logs to investigate deeper on the issue. Hence, closing this action | Oracle DBA Support |  | NA | 20/11/24 | Closed |  |  |  | Gokul | 2025-02-10 | 324 | >60 | November | 2024 | #VALUE!
GTS | ETP-On premise services | 90404927 | 2024-12-11 | Store colleagues unable to access Foods CSSM application functionalities | Currently we do not have relevant alerting and we need to add alerts for the total active session count. | Problem identification & Alerting | JACOB KUZHIVELI JACOB, JISHIN | 27/11: Team has implemented the mail alert job which will trigger for every 5 mins to check if the session count is more than the threshold value of 250. Once the session count goes beyond the value of 250 then the mail will be triggered with the session count. 21/11: Oracle DB team has alerts, however team is working on improvising the alert to monitor the total active session count and to trigger as a SCOM alert | Oracle DBA Support |  | NA | 27/11/24 | Closed |  |  |  | Gokul | 2025-02-10 | 324 | >60 | November | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 90404927 | 2024-12-11 | Store colleagues unable to access Foods CSSM application functionalities | We need to revisit the long running query alert which is currently set at 20 secs. However, in CSSM there are a lot of queries that run for more than 20 seconds. We therefore need to reanalyse the threshold this alert should be set at. | Problem identification & Alerting | Gunapati, Srinivasulu | 05/12: Srini confirmed that the long running queries alert has been modified. 02/12: Srini updated that team has done the required changes and validations is in progress 27/11: Srini is working with SQL team on the alert 22/11: Colleagues in progress | CSSM |  | NA | 2024-05-12 | Closed |  |  |  | Gokul | 2025-02-10 | 324 | >60 | December | 2024 | #VALUE!
GTS | Enterprise Technology Platform | 90404927 | 2024-12-11 | Store colleagues unable to access Foods CSSM application functionalities | Check with Wintel team if there were any v-motions on the day of the incident that could have caused latency issue. | Root cause | JACOB KUZHIVELI JACOB, JISHIN | 20/11 - Wintel Team confirmed that there were no V-motion occurred recently. | Oracle DBA Support |  | NA | 20/11/24 | Closed |  |  |  | Gokul | 2025-02-10 | 324 | >60 | November | 2024 | #VALUE!
GTS | ETP-On premise services | 90404927 | 2024-12-11 | Store colleagues unable to access Foods CSSM application functionalities | For observability a change is planned post GQ to have Dynatrace monitoring and alerting on prem services - however currently this is not possible as it is causing excess resource consumption - a risk has been raised. | Problem identification & Alerting | Golder, Elizabeth/Sinha, Baxi Kaustubh | 17/12 - Risk has been raised 1746194389 06/12 - Baxi clarified that currently DynaTrace is not possible for On prem servers as it is in testing phase, hence Baxi is checking on the risk. But, additionally we have verified with Satya from tools team that there is no existing risk number and it needs to be raised by the concerned application team. 21/11 - Awaiting for risk details from Liz | Service lead |  | NA | 17/12/24 | Closed |  |  |  | Gokul | 2025-02-10 | 324 | >60 | December | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 90404927 | 2024-12-11 | Store colleagues unable to access Foods CSSM application functionalities | In case of a recurrency of this issue, CSSM team to work with DB teams to create a run book that support can follow to recover service in a timelier manner. | Solution & Recovery | Sinha, Baxi Kaustubh/Ravikumar S | 20/12 - Ravi shared the backlogs part of the backlog CSSM-13289, CSSM-13217 and CSSM-13215. 16/12 - Ravi is still getting the backlog raised for this activity 11/12 - Ravi updated that "We came up with Sot procedue to avoid the manual intervention and there is a query which needs to be validated and it would be planned in Sprint 6 and 7, backlog is available and he will share it shortly. 05/12 - Baxi updated that it is with Ravikumar S for approval and publishing, have followed up with him. 26/11 - Awaiting for the ETA for reviewal completion 21/11 - Baxi updated that the run book has been drafted and is under reviewal | CSSM |  | NA | 20/12/24 | Closed |  |  |  | Gokul | 2025-02-10 | 324 | >60 | December | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 90404927 | 2024-12-11 | Store colleagues unable to access Foods CSSM application functionalities | Analyse the Foods SST environment and see if we are appropriately scaled or whether we require any system uplift in terms of CPU/pods etc. | Permanent Fix | Gunapati, Srinivasulu | 05/12: Srini confirmed that no uplift is required and SQL team added a new alert if max connections exceed 250 with 5 min interval. 26/11: Srini updated that the testing is still in progress 21/11: Srinivasulu updated that SQL team is doing the testing with 30min interval currently | CSSM |  | NA | 2024-05-12 | Closed |  |  |  | Gokul | 2025-02-10 | 324 | >60 | December | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90396012 | 2024-12-11 | Issues with Knapp WCS automation in Welham DC impacting inbound boxed receipt | Overall root cause report to be provided by Knapp | Root cause | Piotr Milkowski (Knapp) | 20/11 - Report Received | KNAPP (3rd Party) |  | NA | 20/11/24 | Closed |  |  |  | Rehan | 2025-02-10 | 324 | >60 | November | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90396012 | 2024-12-11 | Issues with Knapp WCS automation in Welham DC impacting inbound boxed receipt | The alert mechanism at Knapp seems to be lacking, Knapp rely on the DC to report issues which is not a timely way of detention and observability. Knapp to review the alerting for this type of issue. | Problem identification & Alerting | Piotr Milkowski (Knapp) | 24/12: Customer change request raised with Knapp AG Customer Care Manager on 20/11/2024. The request number 236229. The change is in the review process the update would be shared after response from development. As the preventive action on site engineering team checks KiSoft errors on daily basis in Welham Green | KNAPP (3rd Party) |  | NA | 24/12/24 | Closed |  |  |  | Rehan | 2025-02-10 | 324 | >60 | December | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90396012 | 2024-12-11 | Issues with Knapp WCS automation in Welham DC impacting inbound boxed receipt | Change process to be reviewed by Knapp as Welham DC Operations were aware of the change but Customer D&T were not. Knapp to make Sivalingam, Nandakumar of all planned changes. Nanda to plan a joint change session for WG | Problem avoidance | Nandakumar Sivalingam | Change process all agreed | KNAPP (3rd Party) |  | NA | 2024-12-12 | Closed |  |  |  | Rehan | 2025-02-10 | 324 | >60 | December | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90396012 | 2024-12-11 | Issues with Knapp WCS automation in Welham DC impacting inbound boxed receipt | The Knapp MIM process seemed to be lacking and Customer D&T MIM's were leading all the way through. Paul Rowan advised that the WG support process was not followed properly due to Knapp being short staffed, this will be handled and resolved internally within Knapp. Paul to review the escalation process and advise who will lead Knapp issue calls and after how long can we expect engineers to be | Issue handling/Management | Paul Rowan (Knapp) | 24/12:The escalation process has been updated. The new version of the document with new escalation pyramid approved on site. The process is going to be follow in future incidents to reduce reaction time from consecutive escalation levels. 17/12: Chased for an update 02/12: Followed up for an update | KNAPP (3rd Party) |  | NA | 24/12/24 | Closed |  |  |  | Rehan | 2025-02-10 | 324 | >60 | December | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90396012 | 2024-12-11 | Issues with Knapp WCS automation in Welham DC impacting inbound boxed receipt | Knapp to provide a better reconciliation process/recovery process - dashboard. This should have a view for Customer D&T so we can identify issues in the order message flow between WCS and WMS | Solution & Recovery | Piotr Milkowski (Knapp) | This point is related to KiSoft dashboard from change request number 236229. The point taken form the incident for the message’s recovery is that the data should be recovered fully from back up on the server. This would allow reload all messages in around 2 hours. | KNAPP (3rd Party) |  | NA | 24/12/24 | Closed |  |  |  | Rehan | 2025-02-10 | 324 | >60 | December | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90396012 | 2024-12-11 | Issues with Knapp WCS automation in Welham DC impacting inbound boxed receipt | WMS product team to be more proactive with the manner of their collaboration and they need to reduce their dependency on emails - teams should be talking to each other to bring about more timely investigations. Sivalingam, Nandakumar to talk to support teams | Solution & Recovery | Nandakumar Sivalingam | Incident mangement process reiterated by Nanda | Service lead |  | NA | 2024-12-12 | Closed |  |  |  | Rehan | 2025-02-10 | 324 | >60 | December | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90396012 | 2024-12-11 | Issues with Knapp WCS automation in Welham DC impacting inbound boxed receipt | For seven hours, 00:35 - 07:00, support were investigating and trying to understand the issue - Nanda to communicate a standard triage process to all parties so that all teams including knapp can triage on a call. | Solution & Recovery | Nandakumar Sivalingam | IM process revisied to relevant teams | Service lead |  | NA | 2024-12-12 | Closed |  |  |  | Rehan | 2025-02-10 | 324 | >60 | December | 2024 | #VALUE!
Customer Channels | Selling Experience | 90414184 | 2024-11-11 | Digital Cafe stores reporting issue with blank screens on the kiosks impacting transactions | For the permanent fix, the problematic IIS service has been migrated to a higher infrastructure version to align with other critical API services in the environment | Permanent Fix | Pollard, Thomas Counter solutions | This action has been completed on 11/11, during the non-business hours without any disruption to the operations | Counter Solutions |  | NA | 2024-11-11 | Closed | NA | NA | NA | Pavithra | 2025-02-10 | 325 | >60 | November | 2024 | #VALUE!
Customer Channels | Selling Experience | 90414184 | 2024-11-11 | Digital Cafe stores reporting issue with blank screens on the kiosks impacting transactions | Review the existing alerting set-up, Explore the feasibility of enhancements to help capture the incident more proactively | Problem identification & Alerting | Pollard, Thomas Counter solutions | 31/12 - As the digital cafe kiosks functionality is a real time - howevere there is no alerting that we can set-up to capture the issue proactivley - However, resilience programme is which being worked upon is expected to fulful the proactive identification of the issue. 27/11 - Escalation email has been sent to counter solution - awaiting response 11/11 - CS has confirmed that relevant alerts were triggered within the Counter Solution, however whilst CS was performing initial checks, DN has started receiving calls from the stores. We have requested CS to review and enhance their existing alerting setup. | Counter Solutions | NA | NA | 31/12/24 | Closed | NA | NA | NA | Pavithra | 2025-02-10 | 325 | >60 | December | 2024 | #VALUE!
Customer Channels | Selling Experience | 90414184 | 2024-11-11 | Digital Cafe stores reporting issue with blank screens on the kiosks impacting transactions | Counter Solutions to review the synchronisation of the infrastructure hosting the other critical services. | Problem avoidance | Pollard, Thomas Counter solutions | 21/01 - All of CS infrastructal platform has been reviewed and eveything seems to be in-line. 15/01 - Awaiting update from CS 31/12 - Further follow-up will be made on the New year with CS 27/11 - Escalation email has been sent to counter solution - awaiting response | Counter Solutions |  | NA | 29/10/24 | Closed | NA | NA | NA | Pavithra | 2025-02-10 | 325 | >60 | October | 2024 | #VALUE!
Customer Channels | Selling Experience | 90414184 | 2024-11-11 | Digital Cafe stores reporting issue with blank screens on the kiosks impacting transactions | Improve communication process between Counter solutions and Customer. CS has agreed to improvise their communication process to ensure Customer is informed at the earliest as soon as they observe alerts from their end. | Issue handling/Management | Pollard, Thomas Counter solutions | 31/12- We have agreed with DN that they will be responsibile to provide or communicate to MS in case of any future incident within CS 27/11 - Escalation email has been sent to counter solution - awaiting response 11/11 -Counter solution to review their Distribution List (DL) and has agreed to include Customer stakeholders to it so that they can inform Customer as soon as they see the errors/alerts | Counter Solutions |  | NA | 31/12/24 | Closed | NA | NA | NA | Pavithra | 2025-02-10 | 325 | >60 | December | 2024 | #VALUE!
Customer Channels | Selling Experience | 90414184 | 2024-11-11 | Digital Cafe stores reporting issue with blank screens on the kiosks impacting transactions | Enhance the MIM engagement process within counter solutions for better communication and timely updates during a major incident. | Issue handling/Management | Pollard, Thomas Counter solutions | 31/12 - We have agreed with DN that a person from DN will be available on the MIM bridge co-odinating with CS. 27/11 - Escalation email has been sent to counter solution - awaiting response 11/11 -During the MIM bridge, there was no representative from counter solutions which was a challenge during the triage. CS has been advised on the same and it has been agreed. however, we will wait for an official confirmation on the MI process. | Counter Solutions |  | NA | 31/12/24 | Closed | NA | NA | NA | Pavithra | 2025-02-10 | 325 | >60 | December | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90381051 | 2024-07-11 | Intermittent label printing failures across multiple C&H sites | The distribution list (DL) for SORTED communications will be reviewed to ensure all relevant stakeholders are informed of any changes or updates during incident scenarios | Business & IT Communication | Jackie Martin | 28/11: Jackie has reviewed the DL and could confirm the relevant stakeholder are added to the DL to receive Sorted notifications 21/11: Jackie is still validating the DL and identify stakeholders to be added to the DL to receive Sorted comms | Ecomm transport Product team | Y | NA | 28/11/24 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 329 | >60 | November | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90381051 | 2024-07-11 | Intermittent label printing failures across multiple C&H sites | To reduce the recovery time in future incidents, Customer product teams will explore options to quickly identify the source of an issue—whether within SORTED, WMS, or the Mule layer. This will enable faster engagement with SORTED and streamline issue triage. | Problem identification & Alerting | David Moggs | 05/12: JDATE-10749 has been raised to drive this action. 21/11: This action requires engineering work and is currently being worked upon | Engineering manager | N | NA | 2024-05-12 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 329 | >60 | December | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90381051 | 2024-07-11 | Intermittent label printing failures across multiple C&H sites | Given the communication challenges during this incident, SORTED has agreed to notify Customer of any future changes deployed within their environment. Additionally, SORTED will review and improve their overall communication process to ensure timely updates in future instances. Note: SORTED is currently under a change freeze from November 1st. | Business & IT Communication | Sorted/ Jackie Martin | This action is completed, there Is an additional action to review the DL involved in Sorted communication to ensure appropriate stakeholders are updated upon a change implementation at Sorted causing business impact to Customer | Sorted Vendor | Y | NA | 2024-08-11 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 329 | >60 | November | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90381051 | 2024-07-11 | Intermittent label printing failures across multiple C&H sites | Sorted has acknowledged inefficiencies in their pre-deployment testing procedures. To prevent similar issues in the future, Sorted is enhancing their testing protocols to ensure more rigorous validation before deploying any further changes. | Problem avoidance | Sorted/Pragadesh Vasan | Sorted has confirmed that they have upheld their testing protocols to avoid any issues caused due to change. Note: Sorted are in change freeze from 1st Nov | Sorted Vendor | Y | NA | 2024-08-11 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 329 | >60 | November | 2024 | #VALUE!
GTS | ETP-On premise services | 90369835 | 30/10/24 | WMS application was inaccessible impacting Milton Keynes DC operations | Since this change was implemented a year ago, there is insufficient evidence to determine whether the Oracle Client was installed or if an underlying issue might have caused its uninstallation. Therefore, we have agreed to explore the feasibility of incorporating an appropriate logging mechanism after Oracle Client installations to ensure clear documentation of any actions taken on the Oracle database. | Problem identification & Alerting | JACOB KUZHIVELI JACOB, JISHIN | 28/11: We could find the installation logs outside the oracle client installation directory and utilized the same for our analysis. The oracle client was initially installed on the primary server on the same directory during the issue time, hence it reflects the logs on 25th Oct Based on the findings, we could see that Oracle 19c client was not installed in secondary application server - hlxp00dc141. We will append the Oracle client installation document to share this as evidence for any Oracle client installation on application servers. Additionally, validation and sign-off is required from both application and DB teams to ensure there is no gaps in this process. | Oracle DBA Support | N | NA | 28/11/24 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 337 | >60 | November | 2024 | #VALUE!
Foods | Foods Supply Chain | 90369835 | 30/10/24 | WMS application was inaccessible impacting Milton Keynes DC operations | It is recommended to explore the feasibility of performing an application failover after any critical change to verify application functionality and confirm the success of the change. However, this requires further discussions between the product team and site operations, as it may lead to an extended outage window. | Problem avoidance | Sundaravadivelu, Bhuvaneswari | 21/11: This is a stratgic action and requires planning with site for future changes to perform a failover as it involves site outage | TPM | N | NA | 21/11/24 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 337 | >60 | November | 2024 | #VALUE!
GTS | ETP-On premise services | 90369835 | 30/10/24 | WMS application was inaccessible impacting Milton Keynes DC operations | This incident highlighted clear gaps in the implementation plan and the maker-checker process during deployment. To address this, we have agreed to enhance the project template to require sign-off validations from both application and infrastructure teams, along with documented evidence (screenshots etc) following any critical actions. | Issue handling/Management | Selvaraj, Jeevanandhan JACOB KUZHIVELI JACOB, JISHIN | This process has been agreed | Infra | Y | NA | 21/11/24 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 337 | >60 | November | 2024 | #VALUE!
Foods | Foods Supply Chain | 90369835 | 30/10/24 | WMS application was inaccessible impacting Milton Keynes DC operations | While we await a detailed root cause analysis from Red Hat, they have recommended increasing the NFS timeout parameter to 120 seconds. Although this change can be made online, further discussions between the infrastructure and application teams will determine the necessity of this adjustment to ensure there is no cascading impact on the site. | Permanent Fix | Jeeva & Bhuvana | 05/02: Aligned with infra team on accommodating the nfs time out change as part of BY upgrade [22nd Feb - MK & 22-Mar - Bradford]. Task added in cutover plan. for the change -CRQ000000215863 04/02: Lisy to have further discussions with Jeeva on this. 24/01: Jeeva confirmed that this will be addressed as part of patching, however patching is currently on hold. 30/10: Due to Golden Quarter, this requires planning and assess the feasibility of when to perform the action | Infra/ Foods | Y | NA | 2025-06-02 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 337 | >60 | February | 2025 | #VALUE!
GTS | ETP-On premise services | 90369835 | 30/10/24 | WMS application was inaccessible impacting Milton Keynes DC operations | Collaborate with Red Hat to determine the underlying cause of the NFS timeout on the cluster and finalize the root cause analysis. | Root cause | Sathish Selvapilli/ Harish Kumar | REDHAT could not identify the root cause based on the logs provided | Linux | Y | NA | 28/11/24 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 337 | >60 | November | 2024 | #VALUE!
GTS | Enterprise Integration | 90337961 | 29/10/24 | Intermittently customers are seeing "Something went wrong" errors | Understand from Apigee why the issue reoccurred in the afternoon and was not detected and fixed immediately | Root cause | Shayolin | 23/12:The IP configs were incorrect due to issue in clean up process of external IPs from DNS record set as the Apigee router AWS instances went unresponsive. In addition, a dependent service, used by Google Apigee's stale IP cleanup job, was returning errors to somequeries and hence, this failure was not caught by the existing alerting system. The second instance of the issue on 11/1O occured when Google attempted to recreate the instance with IP address, for which the root cause is not known. 18/12: We have escalated this Meabh to get this escalated as there is no update from Apigee on the RCA. 27/11:. APIGEE has advised that their investigations is on hold due to BFCM (Black firday Cyber Monday) event and they still waiting for updates from their internal teams update on RCA. 04/11: Further escalations are being made for receving the RCA from the vendor | Apigee Vendor | Tactical | NA | 23/12/24 | Closed |  |  |  | Kavitha | 2025-02-10 | 338 | >60 | December | 2024 | #VALUE!
GTS | Enterprise Integration | 90337961 | 29/10/24 | Intermittently customers are seeing "Something went wrong" errors | Customer team to review their SOP for raising cases with Apigee | Supplier and support involvement | Shayolin | 27/11: SOP has been updated with the latest info to engagae APIGEE 29/10: The case was raised with Apigee X instead of Apigee Edge, this resulted in wrong engineer joining and caused a delay in investigation. Hence SOP needs to be updated | Enterprise Integration | Tactical | NA | 27/11/24 | Closed |  |  |  | Kavitha | 2025-02-10 | 338 | >60 | November | 2024 | #VALUE!
Customer Channels | Selling Experience | DN ref: 125579373 | 24/10/24 | Digital cafe orders not reaching the kitchen for preparation | We are expecting the root cause and resolution details from QSR - pending - Avalon.smith@countersolutions.com | Root cause | Avalon Smith/ CS | 12/11: We have got the root cause from CS stating "A failure in the underlying system to send an alert indicating an issue with the pod servicing the application. This pod failed to automatically restart after encountering out-ofmemory errors." Hence closing the action. 01/11: Adam Smith updated that CS is still working on the root cause. | Counter Solutions |  | NA | 2024-12-11 | Closed |  |  |  | Gokul | 2025-02-10 | 343 | >60 | November | 2024 | #VALUE!
Customer Channels | Selling Experience | DN ref: 125579373 | 24/10/24 | Digital cafe orders not reaching the kitchen for preparation | We need an incident report from DN as per our contract with them. | Root cause | Laura Whittle | 12/11: Adam Smith shared the incident report sent by CS 06/11: Laura has not yet got the PIR report from DN 29/10: Laura is OOO till 4th Nov | Service Lead |  | NA | 2024-12-11 | Closed |  |  |  | Gokul | 2025-02-10 | 343 | >60 | November | 2024 | #VALUE!
Customer Channels | Selling Experience | DN ref: 125579373 | 24/10/24 | Digital cafe orders not reaching the kitchen for preparation | We need better reporting on the failures from CS as there seems to be a lot of contradictions with the impact assessment from stores - it took time to disseminate which errors related to Customer only. Observability and alerting - Confirm with CS whether this error post resilience would be visible in Customer alerting and appear in logs? This would give us better visibility of the issue. Avalon to take this back to the CS and discuss with CD - head of product Jordan Cope and confirm. Resilience: We are eventually placing cafe kiosks onto the fluid and beanstore network, so they join with the till estate and they will have a Worldline PED like all other tills. This will allow offline capability, We are piloting in Colchester 3rd/4th | Impact analysis | Avalon Smith/ CS | 20/11: Adam shared the board link where we can track the backlogs: https://jira.marksandspencer.app/secure/RapidBoard.jspa?rapidView=10044&projectKey=RDC&view=detail&selectedIssue=RDC-568 12/11: Adam updated that Resilience has been rebaselined until Q4, however there are multiple Jira references are available. Awaiting for a backlog reference to close the action 01/11: Adam Smith updated that there is No Go decision by 6th, he will confirm us on the next action by 8th | Counter Solutions |  | NA | 20/11/24 | Closed |  |  |  | Gokul | 2025-02-10 | 343 | >60 | November | 2024 | #VALUE!
Customer Channels | Selling Experience | DN ref: 125579373 | 24/10/24 | Digital cafe orders not reaching the kitchen for preparation | The logging and replication of a DN log into Remedy does not seem to have been fully working recently. We get a daily report in the morning for all DN tickets that are open and Whittle, Laura will do a reconciliation to see if any are missing. She will then provide any missing tickets to Katie in DN. Katie will then look to see if there is a different way the tickets have been logged that has prevented a copy being created. | Permanent Fix | Whittle, Laura Katie Bullock (DN) | 05/01: As the replication of DN log in remedy is worked upon with another problem action for integration and is being tracked in it, closing this action. 23/12: Naveen hosted the call between DN & tools team and multiple actions have been agreed. Followup call scheduled on 7th Jan 16/12: Follow up mail sent to DN and is being escalated as well. 11/12: Based on 06/12 call, multiple actions have been agreed and are being worked upon. 04/12: DN flow (Customer, DN Out of scope ) is not configured in the QA environment and hence have suggested DN to send it via payload . we have a catch-up call with DN by 06/12 to understand on the way forward 26/11: Further plan is being devised. 18/11: Incidents closed in DN with closure code as "DN Out of scope" is not handled in Remedy, hence the Tools team have agreed to fix it. Awaiting next steps. 11/11: There was a call with Remedy and DN team on the integration and actions have been agreed with both of them. Followup call to be scheduled 29/10: Laura is OOO till 4th Nov | Service Lead |  | NA | 2025-05-01 | Closed |  |  |  | Gokul | 2025-02-10 | 343 | >60 | January | 2025 | #VALUE!
Customer Channels | Selling Experience | DN ref: 125579373 | 24/10/24 | Digital cafe orders not reaching the kitchen for preparation | Remedy team to fix the integration layer as the customer ID is coming up as Customer rather than the actual store. | Impact analysis | Laura Whittle | 29/01: Closing the action based on the BMC case ID as it is being tracked closely. 15/01: Tools team is actively working with DN & BMC (Case ID - Case 01913334) to fix the integration issues 07/01: Latest actions have been agreed with DN and awaiting updates 23/12: Naveen hosted the call between DN & tools team and multiple actions have been agreed. Followup call scheduled on 7th Jan. 11/12: Based on 06/12 call, multiple actions have been agreed and are being worked upon. 04/12: DN flow (Customer, DN Out of scope ) is not configured in the QA environment and hence have suggested DN to send it via payload . we have a catch-up call with DN by 06/12 to understand on the way forward 26/11: Further plan is being devised. 11/11: There was a call with Remedy and DN team on the integration and actions have been agreed with both of them. Followup call to be scheduled 29/10: Laura is OOO till 4th Nov | Service Lead |  | NA | NA | closed |  | BMC Case ID - 01913334 | Open | Gokul | 2025-02-10 | 343 | >60 | NA | #VALUE! | #VALUE!
Customer Channels | Selling Experience | DN ref: 125579373 | 24/10/24 | Digital cafe orders not reaching the kitchen for preparation | Reiterate the proper process on how to raise DN logs in Remedy so that the ticket will correctly appear in DN and Remedy. | Issue handling/Management | Laura Whittle | 07/01: This is related to integration issue and being tracked as part of other action, hence closing 23/12: Naveen hosted the call between DN & tools team and multiple actions have been agreed. Followup call scheduled on 7th Jan 11/12: Based on 06/12 call, multiple actions have been agreed and are being worked upon. 04/12: DN flow (Customer, DN Out of scope ) is not configured in the QA environment and hence have suggested DN to send it via payload . we have a catch-up call with DN by 06/12 to understand on the way forward 26/11: Further plan is being devised. 29/10: Laura is OOO till 4th Nov | Service Lead |  | NA | 2025-07-01 | Closed |  |  |  | Gokul | 2025-02-10 | 343 | >60 | January | 2025 | #VALUE!
Customer Channels | Service Experience | 90346086 | 23/10/24 | Worldine payment issue causing some Mastercard payments to be declined and/or go offline | Create an SOP for when to enable offline payments | Solution & Recovery | Himanshu Khanna | 23/01: Suzanne shared the Jira reference to track until the SOP is approved and published. 20/01: Suzanne has the SOP ready, but needs to secure required approvals and publish it. Hence, I have suggested to help us with a Jira reference to track it with which this action can be closed 16/01: Have scheduled a catchup with Suzanne on 20/01 09/01: Followed up with Suzanne and awaiting further updates 06/01: Suzanne is OOO until 8th Jan 23/12: Suzanne confirmed that she will be able to provide further updates by w/c 6th Jan 17/12: Suzanne updated that she has created a version of the decision tree & just need to complete a couple of updates, then just need to schedule time with the Payments Product team to run through and will update us before Christmas. 02/12: Have followed-up and awaiting further updates from Himanshu 27/11: Himanshu updated that Suzanne Miller is specifically working on it. 19/11: Himanshu updated that the team is working on SOP and will update us on it further 23/10: There needs to be clear guideline on what percentage of payment failure is acceptable, before going offline (can vary depending on time of the day). Moving payments offline, creates order fulfilment delays which could result in potential revenue loss. Offline payments also creates confusion for customers as they do not receive an email confirmation advising that an order has been placed |  |  | NA | 23/01/25 | Closed |  | PCAP-2294 |  | Gokul | 2025-02-10 | 344 | >60 | January | 2025 | #VALUE!
Customer Channels | Service Experience | 90346086 | 23/10/24 | Worldine payment issue causing some Mastercard payments to be declined and/or go offline | Explore options for improving Offline payment experience | Solution & Recovery | Hugh Routley | 23/01: Elaine confirmed that Hugh updated as 1.Offline payments is now implemented for both online and instore functions. 2.Offline for instore will be enacted when the instore checkout team believe that service degradation is significant enough that Offline will be better. Roughly the same criteria will be used by PCAP to do the same for Online. Hence, closing these actions 16/01 - Followed up with Elaine and awaiting further updates from Hugh 06/01 - Elaine updated that Hugh is currently working on both of these actions and they should possibly be completed by 10th 6/11 - 1. Chris advised that they are currently going through a discovery piece looking at offline payments for specific payment types. Once the discovery is complete, development can start. Plan is to get the change deployed in the new year (10/01/2025) 2. Need clear criteria about when to move to offline payments. Hugh will discuss with Jamie for initial thoughts and then work with Chris and Himanshu to confirm the process Nice to have (future requirement) . Once payment moved offline, automate the throttling back of on-line payments. 23/10 - There should be an option to enable offline payments for specific card/payment type or at a more granular level rather than all or nothing. Initial discussion has taken place: Possible options: 1. Card • Visa • Mastercard • Amex 2. Apple Pay 3. Google Pay 4. Sparks Any/all of these on/off in POG so it would work for both old and new world. The caveat - Gift Card, voucher, ClearPay and IFL would work as normal BUT not for a split payment. Need to decide whether or not to take any of this work forward |  |  | NA | 23/01/25 | closed |  |  |  | Gokul | 2025-02-10 | 344 | >60 | January | 2025 | #VALUE!
Customer Channels | Service Experience | 90346086 | 23/10/24 | Worldine payment issue causing some Mastercard payments to be declined and/or go offline | Change Management process | Issue handling/Management | Worldline /Gary Allenby | 22/11 - Gary confirmed that this action is complete. 19/11 - Sent mail to Gary and awaiting updates 23/10 - VIP Account modifications to follow the Change Management Process with the same constraints. Short Term | Worldline |  | NA | 22/11/24 | Closed |  |  |  | Gokul | 2025-02-10 | 344 | >60 | November | 2024 | #VALUE!
Customer Channels | Service Experience | 90346086 | 23/10/24 | Worldine payment issue causing some Mastercard payments to be declined and/or go offline | Train relevant stakeholders - Procedure enhancement to explain TID locking, with red warning message regarding the attention points. Short term action | Issue handling/Management | Worldline /Gary Allenby | 22/11 - Gary confirmed that this action is complete. 19/11 - Sent mail to Gary and awaiting updates 23/10 - VIP Account modifications to follow the Change Management Process with the same constraints. Short Term | Worldline |  | NA | 22/11/24 | Closed |  |  |  | Gokul | 2025-02-10 | 344 | >60 | November | 2024 | #VALUE!
Customer Channels | Service Experience | 90346086 | 23/10/24 | Worldine payment issue causing some Mastercard payments to be declined and/or go offline | Review alerting, steps/ checks that need to be performed to identify promptly the root cause. Short Term action | Problem identification & Alerting | Worldline /Gary Allenby | 22/11 - Gary confirmed that this action is complete. 19/11 - Sent mail to Gary and awaiting updates 23/10 - VIP Account modifications to follow the Change Management Process with the same constraints. Short Term | Worldline |  | NA | 22/11/24 | Closed |  |  |  | Gokul | 2025-02-10 | 344 | >60 | November | 2024 | #VALUE!
Customer Channels | Service Experience | 90346086 | 23/10/24 | Worldine payment issue causing some Mastercard payments to be declined and/or go offline | Gap analysis of Frontend (FE) configuration of the MCC code for each PSPID, brand. Short Term. If applicable plan a change to perform the update of empty MCC code in the FE | Problem identification & Alerting | Worldline /Gary Allenby | 09/12: Gary confirmed that this action was completed on 26th November 29/11: Followed up with Gary and awaiting updates in mail. 22/11: Gary updated that team is working on the Gap analysis and expected to be fixed by next week | Worldline |  | NA | 2024-09-12 | Closed |  |  |  | Gokul | 2025-02-10 | 344 | >60 | December | 2024 | #VALUE!
Customer Channels | Service Experience | 90346086 | 23/10/24 | Worldine payment issue causing some Mastercard payments to be declined and/or go offline | Review incident communication to improve updates to WL CSM/UK support. Short Term | Business & IT Communication | Worldline /Gary Allenby | 23/10: Done | Worldline |  | NA | 2024-06-11 | Closed |  |  |  | Gokul | 2025-02-10 | 344 | >60 | November | 2024 | #VALUE!
C&H and Intl | International Commercial Trading | 90320229 | 2024-10-22 | IFOS application was inaccessible on 4th Oct | Although the issue was identified at 12:30, the Minster team was only engaged at 14:00, contributing to the delay in recovery. It has been agreed that, moving forward, the Minster team will be engaged promptly, alongside the network and server teams, to expedite resolution. | Issue handling/Management | George Loizou | This has been completed | Service lead |  | NA | 2024-01-11 | Closed |  |  |  | Saloni | 2025-02-10 | 345 | >60 | November | 2024 | #VALUE!
C&H and Intl | International Commercial Trading | 90320229 | 2024-10-22 | IFOS application was inaccessible on 4th Oct | During the call, investigations were conducted from both network and server sides. The application server, which is shared between Customer and Minster, hosts multiple applications. A colleague from Minster referenced previous emails, identifying similar symptoms, and recommended a COM+ service restart, which resolved the issue. To reduce MTTR and incident recovery time, ensure a runbook is created to document the COM+ service restart procedure. | Solution & Recovery | Neil Livingstone/ George Loizou | 21/11: In terms of reviewing the Web server log, Minster have added this as a critical step to the runbook so that they can capture as much information as possible in the event of the issue recurring. 01/11: The document is current being creted in concurrence with Customer IFOS team and Minster | Minster |  | NA | 21/11/24 | Closed |  |  |  | Saloni | 2025-02-10 | 345 | >60 | November | 2024 | #VALUE!
C&H and Intl | International Commercial Trading | 90320229 | 2024-10-22 | IFOS application was inaccessible on 4th Oct | Review the IIS logs in the Minster environment to determine the root cause of the issue. | Root cause | Neil Livingstone/ Minster | 21/11: With the available logs, the cause of the issue could not be ascertained. Additional log capturing mechanism have been added to the SOP to identify the root cause in future scenarios. 01/11: We have received an update from Minster that the engineering team are currently reviewing thelogs | Minster |  | NA | 21/11/24 | Closed |  |  |  | Saloni | 2025-02-10 | 345 | >60 | November | 2024 | #VALUE!
Customer Channels | Selling Experience | 90335015 | 21/10/24 | Majority of customers cannot see Home Page content | Incident process /CMS to raise issue in Incident channel | Issue handling/Management | Khalid, Hisham | 02/12: As agreed with Steve Warren, Incident Channel will be used and not Tech Ops 27/11 - Follow-up has been made with the Hisham, waiting for a response 21/10 - The CMS product team was not aware of the incident channel proecss - delaying the incident triage with the right traction. Hisham has spoken to Darren and Satish to get a common agreement about the process. Until we conclude the final incident process - incidents will be posted on the TECH OPs channel and then to the incident channel for a MI call run by the Service Leads. Hisham will conclude the final decision on the agrees process and a huddle will be held to share the same with the engineers. | Service Owner |  | NA | 20/12/24 | Closed | NA | NA | NA | Pavithra | 2025-02-10 | 346 | >60 | December | 2024 | #VALUE!
Customer Channels | Selling Experience | 90335015 | 21/10/24 | Majority of customers cannot see Home Page content | Review the Runbook for restarting the services | Solution & Recovery | Sparkes, Luke/ Steven Warren | 26/12 -CMS team have clarity it is their responsibility to restart the service in event of service issue. Their runbooks have been updated to include how to gain access and how to contact ITops for assistance. 27/11 - Follow-up has been made with the Luke and Steve, waiting for a response 21/10 -There was confusion regarding which team is responsible for restarting the instances,for managing everything to do with their product including infra issues such as re-starting services or are the Infra team (Cloud Ops?) Luke to discuss with Steve and Advise | .com |  | NA | 26/12/24 | Closed | NA | NA | NA | Pavithra | 2025-02-10 | 346 | >60 | December | 2024 | #VALUE!
Customer Channels | Selling Experience | 90335015 | 21/10/24 | Majority of customers cannot see Home Page content | Review the Y accounts and token expiry mechanism | Problem avoidance | Sparkes, Luke/ Steven Warren | 26/12/ - CMS team have configured email notification forwards for their yaccounts. This is resolved for CMS 27/11 - Follow-up has been made with the Luke and Steve, waiting for a response 21/10 -The notification of token expiry was sent to the Y account email address which is not monitored. Although the CMS team now have a process in place so that emails from the Y account are forwarded to other emails, this same issue could impact other teams.The CMS team have suggested avoiding use of MY-account, use either Azure Container Registry or at least Azure - Github integration directly. However, this needs to be a process that all teams adopt not just CMS team. Luke to discuss with Steve. | .com |  | NA | 26/12/24 | Closed | NA | NA | NA | Pavithra | 2025-02-10 | 346 | >60 | December | 2024 | #VALUE!
Customer Channels | Selling Experience | 90335015 | 21/10/24 | Majority of customers cannot see Home Page content | Re-visit the alerting set-up | Problem identification & Alerting | Bychkhoz, Konstantin | 26/12 - . The CMS team have revised their alerting on API instance health and the relevant changes has been made 27/11 - Follow-up has been made with the Konstantin, waiting for a response 21/10 -A New Relic alert did trigger at 08:16 on 10th October (when all of the instances were lost and the incident started). However, more alerts based up Azure infrastructure would help determine that there is a genuine problem. Konstantin to review and set up | .com |  | NA | 26/12/24 | Closed | NA | NA | NA | Pavithra | 2025-02-10 | 346 | >60 | December | 2024 | #VALUE!
Customer Channels | Selling Experience | 90335015 | 21/10/24 | Majority of customers cannot see Home Page content | validate the DR set-up/ the Scaling mechanism | Problem avoidance | Kasmani, Aadil | 20/12 - Microsoft confirmed the instance dropping was caused by maintenance on their end and not related to scaling. Therefore the scaling action does not need to be progressed. Agreement with Luke Sparkes that this action can be closed off 27/11 - Follow-up has been made with the Aadil, waiting for a response 21/10 - Meeting to be held to discuss scaling of containers i.e. why did the container go down on the morning of the 10th, why scaled down to zero containers when we should have 6 healthy instances running. Do we need to progress the ticket raised with Microsoft or can we progress it internally? Aadil to set up a meeting with Luke Sparkes, Konstantin Bychkhoz and Vidhyasagar Balakrishnan 07/11 – Meeting setup for 08/11 with relevant members to follow up on this action | .com |  | NA | 20/12/24 | Closed | NA | NA | NA | Pavithra | 2025-02-10 | 346 | >60 | December | 2024 | #VALUE!
Customer Channels | Selling Experience | 90335015 | 21/10/24 | Majority of customers cannot see Home Page content | How effectively can we asess the impact by determining consumers of API | Impact analysis | Hawthorn, Elaine/ Kasmani, Aadil | 20/12 - Whenever an API is used via Apigee, out of the box it has a mechanism to identify the consumers of an API but for teams that do not use Apigee to connect to APIs, it will be on them to decide how they identify consumers . It varies by scenario. 21/10- Impact was hard to determine because it was not clear who the consumers of the CMS API were. Elaine and Aadil to see whether it is possible to get a central view of API Consumers. 07/11 – Requires a follow up with Elaine when she is back from leave, to clarify whether this needs to be a strategic decision rather than an action specific to this incident. 27/11 - Follow-up has been made with the Aadil, waiting for a response | .com |  | NA | 20/12/24 | Closed | NA | NA | NA | Pavithra | 2025-02-10 | 346 | >60 | December | 2024 | #VALUE!
Customer Channels | Selling Experience | 90335015 | 21/10/24 | Majority of customers cannot see Home Page content | Figure-out on how to make the home Page to take account of error object returned from GQL Mesh | Solution & Recovery | Kasmani, Aadil | 07/11 – Homepage team has created a Jira ticket to display previously cached content in the event an error is returned from the Content API. This action can be closed and followed up through the ticket. HPDLP-3478 21/10 -Generally Home Page team need to take account of error objects returned from GQL mesh. (A 200 response is returned along with an error object.)Also review whether there is any fallback content that should be shown | .com |  | NA | 2024-07-11 | Closed | NA | HPDLP-3478 | NA | Pavithra | 2025-02-10 | 346 | >60 | November | 2024 | #VALUE!
Customer Channels | Selling Experience | 90335015 | 21/10/24 | Majority of customers cannot see Home Page content | Revisit the PLP cache run book | Solution & Recovery | James Anderson | 27/11 - A series of improvements such as "parallalised scale-up operations for each region instead of sequential run", "reduce the wait after the scale-up" and prevent the 3 min delay" - has been made to the workflow for quick recovery 21/10 -James will revisit the runbook and review whether or not they need to have the 10 minute wait for PLP cache clears. | .com |  | NA | 27/11/24 | Closed | NA | NA | NA | Pavithra | 2025-02-10 | 346 | >60 | November | 2024 | #VALUE!
Group Platforms | Finance | 90358279 | 21/10/24 | cSAP linux patching impacting retail orders flow & BEAM reports | As colleagues from Stoke IT , CD IT reported delays in receiving orders in WMS , identify methods to proactively identify potential delays in sending retail orders to DC's and also communicate to them proactively | Problem avoidance | Neeraj Kumar | 25/10 - Team have included the dashboard pre-checks in the Night Shift HOTO mails.This helps the team to check the morning order interfacing details on time and to understand if there are any discrepancies in interfacing based on which we can proactively action if any issues and can send timely communications to the DC's. | WMS |  | NA | 25/10/24 | Closed |  |  |  | Naveen | 2025-02-10 | 346 | >60 | October | 2024 | #VALUE!
Group Platforms | Finance | 90358279 | 21/10/24 | cSAP linux patching impacting retail orders flow & BEAM reports | Amend the GMOR job dependency to ensure it executes only upon the completion of the current order date source jobs in SAP. | Problem avoidance | Bolisetty, Murali Venkata Sri Sai | 6/11 - Team planned to remove(User Hold) the weekly job which has incorrect Order date dependencies and extend the daily job to run on Sunday. Change deployed on 5th Nov and jobs are running fine. 30/10 - Murali discussed on job level changes with BEAM team and will work on job level changes 28/10 - Team is planning a call with BEAM team to make job level changes. Call is set-up tomorrow to finalize this 25/10 - Team collecting details of relevant jobs and have them reconfigured. Update expected on Monday 28th Oct | SAP |  | NA | 2024-05-11 | Closed |  |  |  | Naveen | 2025-02-10 | 346 | >60 | November | 2024 | #VALUE!
Group Platforms | Finance | 90358279 | 21/10/24 | cSAP linux patching impacting retail orders flow & BEAM reports | implement follow-up communication to be sent to relevant downstream systems in the event of any additional delays following a major outage. | Solution & Recovery | Bolisetty, Murali Venkata Sri Sai | Relevant communication will be sent | SAP |  | NA | 21/10/24 | Closed |  |  |  | Naveen | 2025-02-10 | 346 | >60 | October | 2024 | #VALUE!
Group Platforms | Finance | 90358279 | 21/10/24 | cSAP linux patching impacting retail orders flow & BEAM reports | Due to the lack of proactive identification of unprocessed data in SAP, it has been agreed to establish a volume threshold for unprocessed data. Additionally, assess the feasibility of configuring an alert based on this threshold. | Problem identification & Alerting | Karthikeyan Mariappan | 4/11 - Alert configuration is completed as well 28/10 - Feasibility checks completed. dashboard updated with the details, Technical team is working on the alert configuration 25/10 - Karthik in discussion with team on the alert feasibility and also have them reconfigured | SAP |  | NA | 2024-05-11 | Closed |  |  |  | Naveen | 2025-02-10 | 346 | >60 | November | 2024 | #VALUE!
Group Platforms | Finance | 90358279 | 21/10/24 | cSAP linux patching impacting retail orders flow & BEAM reports | On Reviewing gaps in the overall hypercare monitoring , agreed to address below gaps 1.Review the list of jobs in a wait condition during the batch recovery process. 2.Enhance the SOP to include validation of subsequent iterations of critical jobs. 3.Monitor the progress of jobs closely and check for jobs in wait conditions frequently during the batch catch-up process. | Problem identification & Alerting | Pawankumar M | 29/10 - Team reviewed SOP and made relevant corrections 25/10 - PFB status of the 3 action items 1. Team has been instructed to review the list of jobs in wait condition to avoid issues in future - Completed 2. Team reviewing the SOP and making required changes. ETA is on 28th Oct 3. Team has been instructed to monitor the jobs closely | SAP |  | NA | 28/10/24 | Closed |  |  |  | Naveen | 2025-02-10 | 346 | >60 | October | 2024 | #VALUE!
Group Platforms | Finance | 90358279 | 21/10/24 | cSAP linux patching impacting retail orders flow & BEAM reports | Review the implementation plan and incorporate additional steps to ensure proper actions are taken, including addressing jobs whilst holding the jobs and ensuring previous order date jobs are deleted before proceeding with the outage. | Problem avoidance | Pawankumar M | 25/10 - Pawan agreed to review the implementation plan and have a step included to clear the Control M jobs for the previous order dates before the cutover | SAP |  | NA | 25/10/24 | Closed |  |  |  | Naveen | 2025-02-10 | 346 | >60 | October | 2024 | #VALUE!
GTS | ETP-On premise services | 90358279 | 21/10/24 | cSAP linux patching impacting retail orders flow & BEAM reports | While there are existing alerts to identify issues with the first iteration of a cyclic job , there are no proactive alerting for subsequent iterations. Therefore , assess the feasibility of configuring an alert to notify the team if any iteration of a cyclic job fails to execute | Problem identification & Alerting | Sathya Malaiyandi | 26/03: Change implementation done. Verified with Pawan to close this action item 24/03: Change CRQ000000220856 raised for implementation tomorrow 20/03: Team to raise a change for implementation next week. 17/03: SAP confirmed that the pre-requisites are mqet and hence team will raise a change to move the code to production 13/03: Ignio completed End to end development and testing. Awaiting confirmation from SAP team if the requisites were met post which change will be raised next week to move the changes to production 08/03: Resource is aligned and testing ongoing. Will share status 04/03: Discussed with Ignio and confirmed that the development is complete and issues seen while testing. Team requested a SAP POC for testing .Discussed with Pawan who will align a resource for testing 26/02 - Testing/Validations still ongoing. 20/02- Team is planning a testing session with SAP team. Awaiting update from Ignio team 05/02- No ETA on the testing completion. Following up with Ignio team on a regular basis 27/01- Followed up with team and was informed that testing is ongoing and should receive an update by Friday 21/01 - Development is still getting delayed as team is stuck up. expecting an update by 24th Jan 10/01- Discussed with Ignio team and team is in progress to have an alert set-up to monitor the jobs every 30 minutes. If job is in stop state , incident to be triggered to the corresponding queue. Development is still in progress , ETA - 20th Jan 09/12- Ignio team received requirement and confirmed the feasibility. Development and configuration in progress. No changes to be done in SAP during peak . Hence change planned in Jan. ETA - 15th Jan 26/11 - This has escalated to Pradeep Kanna and awaiting for an ETA 21/11 - Still awaiting for an ETA from Ignio team 15/11 - Awaiting ETA from Ignio team 7/11 - Ignio team is still working on the alert configuration 4/11 - List of jobs were provided and Sathya is working with Ignio team for configuration 29/10 - Team still waiting for the list of jobs to validate 25/10 - Alerting not possible to be configured in BMC. Hence Exploring possibilities to configure alerting via Ignio automation . Awaiting details of SAP critical job list to be configured | Control M |  | 28/11/24 | 26/03/25 | Closed |  |  |  | Naveen | 2025-02-10 | 346 | >60 | March | 2025 | 90+ Days
GTS | ETP-On premise services | 90249161 | 20/10/24 | Intermittent label printing issues at Brands Thorncliffe DC | As a proactive measure, we have reached out to RedHat for recommendations on best practices for performing cluster activities. We have also shared our analysis based on previous issues observed with the Linux cluster and are currently awaiting their feedback | Problem avoidance | Harish Kumar | 28/11: On that day, site was able to print after the services were failovered to passive node. RedHat suggested us to get an outage window and failback the services from passive to active node and execute few commands to trace the issue. However, we didn't execute those commands as the issue didn't appear when failback was completed. We have relevant documents detailing recovery actions from Redhat to restore services in similar instances | Linux Support |  | NA | 28/11/24 | Closed |  |  |  | Saloni | 2025-02-10 | 347 | >60 | November | 2024 | #VALUE!
GTS | ETP-On premise services | 90249161 | 20/10/24 | Intermittent label printing issues at Brands Thorncliffe DC | We have agreed to add a step to ping the cluster IP while bringing up the cluster services, and this needs to be performed across all clusters. Additionally, it has been agreed to include the cluster IP reachability action in the recovery SOP for future issues to identify the source of the issue in a timely manner to reduce the recovery time | Solution & Recovery | Harish Kumar | 21/11: The additional step has been added to the implementation plan/SOP. | Linux Support |  | NA | 21/11/24 | Closed |  |  |  | Saloni | 2025-02-10 | 347 | >60 | November | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90249161 | 2024-10-20 | Intermittent label printing issues at Brands Thorncliffe DC | Enhance the existing alert by setting a threshold for sorted call failures within WMS database. This enhancement will ensure that the alert triggers proactively to identify similar scenarios in the future | Problem identification & Alerting | Karthick GC | 28/11: The alert has been created for the sorted call failures within the WMS Database for proactive issue identification | TPM |  | NA | 28/11/24 | Closed |  |  |  | Saloni | 2025-02-10 | 347 | >60 | November | 2024 | #VALUE!
GTS | Digital workplace Services | 90317186 | 2024-10-16 | Store colleagues experiencing issue authenticating when accessing SSO applications | As the work around was identified in a timely manner, impact was mitigated - but the scale of the impact was not clear on the day as we do not have appropriate alerting to identify authentication failures on store workstations. Farid Arab to ask Microsoft on how better we can proactively spot issues with authentication failures, if it is possible then this action may possibly lead to the building of a type of dashboard | Impact analysis | Farid Arab | 21/11 - Microsoft response below: There is no way to predict or prevent Authentication failures, as it’s only possible to identify them when they in fact happen. In a perfectly working environment, Authentication failures should be minimal. – This action can be closed | Active directory Team | Strategic | NA | 21/11/24 | Closed |  |  |  | Rehan | 2025-02-10 | 351 | >60 | November | 2024 | #VALUE!
GTS | Digital workplace Services | 90317186 | 2024-10-16 | Store colleagues experiencing issue authenticating when accessing SSO applications | Informational email sent to Farid Arab by Kocho on 03/10 at 10:24 after the change was done. They did not follow the change process and this needs to be reiterated to Kocho. All their changes now need to be passed to Farid for approval and Farid to communicate this to Kocho. Ideally an informational change should be raised in Remedy | Problem avoidance | Farid Arab | 21/11 - Explained to Kocho about Customer Change process on 16/10/24, and acknowledged by Kocho on the same day. – This action can be closed | Active directory Team | Strategic | NA | 21/11/24 | Closed |  |  |  | Rehan | 2025-02-10 | 351 | >60 | November | 2024 | #VALUE!
r | Digital workplace Services | 90317186 | 2024-10-16 | Store colleagues experiencing issue authenticating when accessing SSO applications | Kocho was not aware that a rename of a CA policy would require the refresh token to be renewed. - Farid Arab to explain Microsoft's root cause theory to Kocho | Root cause | Farid Arab | 21/11 - Explained to Kocho on 16/10/24, and acknowledged by Kocho on the same day. – This action can be closed | Active directory Team | Tactical | NA | 21/11/24 | Closed |  |  |  | Rehan | 2025-02-10 | 351 | >60 | November | 2024 | #VALUE!
GTS | Digital workplace Services | 90317186 | 2024-10-16 | Store colleagues experiencing issue authenticating when accessing SSO applications | The refresh token did not renew itself as it should have done, after it realized that the CA policy had been renamed. Farid Arab to work with Microsoft to find the cause of the failure to renew itself and how we can mitigate this if another policy is changed or renamed. | Root cause | Farid Arab | 21/11 - Microsoft response below: Noor Khaldi mentioned, further analysis on the matter will not be possible moving forward since the issue is not being reproduced at the moment. It would be difficult to provide an accurate analysis without have a complete log for the entire user flow after clicking the SPO link in your app launcher portal, this is mainly because we cannot assume the status of the SPOIDCRL cookie presented to SharePoint without having hard evidence to support our analysis. The issue hasn’t happened again – This action can be closed. | Active directory Team | Tactical | NA | 21/11/24 | Closed |  |  |  | Rehan | 2025-02-10 | 351 | >60 | November | 2024 | #VALUE!
GTS | Digital workplace Services | 90317186 | 2024-10-16 | Store colleagues experiencing issue authenticating when accessing SSO applications | Microsoft have advised that we should not delay any changes required on conditional access policies and have suggested the correct method to do this. Farid Arab to share Microsoft's suggestion on how to change a CA with Kocho | Problem avoidance | Farid Arab | 21/11 - Suggestions Shared with Kocho on 16/10/24, and acknowledged by Kocho on the same day, email response attached – This action can be closed | Active directory Team | Strategic | NA | 21/11/24 | Closed |  |  |  | Rehan | 2025-02-10 | 351 | >60 | November | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 90317186 | 2024-10-16 | Store colleagues experiencing issue authenticating when accessing SSO applications | On the day of the issue and subsequent days, multiple store colleagues called up reporting being impacted- how can we implement a bulk cache clear on store workstations if required? - currently the nightly cache clear excludes Microsoft application - why does it exclude. Microsoft apps? If no valid answer is given can this be remedied - Ramasamy, Valliammai to speak to Mukherjee, Pritamand Ramanujam, Deepakkumar. | Problem avoidance | Ramasamy, Valliammai | 29/01: Deepak advised we cannot do a bulk clear cache. This is the active policy in PROF from AD for Stores domain , where we don’t clear cache for MS based logins/token , the reason behind this is mentioned below If we configure the browser to clear the cache for all sites when Edge is closed. this will create the problems for our cloud based intranet application and Office365 apps , where we used pass through Azure authentication to authenticate. The reactive aspects of handling it through Tachyon will be checked later by team on need basis if required. 02/12: Chased for an update to Valli, Deepak and Pritam 21/11 - Valli chased Pritam and Deepak but with no success. | SIT Team | Strategic | NA | 29/01/25 | Closed |  |  |  | Rehan | 2025-02-10 | 351 | >60 | January | 2025 | #VALUE!
Customer Channels | Service Experience | 90350936 | 15/10/24 | Ready to collect email comms issue | Reiterate the proper process on how to raise DN logs in Remedy so that the ticket will correctly appear in DN and Remedy. | Problem identification & Alerting | Shantanu Singh | 18/12: Process has been reitrated as agree and Additional analysis using trend dashboard for comms volume, any drops can be visible | Service comms | Tactical | NA | 18/12/24 | Closed |  |  |  | Kavitha | 2025-02-10 | 352 | >60 | December | 2024 | #VALUE!
Customer Channels | Service Experience | 90350936 | 15/10/24 | Ready to collect email comms issue | 4 SFMC to Power BI feasibility of adding more frequency in data collection | Problem identification & Alerting | Shantanu Singh | 04/12: We have increased frequency of the data from salesforce but to get this update on Power BI we need to work with the beam as well as the Power BI team which is in progress at the moment. Also, we are simultaneously working with salesforce to create reporting instances for daily sends.A backlog to address this 15/10:Checking feasibility of fetching data from SFMC more frequently for the comms volume | Service comms | Tactical | NA | 18/12/24 | Closed |  |  |  | Kavitha | 2025-02-10 | 352 | >60 | December | 2024 | #VALUE!
Customer Channels | Service Experience | 90350936 | 15/10/24 | Ready to collect email comms issue | Add Service Comms team to the Volume check alerts | Problem identification & Alerting | Vipin Kumar | 18/12:Alerting has been confiruged 15/10; Request has been raised to add service comms team in the Job alert for visibility if any job runs fail. | Sterling Support | Tactical | NA | 18/12/24 | closed |  |  |  | Kavitha | 2025-02-10 | 352 | >60 | December | 2024 | #VALUE!
Customer Channels | Service Experience | 90350936 | 15/10/24 | Ready to collect email comms issue | Volume checks alert config for pending comms | Problem identification & Alerting | Vipin Kumar | 15/10: Additional check has been addedon sterling to check for the pending volumes and trigger alert based on the threshold | Sterling Support | Tactical | NA | 15/10/24 | Closed |  |  |  | Kavitha | 2025-02-10 | 352 | >60 | October | 2024 | #VALUE!
Customer Channels | Service Experience | 90350936 | 15/10/24 | Ready to collect email comms issue | Add a step in Control M job to filter errors and fail job if error found | Problem identification & Alerting | Vipin Kumar | 15/10: Step have been added in the Control-M Job to read the log file with every run and check for the keywords “Error Unable to connect” and Fail the Job on the control-m console helping with alert triggered to the respective teams to investigate the issue for mitigations required. | Sterling Support | Tactical | NA | 15/10/24 | Closed |  |  |  | Kavitha | 2025-02-10 | 352 | >60 | October | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90339674 | 2024-10-12 | Intermittent carrier label printing issues at C&H Ollerton DC | Identify the root cause behind the intermittent label printing failures although the daemons were recovered as per the SOP | Root cause | Girichandramohan, Karthick | 12/11 - Root Cause has been attributed to the long running query (Lib_Extract - responsible for DNR data extraction from WMS to OMS) which caused the order daemon to stall. Based on the existing alerting setup, the long running query was manually cleared which impacted the print Deamon causing the issue. | WMS |  | NA | 2024-12-11 | Closed |  |  |  | Gokul | 2025-02-10 | 355 | >60 | November | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90339674 | 2024-10-12 | Intermittent carrier label printing issues at C&H Ollerton DC | As part of Sev 3 incident, teams had not verified the "IT support Check" report to review the failure rates. Explore the feasibility of having the hourly check reports (IT support check) to cover all failure scenarios, currently it doesn't have physical print failures. Only Mule - > Sorted failure rate is available | Problem avoidance | Velumani, Deepika | 20/11 - Deepika confirmed that the print queue alert has been enabled for ollerton 08/11 - Deepika updated that "WMS team have been instructed to do the health checks including this report verification through out the day. The connectivity issue between the WMS server and the printers can be monitored by checking printer queue depth. Queue depth will be increasing on any connectivity failures." I have asked if there are any alerts, when the queue depth crosses the threshold. | WMS |  | NA | 20/11/24 | Closed |  |  |  | Gokul | 2025-02-10 | 355 | >60 | November | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90339674 | 2024-10-12 | Intermittent carrier label printing issues at C&H Ollerton DC | Enhance our fault-finding mechanism to identify the issue before securing an outage. Look at the automated script responsible for clearing deadlock on the database to ensure it is considering all the long running sessions | Problem identification & Alerting | Velumani, Deepika | 08/11 - Deepika updated that "Daemon stall SOP has been updated to follow the below process , Check for any long running session, Investigate the reason for long running deamon query Kill the long running session and deamon query, Restart the deamon. Do not restart the deamon multiple times." Based on this action is being closed | WMS |  | NA | 2024-09-11 | Closed |  |  |  | Gokul | 2025-02-10 | 355 | >60 | November | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90339674 | 2024-10-12 | Intermittent carrier label printing issues at C&H Ollerton DC | During Golden Quarter until the root cause and steps to investigate are known, if there is a recurrence of the issue, agree on a process to restore services without securing a site outage as a standard approach. | Solution & Recovery | Velumani, Deepika | 08/11 - Deepika updated that "Daemon stall SOP has been updated to follow the below process , Check for any long running session, Investigate the reason for long running deamon query Kill the long running session and deamon query, Restart the deamon. Do not restart the deamon multiple times." Based on this action is being closed | WMS |  | NA | 2024-09-11 | Closed |  |  |  | Gokul | 2025-02-10 | 355 | >60 | November | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90339674 | 2024-12-10 | Intermittent carrier label printing issues at C&H Ollerton DC | Enhanced SOP with respect to stale daemon alerts: To add the additional step to check the print request sessions on the database and relevant queries which are linked to the Daemon. | Issue handling/Management | Girichandramohan, Karthick | NA/10: Carrierprogress | WMS |  | NA | 2024-12-10 | Closed |  |  |  | Gokul | 2025-02-10 | 355 | >60 | October | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90339674 | 2024-12-10 | Intermittent carrier label printing issues at C&H Ollerton DC | Agree on a streamlined process in terms of site communication ensuring the right escalation process is followed during an issue - in this case, site should have reached out to the Service lead much earlier to report an issue. | Business & IT Communication | Davies, Mark Sivalingam, Nandakumar | NA/10: Carrierprogress | Service Lead |  | NA | 2024-12-10 | Closed |  |  |  | Gokul | 2025-02-10 | 355 | >60 | October | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90339674 | 2024-12-10 | Intermittent carrier label printing issues at C&H Ollerton DC | Tech communication to prioritize the label print incidents in collaboration with site ops through bridge calls | Business & IT Communication | Sivalingam, Nandakumar | NA/10: Carrierprogress | Service Lead |  | NA | 2024-12-10 | Closed |  |  |  | Gokul | 2025-02-10 | 355 | >60 | October | 2024 | #VALUE!
GTS | Operations | 90331061 | 2024-10-10 | Windows CE (compact edition) HHTs unable to connect to the network across various Foods and C&H DCs | During the security vulnerability remediation of the radius servers, proper impact assessment and testing was not performed. Hence, Service (Change) Management to review the communication and approval aspect of changes to ensure all relevant stakeholders are aware of the context of the change and implementation window | Problem avoidance | Priyadharshini S | 15/10: Change Team was reinstated to review the communication and approval aspect of changes to ensure all relevant stakeholders are aware of the context of the change and implementation window | Service Management |  | NA | 23/10/24 | Closed |  |  |  | Gokul | 2025-02-10 | 357 | >60 | October | 2024 | #VALUE!
C&H and Intl | C&H and Intl supply chain | 90331061 | 2024-10-10 | Windows CE (compact edition) HHTs unable to connect to the network across various Foods and C&H DCs | There was challenge in collating the number of Windows CE devices available in the estate during the issue. There is a central repository, where the list of Android and Windows CE devices are available. Also the plan for decommissioning these devices needs to be understood as Android devices may not have these types of issues | Impact analysis | Michael Arundel | 29/10: As expected, the CD report has all the Windows CE HHTs across all DC's in use with which at any point of time, we can access the impact. The plan for windows CE HHTs to be decommissioned is already in place and based on budget allocation, they will be completely changed to Android. Jira reference [WC-18] HHT Replacement and [WC-19] HHT - Truck Mounted device replacement. 15/10: Have got a sample report from CD team and it needs analysis on how it can be used. Also need to discuss with Michael on the plan of decommisioning these devices. 10/10: We (Warehouse Colleague Product / Castle Donington IT Support) also have an Excel which captures the data. \\gbhgmercser0021\pdg\Castle Donington Onsite IT Support\RDT's\AD_AllEnabledHHT Details.xlsx | Warehouse Colleague Team |  | NA | 29/10/24 | Closed |  | WC - 18, 19 |  | Gokul | 2025-02-10 | 357 | >60 | October | 2024 | #VALUE!
GTS | ETP-On premise services | 90331061 | 2024-10-10 | Windows CE (compact edition) HHTs unable to connect to the network across various Foods and C&H DCs | Review the description of the two radius servers in the CMDB as the Wintel team said that it does not reflect the fact that these radius servers are for windows CE device authentication in DC's | Impact analysis | Chandrakanth M | 13/11: Chandrakanth confirmed that is it complete 10/11: Work Order has been raised to update the details 29/10: Chandra had got the details from NOC team and to work with CMDB team to update the details 15/10: Chandra is raising a request to update it in the CMDB | Patching Team |  | NA | 13/11/24 | Closed |  |  |  | Gokul | 2025-02-10 | 357 | >60 | November | 2024 | #VALUE!
GTS | ETP-On premise services | 90331061 | 2024-10-10 | Windows CE (compact edition) HHTs unable to connect to the network across various Foods and C&H DCs | After applying any change to the group policy object, a reboot should be done so that the changes can take effect, we can see that this reboot was done but we need to investigate why the change did not take effect. At this stage the feeling is that the reboot was done too early and the change did not have time to replicate across the servers. We need to investigate this further - and review the method used - 15 minutes is needed to allow replication. | Problem identification & Alerting | Muthunagappan and Chandrakanth | 09/01: Muthu reconfirmed that Microsoft had no answers for the delay in replication of the change after the immediate restart of the server and also this is related to the HHT's being not compatible. Closing the action as the HHT's upgrade is being tracked as part of another action with Arundel and Colin to raise a risk. 06/01: Michael advised that Colin will be help us in raising the risk and he has been reached out 31/12: Have reached out to Michael Arundel on raising the risk and waiting for his update. 23/12: Had a connect with Nanda and he adivsed that Michael Arundel would be able to help in raising the risk and Mike is OOO till 30th Dec. 16/12: Had a connect with Balaji and Senthil, confirmed that the application team has to raise the risk. Need to check with NAnda on it. 26/11: Working with patching team to get a risk raised 20/11: Network team confirmed that the PEAP protocol will be supporting TLS version upgrades, however the Windows CE HHT devices are not compatible. Hence, a risk needs to be raised by patching team and mapped to C&H portfolio. 12/11: Call to be scheduled with Network team. 30/10: Based on the call with Microsoft, Muthu updated that " The communications are happening through TLS V1.0 and moreover HHT supports all the TLS versions up to TLS V1.2 which was confirmed by @Arundel, Michael so the wireless controller that connects HHT with Radius Server only supports PEAP which uses only TLS V1.O Protocol is the problem. Unless they allow from network layer, we cannot disable legacy TLS protocols. Need to get the plan of action with the Network team to allow latest TLS Protocols to sort out this issue." 22/10 - Microsoft has asked for additional logs and Muthu has shared it. 16/10: Microsoft went through the radius logs during the call, the TLS specialist referred the ticket to the network team to investigate further. 14/10: Muthu has raised a case with MS to understand this and we have a call scheduled at 8 PM on 15/10. 09/10: To investigate and get the policy change time and reboot time. Also, MSHSRMNSUKPU202 & MSHSRMNSUKP8202 - are win2019 and therefore in support, so raise a log with MS if the investigation with Muthu and Chandra doesn't make progress. | Patching Team |  | NA | 2025-09-01 | Closed |  |  |  | Gokul | 2025-02-10 | 357 | >60 | January | 2025 | #VALUE!
GTS | ETP- Connectivity,service & solution | 90331061 | 2024-10-10 | Windows CE (compact edition) HHTs unable to connect to the network across various Foods and C&H DCs | During the course of the MIM call, initially we were investigating the wrong Radius server which significantly delayed our investigation. The details were provided to us by Mustafa. We need to ascertain where Mustafa got these details from so we can correct any issues | Problem avoidance | Mustafa, Muzamil | 16/10: It was also agreed that the network team has to check in the SSID to provide the correct details. 09/10: Mustafa gave the stale radius configuration from the Wireless controller initially during the call and they were removed immediately | Network |  | NA | 16/10/24 | Closed |  |  |  | Gokul | 2025-02-10 | 357 | >60 | October | 2024 | #VALUE!
GTS | Digital Workplace Services | 90331061 | 2024-10-10 | Windows CE (compact edition) HHTs unable to connect to the network across various Foods and C&H DCs | Check all other radius servers to ensure they have been rebooted to ensure the risk of enabling an incompatible legacy protocol. | Problem avoidance | Muthunagappan | 20/11: Muthu confirmed that all the servers are rebooted and hence no impact. So, closing this action 29/10: Radius server details are obtained from NOC and Muthu is working on it further 16/10: Create a DC level mapping document, so that each radius server is mapped to its portfolio/application/devices etc. Ascertain who will be responsible for this document, where will it be stored etc. Also, muthu advised that TLS 1.0 and 1.1 has been re-enabled on Radius servers - plan to re-disable in a safe manner on all servers. | Active directory Team |  | NA | 20/11/24 | Closed |  |  |  | Gokul | 2025-02-10 | 357 | >60 | November | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90331061 | 2024-10-10 | Windows CE (compact edition) HHTs unable to connect to the network across various Foods and C&H DCs | As we disabled TLS version 1.0 and 1.1 and subsequently reverted this change, we are still running on legacy protocols. Chandra to devise a plan to address the vulnerability on the affected two radius servers | Problem avoidance | Colin Haworth/Duane B | 20/02: The existing risk 1574299878 - Active Directory Certificate Services (ADCS) unsupported for Handheld Terminals (HHT’s). Closing the action based on this. 18/02: Duane confirmed that there is an existing risk for the HHT issue, awaiting for risk ID to close this action. 10/02: We had a call with Colin and Duane, Duane agreed to raise a risk the radius servers are unable to patched 05/02: Sent a followup mail to Colin. 29/01: Spoke to Nanda and understood that David Moggs would be co-ordinating for the risk to be created and conveyed the same to Colin. 22/01: Understood from Serge that only Nanda/Murali have access to create risk 20/01: Colin has agreed to raise a risk and checking for the required access 06/01: Michael advised that Colin will be help us in raising the risk and he has been reached out 31/12: Have reached out to Michael Arundel on raising the risk and waiting for his update. 23/12: Had a connect with Nanda and he adivsed that Michael Arundel would be able to help in raising the risk and Mike is OOO till 30th Dec. 16/12: Had a connect with Balaji and Senthil, confirmed that the application team has to raise the risk. Need to check with NAnda on it. 26/11: Working with patching team to get a risk raised 20/11: Network team confirmed that the PEAP protocol will be supporting TLS version upgrades, however the Windows CE HHT devices are not compatible. Hence, a risk needs to be raised by patching team and mapped to C&H portfolio. 12/11: Call to be scheduled with Network team. 30/10: Based on the call with Microsoft, Muthu updated that " The communications are happening through TLS V1.0 and moreover HHT supports all the TLS versions up to TLS V1.2 which was confirmed by @Arundel, Michael so the wireless controller that connects HHT with Radius Server only supports PEAP which uses only TLS V1.O Protocol is the problem. Unless they allow from network layer, we cannot disable legacy TLS protocols. Need to get the plan of action with the Network team to allow latest TLS Protocols to sort out this issue." 22/10 - Microsoft has asked for additional logs and Muthu has shared it. 16/10: Microsoft went through the radius logs during the call, the TLS specialist referred the ticket to the network team to investigate further. 14/10: Muthu has raised a case with MS to understand this and we have a call scheduled at 8 PM on 15/10. 09/10: To investigate and get the policy change time and reboot time. Also, MSHSRMNSUKPU202 & MSHSRMNSUKP8202 - are win2019 and therefore in support, so raise a log with MS if the investigation with Muthu and Chandra doesn't make progress. | Patching Team/Product Manager-Warehouse Planning |  | NA | 20/02/25 | Closed |  |  |  | Gokul | 2025-02-10 | 357 | >60 | February | 2025 | #VALUE!
Customer Channels | Selling Experience | 90321513 | 2024-10-09 | Order Drop on Customer.com Website | Review option of using Optimizely to throttle down front-end traffic | Problem avoidance | Carles Andres | 27/11: Engineering Manager Peter Mouland rejected this proposal as it does not follow any standard practice at Customer to mitigate a backend problem by disabling a frontend feature. 21/10: In progress | Platform Runtime Team | Strategic | NA | 27/11/24 | Closed |  |  |  | Kavitha | 2025-02-10 | 358 | >60 | November | 2024 | #VALUE!
Customer Channels | Selling Experience | 90321513 | 2024-10-09 | Order Drop on Customer.com Website | Review whether there is scope for using the ongoing workstream for holding page/visitor prioritization to throttle front-end traffic when backend services are exhausted | Problem avoidance | Parit Shah | 16/01: We are not using Akamani and hence hold page is not feasible as the throttling is done using Optimizely 21/10: Review in progress | Platform Runtime Team | Strategic | NA | 16/01/25 | Closed | NA | NA | NA | Kavitha | 2025-02-10 | 358 | >60 | January | 2025 | #VALUE!
GTS | ETP- Connectivity,service & solution | 90321513 | 2024-10-09 | Order Drop on Customer.com Website | Establish root cause of latency observed on Availability Service | Root cause | Santhosh Gunda | 27/11: We found the network pool ( servers are mapped in the POOL for load balancing) was down on during the issue window. After the problem was reported the network team enabled the pool from Infoblox to fix the issue.However, we don't any information in the logs to indentify the RCA. 17/10: This was the first issue that occurred in the timeline and we should understand the cause of this behaviour and what can be done to prevent it in the future | Availability services | Tactical | NA | 27/11/24 | Closed |  |  |  | Kavitha | 2025-02-10 | 358 | >60 | November | 2024 | #VALUE!
Customer Channels | Selling Experience | 90327372 | 2024-10-09 | Delay in CSSM application availability after the SQL upgrade | During the incident the impact to Assist and ISF were not highlighted therefore It has been agreed to validate the existing alerting configuration for Assist and ISF applications | Problem identification & Alerting | Bakali, Junaid | 15/11- assist application had the right alerting and during the outage the alerts were observed and triaging was performed by the relevant product team, 16/10 -It has been confirmed that the alerts were suppressed during the change deployment. Assist and ISF applications the impacts were not called out during the incident. |  |  | NA |  | Closed |  |  |  | Pavithra | 2025-02-10 | 358 | >60 | January | 1900 | #VALUE!
Customer Channels | Platform & Store Ops | 90327372 | 2024-10-09 | Delay in CSSM application availability after the SQL upgrade | Review the impact statements and the underlying risk's associated whenever CSSM application is inaccessible/unavailable and ensure we review the communications that are being sent during any major outages in accordance with the systems that are impacted. | Impact analysis | Ramasamy, Valliammai/ Arunprasath, VijayS, Ravikumar | 15/11 - This action has been addressed -Impact statements are amended and updated as per the services that were impacted that day, 16/10 - Assist and ISF applications were impacted due to the delay in the CSSM application availability. However, as these applications were not highlighted as part of the impact statement, appropriate communications were not sent the respective stakeholders. |  |  | NA |  | Closed |  |  |  | Pavithra | 2025-02-10 | 358 | >60 | January | 1900 | #VALUE!
Customer Channels | Platform & Store Ops | 90327372 | 2024-10-09 | Delay in CSSM application availability after the SQL upgrade | Perform a detailed review of the implementation plan and the impact statement before planning a change. Also, make sure we have a simplified implementation plan with the categorizations of criticality for each of the steps and align with the right SME's to review each of the step. | Impact analysis | vs, RajaramanRamasamy, ValliammaiGunapati, Srinivasulu | 15/11 - This action has taken effect - It has been agreed by the with the product team and the servie management team - For a smooth incident transition and also to have a simplified change implementation document |  |  | NA |  | Closed |  |  |  | Pavithra | 2025-02-10 | 358 | >60 | January | 1900 | #VALUE!
GTS | ETP- Connectivity,service & solution | 90327372 | 2024-10-09 | Delay in CSSM application availability after the SQL upgrade | Ensure the availability of appropriate SME's and escalation contacts during any major changes | Solution & Recovery | Singarajan, Rajesh KumarPurushothaman, Lokesh/NOC Team | 14/11: Network to work with the change mgt and the owner of the team - any change should identofy the correct owners and SME's - this has been agreed and communicated. There was a challenge to engage the right Network SME to mitigate the issue since 05:50, which eventually delayed the CSSM availability beyond the change window. |  |  | NA | 14/11/24 | Closed |  |  |  | Pavithra | 2025-02-10 | 358 | >60 | November | 2024 | #VALUE!
GTS | Operations | 90327372 | 2024-10-09 | Delay in CSSM application availability after the SQL upgrade | Perform a thorough review of the change and incident transition process to ensure a proper and smooth handover in the future. | Issue handling/Management | Maluroutu, Dinesh Vijayan, Pavithra | 15/11 - It has been agreed by the with the product team and the servie management team - For a smooth incident transition and also to have a simplified change implementation documen 16/10 - There was a delay in the CSSM application availability beyond the planned change window, which impacted store operations and led to the issue being escalated as a high-severity incident. During the change implementation, the situation was handled differently by the project/product team, and the Major Incident Management (MIM) team did not switch over the technical teams to a separate MIM bridge to begin triaging the issue - this could have delayed the entire recovery process. Although the MIM team was involved at 8:30, by that time, the network issue had already been resolved and post-validation activities were in progress. However, there was a challenge with the control of the call, as there was no clear ownership. |  |  | NA |  | Closed |  |  |  | Pavithra | 2025-02-10 | 358 | >60 | January | 1900 | #VALUE!
GTS | ETP- Connectivity,service & solution | 90327372 | 2024-10-09 | Delay in CSSM application availability after the SQL upgrade | Change management team and the network team to update their SOP's and documentation to capture the above information for future scenario's | Problem avoidance | Somasundaram, Priyadharshini, Purushothaman, Lokesh Singarajan, Rajesh Kumar | 10/10: As part of due diligence, change management team will continue to review the network steps inline to the newness in the system (SP Exit) 09/10: As part of the SP exit, majority of the applications are migrated to Swindon which has led to various changes with the IP's and configurations. Thus going forward for any upgrades or migrations, review the network actions/task and validate if any extra steps or action is required at the network layer. |  |  | NA | 14/11/24 | Closed |  |  |  | Pavithra | 2025-02-10 | 358 | >60 | November | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 90327372 | 2024-10-09 | Delay in CSSM application availability after the SQL upgrade | Feasibility of enhancing the testing environments to more closely mirror the production setup. Additionally, there is a recommendation to reiterate the change management process, with a focus on thorough pre-implementation checks. | Problem avoidance | Arunprasath, Vijay/ S, Ravikumar Somasundaram, Priyadharshini | 15/11 - The process on effective testing has been re-iterated to the prodcut teams by the change management team. 10/10: Change Team was reinstated to review the pre-implementation checks during the cab review. 09/10: Although relevant testing was conducted in both the Cate and SIT environments, an issue arose during the change implementation in the production (PROD) environment. This occurred because the testing environments did not have disaster recovery (DR) capabilities and did not require host-based routing, which meant the issue was not identified during testing |  |  | NA |  | Closed |  |  |  | Pavithra | 2025-02-10 | 358 | >60 | January | 1900 | #VALUE!
Customer Channels | Platform & Store Ops | 90327372 | 2024-10-09 | Delay in CSSM application availability after the SQL upgrade | Once this information is provided, an internal meeting will be scheduled with the relevant teams to address any gaps and ensure alignment. | Business & IT Communication | vs, Rajaraman/ Gunapati, Srinivasulu | 15/11 - Timeline of the change implementation process has been shared by the project managers to the product team and internal review has been done and action has been agreed from the lessons learnt 16/10 -There were initial conflicts and disagreements between the product team and the infrastructure teams regarding the overall change review process. As a result, the product manager has been advised to provide a detailed timeline of the change review and the pre-checks that were conducted. |  |  | NA |  | Closed |  |  |  | Pavithra | 2025-02-10 | 358 | >60 | January | 1900 | #VALUE!
C&H and Intl | C&H and Intl supply chain | 90312719 | 2024-10-05 | Carrier label printing impacted across various C&H DC's | Explore options to create a comprehensive dashboard that highlights the impacted distribution centers, which will enhance our ability to assess the impact during incidents: | Impact analysis | Pragadesh vasan | 28/11: JDATE-10727 has been raised to create a dashboard to identify the impacted distribution centres during an incident. 21/11 : This requies collaboration across the TPMs of all sites. Plan being built Awaiting updates. | Donington TPM |  | NA | 28/11/24 | Closed |  | JDATE - 10727 |  | Saloni | 2025-02-10 | 362 | >60 | November | 2024 | #VALUE!
C&H and Intl | C&H and Intl supply chain | 90312719 | 2024-10-05 | Carrier label printing impacted across various C&H DC's | Prepare a runbook outlining the actions to be taken by the MULE and WMS teams when addressing carrier label printing issues | Solution & Recovery | Kunar Chichkar Varun S, Sivasubramani P | 21/11: The runbook has been reviewed by the respective leadership team. 16/10: The teams are currently reviewing their respective SOPs to identify any additional steps need to be incorporated. | WMS/Mule |  | NA | 21/11/24 | Closed |  |  |  | Saloni | 2025-02-10 | 362 | >60 | November | 2024 | #VALUE!
C&H and Intl | C&H and Intl supply chain | 90312719 | 2024-10-05 | Carrier label printing impacted across various C&H DC's | Identify the logic behind triggering the issue on 1st Oct, whether there are any jobs which process the changes made overnight: | Root cause | Sorted/Pragadesh Vasan | 21/11: The Customer Carrier Management Team is a team of Customer Business Users. It is their accountability to have full administrative rights to the Sorted carrier management system. In fact, one of the main reasons why Customer decided to migrate from the Metapack carrier management system to the Sorted carrier management system in 2020 was that the Sorted Carrier Management System allows business users to have full administrative control over the system which is fundamental to their business operation. It was therefore entirely correct that the Customer Carrier Management Team should be regularly housekeeping unnecessary user accounts. What the Customer Carrier Management Team user was not aware of at the time, was that the user account in the name of “Gary Bennett is, in fact, the Sorted Ship API key account. Since the incident on 1st October, the Customer Business Carrier Management Team has now learned the lesson and will leave the user account in the name of Gary Bennett untouched until a more resilient and appropriate system of site-specific Sorted Ship API key accounts will be set up during Q4. This incident was caused purely by a BAU business user housekeeping adminstrative process and has nothing to do with overnight batch jobs or anything similar. Awaiting updates from Sorted | WMS |  | NA | 21/11/24 | Closed |  |  |  | Saloni | 2025-02-10 | 362 | >60 | November | 2024 | #VALUE!
C&H and Intl | C&H and Intl supply chain | 90312719 | 2024-10-05 | Carrier label printing impacted across various C&H DC's | Identify any other user accounts linked to the core authentication API for other DCs | Problem avoidance | Jackie Martin | 08/10: It has been confirmed that the same User Account (Gary Bennett) has been used in the configuration of all the Customer Dispatcher warehouse sites integration with Sorted Ship. There are no other User Accounts which are at risk of causing the same issue if housekept. Bradford C&H warehouse uses a different warehouse management system (not Dispatcher) and, in consequence, the integration architecture with Sorted Ship is designed differently. It is, nevertheless, our intention that the eventual API key model that we adopt in Q4 will follow the same pattern across all shipping locations (warehouses), including the Bradford Clothing & Home warehouse. In fact, the Customer Solution Architect designed a more robust API key structure a couple of years ago as part of a different project, but the design was not progressed (at the time) to implementation. | Ecomm transport Product team |  | NA | 2024-08-10 | Closed |  |  |  | Saloni | 2025-02-10 | 362 | >60 | October | 2024 | #VALUE!
C&H and Intl | C&H and Intl supply chain | 90312719 | 2024-10-05 | Carrier label printing impacted across various C&H DC's | Explore options to either remove the visibility of Gary’s account or grey out any features to prevent any changes or deletions by individuals | Problem avoidance | Sorted/Pragadesh Vasan | 21/11: The "Gary Bennett" user account has already been redefined in the Sorted Ship administrator UI as a technical user account which is not to be housekept. Since the maintenance of user accounts is BAU functionality and is owned by the Customer Carrier Management Team, there is no option to prevent access to the account by any user with full admin permissions. The Customer Carrier Manageemnt Team has already completed an audit of users who have administrative permissions to Sorted Ship and anyone whose role does not require administrative access has been removed Awaiting updates from Sorted | WMS |  | NA | 21/11/24 | Closed |  |  |  | Saloni | 2025-02-10 | 362 | >60 | November | 2024 | #VALUE!
C&H and Intl | C&H and Intl supply chain | 90312719 | 2024-10-05 | Carrier label printing impacted across various C&H DC's | Review the existing admin access for the Sorted UI and perform housekeeping as necessary to ensure that only relevant personnel have access to the Sorted console. This will help prevent any mistakes in the future. | Problem avoidance | Jackie Martin | 08/10: It has been confirmed that the same User Account (Gary Bennett) has been used in the configuration of all the Customer Dispatcher warehouse sites integration with Sorted Ship. There are no other User Accounts which are at risk of causing the same issue if housekept. Bradford C&H warehouse uses a different warehouse management system (not Dispatcher) and, in consequence, the integration architecture with Sorted Ship is designed differently. It is, nevertheless, our intention that the eventual API key model that we adopt in Q4 will follow the same pattern across all shipping locations (warehouses), including the Bradford Clothing & Home warehouse. In fact, the Customer Solution Architect designed a more robust API key structure a couple of years ago as part of a different project, but the design was not progressed (at the time) to implementation. | Ecomm transport Product team |  | NA | 2024-08-10 | Closed |  |  |  | Saloni | 2025-02-10 | 362 | >60 | October | 2024 | #VALUE!
C&H and Intl | C&H and Intl supply chain | 90312719 | 2024-10-05 | Carrier label printing impacted across various C&H DC's | It is mandatory to obtain Customer tech approval before deleting any users or making general admin changes within Sorted | Problem avoidance | Murali Srinivasan | This action is completed | Donington service lead |  | NA | 2024-05-10 | Closed |  |  |  | Saloni | 2025-02-10 | 362 | >60 | October | 2024 | #VALUE!
C&H and Intl | C&H and Intl supply chain | 90312719 | 2024-10-05 | Carrier label printing impacted across various C&H DC's | Relevant stakeholders with admin rights to the Sorted UI console are advised not to modify or delete Gary’s account until further notice | Problem avoidance | Murali Srinivasan | This action is completed | Donington service lead |  | NA | 2024-05-10 | Closed |  |  |  | Saloni | 2025-02-10 | 362 | >60 | October | 2024 | #VALUE!
C&H and Intl | C&H and Intl supply chain | 90312719 | 2024-10-05 | Carrier label printing impacted across various C&H DC's | Devise a plan to change the Sorted API setup across all DCs, eliminating the use of personal accounts like Gary’s. Instead, product teams should aim to adopt a more standardized naming convention, such as ‘Donington Prod.’ etc This is part of a long-term approach currently being managed by the product teams | Permanent Fix | Pragadesh vasan | 28/11: JDATE-10729 has been raised to standardise the Sorted API set up across all DCs 21/11: A Q4/Q1 initiative to migrate each Customer shipping location to a unique and appropriately-named API key user account has already been discussed with Sorted and the Customer Architecture team. The initiatve will be included in Q4 and Q1 Quarterly Planning. The design for Dispatcher WMS locations has already been completed. Awaiting backlog id. 16/10: This is a long term project, we are currently awaiting updates from the initial discussion happened last week | Donington service lead |  | NA | 28/11/24 | Closed |  |  |  | Saloni | 2025-02-10 | 362 | >60 | November | 2024 | #VALUE!
C&H and Intl | C&H and Intl supply chain | 90312719 | 2024-10-05 | Carrier label printing impacted across various C&H DC's | Assess the feasibility of configuring an alert at Sorted to detect a order drop from Customer. This will enable Sorted to begin investigating potential issues on their side proactively, before Customer reports the issue or engages them | Problem identification & Alerting | Sorted/Pragadesh Vasan | 18/12: Sorted has made some modifications to the existing alerting to address the proactive identification of an issue. 12/12: Jackie Martin has raised two CR's regarding improvement of clarity in API response messages which have been accepted into the Sorted product backlog but no delivery timescales have yet been communicated. These changes are being incorporated into Sorted's strategic product and platform for all their customers. It's not like an Customer-specific config change. In due course we will learn from Sorted where these enhancements have been prioritised in their strategic roadmap. Awaiting the Sorted backlog id 05/12: FOllow up with Jackie continues. 28/11: Praga is following up with Jackie Martin to procure an update from Sorted. 21/11: Sorted already has many alerts in place. It is believed that the issue did not rigger alerts in Sorted because the API key information is cached. Sorted investigation is still under way to provide clarity about why there was a delay between the action by the Customer user and the Customer shipping locations being impacted. 16/10: Donington TPM is currently working with Sorted to improve the scope of alerting for effective issue identification | WMS |  | NA | 18/12/24 | Closed |  |  |  | Saloni | 2025-02-10 | 362 | >60 | December | 2024 | #VALUE!
C&H and Intl | C&H and Intl supply chain | 90312719 | 2024-10-05 | Carrier label printing impacted across various C&H DC's | Explore the feasibility of creating an alert or dashboard at Sorted to help identify authentication issues in the future. Additionally, regarding the 400 error that was observed on Sorted’s end, assess the feasibility of configuring a 401 error to clearly indicate authentication issues and streamline issue identification | Problem identification & Alerting | Sorted/Pragadesh Vasan | 18/12: Sorted has made some modifications to the existing alerting to address the proactive identification of an issue. 12/12: Jackie Martin has raised two CR's regarding improvement of clarity in API response messages which have been accepted into the Sorted product backlog but no delivery timescales have yet been communicated. These changes are being incorporated into Sorted's strategic product and platform for all their customers. It's not like an Customer-specific config change. In due course we will learn from Sorted where these enhancements have been prioritised in their strategic roadmap. Awaiting the Sorted backlog id 05/12: FOllow up with Jackie continues. 28/11: Praga is following up with Jackie Martin to procure an update from Sorted. 21/11: Customer Requests to improve the clarity of root cause messaging when a Sorted API call fails are currently in impact assessment by Sorted internal teams. 16/10: Donington TPM is currently working with Sorted to improve the scope of alerting for effective issue identification | WMS |  | NA | 18/12/24 | Closed |  |  |  | Saloni | 2025-02-10 | 362 | >60 | December | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 90310072 | 2024-10-04 | ESEL (electronic shelf edge labels) not updating in a timely manner. | a thorough analysis of logs and metrics was conducted | Root cause |  | A specific job was identified responsible for the disruption | ECS Team |  | NA | 2024-04-10 | Closed |  |  |  | Gokul | 2025-02-10 | 363 | >60 | October | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 90310072 | 2024-10-04 | ESEL (electronic shelf edge labels) not updating in a timely manner. | To avoid recurring of the issue | Permanent Fix |  | The specific job responsible for the issue was disabled | ECS Team |  | NA | 2024-04-10 | Closed |  |  |  | Gokul | 2025-02-10 | 363 | >60 | October | 2024 | #VALUE!
Customer Channels | Selling Experience | 90317889 | 2024-10-03 | Nominated day delivery issue | Switch off calendar Date as a test by end of a calendar month and observe if a similar issue with orders being placed for the day after the closed calendar date (if the issue is reproduced) | Problem identification & Alerting | Ops Hub/WCS Team | 31/12: Aadil updated that issue resurfaces, Whenever CD calendar date is switched off during an activity, then this issue pops up. However, the root cause is still unknown and the teams are regrouping in Jan to discuss and agree on the next steps. As they have identified the initial cause, closing this action. 20/11: Network team is actively analysing the root cause 12/11: We have escalated to Network Lead to get traction 07/11: Aadil has escalated the incident to get update on the analysis 28/10: Aadil updated that ticket has been raised with the network team - 90347907 to analyse 22/10: Teams are still working on this incident. 03/10: Nominated delivery issue has recurred on 3rd Oct after 9th Sep - 90249161 and team is working on this action with the new ongoing incident | WCS |  | NA | 31/12/24 | Closed |  |  |  | Gokul | 2025-02-10 | 364 | >60 | December | 2024 | #VALUE!
Customer Channels | Selling Experience | 90281344 | 2024-09-30 | Central network connectivity issue impacting various services | Digital Cafes: Retail stakeholders had reported that stores encountered challenges in raising incidents through the DN Helpdesk. It appears that they were unable to successfully report issues via the DN Helpdesk system. Investigate what went wrong that caused the stores to be unable to report the issue on the day of the incident. Although the Digital Cafe kiosks were not accepting any transactions due to the issue, Counter Solutions advised that there were no indications of a problem on their end. | Problem identification & Alerting | Katy Bullock (DN) | 12/12: A review of call times was performed by DN inline with the timelines provided by Customer and it has been concluded that there were no issues at DN side. 28/11: We were advised of an ETA by CS of 25/11, however, there has been no update on the actions. We have escalated to every possible levels, however, no update yet. Further actions being agreed with Paul and co. 21/11: Upon multiple follow ups, no response received from CS. An escalation email will be sent with Darren to get further updates | DN |  | NA | 2024-12-12 | Closed |  |  |  | Saloni | 2025-02-10 | 367 | >60 | December | 2024 | #VALUE!
Customer Channels | Selling Experience | 90281344 | 2024-09-30 | Central network connectivity issue impacting various services | Digital Cafes: There was a delay in engaging DN & Counter solutions on the incident call. The DN colleague on our bridge had reached out to the first level team at Counter Solutions. There was no proper representation from counter solutions on the call to address the incident further. Therefore, it is important to identify appropriate contacts eg: Duty manager, especially over weekends or overnight, for efficient engagement during a major incident | Supplier and support involvement | Katy Bullock (DN) | 12/12: RIchard Appleby (DN) has confirmed process agreed that DN and CS will both join the MIM incident calls, CS will confirm they have received the ticket and will drop to continue working on it whilst DN remain as a POC. 28/11: We were advised of an ETA by CS of 25/11, however, there has been no update on the actions. We have escalated to every possible levels, however, no update yet. Further actions being agreed with Paul and co. 21/11: Upon multiple follow ups, no response received from CS. An escalation email will be sent with Darren to get further updates | DN |  | NA | 2024-12-12 | Closed |  |  |  | Saloni | 2025-02-10 | 367 | >60 | December | 2024 | #VALUE!
Customer Channels | Selling Experience | 90281344 | 2024-09-30 | Central network connectivity issue impacting various services | Digital Cafes: Although the Digital Cafe kiosks were not accepting any transactions due to the issue, Counter Solutions advised that there were no indications of a problem on their end. Identify the mechanism and understand why there were no insight of an issue at Counter Solutions when clearly all the Digital Cafe kiosks were unavailable at that moment. This should also include the feasibility of E2E testing of a fix implemented to provide a confirmation of the resolution | Problem identification & Alerting | Katy Bullock (DN) | 12/12: The existing observability at CS includes a 15 mins heartbeat check to the kiosks. A report is being build to highlight the Open/Closed kiosks. A new relic alert has already been configured if there are no records of transactions across each stores/all stores for 5 mins. With Resilience, the scope of alerting will be enhanced. 28/11: We were advised of an ETA by CS of 25/11, however, there has been no update on the actions. We have escalated to every possible levels, however, no update yet. Further actions being agreed with Paul and co. 21/11: Upon multiple follow ups, no response received from CS. An escalation email will be sent with Darren to get further updates | DN |  | NA | 2024-12-12 | Closed |  |  |  | Saloni | 2025-02-10 | 367 | >60 | December | 2024 | #VALUE!
Customer Channels | Selling Experience | 90281344 | 2024-09-30 | Central network connectivity issue impacting various services | Digital Cafes: During the incident, it was advised that due to lack of visibility to the device or kiosk IP address at the store, no further troubleshooting was possible from Customer side. However, Counter Solutions have a remote facility to diagnose issues on a store kiosk. Identify what measures are in place to help facilitate issue identification and troubleshooting. | Problem identification & Alerting | Katy Bullock (DN) | 12/12: CS are using Teams viewer to access the Digital Cafe kiosks, Customer currently have no access to it, upon completion of the Resilience program, Customer will have a visibility to diagnose an issue with Digital Cafe 28/11: We were advised of an ETA by CS of 25/11, however, there has been no update on the actions. We have escalated to every possible levels, however, no update yet. Further actions being agreed with Paul and co. 21/11: Upon multiple follow ups, no response received from CS. An escalation email will be sent with Darren to get further updates | DN |  | NA | 2024-12-12 | Closed |  |  |  | Saloni | 2025-02-10 | 367 | >60 | December | 2024 | #VALUE!
Customer Channels | Selling Experience | 90281344 | 2024-09-30 | Central network connectivity issue impacting various services | Digital Cafes: It was advised that there is a threshold set for DN, where an incident is only treated as critical if more than five stores report a major issue. Review their major incident identification process and improve the overall escalation process. | Supplier and support involvement | Katy Bullock (DN) | 12/12: There is an existing Teams channel with the 17 Digital Cafe store stakeholders and until the resilience programe has been completed, there is no other option for DN to be informed of an issue prior to Customer. The teams channels will be rammed down once the Resilience program is over. 28/11: We were advised of an ETA by CS of 25/11, however, there has been no update on the actions. We have escalated to every possible levels, however, no update yet. Further actions being agreed with Paul and co. 21/11: Upon multiple follow ups, no response received from CS. An escalation email will be sent with Darren to get further updates | DN |  | NA | 2024-12-12 | Closed |  |  |  | Saloni | 2025-02-10 | 367 | >60 | December | 2024 | #VALUE!
Customer Channels | Selling Experience | 90281344 | 2024-09-30 | Central network connectivity issue impacting various services | Digital Cafes: Product teams to identify there is a requirement to enable Zscaler for the stores. Document the existing architecture of these stores, including the local breakout policy. Coordinate with Infosec and other relevant stakeholders to determine the requirements for enabling it. | Problem avoidance | Tony Burke/Charly W/ Adam Smith | The document is created and new Digital Café's are being built following the same approach. | Digitial café |  | NA | 21/11/24 | Closed |  |  |  | Saloni | 2025-02-10 | 367 | >60 | November | 2024 | #VALUE!
Customer Channels | Selling Experience | 90281344 | 2024-09-30 | Central network connectivity issue impacting various services | Digital Cafes: Additionally, we have identified two stores - Camberley store and Cribbs store which are yet to migrated to SDWAN . Document the local breakout policy or direct internet routing policy before migrating Camberley and Cribbs to ensure no further impact. | Problem avoidance | Kamal & Paul Dassan Cutting | 14/11: This action has been completed where NOC and Digital Café team have collaborated and the Camberley stores was configured to locally break out to the internet A call has been scheduled on 4th Oct with network team to streamline the ownership of the runbook. | Network & Digital Café |  | NA | 14/11/24 | Closed |  |  |  | Saloni | 2025-02-10 | 367 | >60 | November | 2024 | #VALUE!
Customer Channels | Selling Experience | 90290812 | 2024-09-27 | Customer.com double discount in basket on desktop and mweb | Standard alerting looks for errors rather than incorrect pricing. Agreed that alerting would be added for incorrect pricing, specifically if the price goes to zero | Problem identification & Alerting | Tawfiq Oladoja | 29/10 - Tawfiq updated that the team is working on it with a Jira backlog PRICE-1167. 15/10: Elaine updated the team is still working on it and expected to complete by end of the week | Selling Experience |  | NA | 29/10/24 | Closed |  | PRICE-1167 |  | Gokul | 2025-02-10 | 370 | >60 | October | 2024 | #VALUE!
Customer Channels | Selling Experience | 90290812 | 2024-09-27 | Customer.com double discount in basket on desktop and mweb | Discuss with the business whether we can set a percentage cap for discounting i.e. never go below x% of product price. | Problem identification & Alerting | Jack Tye and Elaine Hawthorn | 04/11: Jack confirmed that the promo wasn’t actually wrong, so it wouldn’t have flagged. It’s a front end issue so nothing we can do from our side. Hence, closing the action. 28/10 - Jack is working on it. 15/10: Elaine updated the team is still working on it and expected to complete by end of the week | Selling Experience |  | NA | 2024-04-11 | Closed |  |  |  | Gokul | 2025-02-10 | 370 | >60 | November | 2024 | #VALUE!
Customer Channels | Selling Experience | 90290812 | 2024-09-27 | Customer.com double discount in basket on desktop and mweb | Need to ensure that original fix for 8 double dipping products is re-worked and deployed. This requires a fix from both Customer Order and Price domains 1. Customer Order Domain have a ticket to complete their work. Once this is done, Price Domain team can re-work their fix. Rebecca and/or Nicole to prioritise this work 2. Once Customer Order Domain Fix is in place, Price Domain will deploy their fix | Permanent Fix | Rebecca Furborough and /or Nicole Creedon | 22/10: Ram updated that the team is working on it with a Jira [DICP-1889] 15/10: Elaine updated the team is still working on it and expected to complete by end of the week | Selling Experience |  | NA | 22/10/24 | Closed |  | DICP-1889 | Ready for Code Review | Gokul | 2025-02-10 | 370 | >60 | October | 2024 | #VALUE!
Customer Channels | Selling Experience | 90290812 | 2024-09-27 | Customer.com double discount in basket on desktop and mweb | Need to ensure that original fix for 8 double dipping products is re-worked and deployed. This requires a fix from both Customer Order and Price domains 1. Customer Order Domain have a ticket to complete their work. Once this is done, Price Domain team can re-work their fix. Rebecca and/or Nicole to prioritise this work 2. Once Customer Order Domain Fix is in place, Price Domain will deploy their fix | Permanent Fix | Jacqui Colli | 22/10: Ram updated that the team is working on it with a Jira [DICP-1889] 15/10: Elaine updated the team is still working on it and expected to complete by end of the week | Selling Experience |  | NA | 22/10/24 | Closed |  | DICP-1889 | Ready for Code Review | Gokul | 2025-02-10 | 370 | >60 | October | 2024 | #VALUE!
Customer Channels | Selling Experience | 90290812 | 2024-09-27 | Customer.com double discount in basket on desktop and mweb | Need to ensure that original fix for 8 double dipping products is re-worked and deployed. This requires a fix from both Customer Order and Price domains Issue of testing the fix in SIT2 was discussed. There is no appropriate promotional data in SIT2 to enable proper testing. This is a wider issue (not just relevant to this PIR) as there are no regular updates of SIT2 data from Production. To be investigated by Ram Rao | Permanent Fix | Ramachandrarao RVS | 22/10: Got these updates from Ram WCS will be decommissioned in 2 years time and this will help in resolving data issue, So, SIT2 data cannot be updated with Production. But, if required with a sample data, this can be tested. 15/10: Elaine updated the team is still working on it and expected to complete by end of the week | Selling Experience |  | NA | 22/10/24 | Closed |  |  |  | Gokul | 2025-02-10 | 370 | >60 | October | 2024 | #VALUE!
C&H and Intl | C&H and Intl supply chain | 90261991 | 2024-09-27 | Message processing issues from WMS to WCS impacting CD operations | Although the incident was initially identified at 12:00, there was a delay in engaging MIM until 13:29, by which time the site operations had already come to a standstill at 12:58. It was advised that when the service lead tried to reach MIM, the call was not answered due to dialing an incorrect number. Consequently, it has been agreed that the service lead will update the correct number in the knowledge base for future reference to ensure timely engagement | Issue handling/Management | Mark Davies | This has been agreed | Service lead |  | NA | 17/09/24 | Closed |  |  |  | Saloni | 2025-02-10 | 370 | >60 | September | 2024 | #VALUE!
Customer Channels | Customer Engagement | 90295590 | 2024-09-26 | Customers encountering errors when attempting to sign in to the website | Discuss and review the service level agreements with the SecureAuth team (including support model and service design) | Supplier and support involvement | Tim Searle Simon Attard | 15/01 - SLA/Contract conversations with Secure Auth are still ongoing. These will take time as they are around the contract renewal and involve the procurement team as well and it will finlaised only in June 2025. 20/12 - This action is still in progress, Product teams are still discussing with Secure Auth to finalize the Service level agreements. 27/11- Follow-up has been made with Priyabrata 10/09: Encounteringprogress | Secure Auth - 3rd Party |  | NA | 16/01/25 | Closed |  |  |  | Pavithra | 2025-02-10 | 371 | >60 | January | 2025 | #VALUE!
Customer Channels | Customer Engagement | 90295590 | 2024-09-26 | Customers encountering errors when attempting to sign in to the website | Develop a risk assessment for GQ on the potential consequences of a single point failure within Business services that are reliant on Identity service, in the event of a prolonged outage | Impact analysis | Priyabrata Sahu (discuss with Ben Philips) | 15/01 - Risk raised: https://marksandspencer.monday.com/boards/1563841268/pulses/1653190234 20/12 -The Risk is yet to raised by the product teams. 27/11- Follow-up has been made with Priyabrata 04/09: Encounteringprogress | Service Lead Customer enagement |  | NA | 15/01/24 | Closed | https://marksandspencer.monday.com/boards/1563841268/pulses/1653190234 |  |  | Pavithra | 2025-02-10 | 371 | >60 | January | 2024 | #VALUE!
Customer Channels | Customer Engagement | 90295590 | 2024-09-26 | Customers encountering errors when attempting to sign in to the website | Exploring an Optimal Approach to Service Recovery through SecureAuth's Resilience Option. | Solution & Recovery | Simon Attard | 20/12 - A number of resiliency improvements have been made based on this incident - CIAM-1181; CIAM-1183 - Reference backlogs 27/11- Follow-up has been made with Priyabrata 05/09: Encounteringprogress | Secure Auth - 3rd Party |  | NA | 20/12/24 | Closed |  |  |  | Pavithra | 2025-02-10 | 371 | >60 | December | 2024 | #VALUE!
C&H and Intl | C&H and Intl supply chain | 90261991 | 2024-09-17 | Message processing issues from WMS to WCS impacting CD operations | During the incident, a decision was made to flush the WCS queues to process the live messages from WMS to WCS. However, it has been agreed to understand the logic behind flushing the queue, including the sequencing of message types and the queue types | Issue handling/Management | Kunal Chichkar | 01/10: Nirmal spoke with Kunal who advised that no specific logic was followed. The messages are processed in a first in and first out methid and in this case everything was cleared to flush the queue. | WMS |  | NA | 2024-01-10 | Closed |  |  |  | Saloni | 2025-02-10 | 380 | >60 | October | 2024 | #VALUE!
C&H and Intl | C&H and Intl supply chain | 90261991 | 2024-09-17 | Message processing issues from WMS to WCS impacting CD operations | As the automated script is currently failing to handle the manual receipt scenario, if the site encounter an issue with the stock receipt through automation, it has been agreed that the site should contact the tech teams. The tech teams will then create the purchase orders by running the script manually. Additionally, the tech teams will collaborate with the site on the arrival of new stock to revise the operational SOP and implement it immediately. | Issue handling/Management | Pragadesh vasan | 01/10 - Completed. Nirmal spoke to Pragades - The automated script causing the issue has been stopped. Site will reach to support team for execution. | WMS |  | NA | 2024-01-10 | Closed |  |  |  | Saloni | 2025-02-10 | 380 | >60 | October | 2024 | #VALUE!
GTS | Enterprise Integration | 90261991 | 2024-09-17 | Message processing issues from WMS to WCS impacting CD operations | To reduce the effort required after an incident, create an SOP to purge the data from WCS queue manager for retriggering in a controlled manner | Solution & Recovery | Murali Irniki | 31/10: The SOP for purging the data in Middleware has been created and reviewed. 01/10: Nirmal spoke with Kunal who advised that this action should be for Pawan. The SOP creation task should be assigned to middleware team.- Chikkeri Nagaraj, PavanKumar/ Murali In progress | WMS |  | NA | 31/10/24 | Closed |  |  |  | Saloni | 2025-02-10 | 380 | >60 | October | 2024 | #VALUE!
C&H and Intl | C&H and Intl supply chain | 90261991 | 2024-09-17 | Message processing issues from WMS to WCS impacting CD operations | During the incident triage, while attempting to identify the cause of the issue, it was initially conveyed that no changes had been deployed given that no changes were made on September 11th or 12th, we now need to assess changes over a broader timeframe, including the last release, to identify the source of the problem. | Solution & Recovery | Pragadesh Vasan | This has been agreed | WMS |  | NA | 17/09/24 | Closed |  |  |  | Saloni | 2025-02-10 | 380 | >60 | September | 2024 | #VALUE!
C&H and Intl | C&H and Intl supply chain | 90261991 | 2024-09-17 | Message processing issues from WMS to WCS impacting CD operations | For warehousing, establish a streamlined process to ensure that test cases are validated by the relevant engineering head before deployment. Additionally, create a RACI matrix to outline the responsibilities and approvals for the test cases | Solution & Recovery | Pragadesh vasan | 14/11: All changes in production are getting reviewed by senior engineers and after their approval is taken forward. 31/10: Praga is in discussion with Rich and co to determine the RACI for validating test cases for future deployments | TPM |  | NA | 14/11/24 | Closed |  |  |  | Saloni | 2025-02-10 | 380 | >60 | November | 2024 | #VALUE!
C&H and Intl | C&H and Intl supply chain | 90261991 | 2024-09-17 | Message processing issues from WMS to WCS impacting CD operations | Review the overall testing documents and results to enhance and improve the testing process | Solution & Recovery | Pragadesh Vasan | 01/10: Completed. Nirmal spoke to Pragadeesh who advised that Internal CAB process introduced for any changes. Peer Review for codes & testing introduced within DevOPs Team. | WMS |  | NA | 2024-01-10 | Closed |  |  |  | Saloni | 2025-02-10 | 380 | >60 | October | 2024 | #VALUE!
C&H and Intl | C&H and Intl supply chain | 90261991 | 2024-09-17 | Message processing issues from WMS to WCS impacting CD operations | Once all scenarios are captured and tested for the automated script, there is a plan to deploy the updated script by October 1st | Solution & Recovery | Pragadesh Vasan | 30/10: The automation script can be deployed only in Jan 2025 as no major deployments will be performed during GQ. for now, the script is being executed on a daily basis to address the failures. The script automation will be tracked via JDATE-10619 16/10: The automation script required more testing, therefore, an interim workaround has been implemented. Requested Pragadesh to provide more insight on the interim workaround. 01/10: Automation Script planned for 8th Oct Implementation as it requires outage. 17/09: The automated script deployed on September 10th failed to handle the manual receipt scenario. The teams will now collaborate to identify any other scenarios that need to be included in this automated script. | WMS |  | NA | 30/10/24 | Closed |  | JDATE-10619 |  | Saloni | 2025-02-10 | 380 | >60 | October | 2024 | #VALUE!
C&H and Intl | C&H and Intl supply chain | 90261991 | 2024-09-17 | Message processing issues from WMS to WCS impacting CD operations | Document the internal process to ensure we can identify the source of the issue and capture the relevant areas that the investigation needs to focus on. A run book should be created for this purpose | Solution & Recovery | Pragadesh Vasan | 31/10: The SOP document is now created and reviewed with the engineering leadership for future instances 16/10: The SOP is now created and is currently being reviewed with the technical team. 01/10: Nirmal spoke to Pragadesh who advised SOP has been created but yet to be reviewed & shared with Technical team. In progress | WMS |  | NA | 30/10/24 | Closed |  |  |  | Saloni | 2025-02-10 | 380 | >60 | October | 2024 | #VALUE!
C&H and Intl | C&H and Intl supply chain | 90261991 | 2024-09-17 | Message processing issues from WMS to WCS impacting CD operations | Review the current reconciliation mechanism and recovery actions for receiving ASNs from system point of view : We have an existing SOP, this needs reviewing to ensure all scenarios are considered before retriggering to WCS | Solution & Recovery | Pragadesh Vasan | 01/10: Nirmal spoke to Pragadeesh who informed that existing SOP already covers all the steps for Recon. And no new steps followed during the issue. | WMS |  | NA |  | Closed |  |  |  | Saloni | 2025-02-10 | 380 | >60 | January | 1900 | #VALUE!
GTS | ETP-On premise services | 90261991 | 2024-09-17 | Message processing issues from WMS to WCS impacting CD operations | Review the overall alerting configuration within WCS queue manager and explore options to configure alerts based on message age & current depth within the WCS MQ layer and the recipient of the alert to initiate triaging on time | Problem identification & Alerting | Kunal Chichkar/ Murali Irinki | 23/10: Nirmal spoke to Murali who informed that alert is already in place. INC000090261598 created on the date of issue for queue getting full. 01/10: Nirmal spoke to Kunal and been advised that this action for Murali Irinki. In progress | WMS/ Middleware admin |  | NA | 23/10/24 | Closed |  |  |  | Saloni | 2025-02-10 | 380 | >60 | October | 2024 | #VALUE!
C&H and Intl | C&H and Intl supply chain | 90261991 | 2024-09-17 | Message processing issues from WMS to WCS impacting CD operations | Review the threshold on the volume of failed records in the interface table to identify if they are valid or genuine. Alerting is in place on WMS interface queue – Understand what actions were performed and make necessarily changes to prevent incident . Revisit the E2E process after an alert gets triggered, expectation is no failed records by EOD in WMS | Problem identification & Alerting | Kunal Chickar | 30/10: Alerts for key table interface failures are monitored through a controlM job that runs every 30 minutes. A threshold has been set to raise an incident if failures in key tables exceed 500 within this 30-minute window. This setup prevents false alerts, as line records often initially fail but are reprocessed successfully once header records are processed. Additional steps are in progress to automate the clearance of redundant failures, tracked under a jira JDATE10540. 01/10: Alert Threshold is yet to be reveiewed & confirmed. In progress | WMS |  | NA | 30/10/24 | Closed |  | JDATE10540. |  | Saloni | 2025-02-10 | 380 | >60 | October | 2024 | #VALUE!
GTS | ETP-On premise services | 90239114 | 2024-09-16 | Followed by a capacity uplift activity Ollerton WMS application was inaccessible | The cluster start and stop script has been used in multiple DC's but it did not try and recover the situation anywhere but Ollerton - Jaffar in talks with Redhat to ascertain why? | Problem avoidance | Jeeva & Jafar | 21/11: Rehan has contacted Jafar for a further update - he replied: We recreated the issue in different DC and did not had same issue - so the RCA is inconclusive as the cluster did not behave in same way - Redhat also said as script is non compliant there are chances that cluster would have differently - Update 14/10 Rehan has contacted Jafar for a further update | Unix |  | NA | 2024-12-12 | Closed |  |  |  | Rehan | 2025-02-10 | 381 | >60 | December | 2024 | #VALUE!
C&H and Intl | C&H and Intl supply chain | 90239114 | 2024-09-16 | Followed by a capacity uplift activity Ollerton WMS application was inaccessible | Girichandramohan, Karthick and Chichkar, Kunal to talk to vendors JDA and ascertain why the health probe was seeing that the application was up on two nodes, when this was the not the case at all. We need to ascertain what is wrong with the probe and what needs to be done to remediate it | Problem avoidance | Karthick GC, Kunal Chichkar | 02/12: Since July the product team has not answered the correct question and given the time elapsed this will be closed. 02/12: Followed up for an update Update 14/10 Rehan has contacted Kunal for a further update | WMS |  | NA | 2024-02-12 | Closed |  |  |  | Rehan | 2025-02-10 | 381 | >60 | December | 2024 | #VALUE!
Customer Channels | Selling Experience | 90245506 | 2024-09-12 | Intermittent Issue With Nominated Day Delivery | To reproduce the issue with help of various test Scenarios in Lower environment to identify the root cause | Problem identification & Alerting | WLMT (WCS Lifcycle Mgmt Team) | Action was carried out on 08th September and team concluded that they were unable to reproduce the issue | WCS |  | NA | 2024-03-09 | Closed |  |  |  | Gokul | 2025-02-10 | 385 | >60 | September | 2024 | #VALUE!
Customer Channels | Selling Experience | 90245506 | 2024-09-12 | Intermittent Issue With Nominated Day Delivery | Switch off calendar Date as a test by the of a calendar month and observe if a similar issue with orders being placed for the day after the closed calendar date (if the issue is reproduced) | Problem identification & Alerting | Ops Hub/WCS Team | 14/10: Issue has recurred on 3rd 90317889 and this action will be tracked as part of it 12/09: Planned EDC Outage on 9th October, We will monitor to see if a similar issue occurs on 30th September/1st October | WCS |  | NA | 14/10/24 | Closed | NA | NA | NA | Gokul | 2025-02-10 | 385 | >60 | October | 2024 | #VALUE!
Customer Channels | Selling Experience | 90245506 | 2024-09-12 | Intermittent Issue With Nominated Day Delivery | There are currently no alerts to identify if the requested ship date is greater than 7 days for double digit orders placed (single digit is expected). Hence to set up alert when double digit orders are placed with requested ship date > 7 days | Problem identification & Alerting | WLMT (WCS Lifcycle Mgmt Team) | 24/09 - Aadil confirmed that the action is complete 20/09 - Aadil updated that the team is still is working on it and we can expect the update on 23/09. 12/09 - WCS Alert to be configured to identify, if double digit orders are placed with requested ship date > 7 days | WCS |  | NA | 24/09/24 | Closed | NA | NA | NA | Gokul | 2025-02-10 | 385 | >60 | September | 2024 | #VALUE!
Customer Channels | Selling Experience | 90245506 | 2024-09-12 | Intermittent Issue With Nominated Day Delivery | During investigation, it was identified that Content Square (Tool used for replaying the customer session) had a Double Calendar glitch and it was assumed to be the cause of the issue, but eventually it was concluded as not. Hence, the reason for Double Calendar glitch to be identified | Issue handling/Management | Jack Tye/Ops Hub | 19/09 - Content Square have advised that the behaviour of the double calendar was a known issue and have aligned a fix to be deployed on 19th. Fix was deployed on the 19th and Content Square advises that, we should no longer be observing the issues. Note: Content Square is a business tool and they mentioned the following: “The issue doesn't appear to be a global one or a service disruption” Therefore, they do not usually sent out notifications for this or provide a root cause. | Business ops |  | NA | 19/09/24 | Closed | NA | NA | NA | Gokul | 2025-02-10 | 385 | >60 | September | 2024 | #VALUE!
Customer Channels | Selling Experience | 90245506 | 2024-09-12 | Intermittent Issue With Nominated Day Delivery | Request Contact Centre to capture details from the customer about why they were unable to select the expected date, if the issue reoccurs | Impact analysis | Ops Hub | 19/09 - Aadil had spoken to Alys. She will tag service managers in chat with Contact Center, if the issue does reoccur and we can request them directly for the information, we require for the incident. 12/09 - Currently in case of such issues, contact centre has been advised to get the specific reason or error and is being monitored | Business ops |  | NA | 19/09/24 | Closed | NA | NA | NA | Gokul | 2025-02-10 | 385 | >60 | September | 2024 | #VALUE!
Customer Channels | Service Experience | 90220033 | 2024-09-05 | Delayed Parcels incorrectly being marked as Ready to Collect | This deployment pipeline is used by wider Fulfilment team so learnings from this should be shared to avoid similar issues in other applications. | Problem avoidance | David/Omkar | 27/11: The learning have been shared with the team to avoid the reoccurance of the issue 17/10: Awaiting further updates | Fulfillment Expansion | Strategic | NA | 27/11/24 | Closed |  |  |  | Kavitha | 2025-02-10 | 392 | >60 | November | 2024 | #VALUE!
Customer Channels | Service Experience | 90220033 | 2024-09-05 | Delayed Parcels incorrectly being marked as Ready to Collect | Post deployment validation happened at akamai end; team should have validated the deployment logs to check whether the new certificate got reflected in both the environments. FEX-602 | Problem avoidance | David/Omkar | 17/10: Planned to take after PEAK. As all the certificates are upgraded, There is no urgency for this as the next cerrtificate renewal is next year 16/09: FEX-602 backlog has been raised to address this after Peak | Fulfillment Expansion | Strategic | NA | 2024-04-12 | Closed |  | FEX-602 | Open | Kavitha | 2025-02-10 | 392 | >60 | December | 2024 | #VALUE!
Customer Channels | Service Experience | 90220033 | 2024-09-05 | Delayed Parcels incorrectly being marked as Ready to Collect | Fall back to .COM+ should be removed. This will require help from WCS team and inputs from Retail Ops. | Problem avoidance | David/Omkar/Hisham | 27/11: Investigation done from our side and URL details needs to removed have been shared with WCS. 17/10: Awaiting further updates | Fulfillment Expansion | Tactical | NA | 27/11/24 | Closed | NA | NA | NA | Kavitha | 2025-02-10 | 392 | >60 | November | 2024 | #VALUE!
Customer Channels | Service Experience | 90220033 | 2024-09-05 | Delayed Parcels incorrectly being marked as Ready to Collect | Failure in deployment job shown as success, what changed in deployment job as the same job was used last year for certificate renewal? | Root cause | David/Omkar | 17/10: There script was not capture the error to fail and hence a logic has been added to alert if there any issue with script and the certificate update is not successfull. 16/09: The DR namespace was incorrect and it has been corrected. Team is investigating why the script failed to notify the certificate renewal wasn't successful and its has been picked up for investigation in the current sprint and its on 1st Oct. | Fulfillment Expansion | Tactical | NA | 2024-05-12 | closed | NA | NA | NA | Kavitha | 2025-02-10 | 392 | >60 | December | 2024 | #VALUE!
Customer Channels | Service Experience | 90220033 | 2024-09-05 | Delayed Parcels incorrectly being marked as Ready to Collect | Failure of Akamai to re-direct traffic should be investigated | Problem avoidance | David/Omkar | 27/10: Rules have been changed to re-direct the traffic 17/10: Ticket raised to network team. They are looking into it. Latest update is that Network team is created ticket for AKAMAI team and AKAMAI team need to look into it. 16/09: FEX-605 backlog has been raised to address this and its has been picked up for investigation in the current sprint and its on 1st Oct. | Fulfillment Expansion | Tactical | NA | 27/11/24 | Closed |  | FEX-605 |  | Kavitha | 2025-02-10 | 392 | >60 | November | 2024 | #VALUE!
Customer Channels | Service Experience | 90220033 | 2024-09-05 | Delayed Parcels incorrectly being marked as Ready to Collect | Alerts should be configured for akamai health check failures and alerted to product team. | Problem identification & Alerting | David/Omkar | 17/10:Alerts have been configured 16/09: FEX-606 backlog has been raised to address this and its has been picked up for investigation in the current sprint and its on 1st Oct. | Fulfillment Expansion | Tactical | NA | 17/10/24 | Closed |  | FEX-606 |  | Kavitha | 2025-02-10 | 392 | >60 | October | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90240387 | 2024-04-09 | Central issue at Blue Yonder impacting ability to access SRD via Open Access and WLM applications | The issue was identified through Customer alerting, however the BY communications were not sent on time to confirm the outage. | Issue handling/Management | Ganesh Regoubady (BY TAM) | BY has agreed to improve their Major incident management process to ensure that communications are sent out in a timely manner. Also, BY is working out on a status page, to notify the outage details on their portal - Which will be worked upon by them via backlog- as this is a long term action | BY Team |  | NA | 2024-11-11 | Closed | NA | NA | NA | Pavithra | 2025-02-10 | 393 | >60 | November | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90240387 | 2024-04-09 | Central issue at Blue Yonder impacting ability to access SRD via Open Access and WLM applications | This is the second instance of Blue Yonder central change impacting our services, Blue Yonder has been advised to review their change management process and to ensure the stability of our services during the peak trading period. | Problem avoidance | Ganesh Regoubady (BY TAM) | Blue Yonder has agreed to review their change management process, as part of which the doer/checker process has been rigorously enforced to prevent human errors. Also, they have introduced Arista CloudVision configuration management tool to implement their changes on Arista devices in order to prevent human errors. Furthermore, they have consented to limit the execution of changes during weekdays unless absolutely required. | BY Team |  | NA | 2024-11-11 | Closed | NA | NA | NA | Pavithra | 2025-02-10 | 393 | >60 | November | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90240387 | 2024-04-09 | Central issue at Blue Yonder impacting ability to access SRD via Open Access and WLM applications | It took around five hours on the day of the incident to restore services and assess the viability of resilience in the event of such disruptions | Solution & Recovery | Ganesh Regoubady (BY TAM) | Although BY has a disaster recovery setup in place, the root cause of the problem was identified right away at the beginning of the incident and a recovery plan was quickly created. Thus, the BY tech team did not declare the DR initiation. The recovery plan required testing to be carried out within the BY environment which took time. However, they have been advised to review their DR process to ensure stability. | BY Team |  | NA | 2024-11-11 | Closed | NA | NA | NA | Pavithra | 2025-02-10 | 393 | >60 | November | 2024 | #VALUE!
GTS | ETP-On premise services | 90208820 | 2024-09-01 | Delay in Donington planned release impacting operations | The issue with the Mule server did not come up as expected due to an underlying buy in the current OS version. What is the plan of upgrading the node to eliminate the bug in future deployments | Problem avoidance | Jafar Sadiq | 19/09: The bug was found on the Rear Restoration script, which later got fixed by Redhat to bring up the VM. Initially the servers were unable to boot after RHEL upgrade and it went to Dracut mode. For this Redhat wants to have live triage, and this requires an outage to upgrade to RHEL8 | Infra | Tactical | NA | 19/09/24 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 396 | >60 | September | 2024 | #VALUE!
GTS | ETP-On premise services | 90208820 | 2024-09-01 | Delay in Donington planned release impacting operations | During the timeout parameter changes, to fix the NFS issue on the MQ servers, an outage of 4 hours was required from the site. Identify a robust way to execute the sequence of events during future deployments to ensure minimal productivity loss | Solution & Recovery | Jafar Sadiq | 19/09: Total change was completed in 2 hours. The revised timings need to be incorporated while preparing Future changes. Owner: WMS and Mule team will incorporate this in future upgrades | Infra | Tactical | NA | 19/09/24 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 396 | >60 | September | 2024 | #VALUE!
GTS | ETP-On premise services | 90208820 | 2024-09-01 | Delay in Donington planned release impacting operations | Once the trace parameter has been enabled in the MQ cluster, share the logs to RedHat for root cause analysis | Root cause | Jafar Sadiq | 16/10: It has been confirmed by the teams that trace was enabled during the 1st Oct outage within CD MQ cluster, therefore, if the issue occurs again, relevant logs can be captured to identify the root cause. 19/09: We have 2 upcoming outages at Donington in the coming weeks on the 1st & 8th October. To ensure we don’t impact the site any further, it has been agreed to incorporate the trace enblement on 1st Oct to gather logs for Redhat to investigate | Infra | Tactical | NA | 16/10/24 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 396 | >60 | October | 2024 | #VALUE!
C&H and Intl | C&H and Intl supply chain | 90208820 | 2024-09-01 | Delay in Donington planned release impacting operations | As the root cause remains inconclusive on the NFS resource timeout issue on MQ cluster, RedHat has recommended to enable a trace parameter on the cluster nodes to identify the issue. | Root cause | Murali Srinivasan | 16/10: It has been confirmed by the teams that trace was enabled during the 1st Oct outage within CD MQ cluster, therefore, if the issue occurs again, relevant logs can be captured to identify the root cause. 19/09: We have 2 upcoming outages at Donington in the coming weeks on the 1st & 8th October. To ensure we don’t impact the site any further, it has been agreed to incorporate the trace enblement on 1st Oct to gather logs for Redhat to investigate. 01/09: This requires an outage with the site operations. Agree on an approach to utilise the outage to perform the next patching activity. | Donington service lead | Tactical | NA | 16/10/24 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 396 | >60 | October | 2024 | #VALUE!
C&H and Intl | C&H and Intl supply chain | 90206833 | 2024-08-30 | Ollerton DC reporting intermittent HHT issues impacting operations | We have determined that all the relevant alerts are configured with a defined threshold within the database and application layers to identify similar issues with capacity constraints. There are existing run books available for troubleshooting and communication. | Problem identification & Alerting | Karthick Girichandramohan | We have determined that all the relevant alerts are configured with a defined threshold within the database and application layers to identify similar issues with capacity constraints. There are existing run books available for troubleshooting and communication. | TPM |  | NA | 30/08/24 | Closed |  |  |  | Pavithra | 2025-02-10 | 398 | >60 | August | 2024 | #VALUE!
C&H and Intl | C&H and Intl supply chain | 90206833 | 2024-08-30 | Ollerton DC reporting intermittent HHT issues impacting operations | Product team to update the SOP (standard operating procedure)/run book with an additional checkpoints for human error scenario and relevant training is being given to the site operations on the right steps to be followed. | Problem avoidance | Mark Davies | 17/09 - SOP has been updated and communicated to Ollerton site.However the runbook will be fully renewed after the Peak The "run book" is in progress which Ugne Sukaityte is managing as product owner alongside site operations. Mark will further followup with Ugne for the next update. 14/09 - The SOP has been updated for the operations team, however the run book updation is stil lin -progress | C&H Service Lead |  | NA | 2024-10-08 | Closed | NA | NA | NA | Pavithra | 2025-02-10 | 398 | >60 | August | 2024 | #VALUE!
C&H and Intl | C&H and Intl supply chain | 90206833 | 2024-08-30 | Ollerton DC reporting intermittent HHT issues impacting operations | We have agreed with the relevant service leads to engage MIM whenever DC operations are impacted based on the severity/criticality | Issue handling/Management | Karthick Girichandramohan | 10/10 - The field has been removed on the standard option to avoid the confusion for the DC colleagues. So that they do not incorrectly select the c&C option | TPM |  | NA | 30/08/24 | Closed |  |  |  | Pavithra | 2025-02-10 | 398 | >60 | August | 2024 | #VALUE!
C&H and Intl | C&H and Intl supply chain | 90206833 | 2024-08-30 | Ollerton DC reporting intermittent HHT issues impacting operations | 07//11 - The unnecessary field has been removed by the WMS support team - This will further prevent the confusion within colleagues 30/08Product team has agreed to remove the unnecessary field on the standard orders to avoid the confusion | Problem avoidance | Karthick Girichandramohan / Deepika Velumani | NA/08: Dcprogress | TPM |  | NA | 2024-07-11 | Closed | NA | NA | NA | Pavithra | 2025-02-10 | 398 | >60 | November | 2024 | #VALUE!
C&H and Intl | C&H and Intl supply chain | 90206833 | 2024-08-30 | Ollerton DC reporting intermittent HHT issues impacting operations | As per the capacity management team's recommendation, another proactive action was agreed to uplift the capacity for all the WMS servers at Ollerton. As we were seeing an increasing trend in resource utilizations, especially the load on the mule servers has been significantly high for the past couple of months which is suspected to be due to an increase in Ecomm order volume and Bulkies | Problem avoidance | Karthick Girichandramohan | NA/08: Dcprogress | TPM |  | NA | 2024-03-09 | Closed |  |  |  | Pavithra | 2025-02-10 | 398 | >60 | September | 2024 | #VALUE!
GTS | Digital Workplace Services | 90224338 | 2024-08-29 | Some colleagues unable to connect to Salina wireless network on 27/08 | Alerting to be enabled for all certificates that are going to expire / expired in Active Directory. Alerting to be enabled on the Radius Servers based on the errors / event logs / authentication failures. Incident Recovery steps to be updated in SOP | Problem identification & Alerting | Muthunagappan / Farid / Subhapriya / Muzamil | 29/10 - NOC team has provided the required data and alerts are configured by SCOM team already for these. SOP to be updated with these details. 21/10 - NOC team is still working 12/10 - AD team wanted the SSID configured for each of radius servers 08/10 - Muthu confirmed that alerting has been set for all the radius server certificate based on the errors / event logs / authentication failures. Rest of the certificates are being worked by Padmaja (Certificate Mgmt) with Laleth to integrate in power BI dashboard, so that all those certificates are available in central certificate DB. 01/10 - Network team confirmed that the radius servers are used for "SALINA" and "VULCANO" ssids, AD team to set up the alerts. 24/09 - Network team was engaged in the firewall issue, hence the delay. 12/09 - Had a connect with Muthu, Subha and Muzamil and understood that gathering the details of the Radius server is bit time consuming and a mail has been sent to Rajesh and he will help us in getting the details. 10/09 - For radius servers clarity is being discussed with Muzamil Mustafa so that SOP can be updated. | Active directory Team |  | NA |  | Closed | NA | NA | NA | Gokul | 2025-02-10 | 399 | >60 | January | 1900 | #VALUE!
GTS | Operations | 90224338 | 2024-08-29 | Some colleagues unable to connect to Salina wireless network on 27/08 | Share the list of all certificate types (Internal, External, Self-Signed) with the portfolio teams, the portfolio teams are expected to validate their certificates and work with the cert team to update the missing certificates. | Problem avoidance | Padmaja Lemaati/Priyadharshini S | 21/10 - As part of the GQ readiness, all the certificates across portfolios have been identified and are being added to central certificate dashboard. 24/09 - Padmaja has sent the list of Self-Signed certificates to be migrated to internal certificates across the portfolio teams. 06/09 - List of all certificate types (Internal, External, Self-Signed) has been shared with Dinesh M, so that he can send to portfolio teams | Certificate Management |  | NA | 21/10/24 | Closed | NA | NA | NA | Gokul | 2025-02-10 | 399 | >60 | October | 2024 | #VALUE!
GTS | Operations | 90224338 | 2024-08-29 | Some colleagues unable to connect to Salina wireless network on 27/08 | Microsoft was engaged three hours after the issue started - a delay. Vendors should be engaged a maximum of one hour after investigations - consider engaging 3rd party supplier check in the loop | Supplier and support involvement | Rehan Siddiqui | Added it as part of checklist in the MIM | Service Management |  | NA | 29/08/24 | Closed | NA | NA | NA | Gokul | 2025-02-10 | 399 | >60 | August | 2024 | #VALUE!
GTS | Digital Workplace Services | 90224338 | 2024-08-29 | Some colleagues unable to connect to Salina wireless network on 27/08 | SOP Update - As a best practice, once the certificate has been renewed successfully, we need to remove the old / expired certificate | Problem avoidance | Muthunagappan / Farid / Subhapriya | 10/09 - Old certificates will be overwritten, hence removing the old certificates is not required. Hence, closing this action. | Active directory Team |  | NA | 2024-10-09 | Closed | NA | NA | NA | Gokul | 2025-02-10 | 399 | >60 | September | 2024 | #VALUE!
GTS | Digital Workplace Services | 90224338 | 2024-08-29 | Some colleagues unable to connect to Salina wireless network on 27/08 | Liaise with Network team to identify and document which radius servers are pointed to which Distribution centres in WLC, so that the impact for the DC's can be quantified. | Problem avoidance | Subhapriya Gounalene | 29/10 - We have got the required details from NOC 21/10 - We have agreed with NOC team to share the details of "all location WLC details with their Radius servers configured in them ". 08/10 - AD team has asked for the WLC mapped to each of the radius servers to network team and awaiting information. 01/10 - Network team confirmed that the radius servers are used for "SALINA" and "VULCANO" ssids. 24/09 - Network team was engaged in the firewall issue, hence the delay. 12/09 - Had a connect with Muthu, Subha and Muzamil and understood that gathering the details of the Radius server is bit time consuming and a mail has been sent to Rajesh and he will help us in getting the details. 10/09 - For radius servers clarity is being discussed with Muzamil Mustafa so that SOP can be updated. | Active directory Team |  | NA | 29/10/24 | Closed | NA | NA | NA | Gokul | 2025-02-10 | 399 | >60 | October | 2024 | #VALUE!
GTS | Digital Workplace Services | 90224338 | 2024-08-29 | Some colleagues unable to connect to Salina wireless network on 27/08 | It was found that not all laptops were affected by the issue and that some could connect to Salina without any issue. Investigate why some people were unaffected by the issue | Impact analysis | Promode Gnanaguru | 17/09 - Promode confirmed that the colleagues who were connected to the renewed certificate, didn't face the issue. While, the colleagues who were working since morning and moving to different rooms would have been affected | WPT |  | NA | 17/09/24 | Closed | NA | NA | NA | Gokul | 2025-02-10 | 399 | >60 | September | 2024 | #VALUE!
Customer Channels | Service Experience | 90191568 | 2024-08-29 | Waterside and Pantheon stores were unable to take card payments on 50% of tills | Ensure we have a suitable TPV (terminal identifier) model to support our environment. | Solution & Recovery | Jamie Leven | 07/11 - This action has been address - by creating a new NumComm profile for Kiosks. 17/09 - Discussions are ongoing with Worldline - to have a suitable TPV model for Customer environment - Next update at 10/09 23/08: Currently, we have a TPV configuration where one PED device can use only one TPV profile but this is not a recommend solution for Customer environment. Product teams to liaise with WL to revise their solution to allow multiple devices per TPV as it will help in effective testing. | Payments Foundation | Strategic | NA | 2024-07-11 | Closed | NA | NA | NA | Pavithra | 2025-02-10 | 399 | >60 | November | 2024 | #VALUE!
Customer Channels | Service Experience | 90191568 | 2024-08-28 | Waterside and Pantheon stores were unable to take card payments on 50% of tills | Review the impacts before we select the pilot stores for change implementation | Impact analysis | Muthuvelan | Waterside was one of the pilot store which was opted for the enhancement change planned by the POS team. Since it is a critical store, it has created a significant impact during the incident. Thus, a decision has been made not to use Waterside as a pilot store for any of the change testing in future. | POS | Tactical | NA | 22/08/24 | Closed | NA | NA | NA | Pavithra | 2025-02-10 | 400 | >60 | August | 2024 | #VALUE!
Customer Channels | Service Experience | 90191568 | 2024-08-27 | Waterside and Pantheon stores were unable to take card payments on 50% of tills | Update the SOP/run book with the recovery steps | Solution & Recovery | Imanuvel Manickam | 07/11 - The document has been finalized and has been shared with the team. 17/09 -in progress. The final document to be shared by 24/09 23/08 -Details on the workaround applied and the recovery steps will be updated on the SOP for future references. | POS | Tactical | NA | 2024-07-11 | Closed | NA | NA | NA | Pavithra | 2025-02-10 | 401 | >60 | November | 2024 | #VALUE!
Customer Channels | Service Experience | 90191568 | 2024-08-26 | Waterside and Pantheon stores were unable to take card payments on 50% of tills | Ensure we have the right communication process agreed with the store colleagues during the incident triaging | Business & IT Communication | Valliammai Ramaswamy | 17/09 - Usually central comms will be sent to the stores during any central issue- however this incident was only impact 2 stores this there was a challenge in communicating to store colleagues of that store - Valli as agreed to make sure store colleagues follow the comms strictly. 23/08: Store colleagues were advised not to reboot any of the tills during the incident – however there were multiple till reboots performed during the triaging which resulted with elevated impacts. Valli will work along with the Store managers to re-iterate on the communication process. | Service Lead - Platform and store ops | Tactical | NA | 17/09/24 | Closed | NA | NA | NA | Pavithra | 2025-02-10 | 402 | >60 | September | 2024 | #VALUE!
Customer Channels | Service Experience | 90191568 | 2024-08-25 | Waterside and Pantheon stores were unable to take card payments on 50% of tills | Check on the Feasibility to create a Ghost store with the bank as backup - For us to use it for the workarounds - instead of using the TPV from another store | Solution & Recovery | Imanuvel Manickam | 03/12: RPOS-14681 has been created to create a ghost store with the bank as backup to use the terminal ids as a workaround. 27/11- Imman is further checking with the RIT team for the Ghost store set-up 17/09 - Imman has reached out to Dave Tomling's team regarding the feasibility of introducing card payments to RITMock store.Further follow-ups to be made 23/08:Currently we have a dummy store at Stockley park, which is beong used for testing. However the dummy store is not being used for Card payment services. Imman will liaise with David Tomlin will check on the feasibility of leveraging the existing dummy store for card payment services like testing, recovery actions etc. . | POS | Tactical | NA | 2024-03-12 | Closed | NA | RPOS-14681 | NA | Pavithra | 2025-02-10 | 403 | >60 | December | 2024 | #VALUE!
Customer Channels | Service Experience | 90191568 | 2024-08-24 | Waterside and Pantheon stores were unable to take card payments on 50% of tills | Review the change management process – As there was gaps on the change process | Business & IT Communication | Muthuvelan | 22/08- This has been addressed. Appropriate discussions were made with Worldline and they have agreed to inform Customer on all of their major activities. | POS | Tactical | NA | 22/08/24 | Closed | NA | NA | NA | Pavithra | 2025-02-10 | 404 | >60 | August | 2024 | #VALUE!
Customer Channels | Service Experience | 90191568 | 2024-08-23 | Waterside and Pantheon stores were unable to take card payments on 50% of tills | During the initial impact assessment, it was a challenge in capturing the no.of tills impacted. Product teams will review the feasibility to create a single Dashboard to have a holistic view on the Till availability | Problem identification & Alerting | POS (Shikar Kanna) and Payments ( Dan Mac_Hale | 07/11 - This action will be addressed via a jira story - https://jira.marksandspencer.app/browse/COB-590 https://jira.marksandspencer.app/browse/COB-589 17/09 - Follow-up made with the Shikkar Khanna - waiting for the response 22/08 -Currently we have a daily report from SIT, to notify the no.of tills available which can be leveraged to assess the impact when we have a problem with till availability. However, we do not have a dashboard to identify the no of tills which has an issue with the card payments collectively, but there are alerts for payment services (for higher no.of failed/declined transactions). Product team will further analyze and enhancements will be made on the observability. | POS | Strategic | NA | 2024-07-11 | Closed | NA | NA | NA | Pavithra | 2025-02-10 | 405 | >60 | November | 2024 | #VALUE!
Group Platforms | Finance | 90199179 | 2024-08-23 | Delay in EDW Finance Day-1 reporting flow due to cSAP BW job issue | We have been observing frequent issues due to job dependencies causing cascading impact to critical flows. Perform an overall review of the critical jobs and its dependencies | Problem avoidance | Sowmiya Radhakrishnan/ Rhammya Somassoundirame/ Murali Bolisetty | 03/09: The SMEs have performed an overall review of all the jobs in the SAP BW infrastructure and have concluded that no further changes are required in the job configurations. 23/08: The team are in process of performing an overall review of all the jobs in SAP BW system to identify any amendments required in readiness to Golden Quarter. The SOP documents will be updated accordingly. | SAP BW | Tactical | NA | 2024-03-09 | Closed |  |  |  | Saloni | 2025-02-10 | 405 | >60 | September | 2024 | #VALUE!
Group Platforms | Finance | 90199179 | 2024-08-23 | Delay in EDW Finance Day-1 reporting flow due to cSAP BW job issue | Due to a gap in the shift handover process, the morning shift engineer was not aware of any issues/actions taken overnight which incurred additional delays. Improve the shift handover process within the team. | Issue handling/Management | Sowmiya Radhakrishnan/ Rhammya Somassoundirame | 03/09: The relevant TEMs have reiterated to the team members to ensure appropriate handover is given to the consecutive shift person with all the issues during overnight montioring without fail. 23/08: The relevant TEMs/SMEs will educate the team members to follow effective handover process to ensure appropriate actions are taken to avoid impact in future. In addition, a workshop will be conducted within the team to follow the SOP diligently. | SAP BW | Tactical | NA | 2024-03-09 | Closed |  |  |  | Saloni | 2025-02-10 | 405 | >60 | September | 2024 | #VALUE!
Group Platforms | Finance | 90199179 | 2024-08-23 | Delay in EDW Finance Day-1 reporting flow due to cSAP BW job issue | The dependency of the last iteration of the BW job was not considered whilst force completing the previous iteration, and no communication was sent across to the downstream systems. Review the existing SOP document to ensure the engineers are aware of the job designs and steps to follow during an issue | Solution & Recovery | Sowmiya Radhakrishnan/ Rhammya Somassoundirame | 03/09: A workshop was conducted with the engineering associates and all SOP documents have been reviewed by SMEs. 23/08: The relevant TEMs/SMEs will review the SOP document and educate the team to ensure appropriate actions are taken to avoid impact in future. | SAP BW | Tactical | NA | 2024-03-09 | Closed |  |  |  | Saloni | 2025-02-10 | 405 | >60 | September | 2024 | #VALUE!
Group Platforms | Finance | 90199179 | 2024-08-23 | Delay in EDW Finance Day-1 reporting flow due to cSAP BW job issue | The overnight cSAP BW extractor job went into “waiting sate” due to the predefined dependency set with the previous iterations. Identify a process to remove the dependency set for the 3rd extractor job. | Permanent Fix | Murali Bolisetty | 03/09: A controlled resource has been configured to the SAP BW extractor to ensure the job executes without any dependencies in case there are issues with the previous instances. 23/08: Product teams have devised a plan to introduce a controlled resource to the 3rd iteration of the job which means, irrespective of the completion of the previous iterations, the 3rd iteration will run without going into a “waiting” state. There will be no risk to the data processing | SAP BW | Tactical | NA | 2024-03-09 | Closed |  |  |  | Saloni | 2025-02-10 | 405 | >60 | September | 2024 | #VALUE!
Group Platforms | Finance | 90199179 | 2024-08-23 | Delay in EDW Finance Day-1 reporting flow due to cSAP BW job issue | The cSAP BW extractor job was configured to start 02:15, the “Not Started” alert was triggered only at 03:40 which contributed to the initial delay in investigations. Amend the Not started alert to facilitate timely recovery | Problem identification & Alerting | Murali Bolisetty | 03/09: The alert for the problematic extractor job has been ameded to 02:30 to ensure appropriate actions are taken overnight to avoid impact. 23/08: The team have agreed to amend the alert to 02:30 from 03:40 to avoid the additional delay in incident triage. | SAP BW | Tactical | NA | 2024-03-09 | Closed |  |  |  | Saloni | 2025-02-10 | 405 | >60 | September | 2024 | #VALUE!
Customer Channels | Service Experience | 90191568 | 2024-08-22 | Waterside and Pantheon stores were unable to take card payments on 50% of tills | Product teams to check on the feasibility to capture the issue proactively before it impacts the store. | Problem identification & Alerting | Payments team / Jamie Leven | 07/11 - The In-Store Team have recently shifted to Dynatrace so there are discussions ongoing to enhance the alerting and logging - this will further be tracked via a backlog. 17/09 -Jamie to pickup with Dan tomorrow regarding the feasibility on alerrting within Payments but this needs a joint investigation along with POS. 22/08 - As per design, some decline in card payments at store tills are anticipated due to genuine reasons such as incorrect pin, incorrect card etc. However, we have an agreed threshold as a baseline and only when the number of declines go beyond the baseline, it is converted to a sev1. In this scenario, only 50% of the tills were impacted thus it did not go beyond the designated threshold and no alerts were triggered. However, product teams will review the feasible mechanisms to set an alert based on the no.of declines at store level and PED level. | Payments Foundation | Strategic | NA | 2024-07-11 | Closed | NA | (https://jira.marksandspencer.app/browse/PCAP-1806) | NA | Pavithra | 2025-02-10 | 406 | >60 | November | 2024 | #VALUE!
Customer Channels | Selling Experience | 123887531 (DN ticket) | 2024-08-21 | Digital Cafe kiosks were unavailable on 13th Aug and 15th Aug | DR process at Counter Solutions to avoid business impact durring adverse scenarios | Problem avoidance | Avalon Smith/ CS | 16/10: There is a DR set up available at Counter Solutions. In this case, as the issue was identified quickly and resolved within 15 mins, DR was not invoked. 19/09: EVen after multiple follow ups from Service lead and Customer stakeholders, we have not received the PIR document which is supposed to capture the updates on these actions. Therefore, SIAM has now escalated to the product leads to further escalate to DN or Counter Solutions in streamlining this process. 05/09: Awaiting update from CS | Counter Solutions | Tactical | NA | 16/10/24 | Closed |  |  |  | Saloni | 2025-02-10 | 407 | >60 | October | 2024 | #VALUE!
Customer Channels | Selling Experience | 123887531 (DN ticket) | 2024-08-21 | Digital Cafe kiosks were unavailable on 13th Aug and 15th Aug | There is an ongoing Resiliency program to support offline transactions during a similar instance to improve customer experience during a Major incident | Problem avoidance | Adam Smith | 14/11:The Resilience programme is now rebaselined for 2025. https://jira.marksandspencer.app/secure/RapidBoard.jspa?rapidView=10044&projectKey=RDC&view=detail&selectedIssue=RDC-486 28/08: There is an ongoing project to support offline transactions by using a local network/database approach and there is a plan to deploy this solution across to 1 pilot store by end of October. | Tech Sols Lead | Tactical | NA | 14/11/24 | Closed |  | RDC 456 |  | Saloni | 2025-02-10 | 407 | >60 | November | 2024 | #VALUE!
Customer Channels | Selling Experience | 123887531 (DN ticket) | 2024-08-21 | Digital Cafe kiosks were unavailable on 13th Aug and 15th Aug | The stakeholders were kept informed through a Teams chat, actions have been agreed on a process to streamline the stakeholder communication, especially during Golden Quarter | Business & IT Communication | Paul Dasan-Cutting | 14/11: The newly built process of business centric comms will address this action. 16/10: Laura has advised that a workstream is ongoing to standardise an email template and then a DL that ALL Retail comms (this will include Digital Cafe) will be sent as part of Ops Evolution project, but the template hasnt been agreed yet. ETA - end of Oct 19/09: Paul is OOO, PM has sent a note to him asking for the agreement on stakeholder communication. Awaiting updates In Progress. | Senior Product Manager | Strategic | NA | 14/11/24 | Closed |  |  |  | Saloni | 2025-02-10 | 407 | >60 | November | 2024 | #VALUE!
Customer Channels | Selling Experience | 123887531 (DN ticket) | 2024-08-21 | Digital Cafe kiosks were unavailable on 13th Aug and 15th Aug | Agree on a process between DN and Counter Solutions on the post incident review document to be provided to Customer. | Supplier and support involvement | Richard Appleby/ DN | 14/11: This has been agreed with DN and Counter Solutions 16/10: While an incident report has been sent out by DN, it lacks sufficient details, particularly regarding the root cause, load balancing mechanism, communication & alerting. A follow-up email has been sent to DN requesting a response from CounterSolutions. We will continue to work with DN, supported by service leads and the Digital Cafe product team, to expedite a response. 19/09: EVen after multiple follow ups from Service lead and Customer stakeholders, we have not received the PIR document which is supposed to capture the updates on these actions. Therefore, SIAM has now escalated to the product leads to further escalate to DN or Counter Solutions in streamlining this process. 05/09: DN have chased with CS who will have this sent out by the end of the day. the document was supposed to be sentby 29/08 by Avalon however she is now on leave. 28/08: It has been agreed to provide the docuemnt by COP today. Also, CS and DN to share the PIR docuemnt to Customer within 5 days after inc resolution. 21/08: The existing contract between Customer and DN upon occurrence of a major incident is to provide the root cause document within 5 days. This will be picked up between DN and Counter Solutions. | DN | Tactical | NA | 14/11/24 | Closed |  |  |  | Saloni | 2025-02-10 | 407 | >60 | November | 2024 | #VALUE!
Customer Channels | Selling Experience | 123887531 (DN ticket) | 2024-08-21 | Digital Cafe kiosks were unavailable on 13th Aug and 15th Aug | There is an existing alert at Counter Solutions to highlight an issue with the virtual machines. Review options to configure effective alerts for proactive issue identification without causing an impact to our Cafes. | Problem identification & Alerting | Avalon Smith/ CS | 21/11: Alert has been configured within Counter SOlutions 14/11: Inspite of sending multiple emails to DN & CS, there had not been any response, therefore, it has been escalated to Paul Dasan Cutting who is currently following up with Account managers, we are awaiting an update by Monday, 18th Nov 16/10: While an incident report has been sent out by DN, it lacks details, particularly regarding the root cause, load balancing mechanism, communication & alerting. A follow-up email has been sent to DN requesting a response from CounterSolutions. We will continue to work with DN, supported by service leads and the Digital Cafe product team, to expedite a response. 19/09: EVen after multiple follow ups from Service lead and Customer stakeholders, we have not received the PIR document which is supposed to capture the updates on these actions. Therefore, SIAM has now escalated to the product leads to further escalate to DN or Counter Solutions in streamlining this process. 21/08:Counter Solutions had received an alert on 13/08, however, stores reported the issue at the same time. DN were made aware of the issue through store colleagues. On 15/08, Counter Solutions received an alert indicating the issue on the previously impacted virtual machine, which was then recycled to restore services. From Counter Solutions, once an alert is triggered, it is then transferred to their internal teams for triage. Agree on a process to ensure proactive communication are sent out to Customer for awareness. We have also requested Counter Solutions to explore options of configuring a defined threshold-based alert to proactive work on a potential issue. It has been advised that Counter Solutions are working on a Major incident broadcasting notification channel for live updates. In addition, another set of alerting are being configured to identify issues with Digital Café stability – being worked by Counter Solutions. | Counter Solutions | Tactical | NA | 21/11/24 | Closed |  |  |  | Saloni | 2025-02-10 | 407 | >60 | November | 2024 | #VALUE!
Customer Channels | Selling Experience | 123887531 (DN ticket) | 2024-08-21 | Digital Cafe kiosks were unavailable on 13th Aug and 15th Aug | There was no communication sent across to Customer on the event of a code release deployed on 12/08 globally. | Problem identification & Alerting | Avalon Smith/ CS | 21/11: Counter Solutions have been advised to send proactive communication to Customer in the event on an issue/alert identified with their environment. 14/11: Inspite of sending multiple emails to DN & CS, there had not been any response, therefore, it has been escalated to Paul Dasan Cutting who is currently following up with Account managers, we are awaiting an update by Monday, 18th Nov 16/10: While an incident report has been sent out by DN, it lacks details, particularly regarding the root cause, load balancing mechanism, communication & alerting. A follow-up email has been sent to DN requesting a response from CounterSolutions. We will continue to work with DN, supported by service leads and the Digital Cafe product team, to expedite a response. 19/09: EVen after multiple follow ups from Service lead and Customer stakeholders, we have not received the PIR document which is supposed to capture the updates on these actions. Therefore, SIAM has now escalated to the product leads to further escalate to DN or Counter Solutions in streamlining this process. 28/08: CS have put in some measures to improve the communication to Customer through DN. We are still seeing some gaps in communicating an incident to Customer. Rich to pick up with CS and feed back to Laura 21/08: Counter Solutions to discuss with their internal leadership team to ensure appropriate communication are sent out the in terms of global change deployment with effective information on the customer impact. | Counter Solutions | Tactical | NA | 21/11/24 | Closed |  |  |  | Saloni | 2025-02-10 | 407 | >60 | November | 2024 | #VALUE!
Customer Channels | Selling Experience | 123887531 (DN ticket) | 2024-08-21 | Digital Cafe kiosks were unavailable on 13th Aug and 15th Aug | There is no Remedy incident raised for Digital Cafe issue which means for audit purposes, we won’t have any reference number to track these incidents. Agree on a process to enable integration between DN and remedy which will in turn raise a log in Remedy (Like we have for NOC incidents). Also, align the ownership of the incident in remedy. | Issue handling/Management | Richard Appleby/ DN | 14/11: We have validated that during Digital Cafe issues, the intergration between DN and remedy is working as expected. 16/10: DN has confirmed that the integration between Remedy and DN has been fixed, testing in progress with Customer. Awaiting further updates. 19/09: EVen after multiple follow ups from Service lead and Customer stakeholders, we have not received the PIR document which is supposed to capture the updates on these actions. Therefore, SIAM has now escalated to the product leads to further escalate to DN or Counter Solutions in streamlining this process. 28/08: DN has advised that they are still working on fixinfg the issue. ETA : 10th Sep 21/08: There is an issue with integration between DN and BMC Remedy, the solution is being worked through by DN and we await an ETA. | DN | Tactical | NA | 2024-11-11 | Closed |  |  |  | Saloni | 2025-02-10 | 407 | >60 | November | 2024 | #VALUE!
Customer Channels | Selling Experience | 123887531 (DN ticket) | 2024-08-21 | Digital Cafe kiosks were unavailable on 13th Aug and 15th Aug | There is a load balancing mechanism at Counter Solutions for the API transaction traffic (kiosks), however, during the issue on 13th Aug, we have seen a complete outage across all the Digital Cafes. Evaluate the current load balancing set up to ensure the traffic is evenly distributed across the virtual machines. | Solution & Recovery | Thomas Pollar/ Counter Solutions | 27/02: After sending multiple escalations, there had been no further response to this action. Agreed with business to close it off and scrutinise in future scenarios. 06/01: PM has spoken to Paul and have sent another chaser email to DN for an urgent update. ETA: 10/01 18/12: No response received from Counter Solutions yet, Paul is chasing further. 12/12: Paul will now chase Avalon (Cs) further for an update on their loadbalacing solution 28/11: We were advised of an ETA by CS of 25/11, however, there has been no update on the actions. We have escalated to every possible levels, however, no update yet. Further actions being agreed with Paul and co. 21/11: A further escalation to Darren will be done today to get some answers from Counter Solutions 14/11: Inspite of sending multiple emails to DN & CS, there had not been any response, therefore, it has been escalated to Paul Dasan Cutting who is currently following up with Account managers, we are awaiting an update by Monday, 18th Nov 16/10: While an incident report has been sent out by DN, it lacks details, particularly regarding the root cause, load balancing mechanism, communication & alerting. A follow-up email has been sent to DN requesting a response from CounterSolutions. We will continue to work with DN, supported by service leads and the Digital Cafe product team, to expedite a response. 19/09: EVen after multiple follow ups from Service lead and Customer stakeholders, we have not received the PIR document which is supposed to capture the updates on these actions. Therefore, SIAM has now escalated to the product leads to further escalate to DN or Counter Solutions in streamlining this process. 28/08: The way that the load balancing works between the VM’s is not cut and dry to 1 VM serving X amount of devices and VM2 the rest. Each request from the kiosk can be sent to either VM1 or VM2. Therefor in a single transaction journey the start basket request could be sent to VM 1 and then add item request could go to VM2 and so on throughout the journey. This would therefore flag the failed requests on the kiosk as an error based on which VM was serving the request at that time. There are multiple calls throughout a customer journey – if there is an issue with one of the VM, it takes the session back to homepage. 21/08: Within Counter Solutions infrastructure, as one of the VMs had a problem, the load balancer was unable to determine the health of the VM and therefore, by default only traffic going through VM1 should have a problem. Awaiting further update from CS | Counter Solutions | Tactical | NA | 27/02/24 | Closed |  |  |  | Saloni | 2025-02-10 | 407 | >60 | February | 2024 | #VALUE!
Customer Channels | Selling Experience | 123887531 (DN ticket) | 2024-08-21 | Digital Cafe kiosks were unavailable on 13th Aug and 15th Aug | There were further occurrences of the issue on 21st, 23rd Aug impacting the stores, Counter Solutions to investigate further to confirm the root cause of these instances | Root cause | Thomas Pollar/ Counter Solutions | 16/10: Couter Solutions have confirmed that the problematic code had caused the issue on 21st and 23rd August. We are still awaiting further details regarding the memory leak on the virtual machines due to the code deployment. 19/09: EVen after multiple follow ups from Service lead and Customer stakeholders, we have not received the PIR document which is supposed to capture the updates on these actions. Therefore, SIAM has now escalated to the product leads to further escalate to DN or Counter Solutions in streamlining this process. 28/08: We have not received the PIR document from CS through DN. Customer leadership are chasing DN. | Counter Solutions | Tactical | NA | 16/10/24 | Closed |  |  |  | Saloni | 2025-02-10 | 407 | >60 | October | 2024 | #VALUE!
Customer Channels | Selling Experience | 123887531 (DN ticket) | 2024-08-21 | Digital Cafe kiosks were unavailable on 13th Aug and 15th Aug | A code release deployed on 12/08 had resulted in memory leaks on one of the virtual machine serving the API traffic (kiosks) Detailed root cause analysis document from Counter Solutions | Root cause | Thomas Pollar/ Counter Solutions | 21/11: No further root cause details have been provided by CS, however, we still await an update on load balancing mechanism at CS. The root cause of the issue is a change at CS resulting in a memory leak on one of their virtual machines. 14/11: Inspite of sending multiple emails to DN & CS, there had not been any response, therefore, it has been escalated to Paul Dasan Cutting who is currently following up with Account managers, we are awaiting an update by Monday, 18th Nov 16/10: While an incident report has been sent out by DN, it lacks details, particularly regarding the root cause, load balancing mechanism, communication & alerting. A follow-up email has been sent to DN requesting a response from CounterSolutions. We will continue to work with DN, supported by service leads and the Digital Cafe product team, to expedite a response. 19/09: EVen after multiple follow ups from Service lead and Customer stakeholders, we have not received the PIR document which is supposed to capture the updates on these actions. Therefore, SIAM has now escalated to the product leads to further escalate to DN or Counter Solutions in streamlining this process. 28/08: We have not received the PIR document from CS through DN. Customer leadership are chasing DN. 21/08: We have cascaded to Counter Solution on the standard process of providing the RCA document within 5 days after a major incident is resolved. DN will now work with Counter Solution to ensure this is followed through in future instances. For this incident, we have a follow up call scheduled on 28th Aug to get more updates whilst Counter Solution work with their internal teams to provide the detailed root cause. | Counter Solutions | Tactical | NA | 21/11/24 | Closed |  |  |  | Saloni | 2025-02-10 | 407 | >60 | November | 2024 | #VALUE!
Foods | Foods Supply Chain | 90197506 | 2024-08-20 | Foods (Relex and Quantum) ordering and allocations were inflated | Root cause behind the partial data generation in SAND to ASO. | Root cause | Vivek Mehra /Puviyarasu ponnusamy | 08/10: As stated below we need to stablise the connection and this wil be done by upgrading out Azure SDK - Puvi to provide a backlog ticket - FSCLT1-5836 01/10: Puvi is out of office but Lisy was appraised. ETA amended 17/09: Microsoft replied and advised they that found AMQP link timeouts due to the increased volume of incoming requests this led a rapid expansion in entity size - we have asked Puvi what caused the volume increase. Due to timeouts some message didn’t reach the service Bus, the Microsoft server didn't process the messages and the receiver did not consume. Although later ASO re-established the connection and messages were processed.MS asked us to upgrade our Azure SDK to a newer version - Puvi to talk to various stakeholders. 10/09: Puvi advises that the Microsoft colleague dealing with this has gone on leave. Puvi will chase again. 03/09: On the incident day, Microsoft had identified connectivity issues within their infrastructure, all relevant logs have been provided to Microsoft and investigations are in progress. Update 27/08: Puvi advised that we are still awaiting Microsoft to come back with updates. The root cause is suspected to be due to an issue at the MS end. Relevant logs have been shared with MS and we await further updates on the RCA. | Foods- ASO | Tactical | NA | 2024-08-10 | Closed | NA | NA | NA | Pavithra | 2025-02-10 | 408 | >60 | October | 2024 | #VALUE!
Foods | Foods Supply Chain | 90197506 | 2024-08-20 | Foods (Relex and Quantum) ordering and allocations were inflated | Do we have the right alerting/recon mechanism within ASO/SAND service? | Problem identification & Alerting | Puvi | 03/09: Through the weekly catch up with Naveen, it was advised that the ASO team have confirmed that a threshold for the SAND extract in NextGenFOA has been configured, in case of an issue where there is a breach/mismatch/partial data in SAND, a Sev 1 alert will be triggered. Once the alert gets triggered, the Next Gen FOA will engaged ASO team for further triage. 27/08 - SAND is calculated from ASO. Alerting is not possible for intermittent connectivity. If its a full system down we have alerting in place. The NGFOA and ASO teams are working in the threshold for the SAND extract 20/08 - We have the right alerting within ASO and SAND service. However, during the incident, the SAND service was not fully unavailable rather it was intermittent, thus no alerts were generated. Also, there is a challenge in alert/recon configuration based on the SAND data volume through comparison because the data varies everyday based on the time/day/business requirements. However, the product team will further analyse for any possible alerting mechanism. Also a threshold will be defined for comparing the data volume with previous week’s data | Foods- ASO | Strategic | NA | 2024-03-09 | Closed |  |  |  | Pavithra | 2025-02-10 | 408 | >60 | September | 2024 | #VALUE!
Foods | Foods Supply Chain | 90197506 | 2024-08-20 | Foods (Relex and Quantum) ordering and allocations were inflated | Ensure we involve the right support from the relevant teams whenever a slight abnormality is observed during the overnight hypercare. | Problem avoidance | Matt White | 20/08 - During the regular hypercare, the discrepancy with the supplier orders was captured by the business stakeholders, however it was not flagged to the product teams on a timely manner. It has now been re-iterated to the business stakeholders, to report immediately to the relevant product teams whenever we observe any abnormalities/discrepancies with supplier orders/allocations. | Foods business | Tactical | NA | 20/08/24 | Closed |  |  |  | Pavithra | 2025-02-10 | 408 | >60 | August | 2024 | #VALUE!
Foods | Foods Supply Chain | 90197506 | 2024-08-20 | Foods (Relex and Quantum) ordering and allocations were inflated | Do we have the right documentation/SOP in place to give us a straightforward view on the impacts during any over allocation/under allocation scenarios? | Impact analysis | Vivek Mehra /Puviyarasu ponnusamy | 20/08 - Foods allocations/supplier ordering comprises various systems and legacy applications. Whenever there is a discrepancy with the allocation data, it might be due to various reasons/scenario within any of the system. Thus, it is a challenge to ascertain the right impacts as soon the we observe an issue with the allocations (Overallocation/underallocations) . It can only be determined upon detailed investigation on the source of the issue. Meanwhile, relevant SOP’s are in place and they are being updated as and when required. | Foods- ASO | Tactical | NA | 21/08/24 | Closed |  |  |  | Pavithra | 2025-02-10 | 408 | >60 | August | 2024 | #VALUE!
Foods | Foods Supply Chain | 90197506 | 2024-08-20 | Foods (Relex and Quantum) ordering and allocations were inflated | Ensure we send timely communications to the suppliers whenever an impact is observed with the supplier orders. | Business & IT Communication | Vinoth Purushothaman | 20/08 - During the incident, the OFP banner was immediately updated in the OFP portal to communicate the issue to the suppliers. Also, there is an agreed process in place, where we contact Terrance Banyard and Dan Maddox to have it communicated to all the impacted suppliers with the help of the certain leadership team. | Foods | Tactical | NA | 22/08/24 | Closed |  |  |  | Pavithra | 2025-02-10 | 408 | >60 | August | 2024 | #VALUE!
Foods | Foods Supply Chain | 90197506 | 2024-08-20 | Foods (Relex and Quantum) ordering and allocations were inflated | Update the run book/SOP with the recovery steps for future references. | Issue handling/Management | Vivek Mehra | 20/08 - Due to the rarity of the issue within SAND, it was challenge in identifying the missing SAND allocations. A Script/Query was developed during the incident, and it was deployed into Prod after the required testing – and it eventually delayed the incident recovery. We have now documented the query details and the steps taken to fix the issue in the runbook. | Foods- ASO | Tactical | NA | 23/08/24 | Closed |  |  |  | Pavithra | 2025-02-10 | 408 | >60 | August | 2024 | #VALUE!
Foods | Foods Supply Chain | 90197506 | 2024-08-20 | Foods (Relex and Quantum) ordering and allocations were inflated | Ensure we review the contingency file, that we use for the recovery | Issue handling/Management | Matt White | 08/10: Relex action to include the manual orders systemically into the GIST contingency file has been implemented - 04/09 10/09: A Goslin advsies that the backlog for Q3 is still being reviewed with Callum Staff 27/08 - Tamil advised that we are still working on the automation and need to get an ETA from Matt/Programme Team 20/08 - On the incident day, once we have invoked the contingency plan for allocations, it was identified that few manual orders were not included. This has been now addressed. We have a query created in Relex to extract the manual orders and it will be amended by the product teams manually. The feasibility on automation will be analysed on priority. | Foods business | Tactical | NA |  | Closed | NA | NA | NA | Pavithra | 2025-02-10 | 408 | >60 | January | 1900 | #VALUE!
Group Platforms | Finance | 90193515 | 2024-08-18 | C&H weekly sales data understated by 3.7 M in MP and SSI reports | As per the root cause as the 2nd iteration of the SAP BW extractor job had a dependency on i60 completion with a tolerance limit of 120 mins of execution, it was suggested to increase the limit to 180 minutes. Review the implications of the increase of tolerance limit in cSAP BW extractor from 120 to 180 mins. Is there a risk to downstream critical flows? | Problem avoidance | Murali Bolisetty | 19/09: Increased the tolerance limit of CSAP BW extractor from 120 to 180 mins to ensure the data is sent from ECC during an overrunning scenario 18/08: By increasing the tolerance limit of cSAP BW extractor to run its 2nd iteration until 3am, we need to review the implications to the downstream systems. It has been confirmed that Business Objects, MP and SSI have their SLOs at 12:00 noon so there should not be any impact. For BEAM reports, GMOR team will enhance their not started alerts to ensure a proactive communication is sent across to BEAM team on the anticipated delay. | SAP BW | Tactical | NA | 19/09/24 | Closed |  |  |  | Saloni | 2025-02-10 | 410 | >60 | September | 2024 | #VALUE!
Group Platforms | Finance | 90193515 | 2024-08-18 | C&H weekly sales data understated by 3.7 M in MP and SSI reports | Upon recurrence of the issue, the 2nd iteration of the SAP BW extractor did not run, how can we ensure all the data are sent to BW for downstream processing | Solution & Recovery | Murali Bolisetty | 19/09: Adhoc job will be scheduled during GQ to ensure the huge volumes in SAP POSDTA is omitted and hyper care in place for ECC due to split aggregates and IDOCs. 18/08: Product teams are exploring the feasibility of adding an adhoc iteration by eliminating manual intervention. Teams to check with Control M on scheduling a job. In addition, with the help of alerts, relevant communication is sent to inform on the delay. | SAP BW | Tactical | NA | 19/09/24 | Closed |  |  |  | Saloni | 2025-02-10 | 410 | >60 | September | 2024 | #VALUE!
Group Platforms | Finance | 90193515 | 2024-08-18 | C&H weekly sales data understated by 3.7 M in MP and SSI reports | As the i60 job did not complete by 02:00, the dependent SAP BW extractor job did not run on the day due to the 120 mins tolerance set (from 00:00). There was a “Not Started” alert received in SAP BW, what actions were taken at the time? | Problem identification & Alerting | Murali Bolisetty | 19/09: The SOPs /run book hs been updated and teams were advised to strictly follow the same 18/08: The Not started alert was received at 01:00, there was gap in understanding the tolerance limit of 2:00am for the 2nd iteration of SAP BW extractor to run. There is an existing run book, however, due to the rarity of the issue, this scenario was not captured. Agreed with team to update the run book. | SAP BW | Tactical | NA | 19/09/24 | Closed |  |  |  | Saloni | 2025-02-10 | 410 | >60 | September | 2024 | #VALUE!
Group Platforms | Finance | 90193515 | 2024-08-18 | C&H weekly sales data understated by 3.7 M in MP and SSI reports | There was an alert triggered in SAP ECC for i60 overrun, what actions were taken at the time? | Problem identification & Alerting | Narayana Moorthy Kanagaraj | 18/08: There was an Sev 1 overrunning alert received in SAP ECC, the team had monitored the job and informed the SAP BW Team, however, no actions were taken. It has been agreed with the team to conduct a refresher session across the engineers to ensure appropriate impact analysis are performed and relevant communication are sent to notify the business stakeholder | SAP Sales | Tactical | NA | 18/08/24 | Closed |  |  |  | Saloni | 2025-02-10 | 410 | >60 | August | 2024 | #VALUE!
Group Platforms | Finance | 90193515 | 2024-08-18 | C&H weekly sales data understated by 3.7 M in MP and SSI reports | During the MIM bridge, it was advised, that the i60 job in SAP ECC had overrun due to higher volume of idoc failures to be processed. Review the idoc volume for 10th Aug when compared to 3rd Aug to define the reason behind the overrunning job. | Root cause | Narayana Moorthy Kanagaraj | 27/08: It was confirmed that as the data volume coming from POS is huge, it is not feasible to identify the reaon behind the job failure. 18/08: The teams have compared the idoc volume between 10th Aug and 3rd Aug. However, it seems like i60 job had to process 40M idoc on 3rd Aug and completed at 01:40. However, on 10th Aug, the i60 job had to process 36M data which completed at 02:30. There is a possibility that i60 had to reprocess high volume of idoc failures which could have resulted in the job to overrun. Whilst comparing the idoc failure stats, the volume looks usual, we do not have the idoc failure stats for 3rd August, as the data is purged as per design. This needs further investigation to ascertain the reason behind the job overrun | SAP Sales | Tactical | NA | 27/08/24 | Closed |  |  |  | Saloni | 2025-02-10 | 410 | >60 | August | 2024 | #VALUE!
GTS | ETP-On premise services | 90167863 | 2024-08-15 | Message processing issues between WMS and WCS at Donington | As there were intial confusion regarding the scope of triage on the WCS server, SMEs to update the runbook to highlight the health check process/alerting existing in the infrastructure for WCS services along with a refresher session within the team to ensure teams are updated with the relevant knowledge. | Solution & Recovery | Jafar Sadiq | 05/09: A refresher session to the infrastructure team to ensure the infra teams are aware of the server details, IP addresses in terms of support. Refer to the handover document. An activity is being performed to analyse at the capacity planning of the WCS servers as part of GQ readiness. | Infra | Tactical | NA | 2024-05-09 | Closed |  |  |  | Saloni | 2025-02-10 | 413 | >60 | September | 2024 | #VALUE!
GTS | ETP-On premise services | 90167863 | 2024-08-15 | Message processing issues between WMS and WCS at Donington | Explore options on enhanced observability on the WCS servers and database servers – overall infrastructure: | Problem identification & Alerting | Elizabeth Golder | 05/09: We have standard alerting on the WCS servers, database servers for CPU utilisation, memory spikes etc. No improvements are feasible as the infrastructure hardware is out of support. Customer leadership - Daf Michael have highlighted this risk to Head of Logistics - Kevin Bennett and this is now being dealt by them. There is no real risk raised for this in Monday.com. | Service owner | Strategic | NA | 2024-05-09 | Closed |  |  |  | Saloni | 2025-02-10 | 413 | >60 | September | 2024 | #VALUE!
C&H and Intl | C&H and Intl supply chain | 90167863 | 2024-08-15 | Message processing issues between WMS and WCS at Donington | Identify whethere there are alerts configured at Schaefer to notify on multiple WCS services failure to the site/tech ops | Problem identification & Alerting | Murali Srinivasan | 05/09: We would not receive any further details from SSI as per the contract as the site had raised a Sev1 initially. Due to the change in vendor in future, SSI would only provide contractual support during the Golden Quarter. No enhanced support is anticipated. Customer leadersip are aware of the risk. No risk raised in Monday. | CD service lead | Tactical | NA | 2024-05-09 | Closed |  |  |  | Saloni | 2025-02-10 | 413 | >60 | September | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 90167863 | 2024-08-15 | Message processing issues between WMS and WCS at Donington | Vendor SSI had advised that there was a network blip around 16:30 that impacted their WCS services. As the WCS infrastructure is supported by TCS, analyse the infrastructure stats in terms of server, database to determine the root cause. | Root cause | Kamalakkannan Kanniappan | 20/08: Network team had analysed the logs during the incident duration, however, did not identify any anomalies. As we do not have appropriate support from SSI, the detailed root cause could not be ascertained. | Network | Tactical | NA | 2024-05-09 | Closed |  |  |  | Saloni | 2025-02-10 | 413 | >60 | September | 2024 | #VALUE!
GTS | Operations | 90165072 | 2024-08-15 | BMC Helix (Remedy) and Tech support portal inaccessible | Review the mapping of the identity certificate in the central certificate management tracker and ensure its being tracked for future instances | Problem avoidance | Padmaja Lemaati | 15/08: IT has been agreed to track the identity and portal certificate into the central Certificate dashboard. In addition, an exercise needs to be conducted to eliminate the obsolete certificates after SP exit completion. | Certificate Management | Strategic | NA | 15/08/24 | Closed |  |  |  | Kavitha | 2025-02-10 | 413 | >60 | August | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 90165072 | 2024-08-15 | BMC Helix (Remedy) and Tech support portal inaccessible | Create a SOP to document the process of certificate renewal. | Solution & Recovery | Kamalakannan Kanniappan | 15/08:Although, it is certain that we would not have a dependency on the certificate in the upcoming year, as we are moving to Cloud SSO authentication, product teams have created a SOP documenting the relevant steps to refer to in future renewal activity. | Network | Tactical | NA | 15/08/24 | Closed |  |  |  | Kavitha | 2025-02-10 | 413 | >60 | August | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 90165072 | 2024-08-15 | BMC Helix (Remedy) and Tech support portal inaccessible | Understand the relationship between BMC helix and identity certificate to conclude the reason behind the issue after the certificate renewal | Root cause | Kamalakannan Kanniappan | 15/08; For BMC, there are two certificate responsible to enable successful authentication: 1. BMC certificate incorporated into our network F5. – During the renewal, as network team had confirmed that the BMC certificate is active, therefore, we did not liaise with BMC proactively. 2. Update network F5 certificate within BMC infrastructure – This was not identified prior to the impact incurred due to the knowledge gap. | Network | Tactical | NA | 15/08/24 | Closed |  |  |  | Kavitha | 2025-02-10 | 413 | >60 | August | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 90165072 | 2024-08-15 | BMC Helix (Remedy) and Tech support portal inaccessible | Review the SSO certificate renewal process within network layer to avoid any impact to the dependent applications | Problem avoidance | Kamalakannan Kanniappan | 15/08; The certificate has been renewed until July 2029. It seems we will be moving out of identity portal for SSO authentication of majority of the applications, RDA etc. For BMC, a project has been initiated to move the authentication from on prem SSO to Azure SSO and this will get completed before 2029. – therefore, there is no further chance of issue recurrence. BMC Azure SSO authentication: https://jira.marksandspencer.app/browse/CHBRANDC-301 | Network | Strategic | NA | 15/08/24 | Closed |  |  |  | Kavitha | 2025-02-10 | 413 | >60 | August | 2024 | #VALUE!
C&H and Intl | C&H and Intl supply chain | 90174166 | 2024-08-09 | Issues with multiple PLCs at Donington | Due to the dependency of the PLCs and the TSM back up servers, the issues were noticed. Action to ensure that the PLC’s are not dependent on the backup servers. | Problem avoidance | Murali Srinivasan/Pragadeesh | 12/09 - Jira reference [JDATE-10452] New design required for maintaining PLC servers - Jira App (marksandspencer.app) has been created to track this activity. 29/08 - Pragadeesh confirmed that they will create a backlog and share it ASAP. 23/08 - Pragadeesh has shared the recommendation of building new server to the Architect for further comments. 16/08 - Murali and Pragadeesh are still working on and will update further on this by 20th. 09/08 - It is not recommended for a production service at CD to use a backup sever, ideally it should be relying on a different dedicated server. Based on the risk raised for action no3, this action will be proposed to business and necessary measure will be taken. Also, we need to make sure to move the services from unsupported hardware (HP) to any supported hardware. Procuring the hardware will be owned by the CD team and the migration will be assisted by Infra SME’s) | Service lead - CD |  | NA | 2024-12-09 | Closed | NA | JDATE-10452 | NA | Gokul | 2025-02-10 | 419 | >60 | September | 2024 | #VALUE!
GTS | ETP-On premise services | 90174166 | 2024-08-09 | Issues with multiple PLCs at Donington | There were no alerts triggered to identify the file share access issue. Identify the scope of configuring alert to proactively identify issues. | Problem identification & Alerting | Somasekhar N/Sailesh | Configuring an alert for PLC file share access at the server level is not feasible, as these are purely backup servers also there seams to be no feasibility of alerting at the PLC end (supported by DFT). However other preventive measures have been agreed with the teams. | Storage |  | NA | 2024-09-08 | Closed | NA |  | NA | Gokul | 2025-02-10 | 419 | >60 | August | 2024 | #VALUE!
GTS | ETP-On premise services | 90174166 | 2024-08-09 | Issues with multiple PLCs at Donington | Review the existing risk to document the incompatibility of TSM01 and TSM02 with future RHEL upgrades | Issue handling/Management | Somasekhar N/Sailesh | 16/08 - Sailesh has updated the risk #2062 with the PLC services as well in Monday.com, hence closing the action. 09/08 - Infra team has an existing Risk for the hardwares that have not been upgraded to the RHEL 8. PLC services will also be updated to the RISK list. | Storage |  | NA | 19/08/24 | Closed | NA |  | NA | Gokul | 2025-02-10 | 419 | >60 | August | 2024 | #VALUE!
C&H and Intl | C&H and Intl supply chain | 90174166 | 2024-08-09 | Issues with multiple PLCs at Donington | During the incident, we identified Durkopp PLCs were marked as “Decommissioned” which is incorrect, therefore, review MAL to ensure the critical components at Donington are captured appropriately | Problem avoidance | Murali Srinivasan/Pragadeesh | 12/09 - Jira reference [JDATE-10452] New design required for maintaining PLC servers - Jira App (marksandspencer.app) has been created to track this activity. 29/08 - Pragadeesh confirmed that they will create a backlog and share it ASAP. 23/08 - It was agreed with Murali S to be discussed, with the principal architect on the application "Duerkopp Hanging Sorter" in MAL application status to be amended appropriately as "Physical mechanisation components also present in Donington and Bradford NDCs, but controlled by SSI/Knapp WCS software rather than the Duerkopp application used with MUWS." 16/08 - Murali and Pragadeesh are still working on and will update further on this by 20th. 09/08 - Durkopp service has been listed as “decommission” in MAL – Thus the service leads will review the same and will have it amended as required. | Service lead - CD |  | NA | 2024-12-09 | Closed | NA | JDATE-10452 | NA | Gokul | 2025-02-10 | 419 | >60 | September | 2024 | #VALUE!
C&H and Intl | C&H and Intl supply chain | 90174166 | 2024-08-09 | Issues with multiple PLCs at Donington | Whilst planning the RHEL upgrade change, the dependency between the PLCs and TSM servers were not identified which resulted in ineffective impact assessment. Therefore, review the change implementation and validation steps for future instance. | Problem avoidance | Murali Srinivasan/Pragadeesh | 27/08 - Pragadeesh confirmed that their SOP is updated. 23/08 - Pragadeesh confirmed that for any changes in TSM01 and TSM02, his team is made aware of the dependency about PLC. However, have asked him for the reconfirmation if the SOP is updated. Also he wanted to check on the infra end and Jeeva in the PIR call confirmed that they are aware of it and unable to update all minute details in the SOP. 16/08 - Murali and Pragadeesh are still working on and will update further on this by 20th. 09/08 - For any changes in future, make sure we perform further checks and validations on the PLC services and we need to make sure we include DFT’s for validations. Also, Product teams to have this documented on their SOP’s for the exact impact assessment. | Service lead - CD |  | NA | 27/08/24 | Closed |  |  |  | Gokul | 2025-02-10 | 419 | >60 | August | 2024 | #VALUE!
Customer Channels | Customer Engagement | 90169969 | 2024-08-09 | Customers getting Something went wrong error message when attempting to sign-in | We need to understand with Apigee regarding their auto-scaling capabilities, specifically for managing high-demand events | Problem avoidance | Apigee Vendor | 02/09: Apigee has increased Vertical Scaling. Customer should no longer experience issue | .com Service Owner | Strategic | NA | 2024-02-09 | Closed |  |  |  | Kavitha | 2025-02-10 | 419 | >60 | September | 2024 | #VALUE!
Customer Channels | Customer Engagement | 90169969 | 2024-08-09 | Customers getting Something went wrong error message when attempting to sign-in | Comms on any (Critical) business events to Identity team and other product teams (that would help for visibility/transparency) | Business & IT Communication | Elaine | 16/10: Identity team has been included in all relavent communication for visibility 16/08: Gettingprogress | .com Service Owner | Strategic | NA | 16/01/25 | Closed |  |  |  | Kavitha | 2025-02-10 | 419 | >60 | January | 2025 | #VALUE!
Customer Channels | Customer Engagement | 90169969 | 2024-08-09 | Customers getting Something went wrong error message when attempting to sign-in | Getting a detailed RCA from Apigee on and mitigation steps | Root cause | Priya/Aadil | 02/09 - RCA has been shared by Apigee, updated in PIR. Capacity has been scaled up so this issue won't be repeated. | .com Service Owner | Tactical | NA |  | Closed |  |  |  | Kavitha | 2025-02-10 | 419 | >60 | January | 1900 | #VALUE!
Infosec & Tech Risk | Infosec & Tech Risk | 90169969 | 2024-08-09 | Customers getting Something went wrong error message when attempting to sign-in | Amend (If not existing, then create a new one) the Infosec process to understand the impact statement for the changes proposed | Impact analysis | Libin Chandy | 16/01: A MIRO has been created to understand the impact statement any of the changes proposed and all the relavent teams are having access 21/08: Gettingprogress | Infosec & Tech Risk | Tactical | NA | 16/01/25 | Closed |  |  |  | Kavitha | 2025-02-10 | 419 | >60 | January | 2025 | #VALUE!
Infosec & Tech Risk | Infosec & Tech Risk | 90169969 | 2024-08-09 | Customers getting Something went wrong error message when attempting to sign-in | New design approach for Identity on DOS attacks with more collaborations with Akamai | Permanent Fix | Tim S/Simon A | 28/11: we've shared a requirements diagram with the Akamai team: https://miro.com/app/board/uXjVKswaRPE=/?share_link_id=568137858016 and they have updated their policies to reflect these requirements. We have also enabled Bot Manager Premier protection for the login journey. 02/09: Tim & Simon are OOO they will be back mid of next week | Infosec & Tech Risk | Tactical | NA | 28/11/24 | Closed |  |  |  | Kavitha | 2025-02-10 | 419 | >60 | November | 2024 | #VALUE!
Infosec & Tech Risk | Infosec & Tech Risk | 90169969 | 2024-08-09 | Customers getting Something went wrong error message when attempting to sign-in | Are we missing any other Identity downstream nodes/APIs need to be included for Akamai WAF rules? | Problem avoidance | Libin Chandy | 16/01: Due to a knowledge gapthe issue has occured,however going forward as part of the lesson learnt team will going forward check all the internal IP before blocking and inaddition bot automation has been put in place to block the IP. 09/08: Team in validating if any other Identity downstream nodes/APIs need to be included for Akamai WAF rules? | Infosec & Tech Risk | Strategic | NA | 16/01/25 | Closed |  |  |  | Kavitha | 2025-02-10 | 419 | >60 | January | 2025 | #VALUE!
Customer Channels | Customer Engagement | 90169969 | 2024-08-09 | Customers getting Something went wrong error message when attempting to sign-in | Onyx Auth to optimise calls to openid-configuration and jwks.json | Permanent Fix | Pedro Moreira | 16/01: openid-configuration has been optimised, however the work on 'jwks.json' has been blocked from progressing due to its complexeity 09/08: Team is working on optimising the calls to openid-configuration and jwks.json | Onyx Auth | Tactical | NA | 16/01/25 | Closed |  |  |  | Kavitha | 2025-02-10 | 419 | >60 | January | 2025 | #VALUE!
Customer Channels | Selling Experience | 90165269 | 2024-08-08 | Customers getting an error message across various pages and channels | Incident Management process - Need to review process when a .com incident turns into a MIM incident i.e. which bridge to use, how and where comms should be done etc, need a seamless process | Issue handling/Management | Elaine Hawthorn | 09/09: Rams has confirmed to close this action as the new approach of Incident Channel and Loop will be used for better visibility during incidents. We now have a loop process in place to give relevant visibility across all D&T stakeholder. Needs further discussions with Elaine | Service Manager | Tactical | NA | 2024-09-09 | Closed |  |  |  | Saloni | 2025-02-10 | 420 | >60 | September | 2024 | #VALUE!
Customer Channels | Selling Experience | 90165269 | 2024-08-08 | Customers getting an error message across various pages and channels | Mitigation actions: Review of mitigations. 2 strategies discussed. 1. Remove anything in our stack that we do not really need in order to reduce complexity and points of failure. In particular review the use of Azure Front Door. Do we really need it? 2. If we determine that we do need Front Door, is there any value in diversifying our stack?, do we need contingency ? Given that Front Door is used in many places, we need to look at all of the places it is used (i.e. not just the areas that were impacted during this incident). Maebh and Stuart to revie | Problem avoidance | Maebh Booth & Stuart Brown | 14/11: We have an architect starting in a couple of weeks which will take at least a few months to design a solution. This cannot be tracked under a backlog - will be picked up with in the product. 07/10: Maebh has confirmed that she needs to check with the engineers to provide the backlog details as she has not directly raised in the portal 19/09: Maebh updated that they are writing up an RFP , and a backlog to establish specifics for tech stack. Awaiting a backlog id In progress | Sr Head of SW engineering | Tactical | NA | 14/11/24 | Closed |  |  |  | Saloni | 2025-02-10 | 420 | >60 | November | 2024 | #VALUE!
Customer Channels | Selling Experience | 90165269 | 2024-08-08 | Customers getting an error message across various pages and channels | Microsoft engagement - Although Microsoft joined our bridge, the information that they shared did not give us anything over and above what was shared on their portal. Darren to discuss with Rachel and see if we can work with them to get better prioritisation and clarity on expected resolution times | Supplier and support involvement | Darren Gibson | 12/11: Through the Supplier event and weekly connect, Microsoft has been reiterated on the requirement of enhanced cooperation during a major incident/ 16/10: Have been following up with Darren, awaiting a response on his conversation with Rachael to improve Microsoft engagement Awaiting updates from Darren | Heaad of Ops | Tactical | NA | 2024-12-11 | Closed |  |  |  | Saloni | 2025-02-10 | 420 | >60 | November | 2024 | #VALUE!
Customer Channels | Selling Experience | 90165269 | 2024-08-08 | Customers getting an error message across various pages and channels | Configure alerting in the Application layer – Florian to review whether we can have simpler dashboards which are easier to use and give an ‘early warning’ of issues • Review mesh and federation alerting and find gaps and improvements - Thomas Peasgood • Improve SLOs on downstream services and alert when SLOs not met Need a dashboard which helps us see the impact on visitors or conversion rates. This needs to be across product groups. The dashboard should be able to provide the ability to drill down into individual areas/products e.g. App etc . Top level view required. Steve Warren to review | Problem identification & Alerting | Florian Lamotte/ Thomas Peasgood/ Steve Warren | 14/11: We've not had any large scale pieces of work, we are constantly reviewing the thresholds etc of the alerts but nothing like a ticket. The amount of work that would require on the deprecated Mesh system is not something we have scope to do (also the issue is more over alerting than gaps). As for supergraph we have made minor tweaks but the lack on incidents (I may be cursing this) has meant we haven't discovered any gaps. This is being tracked under https://github.com/DigitalInnovation/supergraph/issues/702 31/10: This action has been escalated to Steve and awaiting further updates. 16/10: The team has confirmed that the alert configuration at the application layer is being prioritized, though we are still awaiting an ETA from the relevant teams. Once the alerting is configured, discussions will follow on improving downstream SLOs and setting up alerts for when those SLOs are not met. 19/09:- "• Review mesh and federation alerting and find gaps and improvements - Thomas Peasgood. This action is completed. Creating an alert and dashboard is currently being worked through as part of Golden Quarter readiness 13/09: NO updates received yet, following up with Steve Warren 20/08: There are 3 actions in terms of observability. All 3 owners are working on it and next update is due for 30th Aug. | Web app | Tactical | NA | 14/11/24 | Closed |  |  |  | Saloni | 2025-02-10 | 420 | >60 | November | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 90177992 | 2024-08-08 | Stores colleagues unable to access CSSM C&H returns functionality on honeywells | There are multiple application functionalities dependent on the CSSM user group – ST APP CSSM GM Users. Identify the reason behind the impact being limited to C&H Returns. Consolidate the mechanism on how other functions are getting authenticated in AD either by LDAP calls or any other methods. | Root cause | Usman Ahmed | 23/08 - Completed and all the details are captured as part of the backlog CHSM-1223. 20/08 - Team is still working internally to reconfirm if the understanding is correct. 08/08 - It has been confirmed that the impacted functionality uses the LDAP security check to authenticate, as the incorrect user group was still cached in the application server, these functions were impacted. Also, other functions are using cloud-based ways to authenticate which is not depending on the user group authentication, however this needs confirmation. | Honeywells |  | NA | 23/08/24 | Closed |  |  |  | Gokul | 2025-02-10 | 420 | >60 | August | 2024 | #VALUE!
GTS | Digital Workplace Services | 90177992 | 2024-08-08 | Stores colleagues unable to access CSSM C&H returns functionality on honeywells | Currently, Service Desk team are only responsible of the process of adding a store colleague to a particular AD group. As there are no other actions required to perform in AD, it has been agreed to revoke the privileged access across all Service Desk members in AD and keep it limited to AD group addition. | Permanent Fix | Muthunagappan | 23/08 - After securing the required approvals, Muthu has created AD group named "IT ADM SD User Management" in MNSUK and MNSSTORES domain and restricted the permission to only modify the membership of the group. Testing also done, hence closing. 21/08 - Muthu confirmed that he is in the process of securing required approvals to a seperate group creation for SD and access provision. 16/08 - Muthu is OOO, team is not aware of this action. Hence, will check with him once he is back by 20/08. 08/08 - Active Directory team will lead the process of revoking the edit, delete access of all Service Desk members. | Active directory Team |  | NA | 23/08/24 | Closed |  |  |  | Gokul | 2025-02-10 | 420 | >60 | August | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 90177992 | 2024-08-08 | Stores colleagues unable to access CSSM C&H returns functionality on honeywells | In the CSSM Event viewer logs, 503 errors were captured against the authentication failures on a colleague level. Configure alerting based on the 503 error logs in the event viewer to proactively identify issues | Problem identification & Alerting | Yogesh Verma | 19/11 - WO0000001506011 has been raised after testing the SCOM alert with AMS Doc and hence closing. 28/10 - SCOM team is checking the threshold limit as requested by SCCM team, so that the alerts can be set 21/10 - CSSM team is still working on configuring the alerts 10/10 - Testing alert got triggered in SCOM console for the event id 503. Team to work on configure in production. 03/10 - No approach has been successful and the team is working with SME's and will confirm by 8th if it is feasible or not. 26/09 - CSSM team is trying with all possible ways in triggering the error, but still couldn't able to replicate the issue. They will try with different approach and update us. 23/09 - 503 error is not triggering in CATE and CSSM team is adding a similar event to do this. 12/09 - Testing in CATE is still in progress 03/09 - Awaiting test results from SCOM team. 29/08 - SCOM team is testing the alert in cate environment today. 23/08 - https://jira.marksandspencer.app/browse/CHSM-1224 - connected with SCOM team and they are exploring this in non-prod and then we can do in production. 20/08 - Team is still working with tools team to set the alert. 08/08 - CSSM team will liaise with Netcool team to configure a 503-error alert integrated with Remedy. Note: this is a proven process as there is an existing Netcool alert configured for a separate error in Event Viewer. | CSSM |  | NA | 19/11/24 | Closed |  |  |  | Gokul | 2025-02-10 | 420 | >60 | November | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 90177992 | 2024-08-08 | Stores colleagues unable to access CSSM C&H returns functionality on honeywells | Explore options to configure alerting based on LDAP/ authentication call failures to identify application functionality access issues using Newrelic | Problem identification & Alerting | Saipriyadarshini Thangavel | 23/08 - Got the required information from POS and captured details in backlog https://jira.marksandspencer.app/browse/CHSM-1236. This is currently not being done as there are no alerting for on prem to cloud, and this is still being explored based on the backlog information obtained. 20/08 - Analysis on existing alerts and new possible alerts which can be configured is still being explored. 08/08 - The teams will explore options within the product teams. | CSSM |  | NA | 23/08/24 | Closed |  |  |  | Gokul | 2025-02-10 | 420 | >60 | August | 2024 | #VALUE!
GTS | Digital Workplace Services | 90177992 | 2024-08-08 | Stores colleagues unable to access CSSM C&H returns functionality on honeywells | There were no alerts triggered for the amendment in AD group name. Only during the triage, it was identified that the AD group name might have been amended. Therefore, we have agreed to audit the Sentinel logs in terms of AD group name changes to understand the frequency of the changes. If the interval is less, explore options to configure an alert. | Problem identification & Alerting | Muthunagappan | 21/08 - For all changes, 4625 is the event id, there is no specific event id for group name change. Hence, closing the action. 16/08 - Muthu is OOO, team is not aware of this action. Hence, will check with him once he is back by 20/08. 08/08 - AD team will now liaise with Cyber Security team to audit the Sentinel logs and identify the frequency of the AD group name changes to proceed in configuring an alert. | Active directory Team |  | NA | 21/08/24 | Closed |  |  |  | Gokul | 2025-02-10 | 420 | >60 | August | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 90177992 | 2024-08-08 | Stores colleagues unable to access CSSM C&H returns functionality on honeywells | There were challenges in identifying the impacted functionality and the scale of impact during this incident. Explore the feasibility of identifying a mechanism to identify impacted functionalities. | Impact analysis | Saipriyadarshini Thangavel | The teams have reviewed the backend code and LDAP logic involved in the functionalities to identify the impacted functions. However, during future scenarios, the team would still need time to triage the code and confirm the impacted functionalities to identify the scale of impact. | CSSM |  | NA | 2024-08-08 | Closed |  |  |  | Gokul | 2025-02-10 | 420 | >60 | August | 2024 | #VALUE!
GTS | Digital Workplace Services | 90181725 | 2024-08-08 | Finance & HR colleagues in Salford Quays were experiencing connectivity issues | Both SQ issues occurred on a Monday and as such we have arranged for Arjun to attend site at 07:00 to carry out checks just prior to colleagues starting work. | Impact analysis | David Bruce | David Bruce has agreed and Arjun will be in SQ on Monday 12/08 at 7am | dws | Tactical | NA | 2024-08-08 | Closed | NA | NA | NA | Pavithra | 2025-02-10 | 420 | >60 | August | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 90181725 | 2024-08-08 | Finance & HR colleagues in Salford Quays were experiencing connectivity issues | Root cause investigations and testing ongoing with Vodafone | Root cause | Kamal and Mustafa | 17/09: Kamal advised that VF have not found any root cause and cannot proceed further with RCA 07/09: Raised TAC 12565952 with VF- The VF team has reviewed all the interface logs and have not found any issues that could have caused the issue on the 5th of August. If the issue reoccurs then NOC to provide trace logs and VF is available for troubleshoot call. Therefore, the root cause remains unknown. However, to proactively identify the issue in future, an OSPF Route change alert needs to be configured - this needs to be a Sev1 and tagged to Network team 16/08 -The RCA seems to inconclusive, as Vodafone isnot able to replicate the issue in the lower environment - Further follow-up will be done with VF. | Network | Tactical | NA | 17/09/24 | Closed | NA | NA | NA | Pavithra | 2025-02-10 | 420 | >60 | September | 2024 | #VALUE!
Foods | Foods Supply Chain | 90158804 | 2024-08-02 | Some Foods suppliers did not receive the 28 day order plan. | What caused the connectivity issue between CXM and Power BI paginated reports? | Root cause | Naveenkumar bojjankula | 16/08 - Microsoft have confirmed that it’s a temporary issue and they are unable to track the logs at their end. Thus RCA is inconclusive due to insufficient logs. however, for the re-occurence of the issue, additional logging has to be captured as recommended by MS - (MS recommendatoins has been documented for future reference) 02/08 -The initial root cause was attributed to a connectivity issue between CXM (Category Exception Management) and Power BI paginated reports. Investigations within CXM revealed error responses from PowerBI for requests from CXM, thus investigations are now focussed on Power BI connectivity. A case has also been raised with Microsoft and we have shared logs shared for further investigations for root cause analysis. | Foods product team | Tactical | NA | 16/08/24 | Closed | NA | NA | NA | Pavithra | 2025-02-10 | 426 | >60 | August | 2024 | #VALUE!
Foods | Foods Supply Chain | 90158804 | 2024-08-02 | Some Foods suppliers did not receive the 28 day order plan. | What sort of alerting do we have currently? Have we configured a PD/incident alert whenever there is a data transfer issue between two systems? | Problem identification & Alerting | Pradeep Rathinam | 16/08 - Additional Alerts were configured and deployed thru CRQ000000206094 on 01/08/24 02/08 - There was a mail-based PD callout alert configured, however during the incident the PD callout did not trigger as expected and though the email was received it was overlooked - Product team to review the gaps with the PD callout process. Meanwhile we have additional alerting in place such as API based PD callouts and extensive manual hypercare. | Foods product team | Tactical | NA | 16/08/24 | Closed | NA | NA | NA | Pavithra | 2025-02-10 | 426 | >60 | August | 2024 | #VALUE!
Foods | Foods Supply Chain | 90158804 | 2024-08-02 | Some Foods suppliers did not receive the 28 day order plan. | Explore the feasibility for data reconciliation between the source (NGFOA/CXM) and destination (OFP/suppliers) | Problem avoidance | Pradeep Rathinam/ Prasath Natarajan /Sundar ram D | 27/08 - 1. NGFOA to CXM : Manual recon scirpt is in place. 2. CXM to OFP and OFP to Sendgrid : Manual recon already in-place for week days and it has been be extended to weekends now after acquiring access to Send Grid. 04/08 - FSP-5655 backlog has been raised to enable automation to have a better reconsilation between CXM and Sendgrid - Meanwhile we have a manual recon in place between the two systems. 16/08 - 1. NGFOA to CXM : Manual recon scirpt creation inprogress. 2. CXM to OFP and OFP to Sendgrid : Manual recon already in-place for week days. Will be extended to weekends provided if we have Sendgrid access. Discussion in-progress for obtaining the access. - 04/08 - FSP-5655 backlog has been raised to enable automation to have a better reconsilation between CXM and Sendgrid - Meanwhile efforts are being made to have a manual recon in place between the two systems. 02/08 - A manual reconciliation between CXM and OFP exists, where validations are made system by system with dedicated resources. However, there is another option to receive an extract from “Send grid” (the end system) which will be useful for the recon between source and destination. Product team will collaborate with OFP team to get this implemented by 15/08. This method is a manual process and options on automation will be considered on next quarter (Q3). | Foods product team | Tactical | NA | 27/08/24 | Closed | NA | FSP-5655 | NA | Pavithra | 2025-02-10 | 426 | >60 | August | 2024 | #VALUE!
Foods | Foods Supply Chain | 90158804 | 2024-08-02 | Some Foods suppliers did not receive the 28 day order plan. | How can we communicate to the suppliers on the incident? | Business & IT Communication | Naveenkumar bojjankula/ Kallidos | 27/08 - It has been agreed to "intially send a broadcasting to supplier to inform about the delay and subsequent updates via OFP banner to supplier. Will be taken up with OFP team accordingly. " 16/08 -Discussions have been made with Robert and it has been suggested to intially send a broadcast message to supplier to inform about the delay and subsequent updates via OFP banner to supplier. However this further needs to be analysed with business to finalise the supplier details. 02/08 - There are two options available to notify the suppliers on the delay with 28DOP. OFP banner (within OFP Portal) but suppliers might not check the portal for 28DOP. OFP Broadcast. (External email will be sent to the list of suppliers) Product team will check with Robert George (Supplier SPOC) and agree on a viable process to communicate the suppliers on a timely manner. | Foods product team | Tactical | NA | 27/08/24 | Closed | NA | NA | NA | Pavithra | 2025-02-10 | 426 | >60 | August | 2024 | #VALUE!
Foods | Foods Supply Chain | 90158804 | 2024-08-02 | Some Foods suppliers did not receive the 28 day order plan. | Ensure everyone in the teams gets access to “send grid” - to reduce the dependency | Solution & Recovery | Vinoth/Naveen | 27/08 - Team has now got the access to Sendgrid. 16/08 - Discussion are in-progress 02/08 - “Send Grid” is the azure service used to send the emails to the supplier by calling the OFP API service. There are scenario’s where some emails can get blocked within SendGrid. Currently we rely on one specific associate who has access to SendGrid to remove the blockages. In-order, to eliminate the dependency – Product leads will review how to acquire additional logins/access to send Grid – this will contribute for the timely recovery. | Foods product team | Tactical | NA | 27/08/24 | Closed | NA | NA | NA | Pavithra | 2025-02-10 | 426 | >60 | August | 2024 | #VALUE!
Foods | Foods Supply Chain | 90158804 | 2024-08-02 | Some Foods suppliers did not receive the 28 day order plan. | Review and update the SOP accordingly | Issue handling/Management | Pradeep Rathinam | 21/08 - SOP has been finalized and has been shared within the team 02/08 - The SOP documentation is still in draft and is yet to be finalised/published. | Foods product team | Tactical | NA | 21/08/24 | Closed | NA | NA | NA | Pavithra | 2025-02-10 | 426 | >60 | August | 2024 | #VALUE!
GTS | Digital Workplace Services | 90181725 | 2024-07-31 | Colleagues in Salford Quays affected by Wi-Fi connectivity issues | We need to ascertain if there is any way we can provide resilience to the access points and wireless controllers in the event of a power cut. Check UPS availability in comms room and see feasibility to attach core services to it. | Problem avoidance | Corey Cummings/ Arjunraj Edayilliam plus NOC team | 14/02 - A new CISCO WLC has been deployed at Chester HO with flex connect option enabled, providing enhanced resilience. Flex connect allows AP to continue functioning and providing network connectivity even if the connection in the controller is lost 29/01 - Another follow-up has been made with escalation - to get the Risk-ID raised 15/01 - Lokesh needs to check with Suganya C from his team for the Risk ID - awaiting further update 20/12 - Lokesh/NOc will raise a Risk for this action. 21/11 - Having a UPS a the coms room involves lost of cost and extra approvals - thus we will take this into consideration on the incident re-occurences meanwhile we will have the Risk raised for the same. 04/10 - Rehan to email Kamal and ask for next steps so he can talk to Ian/Simon 08/08 - We do not have an UPS in the comms room. To get a UPS we need an approval from the Tech Team | DWS |  | NA | 14/02/24 | Closed | NA | NA | NA | Pavithra | 2025-02-10 | 428 | >60 | February | 2024 | #VALUE!
GTS | Digital Workplace Services | 90181725 | 2024-07-31 | Colleagues in Salford Quays affected by Wi-Fi connectivity issues | 31/07 - To ensure we can advise all impacted business areas of the incident in a timely manner onsite engineers have been advised, in the event of a recurrence to call NOC and MIM. We have provided the link to the contact repository so that UAT can be arranged ASAP after the power is restored. | Solution & Recovery | Corey Cummings/ Arjunraj Edayilliam | We have provided the link to the contact repository so that UAT can be arranged ASAP after the power is restored. | DWS |  | NA | 31/07/24 | Closed |  |  |  | Pavithra | 2025-02-10 | 428 | >60 | July | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 90181725 | 2024-07-31 | Colleagues in Salford Quays affected by Wi-Fi connectivity issues | 31/07 - We need to ensure that after any power cut, all network associates are aware and able to carry out a standard set of best practice checks so that we can arrive at a problem statement and impact assessment in a timely manner. Create a SOP for NOC of best practice health checks and steps to follow. | Solution & Recovery | Rajesh Kumar Singarajan | 17/09: The necessary checks have been agreed and we can close this 05/09: There are 2 Key actions : [1. Device access guide, 2. Scope document ] 1. WPT to perform UAT on any major outages onsite 2. Suggestion to train WPT onsite engineers & supply the team with proper equipment [Corey Cummings & Arjun ] - Need to inform Ian & get his concurrence 02-09 - We have genric SOP for wifi issue check and modifications has been made with the right validation steps. 16/08 - SOP is being prepared - not yet finalised | Network | Tactical | NA | 17/09/24 | Closed | NA | NA | NA | Pavithra | 2025-02-10 | 428 | >60 | September | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 90181725 | 2024-07-31 | Colleagues in Salford Quays affected by Wi-Fi connectivity issues | 31/07 - We need to know why the access points went into a hung state after the power cut and why they did not fully recover after power was restored. Raise a log with vendor SCT and ask for known bugs or issues which would affect AP’s or controller after a power cut. | Root cause | Rajesh Kumar Singarajan | 14/02 - Based on the TAC logged with SCT, There is no bug with the existing firmware the device running. Additionally, since the device was rebooted, the logs could not be recovered to determine the root cause of the issue. Currently device is in healthy state. 29/01 - Another follow-up has been made with escalation - to get the Risk-ID raised 15/01 - Lokesh needs to check with Suganya C from his team for the Risk ID - awaiting further update 10/12: Kamal is having calls with vendor management team - raise a risk and close 14/11 - The conversation with M.Muzamil has not happened and will happen 15/11 17/09 - This controller is in production but SCT is saying it is not in support and we have to get it in support. Suganya to talk to Mustafa 07/09 - Reached TAC support & FCL25160049 is not under SCT support - Agree on the next action plan. 02/09 - Case has been raised with SCT to check and provide the recommendation from Cisco - we await for further update 16/08 - Rajesh to provided an update | Network |  | NA | 14/02/24 | Closed | NA | NA | NA | Pavithra | 2025-02-10 | 428 | >60 | February | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 90181725 | 2024-07-31 | Colleagues in Salford Quays affected by Wi-Fi connectivity issues | 31/07 - Note from the PIR discussion: The AP’s in Salford Quays are old and hence there is limited tech support. There is no plan to replace these until 2027. There is a LAN refresh project ongoing, but this is targeted at critical areas first and then head offices will be addressed. The risk of this has been highlighted many times. | Permanent Fix | Rajesh Kumar Singarajan | There is a LAN refresh project ongoing, but this is targeted at critical areas first and then head offices will be addressed. The risk of this has been highlighted many times. | Network |  | NA | 2024-08-08 | Closed |  |  |  | Pavithra | 2025-02-10 | 428 | >60 | August | 2024 | #VALUE!
GTS | Operations | 90181725 | 2024-07-31 | Colleagues in Salford Quays affected by Wi-Fi connectivity issues | 31/07 - We were under the impression that the 3rd floor was the only floor impacted where Colleague Services sit. Later as the investigation progressed, our engineers at site advised that the 4th floor was also impacted. At this stage we should have called our Finance service lead, but as we were deep in investigation this was overlooked, the call however was made but not in a timely fashion. | Business & IT Communication | MIM | As a learning, we now have a note added on our action plan to remind us to call the relevant business leads according to the impacted portfolios. | Operations |  | NA | 31/07/24 | Closed |  |  |  | Pavithra | 2025-02-10 | 428 | >60 | July | 2024 | #VALUE!
Foods | Foods Supply Chain | 90169094 | 2024-07-30 | FIND application was inaccessible for a brief period on 15/07 | Do we have any alerting inplace to identify the application inaccessibility? | Problem identification & Alerting | Shrikanth Shetty | 27/08 - FIND application has been added to a Weekly job which is responsible to check on the Certificate expiry data and will produce the relevant alerts as required. Thus the alerting for the FIND applications certificate is sorted. 30/07 : FIND is a SAAS product managed by Vendor TraceOne. Where alerts are configured for application performances however, this incident was only impacting Customer colleagues authentication and it was not an application issue thus no alerts were captured at the application end. However, the below action have been agreed to check on the feasibility on alerting for secret key expiry. | Foods product team | Tactical | NA | 27/08/24 | Closed | NA | NA | NA | Pavithra | 2025-02-10 | 429 | >60 | August | 2024 | #VALUE!
Foods | Foods Supply Chain | 90169094 | 2024-07-30 | FIND application was inaccessible for a brief period on 15/07 | Review an alerting mechanism to notify the product team (FIND) proactively on the Secret key expiry. Next expiry : 15th July 2026 | Problem avoidance | Shrikanth Shetty | 27/08 - FIND application has been added to the weekly job. 30/07 - Foods support has got an existing method where a weekly job is configured to proactively notify the applications owners on the secret keys expiry. FIND application will also be added to the list once the pre-requisites are completed. | Foods product team | Tactical | NA | 27/08/24 | Closed | NA | NA | NA | Pavithra | 2025-02-10 | 429 | >60 | August | 2024 | #VALUE!
GTS | Digital Workplace Services | 90169094 | 2024-07-30 | FIND application was inaccessible for a brief period on 15/07 | Explore a proactive mechanism within AD to notify on the expiring secret Keys in Oauth | Problem avoidance | Muthunagappan | 17/09 - Muthu had checked with the Cloud team and seems like it is an Azure Script that the cloud team use- which cannot be used for AD and secret keys. - however, we have sent the all the expirying secret Keys across all the portfolio's - and validations are performed by the respective portfolio. This should help in proactively renewing the keys. 02/09 - Muthu had checked with the Foods Job and identified that they are using a Logical App for getting notifications which is specificcally in scope of the product team. AD team doest not have access to that application. Final checks will be done with the Cloud team to check if we can get access to AD 30/07 - AD team to explore the above existing job to check on the feasibility to have it enabled for other critical applications in OAuth using secret keys. | Active directory Team | Strategic | NA | 17/09/24 | Closed | NA | NA | NA | Pavithra | 2025-02-10 | 429 | >60 | September | 2024 | #VALUE!
GTS | Digital Workplace Services | 90169094 | 2024-07-30 | FIND application was inaccessible for a brief period on 15/07 | Gather the list of other critical Secret Key’s that are due for expiry in AD. | Problem avoidance | MIM/Muthunagappan | The List has been shared to the respective service leads- If they report any expiry/issue - it will be addressed then and there | Active directory Team | Strategic | NA | 21/08/24 | Closed | NA | NA | NA | Pavithra | 2025-02-10 | 429 | >60 | August | 2024 | #VALUE!
Foods | Foods Supply Chain | 90169094 | 2024-07-30 | FIND application was inaccessible for a brief period on 15/07 | Feasibility to migrate the application from OAuth to SAML protocol (Which is advanced with new features on notifications) - | Permanent Fix | Shrikanth Shetty | 30/07 -Since OAuth is a legacy AD protocol using secret keys, a recommendation was made by the AD team to migrate their services to SAML (Security Assertion Markup Language) as advised by MS. Based on this discussion, the product team has raised a backlog with Trace One. Once the backlog request is accepted by them, it will be raised in our system (Jira). | Foods product team | Strategic | NA | 21/08/24 | Closed | NA | NA | NA | Pavithra | 2025-02-10 | 429 | >60 | August | 2024 | #VALUE!
Foods | Foods Supply Chain | 90169094 | 2024-07-30 | FIND application was inaccessible for a brief period on 15/07 | Ensure we have the right process agreed within the portfolio for decisions on MIM comms. | Issue handling/Management | Lisy Eucharista | - Process has been re-iterated and it has been agreed on the same - The issue was handled as a sev-2 as the suppliers were not impacted – But since the application was down for more than 3 hours the incident severity was increased during the weekly Operations call– A process will be agreed with the Service lead on MIM engagement for timely communications. | Foods product team | Tactical | NA | 21/08/24 | Closed | NA | NA | NA | Pavithra | 2025-02-10 | 429 | >60 | August | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 90144274 | 2024-07-26 | Wireless connectivity issues at Welham Green DC impacting site operations | Document the dependency with Locus Robots traffic to help triaging | Solution & Recovery | Mustafa, Muzamil | 26/07: The design document is already in place. | Network | Tactical | NA | 26/07/24 | Closed |  |  |  | Kavitha | 2025-02-10 | 433 | >60 | July | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 90144274 | 2024-07-26 | Wireless connectivity issues at Welham Green DC impacting site operations | Configure an alert to proactively notify if there any port flaps (0023/1023) which are connecting to the Locus switches | Problem identification & Alerting | Rajasekar Sankaranarayan | 26/07: Alerting has been enabled to notify if the interface port (0023/1023) is down for more than a 1 min | Network | Tactical | NA | 26/07/24 | Closed |  |  |  | Kavitha | 2025-02-10 | 433 | >60 | July | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 90144274 | 2024-07-26 | Wireless connectivity issues at Welham Green DC impacting site operations | Why was the DMZ switch and the WLCs rebooted during the issue? | Solution & Recovery | Mustafa, Muzamil | 26/07: The DC WLC firmware is working on a non- supported version with an existing bug. Based on the previous instance of the issue, we presumed that the issue was caused due to this existing bug and hence the WLCs and the switch were restarted. | Network | Tactical | NA | 26/07/24 | Closed |  |  |  | Kavitha | 2025-02-10 | 433 | >60 | July | 2024 | #VALUE!
C&H and Intl | C&H and Intl supply chain | 90144274 | 2024-07-26 | Wireless connectivity issues at Welham Green DC impacting site operations | Locus to review their alerting to proactively identify any issues on the Locus firewall and inform Welham operations. | Problem identification & Alerting | Stuart Dunn / Nandha | 03/09: The Locus had reuqested for processflow which has been shared with them. Considering that we don’t have any direct contract with Locus we cannot chase up for updates like other vendors. 16/08: Locus team assessment on alerting is ongoing 26/07: Locus team is working on the configuring the alerting | Locus Vendor | Tactical | NA | 2024-03-09 | Closed |  |  |  | Kavitha | 2025-02-10 | 433 | >60 | September | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 90144274 | 2024-07-26 | Wireless connectivity issues at Welham Green DC impacting site operations | Explore feasibility of isolating the issue with specific VLAN traffic to avoid the impact to the entire network | Problem avoidance | Mustafa, Muzamil | 17/09 - We did not the approval yet hence all the delays - we are still planning this. 03/09: The change has postponed, to be finalised next week 10/09 20/08: The change has been planned to deploy on 03/09 15/08: A change is being to be implemeted 17/08 26/07: Storm control to be enabled on the Juniper switches to limit to Multicast traffic Mustafa, Nandha and Locus to liaise to agree a change window and implement the changes | Network | Strategic | NA | 2024-07-10 | Closed |  |  |  | Kavitha | 2025-02-10 | 433 | >60 | October | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 90144274 | 2024-07-26 | Wireless connectivity issues at Welham Green DC impacting site operations | onyx Auth to optimise calls to openid-configuration and jwks.json | Problem avoidance | Mustafa, Muzamil | 26/07: Design review has been completed and agreed to enable RSTP and Strom Control. | Network | Strategic | NA | 26/07/24 | Closed |  |  |  | Kavitha | 2025-02-10 | 433 | >60 | July | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 90144274 | 2024-07-26 | Wireless connectivity issues at Welham Green DC impacting site operations | Investigate whether the change made on 20/07 to migrate the Palo Alto firewall to FortiGate in building 1 (hanging) had caused the issue | Root cause | Mustafa, Muzamil | 26/07: Customer network team analysed and confirmed the DIA firewall migration change was not the cause of this issue and we are confident to go ahead for the change in building 2 (boxed). | Network | Tactical | NA | 26/07/24 | Closed |  |  |  | Kavitha | 2025-02-10 | 433 | >60 | July | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 90144274 | 2024-07-26 | Wireless connectivity issues at Welham Green DC impacting site operations | Analyse and find any solutions that will proactively identify and break the network ‘Layer 2’ loop automatically without any intervention | Problem avoidance | Mustafa, Muzamil | 07/10: The change to enable RSTP has been implemented 17/09 - We did not the approval yet hence all the delays - we are still planning this. 03/09: The chnage has postponed, to be finalised next week 10/09 20/08: The change has been planned to deploy on 03/09 15/08: A change is being to be implemeted 17/08 26/07: Spanning tree (RSTP) will be enabled on the juniper switches to detect and prevent the layer 2 network loop. Mustafa, Nandha and Locus to liaise to agree a change window and implement the changes. | Network | Strategic | NA | 2024-07-10 | Closed |  |  |  | Kavitha | 2025-02-10 | 433 | >60 | October | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 90144274 | 2024-07-26 | Wireless connectivity issues at Welham Green DC impacting site operations | How did the port on backup switch up became active at 10:28? | Root cause | Locus/Network | 26/07We believe an interface reset might have caused the port on the backup switch to become active causing a network ‘layer 2’ loop resulting in multicast traffic, thus bringing the entire wireless network down at the site. All the available Locus firewall logs and Juniper switch logs were analysed and there is no conclusive evidence on how the port became active. | Network | Tactical | NA | 26/07/24 | Closed |  |  |  | Kavitha | 2025-02-10 | 433 | >60 | July | 2024 | #VALUE!
Customer Channels | Customer Engagement | 90147084 | 2024-07-26 | Customers were unable to apply new Sparks Pay & use account service | Will there be any other access token expiry across the Sparks Pay application? | Problem avoidance | Ramavtar Meena | 27/08: It has been confirmed by Priyabrata Sahu - No other application or flow will be affected by PAT expiry, other than this scenario. Once Sparks Pay moves completely from FESK to ONYX, this will no longer be an issue. 26/07: Further investigation required | Wallet Experience | Strategic | NA | 28/08/24 | Closed |  |  |  | Saloni | 2025-02-10 | 433 | >60 | August | 2024 | #VALUE!
Customer Channels | Customer Engagement | 90147084 | 2024-07-26 | Customers were unable to apply new Sparks Pay & use account service | Business impact was unclear for incident comms Product Manager advised on the services availability (Number of customers were calculated later in the week | Impact analysis | Sandy Flakelar | No further actions as the teams are now aware on how to calculate the impacted customer count to highlight in the incident comms | Wallet Experience | Tactical | NA | 26/07/24 | Closed |  |  |  | Saloni | 2025-02-10 | 433 | >60 | July | 2024 | #VALUE!
Customer Channels | Customer Engagement | 90147084 | 2024-07-26 | Customers were unable to apply new Sparks Pay & use account service | There was no remedy incident raised for this PD incident. Reviewing the integrations for Remedy from PagerDuty and align both the systems | Issue handling/Management | Tom Dobsonsmith | 26/07: This action is closed now (currently integrations are established in both PagerDuty & Remedy) | Wallet Experience | Tactical | NA | 26/07/24 | Closed |  |  |  | Saloni | 2025-02-10 | 433 | >60 | July | 2024 | #VALUE!
Customer Channels | Customer Engagement | 90147084 | 2024-07-26 | Customers were unable to apply new Sparks Pay & use account service | Was there any email for PAT expiry? Reviewing PAT expiry date process and setting up required notification process going forward? To update the expiry notification email to a group email address rather than individual | Problem avoidance | Rameshreddy Atula | 27/08: An alert has been set up for next year in Azure to a group email address (grp-walletexperience@mnscorp.onmicrosoft.com) However this issue shouldn’t recur because Sparks Pay should have completely moved to ONYX by then. 26/07: Need to understand email notification process before any token expiry. Discuss with Messaging & Cloud Ops team to validate email notification rules and set a forwarding action to team’s group email id | Wallet Experience | Tactical | NA | 28/08/24 | Closed |  |  |  | Saloni | 2025-02-10 | 433 | >60 | August | 2024 | #VALUE!
Customer Channels | Customer Engagement | 90147084 | 2024-07-26 | Customers were unable to apply new Sparks Pay & use account service | First PagerDuty alert raised at 02:35 Incident has been acknowledged immediately. How can we ensure the incident has been progressed with initial triage and findings? | Issue handling/Management | Ramavtar Meena | 27/08 This will be an ongoing process improvement for the team on ensuring accountability of PagerDuty alerts. There was also an issue with the primary and secondary alerts, which are now set up correctly to ensure the incident is triaged in time. 26/07: Impact of that PagerDuty alert and understand the services. Engineering process improvement for managing incident. | Wallet Experience | Tactical | NA | 28/08/24 | Closed |  |  |  | Saloni | 2025-02-10 | 433 | >60 | August | 2024 | #VALUE!
Foods | Foods Supply Chain | 90135982 | 2024-07-25 | Foods Final Orders (FFO) delayed due to delay in Relex nightly batch run | Relex files are received into FOAL by 3 AM. On 17th June, due to the combination of 30 minutes delay in sending the file to Relex and additional 45 minutes in Relex batch processing, we identified the Relex files were received into FOAL by 04:43. Relex to investigate the 30 minutes additional delay in sending the file to FOAL. | Root cause | James/Anshuman/Divya | 08/08 - The additional 30 mins delay was due to 2 other workflows changes for 'multi-tray'. 10 mins on 15.4.1 workflow and 20 mins on the 18.1 workflow. Backlog items already in place to address these additional delays (FOATR-23983). It was agreed in the call and action closed 06/08: Call has been rescheduled to 7th August. 25/07: Call has been scheduled on 6th August to identify the reason for the additional delay by Relex | Relex |  | NA | 2024-08-08 | Closed |  |  |  | Gokul | 2025-02-10 | 434 | >60 | August | 2024 | #VALUE!
Foods | Foods Supply Chain | 90135982 | 2024-07-25 | Foods Final Orders (FFO) delayed due to delay in Relex nightly batch run | Review the Service Design document to agree the KPI/SLA's for the outbound files from Relex to downstream. | Problem avoidance | Andrew/Matt White | 10/12: This has been completed. 21/11 - Service Design document is pending for approval due to multiple risks 12/11 - Lisy confirmed this is still under review 31/10 - Tamil updated that they are in review stage and 2 rounds of review are completed. Next review is planned by 6th 21/10 - Tamil updated that the document would be finalized by end of the month 11/10 - Have checked with the Service Design team on the status of the document. 01/10 - Matt advises that the final view of SLA's and SLO's will be available on 08/10 - the overnight batch 07/10 will be the first batch that will be run on the second environment so that we can split foods products into the two environments. Once the timings have been recorded and put into the document. Take an average of a few days. 23/09 - Service design team is working on the gaps, draft is ongoing and yet to move to final process. 12/09 - Priya confirmed that the Service Design team (Pratibha) is working on it. 10/09 - Have an internal call setup with Priya today to discuss on the status of the Service Design review. 21/08: Andrew updated that the Service Design will be reviewed by Service Management (Priyadharshini) and it is expected to done by 30th September. 08/08: Andrew is working with Matt 06/08: Call has been rescheduled to 7th August. 25/07: Call has been scheduled on 6th August to identify the reason for the additional delay by Relex | Foods product team | Tactical | NA | 2024-10-12 | Closed |  |  |  | Gokul | 2025-02-10 | 434 | >60 | December | 2024 | #VALUE!
Foods | Foods Supply Chain | 90135982 | 2024-07-25 | Foods Final Orders (FFO) delayed due to delay in Relex nightly batch run | There was no change reference for the MultiTray change at Relex. Review the Relex change management process | Issue handling/Management | Andrew/Matt White | 21/08 - Andrew confirmed that Relex are raising informative all changes that are being done in their environment. Hence, closing this action. 10/08 - Andrew discussed with Matt on this and he is OOO and will be back by 19/08. 06/08: Call has been rescheduled to 7th August. 25/07: We have agreed with Relex and Accenture FOAL that an information change will be raised for notification, however, this was not followed for this scenario, therefore, this still needs discussion to streamline the process with Matt and Rich. Call has been scheduled on 6th August to identify the reason for the additional delay by Relex | Foods product team |  | NA | 21/08/24 | Closed |  |  |  | Gokul | 2025-02-10 | 434 | >60 | August | 2024 | #VALUE!
Foods | Foods Supply Chain | 90135982 | 2024-07-25 | Foods Final Orders (FFO) delayed due to delay in Relex nightly batch run | NOTE: During the multi-tray change testing, Relex didn’t consider the Master Data file processing batch performance/ critical path. | Root cause | James L | Relex confirmed that the Master Data file processing also will be considered as critical and will be considered during the optimization for any future enhancements. Relex confirmed that from the next day, Master Data files were included as part of critical path and the performance was optimized | Relex |  | NA | 26/07/24 | Closed |  |  |  | Gokul | 2025-02-10 | 434 | >60 | July | 2024 | #VALUE!
Foods | Foods Supply Chain | 90135982 | 2024-07-25 | Foods Final Orders (FFO) delayed due to delay in Relex nightly batch run | The 28 Day order plan (DOP) was delayed by 3 hours, due to a configuration issue in the 28 DOP file received from Relex. Identify a permanent fix to address the configuration issue | Solution & Recovery | James L | Relex advised that the configuration issue was identified as part of the testing multi-tray change in the lower environment and a fix was developed. However, while implementing the multi-tray change, this fix was not deployed which resulted in the issue. Note: The fix was deployed in production as part of the recovery action Additional validations to be performed before the production deployment to address the defects identified during testing | Relex |  | NA | 26/07/24 | Closed |  |  |  | Gokul | 2025-02-10 | 434 | >60 | July | 2024 | #VALUE!
GTS | ETP-On premise services | 90149789 | 2024-07-23 | Control-M was unavailable for a brief period. | BMC found that services had been failed over to secondary, but the webserver services were not able to start and Control-M configuration manager was not able to login. BMC are asking us to check our network and OS layer as there could be a block somewhere | Root cause | Satya Malaiyandi | 24-08-2024 - Due to inadequate logs in the OS and the network layer - BMC couldt not further investigate on the root cause. Thus the RCA remains inconclusive. 16/08 - Control-M application failover from primary to secondary, failover has got failed due to web server not able to start in secondary server and port was used by another process. With help of BMC, we have started the web server manually in secondary server. It got failed due to port unavailable | System management team | Tactical | NA | 24/08/24 | Closed | NA | NA | NA | Pavithra | 2025-02-10 | 436 | >60 | August | 2024 | #VALUE!
GTS | ETP-On premise services | 90149789 | 2024-07-23 | Control-M was unavailable for a brief period. | When we tried falling back to primary using the command line, this failed due to a login failure on the DB – BMC to advise why. | Solution & Recovery | Satya Malaiyandi | 24/08 -Due to inadequate logs in the OS and the network layer - BMC couldt not further investigate on the root cause. 16/08 - Control-M application failover from primary to secondary, failover has got failed due to web server not able to start in secondary server and port was used by another process. With help of BMC, we have started the web server manually in secondary server. It got failed due to port unavailable | System management team | Tactical | NA | 24/08/24 | Closed | NA | NA | NA | Pavithra | 2025-02-10 | 436 | >60 | August | 2024 | #VALUE!
GTS | Operations | 90149789 | 2024-07-23 | Control-M was unavailable for a brief period. | Why was the last failover 3 years ago in Production, stakeholders in the PIR advised that they couldn’t approval for a test failover outage. Trace back when the outage was requested and why appropriate responses were not received. Evaluate if the change approval process is fit for purpose to secure planned outages. Priya to instigate and arrange a discussion | Problem avoidance | Priyadharshini Somasundaram | 10/10 - Discusssions has been made with the relevant product team and points has been noted by the change management team | Change Management | Tactical | NA | 2024-10-10 | Closed | NA | NA | NA | Pavithra | 2025-02-10 | 436 | >60 | October | 2024 | #VALUE!
GTS | ETP-On premise services | 90149789 | 2024-07-23 | Control-M was unavailable for a brief period. | We need to test the failover process in non-prod but with the same patch levels as in Prod. Arrange a test failover in in-prod but with the secondary patched. | Problem avoidance | Satya/Chandra | 16/08 - The test failover was planned via CRQ000000206869 - however proper approvals were not secured - We are not planning to do this before this peak as advised by the C&H team. Thus this action will now be closed and will be further tracked via Service continuity team | System management team | Tactical | NA | 24/08/24 | Closed | NA | NA | NA | Pavithra | 2025-02-10 | 436 | >60 | August | 2024 | #VALUE!
GTS | ETP-On premise services | 90149789 | 2024-07-23 | Control-M Unavailable | Review future patching processes and ensure that the process is tested in non-prod with the same levels of patching as in Prod. | Issue handling/Management | All | NA/07: Mprogress | All | Tactical | NA | 23/07/24 | Closed | NA | NA | NA | Pavithra | 2025-02-10 | 436 | >60 | July | 2024 | #VALUE!
GTS | Operations | 90140291 | 2024-07-23 | Global issue at CrowdStrike impacting multiple services hosted on Microsoft platforms | MIM team to review the loop template as it needs an area where we can prioritise the recovery of applications. | Issue handling/Management | Rehan Siddiqui | Priority of application recovery added to template | Service Management | Tactical | NA | 2024-01-08 | Closed |  |  |  | Rehan | 2025-02-10 | 436 | >60 | August | 2024 | #VALUE!
GTS | Digital Workplace Services | 90140291 | 2024-07-23 | Global issue at CrowdStrike impacting multiple services hosted on Microsoft platforms | Even though this wasn’t caused by an in-house update, the PIR attendees discussed our own wide scale release of software, there should be a gradual roll out strategy, so that any issues do not cause estate wide impact. | Problem avoidance | Darren Gibson | This is to be covered in overall strategy of operational and is only to be recorded in the PIR. | Leadership team |  | NA | 23/07/24 | Closed |  |  |  | Rehan | 2025-02-10 | 436 | >60 | July | 2024 | #VALUE!
C&H and Intl | C&H and Intl supply chain | 90140291 | 2024-07-23 | Global issue at CrowdStrike impacting multiple services hosted on Microsoft platforms | Editrack – what is their business continuity strategy and what actions do they have in place? Could they have mitigated impact sooner? | Supplier and support involvement | Naga Shivaswamy | 13/08: BC plan received and stored 08/08: Rehan spoke to Naga who advised that many people are on holiday. He has contacted Editrack but is awaiting a response. | Service Lead | Strategic | NA | 13/08/24 | Closed |  |  |  | Rehan | 2025-02-10 | 436 | >60 | August | 2024 | #VALUE!
GTS | Digital Workplace Services | 90140291 | 2024-07-23 | Global issue at CrowdStrike impacting multiple services hosted on Microsoft platforms | Understand the TCS central learnings from this – what actions are they taking to prevent similar large scale issues in the future. | Issue handling/Management | Darren/Seema Nair | 25/09: This has now been sent to Darren Gobson 23/09: Followed up Seema via Teams and she is sending the pack to Darren today 02/09: Followed up with Seema by mail 08/08: Rehan has emailed both Seema and Darren for reassuarnce that they have connected and that the TCS central learnings from this global issue are now being collated. Seema replied and advised she was not tracking this action yet, she will share TCS central learnings from the issue by mid next week ( 14th). | Leadership team | Tactical | NA | 25/09/24 | Closed |  |  |  | Rehan | 2025-02-10 | 436 | >60 | September | 2024 | #VALUE!
GTS | Operations | 90140291 | 2024-07-23 | Global issue at CrowdStrike impacting multiple services hosted on Microsoft platforms | We were unclear how Microsoft were impacted. There were comments that Teams may have been impacted. What is our strategy for running a MIM call if Teams is impacted? | Issue handling/Management | Rehan Siddiqui | 10/04: Ian is now getting a quote based on our bespoke requirements 26/03: Decision from Andy requested 05/02: proposal sent to Andy Neilson 29/01: Rehan to propose to Andy Neilson 05/11: Update from Ian: We have reviewed the major web conferencing platforms, features, pricing and licensing etc. The best fit for the stated requirements appears to be Webex. This platform would provide a completely seperate web conferencing platform from Microsoft Teams with dial-in capability and a dial-out add-on license available, both of which support India numbers and the other countries stated. Webex business £162 per host per year. Meetings up to 200 participants or Webex starter £114 per host per year - 150 participants. Both include local toll dial-in for UK, Ireland & India. Dial-out add-on available for £357 per host license per year (supports UK, Ireland and India). Note: max meeting duration 24 hours, prices quoted here are MRSP for annual billing (monthly pricing available). Zoom and Google Meet both have some limitations around dial-in/dial-out support for India so are not recommended above the Webex solution. Discuss with Sathish/Dinesh 14/10: Rehan has chansed up Saran and Ian for a reaslistic update but also copying in Stephen Bolton 02/09: Ian Hurley is out of office, further follows up to be made once Ian is back. 08/08: There is an ongoing discussion between Ian Hurley-Love (Tech Solutions Lead) Saran, Dinesh, Rehan and Sathish on a backup MIM communication solution in the case that Teams is unavailable. We have had our first meeting and await Ian to come back with options. | Service Management | Strategic | 17/04/25 |  | Open |  |  |  | Rehan | 2025-02-10 | 436 | >60 | January | 1900 | 90+ Days
GTS | Operations | 90140291 | 2024-07-23 | Global issue at CrowdStrike impacting multiple services hosted on Microsoft platforms | Send cyber security incident process to Darren and Steve Cottrell. | Issue handling/Management | Rehan Siddiqui | 01/08: Process sent | Service Management | Tactical | NA | 2024-01-08 | Closed |  |  |  | Rehan | 2025-02-10 | 436 | >60 | August | 2024 | #VALUE!
GTS | Operations | 90137938 | 2024-07-22 | Multiple servers which are running as primary in Swindon moved to Stockley | We have had the issue of the link going down before but we did not have significant impact as services were mainly running from SP not SW. before the SP Exit programme. If the change was better appreciated and understood by other infra teams, they would have advised to postpone the change. Platform level changes should be reviewed with network and SME’s from other infra teams and this should be on the checklist prior to change approval. | Problem avoidance | Priyadharshini Somasundaram and Infra teams | Update 23/09: It has been agreed that for these type of changes the IODM process will be followed where cross infra teams have to review and approve the change. | Change Management / Infra Teams |  | NA | 23/09/24 | Closed |  |  |  | Rehan | 2025-02-10 | 437 | >60 | September | 2024 | #VALUE!
GTS | ETP-On premise services | 90137938 | 2024-07-22 | Multiple servers which are running as primary in Swindon moved to Stockley | The failover of the servers from Swindon to Stockley occurred very quickly after the reboot of the Nexus 7k. There is no time setting on the VSAN or witness server that we can set to allow the system to recover from any disconnect prior to failing over. We have raised this with Broadcom (previously known as VMware). Do we want the failover to be automated, semi-automated or manual to give us more control? – consult with Broadcom. | Problem avoidance | Dharmaraj Balasubramanian | 26/7: Broadcom confirmed that there is no delay timer on the vSAN or the Witness to delay the DR in case of a failure scenario as it polls for heartbeat every second. This DR situation is always automated by design. We will have to focus on the 3rd action with NOC team to implement host based routing for the vSAN in order to avoid this issue in future. Agreed to close and talk to NOC. | Wintel | Tactical | NA | 26/07/24 | Closed |  |  |  | Rehan | 2025-02-10 | 437 | >60 | July | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 90137938 | 2024-07-22 | Multiple servers which are running as primary in Swindon moved to Stockley | The VSAN VLAN sits in Stockley Park and this is the only route. If the Witness server loses visibility it will instigate a failover. We therefore need to create a resilient route. | Problem avoidance | Rajeshkumar Singarajan | 05/09: Discussed & agreed on the following, Option 1 – No design change.. instead. - Setup a process to periodically check the status of the N7K Supervisors flash drive and where required run the flash recovery tool. This will prevent a recurrence of the need to reload the N7K to recover the flash drives. - In the event of future maintenance windows required on the Nexus 7K’s, Dharma will disable VMware HA. This will prevent the automatic failover triggered by the witness. - Note 1.. the Witness/VSAN environment will become redundant as part of the SP exit. The new Gen11 platform will use iSCSI protocol and not VSAN. - Note 2.. This type of failure has only occurred twice in the last 9 years. 08/08: Redesigning for the witness server ongoing | Network |  | NA | 2024-05-09 | Closed |  |  |  | Rehan | 2025-02-10 | 437 | >60 | September | 2024 | #VALUE!
Foods | Foods Supply Chain | 90137938 | 2024-07-22 | Multiple servers which are running as primary in Swindon moved to Stockley | The impact to Food batches and also to Milton Keynes Food DC was not fully appreciated - Andrew Goslin has already spoken with the Food team to encourage them to call out impacts and be more proactive. | Problem identification & Alerting | Andrew Goslin | This action was placed as a note | Foods product team |  | NA | 2024-08-08 | Closed |  |  |  | Rehan | 2025-02-10 | 437 | >60 | August | 2024 | #VALUE!
GTS | ETP-On premise services | 90137938 | 2024-07-22 | Multiple servers which are running as primary in Swindon moved to Stockley | During the incident call the food team reported that the days Food sales had not reached Quantum because the FSSD file had not reached Quantum. Ascertain if this was caused by this incident. | Root cause | Elizabeth Golder | 23/09: Raj advised that 23/09: Raj advised that during the central network issue, the AIX server(Quantum ) was also impacted and the MQFTE agent running in the Quantum server went down and later it was started. This agent down time affected the file transfer for FFO processing. 02/09: Followied up with EG who has asked Jafar to provide updates 01/08: Rehan spoke to Elizabeth and she needs to follow up | Service Lead - GTS | tactical | NA | 23/09/24 | Closed |  |  |  | Rehan | 2025-02-10 | 437 | >60 | September | 2024 | #VALUE!
GTS | ETP-On premise services | 90137938 | 2024-07-22 | Multiple servers which are running as primary in Swindon moved to Stockley | CSSM – is on stretched cluster. It has not been migrated to Swindon. On the day of the issue some CSSM servers failed over from SW to SP and needed to be restarted in the correct order. The PIR discussion noted that some CSSM servers don’t have rules in place to keep them in Swindon/Stockley so they move around according to issues encountered. We are migrating CSSM to SW on the weekend and with this the affinity rules will be added to keep them where they are. | Problem avoidance | Elizabeth Golder | 01/08: Completed on the weekend 28/07 | Service Lead - GTS | Tactical | NA | 28/07/24 | Closed |  |  |  | Rehan | 2025-02-10 | 437 | >60 | July | 2024 | #VALUE!
GTS | ETP-On premise services | 90137938 | 2024-07-22 | Multiple servers which are running as primary in Swindon moved to Stockley | Connectivity between POS trade servers and SQL database server was also impacted during the incident – Bala/Siva in POS to confirm if and how they were impacted, and if so pass on the information to Elizabeth Golder, | Root cause | Bala/Siva/Elizabeth Golder | 01/10: Rehan has spoken with Pappusamy, Sivasubrmani and he is correct in stating that many services not just MQ running in SP were affected and its not going to be possible to get the cause for this. 02/09: Followied up with EG who has asked Jafar to provide updates | Service Lead - GTS |  | NA | 2024-01-10 | Closed |  |  |  | Rehan | 2025-02-10 | 437 | >60 | October | 2024 | #VALUE!
GTS | ETP-On premise services | 90137938 | 2024-07-22 | Multiple servers which are running as primary in Swindon moved to Stockley | SAP PO was impacted during the incident – Why? In the PIR the cause for this was stated as the routing for SAO PO to Swindon didn’t fully commit when it was migrated because of the Nexus 7k disc issues and when the 7k was rebooted for the change the routing for PO reverted to Stockley. This has now been remedied. | Problem avoidance | Elizabeth Golder | NA/07: Serversprogress | Service Lead - GTS |  | NA | 2024-01-10 | Closed |  |  |  | Rehan | 2025-02-10 | 437 | >60 | October | 2024 | #VALUE!
GTS | ETP-On premise services | 90137938 | 2024-07-22 | Multiple servers which are running as primary in Swindon moved to Stockley | During the incident the Brands Thorncliffe DC MQ server was impacted. At the time of the issue the server was pointing to SP but we still had impact. The MQ cluster was restarted and a Mule restart was done to restore service but we still need to find out why this incident caused impact to this service. | Root cause | Elizabeth Golder/ Sathish Selvapillai | 01/10: Rehan has spoken with Pappusamy, Sivasubrmani and he is correct in stating that many services not just MQ running in SP were affected and its not going to be possible to get the cause for this. 02/09: Followied up with EG who has asked Jafar to provide updates 01/08: Rehan spoke to Elizabeth and she needs to follow up | Unix/Service Lead - GTS |  | NA | 2024-01-10 | Closed |  |  |  | Rehan | 2025-02-10 | 437 | >60 | October | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 90109761 | 2024-07-18 | Intermittent CPU spikes in Stockley Park network firewall | The CPU spikes only last for a few seconds and not enough for Solar Winds to detect – NOC team to look for alternative alerting options. | Problem identification & Alerting | Kamal | 07/09: Network team will now receive traps in FortiGate and alerts has been enabled via Email 07/08 - Action has been assigned to network team members as advised by kamal | Network | Tactical | NA | 2024-07-09 | Closed |  |  |  | Rehan | 2025-02-10 | 441 | >60 | September | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 90109761 | 2024-07-18 | Intermittent CPU spikes in Stockley Park network firewall | Fortigate to reassure Customer about version 7.4.4 which the custom build will sit on with examples of previous deployments of 7.4.4 and what level of testing FortiGate have done internally for this version. | Problem avoidance | Paul (Fortinet)/Adam Davies | 17/09 The custom build had been deployed into prod for SW and SP. | Fortinet firewall | Tactical | NA | 17/09/24 | Closed |  |  |  | Rehan | 2025-02-10 | 441 | >60 | September | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 90109761 | 2024-07-18 | Intermittent CPU spikes in Stockley Park network firewall | Create a full plan to mitigate risk when deploying 7.4.4 and the custom build as much as possible – as well as action two Adam Davies and Kamal (NOC) to ascertain what testing is feasible for Customer to do in house in the absence of a like for like environment. There is no 2600F in test. | Problem avoidance | Adam Davies/ Kamal | 17/09 The custom build had been deployed into prod for SW and SP. 05/09: The OS upgrade activity has been planned for Swindon on 11th Sep & SP on 17th Sep.Teams need to ensure all lessons learnt are applied before deploying the change. 08/08 – Planning and testing review to continue. We are targeting 30/08 for upgrade | Network | Tactical | NA | 17/09/24 | Closed |  |  |  | Rehan | 2025-02-10 | 441 | >60 | September | 2024 | #VALUE!
C&H and Intl | C&H and Intl supply chain | 90123458 | 2024-07-17 | Castle Donington customer orders issue due to a Job failure | Do we have the right alerting in place? | Problem identification & Alerting | Murali Srinivasan/Kunal | 30/07 - Proper alerting has been set-up and PCM is advised not to suppress the alerts if they are of different intervals. 17/07 : We have two alerting mechanisms for this scenario. Control-M job alert :- We have relevant sev-1 alerts in place however, as there was a job failure in the morning due to a different reason, the other related alerts were suppressed within the parent ticket. A request has been raised to PCM and WMS to backtrack the alerts triggered during the incident and actions will be agreed for effective alert handling. -In-progress Site flagging the issue: The issue was observed at the site as well since 04:00 – however they raised it as a sev4 and once the impact was magnified the severity was increased. Site has now been informed to raised an immediate Sev1 when they see an impact to the must go orders/any other critical operations at site - Completed | WMS devops | Tactical | NA | 30/07/24 | Closed |  |  |  | Pavithra | 2025-02-10 | 442 | >60 | July | 2024 | #VALUE!
C&H and Intl | C&H and Intl supply chain | 90123458 | 2024-07-17 | Castle Donington customer orders issue due to a Job failure | Ensure we have the SOP updated with the new scenario. | Solution & Recovery | Murali Srinivasan/Kunal | This is the first instance of exception errors for these control-M jobs, thus the error details and the recovery steps have been captured in the SOP for future references. | WMS | Tactical | NA | 2024-11-07 | Closed |  |  |  | Pavithra | 2025-02-10 | 442 | >60 | July | 2024 | #VALUE!
C&H and Intl | C&H and Intl supply chain | 90123458 | 2024-07-17 | Castle Donington customer orders issue due to a Job failure | What is the Permanent fix to address the order allocation job failure? | Permanent fix | Rajasekar Ravichandran/ Bhupinder Kang | 08/08 - Both of these fixes are implemented into PROD and validations are positive. 17/07 -There are two permanent fixes planned to be deployed: Fix1 – Code change will be done on the control-M job to handle the exception scenario (parked and offline) ETA: 18/07 Fix2: To address the generic scenario of the same order line being allocated by different zones (manual/Automation). ETA : Next week. | WMS devops | Tactical | NA | 2024-08-08 | Closed |  |  |  | Pavithra | 2025-02-10 | 442 | >60 | August | 2024 | #VALUE!
Foods | Foods Supply Chain | 90126150 | 2024-07-16 | Some suppliers have received higher than expected volumes for certain Food product lines | Provide a time line of the work done from 05:50 (CXM job failure) to 07:23 | Issue handling/Management | Promoth/Matt/Lisy | 23/07 Andrew advised given the current work load with more critica activities it would not be feasile to get this timeline nor will it add value to the investigation | Service lead | Tactical | NA | 23/07/24 | Closed |  |  |  | Rehan | 2025-02-10 | 443 | >60 | July | 2024 | #VALUE!
Foods | Foods Supply Chain | 90126150 | 2024-07-16 | Some suppliers have received higher than expected volumes for certain Food product lines | Build a process to systemically spot a large forecast and then alert. Agree tolerances in forecasts which should trigger the use of previous forecasts. This process should be to include holding PO’s to suppliers if there is an issue. Provide a backlog for this. Andrew and Matt | Problem identification & Alerting | Andrew and Matt | 12/09 For demand forecasts, RDC allocations, NDC allocations and the suuplier orders - checks are carried out with the volumes and how they compare to yesterday and the same day last week - the analysis is done and any issues are flagged. This will be automated in the long term - Closed. Tolerances have been agreed as part of the analysis. The batch will be stopped if there is an issue. Under the review of the Relex/FOAL service design - the following topics are being reviewed IM process, SLA, RACI, serveral meetings will be held over the next few days with a gal to close by 30/09 Update 27/08 - No update - Rehan to email Matt. Update 05/08 - Matt advised that alerts have been added at each step of the batch to include volume. Support team track and analyse this every day. Matt to speak with Promoth about the proces that happens once an alert is generated. Previous update: This needs to be carried out via a backlog - Andrew has a working group 23/07 and will ask for a backlog ID | Foods product team | Tactical | NA | 2024-12-09 | Closed |  |  |  | Rehan | 2025-02-10 | 443 | >60 | September | 2024 | #VALUE!
Foods | Foods Supply Chain | 90126150 | 2024-07-16 | Some suppliers have received higher than expected volumes for certain Food product lines | We could have cut to the systemically created contingency allocations in a timely manner – review the process of the scenarios and tolerance to deploy contingency. | Solution & Recovery | Matt/Chris John | 12/09 This process has now been agreed and was successfully used in the incident on 11/09. Update 10/09: This will also be reviewed with the Relex/FOAL service design due to completed by 30/09 Update 05/08: The guidance we have agreed is that if there is any impact to allocations we cut to contingency first. We can revert easily to the calculated allocations as confirmed by Promoth. However we need a back log to systemically revert to contingency for NDC allocations 23/07: Andrew will remind Chris of the action | Foods product team | Tactical | NA | 2024-12-09 | Closed |  |  |  | Rehan | 2025-02-10 | 443 | >60 | September | 2024 | #VALUE!
Foods | Foods Supply Chain | 90126150 | 2024-07-16 | Some suppliers have received higher than expected volumes for certain Food product lines | Confirm with Dan Maddox the process around mitigation steps if we think that supplier orders are impacted by an incident. | Solution & Recovery | Lisy/Dan/Matt | 21/08: Discussed with Dan on mitigation of PO delays / issues would reverting to previous day 28 day order plan for the supplier planning perspective 08/08: This action is to do with at point suppliers need to revert to the 28 day order plan if there is an issue with supplier orders. Lisy to have a further call with Dan to agree this | Foods product team | Tactical | NA | 21/08/24 | Closed |  |  |  | Rehan | 2025-02-10 | 443 | >60 | August | 2024 | #VALUE!
Foods | Foods Supply Chain | 90126150 | 2024-07-16 | Some suppliers have received higher than expected volumes for certain Food product lines | There are multiple UPC combinations making impact assessement difficult. Create a summary of orders/allocations during key steps of the batch so that reconciliation and matching is easier, enabling us to decide whether we need to use contingency in a timelier manner – Relex scrum team – back log to be raised. | Solution & Recovery | Matt/Callum Staff | 05/08: It has been agreed that in a similar scenario, once contingency has been applied, the FOA super users can be called out to help find where the anomalies are. 23/07: Andrew will remind Matt of the action | Foods product team | Tactical | NA | 2024-05-08 | closed |  |  |  | Rehan | 2025-02-10 | 443 | >60 | August | 2024 | #VALUE!
Foods | Foods Supply Chain | 90126150 | 2024-07-16 | Some suppliers have received higher than expected volumes for certain Food product lines | Create a structured checklist of investigation protocol to ensure the key flows are safe and working for every foods issue. Retail impact, stores impact, DC impact. | Issue handling/Management | Matt/Andrew/Lisy and Promoth to review. | Update 05/08: As we have added checks at each step, this has made investigation easier as the root cause would become easier to spot. 23/07: To be initiated when Matt is back from holiday - Andrew aware | Foods product team | Tactical | NA | 2024-05-08 | closed |  |  |  | Rehan | 2025-02-10 | 443 | >60 | August | 2024 | #VALUE!
Foods | Foods Supply Chain | 90126150 | 2024-07-16 | Some suppliers have received higher than expected volumes for certain Food product lines | Review recovery options for ambient (NDC allocations) compared to chilled. | Solution & Recovery | Tamil | Update 01/10: Relex action to include the Manual order into GIST contingency file has been implemented in RELEX on 4th Sep 2024. JIRA ticket id TR-24487 Update 12/09: There is a manual activity at the moment. Tamil is working with the PO to automate this. Update 10/09: This will also be reviewed with the Relex/FOAL service design due to completed by 30/09 Update 27/08: Tamil advised they are still working on the service document and will complete by 30/09 Update 05/08: Tamil is creating a backlog to define the steps of recovering ambient and to place these in the service document. | Foods product team | Tactical | NA | 2024-01-10 | Closed |  |  |  | Rehan | 2025-02-10 | 443 | >60 | October | 2024 | #VALUE!
Foods | Foods Supply Chain | 90126150 | 2024-07-16 | Some suppliers have received higher than expected volumes for certain Food product lines | Checklist should have key SME’s to include key business | Business & IT Communication | Dan and Chris John | This has been sent | Head of supply chain | Strategic | NA | 16/07/24 | Closed |  |  |  | Rehan | 2025-02-10 | 443 | >60 | July | 2024 | #VALUE!
Foods | Foods Supply Chain | 90126150 | 2024-07-16 | Some suppliers have received higher than expected volumes for certain Food product lines | Create initial comms to business and suppliers Dan Maddox/Lisy. Once agreed place into a central area where the service lead can quickly access. | Business & IT Communication | Dan Maddox/Lisy | 08/08: Dan has provided a template to Lisy for a comms to be placed on the OFP banner so that suppliers know there is an issue. Update 05/08 - This needs to be started Follow up meeting set up for 05/08 | Service lead | Tactical | NA | 2024-08-08 | Closed |  |  |  | Rehan | 2025-02-10 | 443 | >60 | August | 2024 | #VALUE!
Foods | Foods Supply Chain | 90126150 | 2024-07-16 | Some suppliers have received higher than expected volumes for certain Food product lines | A request has been made by key business sme’s to be included on MIM comms, MIM calls and D&T channels. This conversations will now be taken forward | Business & IT Communication | Andrew Goslin/Matt White | This will be decided upon on a case by case basis depending on the impact and problem scenario | Foods product team | Tactical | NA | 2024-08-08 | Closed |  |  |  | Rehan | 2025-02-10 | 443 | >60 | August | 2024 | #VALUE!
Foods | Foods Supply Chain | 90126150 | 2024-07-16 | Some suppliers have received higher than expected volumes for certain Food product lines | Review the business comms list for foods | Business & IT Communication | Dan/Lisy | 08/08: Lisy confirmed that this has been done and all the latest chilled, ambient and other key contacts have been added from the business. | Service lead | Tactical | NA | 2024-08-08 | Closed |  |  |  | Rehan | 2025-02-10 | 443 | >60 | August | 2024 | #VALUE!
Foods | Foods Supply Chain | 90126150 | 2024-07-16 | Some suppliers have received higher than expected volumes for certain Food product lines | Changes have been proposed that will safeguard the screen and this with the product teams (led by Magda) – she will look at the dev effort required and progress as relevant. | Problem avoidance | Callum Staff | 15/10: These are in our Data Validation epic, but we are not picking up this epic this quarter. Here are the links for reference: https://confluence.marksandspencer.app/display/FOATR/Peak+2025+TBC+%7C+Pre-Batch+Data+Validations https://jira.marksandspencer.app/browse/FOATR-21976 It is unlikely we would tackle these epics in Q4, since we need to do epics that allow us to decommission Quantum. From Q1 25 we will probably look at additional epics, this particular topic we might tackle before Peak 2025 FYI Follow up meet14/10: Rehan spoke with Magda today and she is checking with her team regarding progress on this. | Foods product team | Strategic | NA | 15/10/24 | Closed |  |  |  | Rehan | 2025-02-10 | 443 | >60 | October | 2024 | #VALUE!
Customer Channels | Selling Experience | 122969603 | 2024-07-16 | Intermittent issues with Digital cafés | Review the feasibility of having a monitoring and alerting tool to identify the issue and its impact as part of the post resilient program | Problem identification & Alerting | Charle Webster | 18/07: We have been advised that it is feasible to configure an alert based on heart beat checks – needs Counter Solutions input. Post Resilient is in pilot phase, so this is a long term action and is anticipated to complete by next year. Will be tracked under - RDC-262 | Digitial café | Tactical | NA | 18/07/24 | Closed |  | RDC-262 |  | Kavitha | 2025-02-10 | 443 | >60 | July | 2024 | #VALUE!
Customer Channels | Selling Experience | 122969603 | 2024-07-16 | Intermittent issues with Digital cafés | Engage DN in all Major incident management calls going forward considering DN is maintaining the relationship with CS | Supplier and support involvement | Laura Whittle | 16/07: This is just a note to all action. It has been agreed on the call the Laura will engage DN for all the major incidents going forward | Service lead | Tactical | NA | 16/07/24 | Closed |  |  |  | Kavitha | 2025-02-10 | 443 | >60 | July | 2024 | #VALUE!
Customer Channels | Selling Experience | 122969603 | 2024-07-16 | Intermittent issues with Digital cafés | Review the feasibility of handling the error scenario internally within the system instead of taking down the Kiosk. | Problem avoidance | Tony Burke | 17/10: A date for the release of the code for Customer has not been set. This is because CS have been focused upon Resilience.Resilience is going into pilot on 4th Nov (Colchester) and from this point we will have access to the error logs. It will also give the the ability to remotely log onto kiosks and also we will have dynatrace implemented to collect data to feed into reports etc 07/08: Tony has confirmed that the action will picked up in Counter solutions current sprint, which has started on Aug 7, The sprint period is 4 weeks. Further updates to follow on the completion of the sprint 18/07: RDC-370 has been created to track the investigations on error handling. 16/07: To be discussed with Counter solution on 16/07 call | Digitial café | Strategic | NA | 21/11/24 | Closed |  | RDC-370 |  | Kavitha | 2025-02-10 | 443 | >60 | November | 2024 | #VALUE!
Customer Channels | Selling Experience | 122969603 | 2024-07-16 | Intermittent issues with Digital cafés | Review the feasibility of configuring an alert for kiosk crash so that issues can be spotted in a timely manner. | Problem identification & Alerting | Tony Burke | 07/10: Though Counter solution continue to work on the configuring an alert. The head of engineering team has created reports which we can now access and monitor kiosks and when they go offline. This is integrated in new relic as well 07/08: Tony has confrimed that the action will picked up in Counter solutions current sprint which has started on Aug 7, the sprint period is 4 weeks. Further updates to follow on the completion of the sprint 16/07: To be discussed with Counter solution on 16/07 call | Digitial café | Tactical | NA | 2024-07-10 | Closed |  |  |  | Kavitha | 2025-02-10 | 443 | >60 | October | 2024 | #VALUE!
Customer Channels | Selling Experience | 122969603 | 2024-07-16 | Intermittent issues with Digital cafés | Implement a change control process to deploy business changes in Prod. | Problem avoidance | Paul Dasan-Cutting | 16/09: A process has been agreed that all the configuration changes should be implemented with the CR in th prod and its being familiarised with the team 13/08: The draft version of the change process has been designed, it needs to formalised and its tracked as part of the operational stability backlog. This is expected to closed by end of the quarter 16/07: Paul to discuss and internally finalise the change control approach | Digitial café | Strategic | NA | 16/09/24 | Closed |  |  |  | Kavitha | 2025-02-10 | 443 | >60 | September | 2024 | #VALUE!
Customer Channels | Selling Experience | 122969603 | 2024-07-16 | Intermittent issues with Digital cafés | Review all the configuration documents so that the end-to-end configuration is understood to prevent this issue from occurring | Problem avoidance | Paul Dasan-Cutting | 07/10: The end-to-end config has been documented 13/08: Team is still working on this actions and its part of their operational stabaility back log as well. Its expected to complete a that end of this Quarter 16/07: To be discussed with Counter solution on 16/07 call | Digitial café | Strategic | NA | 2024-07-10 | Closed |  |  |  | Kavitha | 2025-02-10 | 443 | >60 | October | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 90121906 | 2024-07-15 | Store colleagues unable to log in to Honeywells | Architectural diagram to track the traffic flow across the store device for effective identification of the issue and facilitate timely resolution | Solution & Recovery | Pritam Mukherjee/ Shabir Mookhtihar | 03/09:A page has been creatd in the MIRO board: https://miro.com/app/board/uXjVKxNF0M8=/?share_link_id=254349005889 to store the network flow diagram. this has been reviewed to refer to in future incidents - 15/07: There is an existing document highlighting the network traffic flow and identify ways to improve the usage of the flow in future incidents. Test the effectiveness of the diagram. | Store Infra/ Honeywells | Strategic | NA | 2024-03-09 | Closed |  |  |  | Saloni | 2025-02-10 | 444 | >60 | September | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 90121906 | 2024-07-15 | Store colleagues unable to log in to Honeywells | Improve the alerting mechanism to identify issues with individual stores related to local stores proxy server What caused the issue with the stores with local store proxy server? VLAN config change issue | Problem identification & Alerting | Pritam Mukherjee | 19/09: A report has been built to identify issues with stores on local proxy servers. This will help in identifying the impacted stores and resolve the issue in a timely manner 15/07: Review the standard config management process across the store estate to avoid issues | Store Infra | Strategic | NA | 19/09/24 | Closed |  |  |  | Saloni | 2025-02-10 | 444 | >60 | September | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 90121906 | 2024-07-15 | Store colleagues unable to log in to Honeywells | Availability of right SMEs on the MIM call to facilitate root cause triage and resolution. | Supplier and support involvement | Valliammai Ramasamy | 19/09: The oncall rota for Honeywell team is now in place. 15/07: It has been agreed to enable on call rota for Honeywell team. In addition, we have agreed with Stores Infrastructure team to ensure all engineers are equipped with relevant knowledge to facilitate incident resolution especially during non-business engineers. | Service lead | Tactical | NA | 19/09/24 | Closed |  |  |  | Saloni | 2025-02-10 | 444 | >60 | September | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 90121906 | 2024-07-15 | Store colleagues unable to log in to Honeywells | Review the store comms process to ensure appropriate information is cascaded to the store colleagues. | Business & IT Communication | Valliammai Ramasamy | 19/09: We have enabled a report to know which store is running on local and which is running in central proxy to ensure our comms are effective and intended to the impacted stores only for next instance 15/07: Store comms was sent in a timely manner, however, due to ineffectiveness in identifying the scale of impact, comms were sent across the estate. This had resulted in some stores running on local store proxy servers experiencing inconvenience as there were no real impact at the stores. We have agreed actions on effective scope of observability through alerts, dashboards to identify the scope of impact to send relevant comms. | Service lead | Strategic | NA | 19/09/24 | Closed |  |  |  | Saloni | 2025-02-10 | 444 | >60 | September | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 90121906 | 2024-07-15 | Store colleagues unable to log in to Honeywells | Scopes of observability – create alerting mechanism to identify if the honeywells are functioning as expected, scale of impact based on its usage. | Problem identification & Alerting | David Gutteridge/ Shabik Mookhtihar | 15/08:This actions is completed. CXT-708 has been updated with the details of the alerting. 699 has made us make updates to the respective runbooks. 31/07: The team are currently setting up the alerting this sprint so that we are informed of any problems users may be experiencing with authentication.https://jira.marksandspencer.app/browse/CXT-699 https://jira.marksandspencer.app/browse/CXT-708 15/07: If there is a discrepancy between the Honeywell usage vs the normal load, Configure the new relic alert relating to the proxy errors to ascertain the scale of impact Creation of a dashboard to identify the health of the store devices. Identify options to track the traffic flow across the store devices. Feasibility of utilising Dynatrace | Honeywells | Tactical | NA | 15/08/24 | Closed |  |  |  | Saloni | 2025-02-10 | 444 | >60 | August | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 90121906 | 2024-07-15 | Store colleagues unable to log in to Honeywells | Generate an automated report for store devices (tills/HHT) pointing either store / central proxy server using 1E Tachyon – this will help our initial impact assessment | Problem identification & Alerting | Pritam Mukherjee | 19/09: We have configured a report which will provide the detail of devices pointing to central server . We have shared the report with Valli and Laura to fix the devices which are not in correcr VLAN 04/09: We have working on an automation to get a report for the stores which are running in central proxy server as per the team it should be ready 16/09 15/07: Tech teams are currently exploring options. | Store Infra | Strategic | NA | 19/09/24 | Closed |  |  |  | Saloni | 2025-02-10 | 444 | >60 | September | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 90121906 | 2024-07-15 | Store colleagues unable to log in to Honeywells | Track the progress of configuring a separate route - FG firewall, Zscaler for store honeywell traffic. | Permanent fix | Rav Dale | 07/10: We have received a confirmation that the activity is now completed. All stores are now having their honeywell traffic to go through FortiGate firewall 04/09: The activity is progressing well. All mainchain store traffic will flow via mid of September where as rest of the Francise should be by end of this month . ETA: 30/09 15/07: The solution that we are currently using is a legacy solution. A project is ongoing to migrate the honeywell traffic to go through FortiGate firewall/Zscaler instead of central/local proxy servers. Pilot process to test with 6 stores HHT traffic in progress. | Store Infrastructure TPM | Strategic | NA | 2024-07-10 | Closed |  |  |  | Saloni | 2025-02-10 | 444 | >60 | October | 2024 | #VALUE!
GTS | Digital Workplace Services | 90121906 | 2024-07-15 | Store colleagues unable to log in to Honeywells | Ensure all recovery steps are clearly called out in the MIM call to ensure relevant awareness and approvals are in place. Create a SOP to document the recovery steps to ensure we resolve the issue in a timely manner. | Solution & Recovery | Deepakkumar Ramanujam | 31/07: This has been agreed with the team to clarify any actions being performed on a MIM Call for everyone's visibility and attention 15/07: The recovery step performed to manually register the IP address to the DNS records was not clarified/updated on the call which resulted in a volatile discussion around the root cause and resolution. It has been agreed that any technical steps being performed on the call needs to be discussed on the call with the relevant stakeholder. In addition, a SOP will be created to document the steps involved in the triage and resolution of the issue for future use. | Store Infra | Tactical | NA | 31/07/24 | Closed |  |  |  | Saloni | 2025-02-10 | 444 | >60 | July | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 90121906 | 2024-07-15 | Store colleagues unable to log in to Honeywells | Review and establish the like-to-like configuration between non prod to ensure successful pre prod testing and avoid any change failures or impact. | Problem avoidance | Pritam Mukherjee | 19/09: HHT proxy removal almost completed so there will not be any dependency on central proxy with HHT by end of this month. 31/07: Further follow up is required to track the progress of syncing the prod and non prod environment. 15/07: The DNS records for Honeywell device (android.lsz) are configured with IP address resolution, however, the configuration is set up as FQDN in production. Due to difference in the configuration between non prod and prod environment, the issue was not highlighted whilst testing. A plan will be devised to ensure sync between the two environments | Store Infra | Tactical | NA | 19/09/24 | Closed |  |  |  | Saloni | 2025-02-10 | 444 | >60 | September | 2024 | #VALUE!
GTS | Digital Workplace Services | 90121906 | 2024-07-15 | Store colleagues unable to log in to Honeywells | Implement effective pre checks & post validation checks to confirm service stability after an outage. | Problem avoidance | Pritam Mukherjee | 31/07: The teams have incorporated additional steps to ensure appropriate pre and post checks are performed to confirm the health of the servers before putting the traffic through it. 15/07: We have agreed to perform a thorough review of the post implementation checks to confirm the server in healthy state and all connections are successfully established | Store Infra | Tactical | NA | 31/07/24 | Closed |  |  |  | Saloni | 2025-02-10 | 444 | >60 | July | 2024 | #VALUE!
GTS | Digital Workplace Services | 90121906 | 2024-07-15 | Store colleagues unable to log in to Honeywells | Review the implementation plan involved in the server cloning process to ensure the steps are clearly defined to avoid any further misses? | Problem avoidance | Pritam Mukherjee | 31/07: A workshop was conducted to ensure the implementation plan whilst cloning a server or performing similar activites is defined with clear steps to avoid this particular issue scenario. 15/07: We have agreed with the teams to ensure that the implementations steps are properly defined with appropriate sequence to avoid any further impact to production: first change the host name of the new server map the IP address of the new server as required | Store Infra | Tactical | NA | 31/07/24 | Closed |  |  |  | Saloni | 2025-02-10 | 444 | >60 | July | 2024 | #VALUE!
Customer Channels | Service Experience | 90124327 | 2024-07-15 | Credit card payments being declined in stores and website | We await root cause details from Worldline and what was done to resolve the issue Dan L to chase up VISA root cause. | Root cause | Laura Whittle/Dan Louden | 08/08: We now have the root cause from Worldline - The issue was triggered by unexpected CPU overload during the deployment of the load balancer HA PROXY upgrade from 2.4 to 2.6, preventing normal access to decryption services. We have the full report. 01/08: Laura advised that she will be following this up on 02/08 | Service Lead | Tactical | NA | 2024-08-08 | Closed |  |  |  | Rehan | 2025-02-10 | 444 | >60 | August | 2024 | #VALUE!
GTS | Operations | 90124327 | 2024-07-15 | Credit card payments being declined in stores and website | If there is a store payments declined issue, the incident stakeholders need to check the dashboards/test to see if .com is impacted – amend Teams comms process notes | Problem identification & Alerting | Rehan Siddiqui | 08/08 - Rehan added this check in the Worldline check list/comms process. | Service Management | Tactical | NA | 2024-08-08 | Closed |  |  |  | Rehan | 2025-02-10 | 444 | >60 | August | 2024 | #VALUE!
Customer Channels | Service Experience | 90124327 | 2024-07-15 | Credit card payments being declined in stores and website | We need to have the data in a more structured format, so it is easily understood. Suggest split data between card types/stores etc. Review the data and make amendments where needed. Are we using metric or logs – review. | Problem identification & Alerting | Chris Etherington & Imanuvel Manickam | Update 01/10: there was a meeting on 17/09 meeting with Tim Mason and actions were: Estimate the cost to collect payment logs (d_logs) to New Relic for problem identification and alerting - Tim to update Feasibility check to include payments logging on to pos error logs (errlog.out) - Iman working with Flooid on this This can now be tracked under https://jira.marksandspencer.app/browse/RPOS-14144 and be taken off here Update 08/08: POS team say there are limitations on what can be logged. We will outline our challenges to Worldline and see what they say. | POG | Tactical | NA | 23/09/24 | Closed |  |  |  | Rehan | 2025-02-10 | 444 | >60 | September | 2024 | #VALUE!
Customer Channels | Service Experience | 90124327 | 2024-07-15 | Credit card payments being declined in stores and website | New Relic was slow possibly caused by poor performance on queries – investigate and remedy. Include payment logs into New Relic. Dan/Shikar | Problem identification & Alerting | Shikar & Dan Mac Hale | 23/09 - We've done a review on the .com things and a lot of the slowness will come from the queries using log searches in our old POG application. We've added OTEL to the application and we're re writing the queries to make them more efficient, its a process. This is for .com traffic only. This can now be tracked under https://jira.marksandspencer.app/browse/PCAP-883 08/08: Jamie’s team has work streams to improve query performance during sprint 5 – starting 16/08 – agreed to followup last week of August | POG | Tactical | NA | 23/09/24 | Closed |  |  |  | Rehan | 2025-02-10 | 444 | >60 | September | 2024 | #VALUE!
Customer Channels | Service Experience | 90124327 | 2024-07-15 | Credit card payments being declined in stores and website | If we go offline (via the disconnect switch) we can auto approve everything up to £150. This scenario will be reviewed as part of the review in row 102 below. | Solution & Recovery | Note | Impact Analysis: Do we understand why this incident affected all payments below the offline limit, and what measures can we implement to prevent this in the future? | POG | Tactical | NA | 15/07/24 | Closed |  |  |  | Rehan | 2025-02-10 | 444 | >60 | July | 2024 | #VALUE!
Customer Channels | Service Experience | 90124327 | 2024-07-15 | Credit card payments being declined in stores and website | Review the different incident scenarios (ensure the relevant ones are included in runbooks) and look to get business pre-approval for activating the in-store disconnect switch including highlighting the challenges such as the 10 second card txn delay. | Solution & Recovery | Shikar/Iman | 03/12: RPOS-14680 has been created to review the incident scenarios for activating instore disconnect switch 03/09 - Network Kill Switch (Store-level) is tested OK from Stockley Park. This will be a back up option. Chris to update the plan to try the same from a live Store (after trade hours). Primary option: Application level Kill Switch is being worked out. We have an approach that needs to reviewed with Worldline. 08/08 - Mock store validation completed and once the disconnet switch was activated we could see the transactions went offline and chip and pin txns were approved. Chris advised we would like to this in a live store environment. This needs to be planned. Meeting set up with Jamie and Sam to look at use case scenarios. Will approach for business approval once we have confidence in the switch. | POG | Tactical | NA | 2024-03-12 | Closed |  | RPOS-14680 |  | Rehan | 2025-02-10 | 444 | >60 | December | 2024 | #VALUE!
Customer Channels | Service Experience | 90124327 | 2024-07-15 | Credit card payments being declined in stores and website | Dan to speak with Kamal (NOC) to discussed the need for testing the disconnect switch in a low traffic store possibly out of hours even though the testing has been completed in the mock store at SP. | Solution & Recovery | Dan M/Kamal | 08/08: We can close this as it is the same as row 102 | POG | Tactical | NA | 2024-08-08 | Closed |  |  |  | Rehan | 2025-02-10 | 444 | >60 | August | 2024 | #VALUE!
Customer Channels | Service Experience | 90124327 | 2024-07-15 | Credit card payments being declined in stores and website | Laura to speak to Darren who will speak to senior stakeholders to get an pre-approval/confirmation process to activate the switch. It should not be a question, rather an advisory. | Solution & Recovery | Laura/Darren | 08/08: Action CANCELLED AS PER ACTION IN ROW 102 01/08: Laura advised that she will be following this up on 02/08 | Service Lead | Tactical | NA | 2024-08-08 | Closed |  |  |  | Rehan | 2025-02-10 | 444 | >60 | August | 2024 | #VALUE!
Customer Channels | Service Experience | 90124327 | 2024-07-15 | Credit card payments being declined in stores and website | If we use the "Payment Offline Switch," for stores we need a well-defined process for safely reconnecting when we are confident the service is restored. | Solution & Recovery | Imanuvel Manickam | 08/08: We can close this as it is the same as row 102 | POG | Tactical | NA | 2024-08-08 | Closed |  |  |  | Rehan | 2025-02-10 | 444 | >60 | August | 2024 | #VALUE!
Customer Channels | Service Experience | 90124327 | 2024-07-15 | Credit card payments being declined in stores and website | The run book will assist in communications being more timely. Our agreed process is already to send out a generic comms in the first 15 minutes – the run book will be amended to include a landing comms in the first 15 mins. Runbook to be accessible/centralised – repository of runbooks – Darren | Issue handling/Management | Darren Gibson | 08/08: Darren advised that we are doing this as part of the centralised site for service management within D&T Hub. Close action and let the work carry on under that. | Leadership team | Tactical | NA | 2024-08-08 | Closed |  |  |  | Rehan | 2025-02-10 | 444 | >60 | August | 2024 | #VALUE!
Customer Channels | Service Experience | 90124327 | 2024-07-15 | Credit card payments being declined in stores and website | An end to end diagram is available – Laura to find and check to see if it is in the runbook with Dan. | Issue handling/Management | Laura/Dan L/Dan M | 21/11: MIRO board added to our Card Resolution under the Runbook https://confluence.marksandspencer.app/display/DCP/Card+Resolution+Steps 14/10: Dan M advised that we have diagrams for website but not for instore as the store/PEDS go straight to the providers (worldline). The diagram for .com isn't in the runbook but it can be by 18/10 08/08: Dan Mac Hale says there are diagrams and these need to be simplified. 01/08: Laura advised that she will be following this up on 02/08 | Service Lead | Tactical | NA | 2024-12-12 | Closed |  |  |  | Rehan | 2025-02-10 | 444 | >60 | December | 2024 | #VALUE!
Customer Channels | Service Experience | 90124327 | 2024-07-15 | Credit card payments being declined in stores and website | The 2 hour limit is only for those orders captured in iframe (before we activate the process offline switch). For totally offline (once we activate the switch) orders, there is no limit for the number of transactions but there is a £500 limit. This is a limitation with Worldline. The cvv is stored locally and worldline wont process it if its older than 2 hours. The job should be constantly retrying and process the backlog automatically once the system is available. Chris Etherington to summarise this and add to relevant run books | Solution & Recovery | Chris Etherington | 08/08: All constraints and risks have been added to the run book – closed | Payment Foundation Team | Tactical | NA | 2024-08-08 | Closed |  |  |  | Rehan | 2025-02-10 | 444 | >60 | August | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90107367 | 2024-07-11 | Issues in Castle Donington when processing messages from WMS to WCS | When the new flow was launched in April 2024, what level of traffic and files was it tested with, and can we prove that the number of files opened by the DB at any one time increased during the “back-to-school” campaign? | Root cause | Kunal Chichkar | 08/08 - This can be closed. Code fix at WMS and MULE applied as part of WMS Stabilization after dispatcher upgrade. | WMS |  | NA | 2024-08-08 | Closed |  |  |  | Rehan | 2025-02-10 | 448 | >60 | August | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 90097755 | 2024-07-10 | Network connectivity issue at stores on 29th June | Enable primary DIA in SP on 10th July between 22:00 and 23:00 to bring back resilience | Problem avoidance | Kamalakannan Kanniappan | 10/07: The activity is completed and the services are now currently running with resilience in SP | Network | Tactical | NA | 2024-10-07 | Closed |  |  |  | Saloni | 2025-02-10 | 449 | >60 | July | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 90097755 | 2024-07-10 | Network connectivity issue at stores on 29th June | Agree actions on effective impact assessment | Impact analysis | Kamalakannan Kanniappan/Dinsh Maluroutu | 12/12: The initial impact assessed Stores experiencing network connectivity issue for max 3 mins (during the failover) during the outage window. All instore operations were impacted – tills & honeywells in offline state, contactless payments, wifi connectivity instore etc. Digital Cafe were non functional in Swindon - however, as the traffic has been routed locally now, there should not be any impact. 28/11: Due to the ongoing network security incident, it is difficult to get the teams to focus on capturing the impact, therefore, agreed to schedule a call after GQ 14/11: The action is to define what areas would be impacted if there is a DIA link failure. Saloni to arrange catchup to discuss. 31/10: This needs further discussions with DInesh and Kamal as there is no easy way of identifying the impacted areas during an issue. 07/10: This is still being worked through. 05/09: As part of weekly updates, Suganya updated "All the DIA traffics routed to Primary DIA Circuit seamless did not observe any issues." Need further clarification 08/08: Kamal says that the NOC team can assist in the impact assessment should a DIA link fail but they would need to work with each of the service leads and applications teams. Kamal/Dinesh to speak on how to work through this. 09/07: This is a long-term activity. Each product team to analyse their respective application/service flow diagram to conclude on the dependency on the DIA links. This needs further discussion. | Network | Strategic | NA | 2024-12-12 | Closed |  |  |  | Saloni | 2025-02-10 | 449 | >60 | December | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 90097755 | 2024-07-10 | Network connectivity issue at stores on 29th June | Identify the reason behind the power outage/recovery works impacting the secondary link in SP | Root cause | Claire Magee/ VF | 09/07: We have now confirmed that the primary and secondary DIA link in SP is served by different datacentres at Vodafone. Our secondary DIA link is served through the Iver data centre where there was an unplanned power outage which caused the issue. | Network | Tactical | NA | 2024-09-07 | Closed |  |  |  | Saloni | 2025-02-10 | 449 | >60 | July | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 90097755 | 2024-07-10 | Network connectivity issue at stores on 29th June | Follow up with Vodafone to identify the root cause behind the issue | Root cause | Rajeshkumar Singarajan | 09/07: We have now confirmed that there was an unplanned power outage at Vodafone datacentre in Iver at 07:55 am on 29th June. Although, the traffic transmission kit was running with the help of backup battery, however, at 12:50, the backup battery ran out of charge resulting in the traffic to failover to Swindon DIA link. – This caused the first blip at 12:51. Power was restored by VF at 13:20 and our traffic therefore failed back to secondary DIA in SP resulting in the 2nd network blip 04/07: VF have advised of an unplanned power outage at Iver datacentre at 07:55 am on 29th June. We were further informed of some recovery works carried out by VF to fix the power outage between 12:00 and 13:00 which would have caused the issue. We have requested VF to ensure a detailed investigation with their technical engineers and provide a concrete update on root cause on 9th July. A follow up call has been scheduled. | Network | Tactical | NA | 2024-09-07 | Closed |  |  |  | Saloni | 2025-02-10 | 449 | >60 | July | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90096085 | 2024-07-09 | Carrier label printing issues at Stoke DC | There is an existing alert configured to identify failures in WMS db layer based on number of requests triggered vs the no. of successful responses every 1 hour, however, the create shipment flow is real time, therefore, the DC colleagues would report the issue prior to us getting the alerts. Fine tune the existing alert based on failures every 10 mins by creating a threshold based on business requirements. | Problem identification & Alerting | Nandakumar Sivalingam | 31/07: the current hourly notification holds good, but any Tech changes require proper validation in the cutover and hypercare with pack bench label printing involving site operations 12/07: Alerting optimisation is currently in progress to proactively identify issues before the DC reports. | WMS | Tactical | NA | 31/07/24 | Closed |  |  |  | Saloni | 2025-02-10 | 450 | >60 | July | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90096085 | 2024-07-09 | Carrier label printing issues at Stoke DC | In addition to the DC colleagues logging off from the pack benches, WMS team to revalidate any active session in the database and clear them before the activity: Identify the inactive user sessions in future scenarios to feedback to the operations | Problem avoidance | Nandakumar Sivalingam | 12/07: This has been agreed with the team and the SOP has been updated to avoid any further impacted after any such activities. | WMS | Tactical | NA | 2024-12-07 | Closed |  |  |  | Saloni | 2025-02-10 | 450 | >60 | July | 2024 | #VALUE!
GTS | Enterprise Integration | 90096085 | 2024-07-09 | Carrier label printing issues at Stoke DC | Ensure an additional post validation step is incorporated into the implementation plan for future certificate changes to validate the label printing functionality in collaboration with site operations | Problem avoidance | Nandakumar Sivalingam/ Sivasubramani Pappusamy | 31/07: This has been updated int he WMS runbook to advise colleagues to log off from the pack benches before an activity. 12/07: It has been agreed that from WMS perspective, as a pre-requisite, DC will be advised to log off properly from all pack benches before the change window and add an additional step in the post validation plan to check with site on successful label printing functionality before handing over to the site. From Mule perspective, the post validation step to confirm on create shipment functionality has been incorporated to the KEDB for future references. | Mule/ WMS | Tactical | NA | 31/07/24 | Closed |  |  |  | Saloni | 2025-02-10 | 450 | >60 | July | 2024 | #VALUE!
Customer Channels | Service Experience | 90105509 | 2024-07-09 | Post purchase fraud check issues with Accertify | Discuss the feasibility of directly reaching out to Accertify technical team rather than going through the account manager. | Supplier and support involvement | Suzzanne / Chris | 16/09: The Accertify support contact are updated 09/07; The next update is expected on 16/08 | Accertify | Strategic | NA | 16/09/24 | Closed |  |  |  | Kavitha | 2025-02-10 | 450 | >60 | September | 2024 | #VALUE!
Customer Channels | Service Experience | 90105509 | 2024-07-09 | Post purchase fraud check issues with Accertify | Workshop to review when to instigate the kill switch and who should decide etc. For example, if OMS team find the issue first and there is a delay in reaching out to other teams, should they switch off Fraud Checks and protect fulfilment | Solution & Recovery | Chris, Dan McHale, Dino, Aravind, Vipin, Nilesh, Hisham | 17/09: Its has been agreed to close this actions as the workshop detail around Kill-switch, this is being considered as a wider piece around Accertify resilience, not for now but in the backlog.In the meantime, we should follow existing processes 07/08: Awaiting further updates from Nilesh 09/07; The next update is expected on 31/07 | OMS/POG | Strategic | NA | 17/09/24 | Closed |  |  |  | Kavitha | 2025-02-10 | 450 | >60 | September | 2024 | #VALUE!
Customer Channels | Service Experience | 90105509 | 2024-07-09 | Post purchase fraud check issues with Accertify | Define process for making these changes, impact assessment and peer reviews. | Problem avoidance | Jamie Leven | 16/09: The process has been agreed and is being documented 07/08: Awaiting further updates from Nilesh 09/07; The next update is expected on 31/07 | POG | Strategic | NA | 16/09/24 | Closed |  |  |  | Kavitha | 2025-02-10 | 450 | >60 | September | 2024 | #VALUE!
Customer Channels | Service Experience | 90105509 | 2024-07-09 | Post purchase fraud check issues with Accertify | Reassess the naming conventions of the userids to avoid confusion and make changes simpler for the technical teams | Problem avoidance | Niraj | 16/09: The validations of userid naming conventions has been completed and all the necessary changes has been made. 09/07; The next update is expected on 16/08 | POG | Strategic | NA | 16/09/24 | Closed |  |  |  | Kavitha | 2025-02-10 | 450 | >60 | September | 2024 | #VALUE!
Customer Channels | Service Experience | 90105509 | 2024-07-09 | Post purchase fraud check issues with Accertify | Review alerting in OMS. Currently OMS only considers orders older than 30 mins which are in fraud hold status. So, there is automatically a delay of 30 mins in picking up an issue. | Problem identification & Alerting | Vipin | 17/07: The average time for response was less than 5 mins. So team have changed the alert to run every 30 mins to check condition "More than 100 orders placed before 10 mins are still awaiting response". | OMS | Tactical | NA | 17/07/24 | Closed |  |  |  | Kavitha | 2025-02-10 | 450 | >60 | July | 2024 | #VALUE!
Customer Channels | Service Experience | 90105509 | 2024-07-09 | Post purchase fraud check issues with Accertify | Configure alerting in POG | Problem identification & Alerting | Niraj | 17/07: Alerting has been configured in POG under the JIRA reference - PCAP-1364 | POG | Tactical | NA | 17/07/24 | Closed |  |  |  | Kavitha | 2025-02-10 | 450 | >60 | July | 2024 | #VALUE!
Customer Channels | Service Experience | 90102001 | 2024-07-03 | Proof of deliveries not created for food suppliers | There is a gap in the way variances are investigated and Bala from Sap Buy and Move will be joining a call to discuss how to progress investigations. Foods to be part of the call. | Solution & Recovery | Lisy/Bala/Remko | 04/11: It has been agreed to ensure all relevant stakeholders to be involved whilst investigating the issue. 18/08: Followed up awaiting further updates 08/08: Lisy to check with Bala and Remko to see how this investigation should be carried out in a standardised way. They are already holding discussions - Lisy to get the latest | SAP PI |  | NA | 2024-04-11 | Closed |  |  |  | Rehan | 2025-02-10 | 456 | >60 | November | 2024 | #VALUE!
Group Platforms | Finance | 90102001 | 2024-07-03 | Proof of deliveries not created for food suppliers | Create an alert to trigger when the consumer application (SAP BTP in our case) is experiencing a connectivity issue between Sap BTP and kafka. | Problem identification & Alerting | Jothi | 08/08 - Jothi advises that the alert is configured for a lag but not for connectivity issues. This alert needs tuning as too many alerts are being triggered due to the thresshold not being set appropriately. 15/07 - SAP BTP had discussion with the Kafka team - they suggested Jothi go through a document which shows how to implement alerts - this is now being studied. | SAP PI | Tactical | NA | 2024-08-08 | Closed |  |  |  | Rehan | 2025-02-10 | 456 | >60 | August | 2024 | #VALUE!
Group Platforms | Finance | 90102001 | 2024-07-03 | Proof of deliveries not created for food suppliers | Create an alert to trigger when the consumer application (SAP BTP in our case) is experiencing a lag in reading messages from the kafka side. | Problem identification & Alerting | Veera and Jothi | 04/11: The alerting has been implemented in production and has been monitored for a month. 18/08: Followed up awaiting further updates 08/08 - Jothi advises that the alert is configured for a lag but not for connectivity issues. This alert needs tuning as too many alerts are being triggered due to the thresshold not being set appropriately. 15/07 - SAP BTP had discussion with the Kafka team - they suggested Jothi go through a document which shows how to implement alerts - this is now being studied. | SAP PI |  | NA | 2024-04-11 | Closed |  |  |  | Rehan | 2025-02-10 | 456 | >60 | November | 2024 | #VALUE!
Group Platforms | Finance | 90102001 | 2024-07-03 | Proof of deliveries not created for food suppliers | Certificates update automatically from the publisher. SAP BTP have SOP’s to update a cert once its expired. Jothi to work on making i808 to work with just an API key. Other interfaces do not require certificate and Jothi will compare to see how this is possible | Problem avoidance | Jothi | 03/09: THe issue has been fixed by replacing root certificate on back of an issue 18/08: Followed up awaiting further updates 08/08: Jothi advises that acert is needed and cannot work on API key alone. This has been proved in the lower environment. The idea now is that we can maintain this via a root certificate as root certs dont expire as often. Jothi's team will now raise a CR and replace the interim cert with a root cert. 15/07: Jothi says this discussion has not happened yet and is planned for this week to work out how to do his. Jothi to plan the meeting for this week | SAP PI |  | NA | 2024-03-09 | Closed |  |  |  | Rehan | 2025-02-10 | 456 | >60 | September | 2024 | #VALUE!
Group Platforms | Finance | 90102001 | 2024-07-03 | Proof of deliveries not created for food suppliers | Raise a risk in the meantime because publishers could update a CA cert for any reason. How will BTP be aware from the publishing authority? Mantha and jothi to discuss a proactive solution and create a sop. | Problem avoidance | Mantha/Jothi | 08/08: Jothi advises that a cert is needed and cannot work on API key alone. This has been proved in the lower environment. The idea now is that we can maintain this via a root certificate as root certs dont expire as often. Jothi's team will now raise a CR and replace the interim cert with a root cert in production. Closed and refer to action 119 15/07: As stated above we want to go to an API key solution rather than certificates, untIl then we are monit¦oring the flow every day manually to ensure the flow is working - Jothi says no risk to be rasied for the Time being - all depends on the discussion planned above. | SAP PI |  | NA | 2024-08-08 | Closed |  |  |  | Rehan | 2025-02-10 | 456 | >60 | August | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 90099610 | 2024-07-02 | Stores reporting issue with various functionalities in CSSM | What was the root cause of the issue | Root cause | CSSM, Middleware Admin and Wintel Teams | 04/07 – CSSM team informed that based on their analysis of similar issues in the past twice (2016 and 2020), the root cause has been inconclusive. However, it has been agreed with the teams to follow the SOP when similar errors are observed. 02/07 - The root cause is still being investigated, we have advised the relevant technical teams to validate the error logs across the application and middleware layers. Follow-up call is scheduled on 4th July to discuss further on this. | CSSM |  | NA | 2024-05-07 | Closed |  |  |  | Gokul | 2025-02-10 | 457 | >60 | July | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 90099610 | 2024-07-02 | Stores reporting issue with various functionalities in CSSM | An alert was triggered at 5 AM, indicating an issue with one of the CSSM webserver, however, no actions were taken. Agree on a plan to ensure effective alert handling. Update the existing SOP to ensure the relevant alert are addressed with minimal impact. | Problem identification & Alerting | Ravikumar S/ CSSM TPM | 14/08 - Both Vijay & Ravi confirmed that the on-call SME support for foods and C&H CSSM are addressed. Hence, closing the action. 07/08 - Have reached out to C&H TPM Vijay Baskar to know the on call SME and he is working with the team and it should be finalized by 08/08. 30/07 - Call was rescheduled to today and expect the ROTA finalization by tomorrow. 25/07 - Ravi updated that he has a call today with C&H to confirm the ROTA and to publish. It has been delaying as team is held up with Colo migration activities. 17/07 - Ravi confirmed that the on-call SME plan is to be published today after having got all the required approvals. 11/07 - CSSM TPM Ravikumar S said that he is working on the plan and would publish it by 12/07 EOD, awaiting further details. 04/07 – CSSM Team confirmed that as part of the SOP, IIS restart to be performed when the errors are observed. Team to work on the on-call SME support and confirm. 02/07 - We have agreed with the product team to accommodate an oncall backup senior engineer to assist on the onshift associate in technical triage during an incident. As per the current SOP, whenever an alert is received indicating 500 internal server error along with IO error in one server – team will validate the logs in the other 2 servers. If this error is not observed on any other servers, an action is taken to manually restart the IIS and application service on the problematic server. It has been agreed to update the SOP to ensure we perform a restart of application service first, if the issue is not resolved, then we should proceed with IIS service restart. | CSSM |  | NA | 14/08/24 | Closed |  |  |  | Gokul | 2025-02-10 | 457 | >60 | August | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 90099610 | 2024-07-02 | Stores reporting issue with various functionalities in CSSM | Review the daily scheduled restart plan of the IIS service across all the CSSM webservers. | Problem avoidance | Shanmuga Priya/CSSM | 04/07 – CSSM team confirmed that only IIS restart is done as part of the schedule at 00:30 and 05:00. 02/07 - Product teams are currently checking if the scheduled restart every morning involves only the IIS service restart of there is automatic scheduler to restart the application service. | CSSM |  | NA | 2024-05-07 | Closed |  |  |  | Gokul | 2025-02-10 | 457 | >60 | July | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 90099610 | 2024-07-02 | Stores reporting issue with various functionalities in CSSM | Load balancing is enabled across all the 3 existing web servers, the application traffic served through the 2 healthy servers did not encounter any issue and therefore the issue was intermittent across the stores. Review the load balancing mechanism to route the entire traffic to other healthy servers. | Problem avoidance | Valliammai R and Kamalakannan K | 22/10 - Valli reconfirmed that it will be handled as part of CSSM modernization project, hence closing the action 08/10 - Valli confirmed that she will get a backlog raised as this could be handled as part of CSSM modernization. 03/10 - Valli is busy with CSSM SQL upgrade activity, she will confirm early next week. 26/09 - Valli is yet to check with the product owner and it would be tough to deploy before peak, I have requested for a backlog. But, as part of CSSM modernization, this may not be required it seems. Hence, she will reconfirm. 18/09 - We had a call with CSSM & Kamal and it was agreed that the auto load balancing can be done and Valli to check with the product owner and confirm 23/08 - Kamal is still working on this and will update us ASAP. 16/08 - Kamal updated that he is working on this and will update us further next week. 08/07 - This action continues - there is a health probe configured which checks the back end node. Check what kind of error is configured and what needs to be changed to set the node to failed. 04/07 – This is a design change, Valli to check with Kamal for backlog to work on it. 02/07 - Valli is in discussion with Kamal to identify the feasibility to improve the load balancing option during an issue | Service Lead |  | NA | 22/10/24 | Closed |  |  |  | Gokul | 2025-02-10 | 457 | >60 | October | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 90099610 | 2024-07-02 | Stores reporting issue with various functionalities in CSSM | The IIS service was restarted along with the application service on the problematic CSSM webserver manually. Feasibility of automating the restart of the services during an issue to avoid manual intervention | Solution & Recovery | Shanmuga Priya/CSSM | 06/12 - We have the backlog CSSM-13243 to track it, hence closing 28/11 - Demo date is finalized as 29/11, once approved it can be deployed by Monday 20/11 - Development and testing has been done by Ignio team and awaiting for a Demo date with CSSM team 07/11 - In CATE server, the system will restart daily from 12:00 am BST to 12:30 am BST and again from 5:00 am BST to 5:30 am BST. If the first restart fails, a batch file will run to attempt a second restart. If the second restart fails, it will be triggered using a keyword in the log file. If this attempt also fails, an acknowledgment email will be sent, and the restart will need to be performed manually. This setup dry run will be done tomorrow and Demo by tuesday/wednesday to deploy to prod 05/11 - Ignio team has got the required access to Cate server and 28/10 - Ignio team while testing in SCCM Cate server, few modules were not coming and they have asked to give connectivity between the cate servers to ignio servers to the respective team. 22/10 - Ignio team has installed python in SCCM cate server and dry run in UAT is planned today. 17/10 - Demo is completed by Ignio team and CSSM team has provided feedback and revision Demo is planned by 22nd 08/10 - Code deployment with the required changes have been completed and Demo is planned on 09/10. 24/09 - Due to the Digitate changes, the code had to revisted and the deployment is expected to be completed by 27/09 12/09 - After the proxy upgradation the deployed code isn't working and Ignio team is working on this issue with DIgitate 29/08 - Development is completed by Ignio team, post testing they will schedule a Demo by 4th September 07/08 - Ignio team confirmed that the team is working on it with a Go Live by 29th August. 30/07 - Have asked the Ignio team for the Jira reference of the automation. 25/07 - Bharath shared the Jira ID - CSSM-12457 (closed) with which they were working with Ignio team, have asked their Jira reference to close this action. Also, runbook will be updated in the coming weeks. Owner: Bharath/Ravi. 17/07 - Bharath Murugan confirmed that as part of the sprint with a backlog, they have discussed with Ignio team for the automation and they have agreed for the same. Hence, the Jira has closed. Awaiting CSSM and Ignio backlog details, once we have Ignio backlog the action will be closed with it. 13/07 - Have asked Shanmuga Priya if we are on track to complete this action by 16/07. 04/07 – The automation is taken in the current sprint started 03/07 and expected to complete by 16/07. 02/07 - Product team are currently attempting to enable the automatic service restart (IIS and Application service) in the next Sprint | CSSM |  | NA | 2024-06-12 | Closed |  | CSSM-13243 |  | Gokul | 2025-02-10 | 457 | >60 | December | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 90099610 | 2024-07-02 | Stores reporting issue with various functionalities in CSSM | Creation of a New Relic Dashboard to reflect the failure rate based on a time period | Impact analysis | Anees Ahmed | A new relic dashboard has been created to reflect the failure rate in the application layer based on time level. | CSSM |  | NA | 2024-02-07 | Closed |  |  |  | Gokul | 2025-02-10 | 457 | >60 | July | 2024 | #VALUE!
Customer Channels | Selling Experience | 90099341 | 2024-07-02 | Customers & Store Colleagues unable to book Bra & Suit fit appointments both Online and In-Store | Do we have existing alerts for password expiry? What actions were taken? | Problem identification & Alerting | Assist Team/ Deepak D | 02/07 - There is no alerting mechanism in place to notify on password expiry. Action 4 is to ensure we identify a robust way to handle password expiry scenarios. Therefore, this action is being closed. | Platform & Store Ops |  | NA |  | Closed |  |  |  | Gokul | 2025-02-10 | 457 | >60 | January | 1900 | #VALUE!
Customer Channels | Selling Experience | 90099341 | 2024-07-02 | Customers & Store Colleagues unable to book Bra & Suit fit appointments both Online and In-Store | Identify the existing alerting during pods restart. What actions were taken? Are there any scopes of improvement. | Problem identification & Alerting | Cloud ops/ Assist/ Biju George | 09/07 - Required alerts are configured to identify such issues. 02/07 - There are no alerts for application pod restart issues, tech teams are in process of configuring alerts to proactively identify issues with application pods. | Cloud ops/ Assist |  | NA | 2024-09-07 | Closed |  |  |  | Gokul | 2025-02-10 | 457 | >60 | July | 2024 | #VALUE!
Customer Channels | Selling Experience | 90099341 | 2024-07-02 | Customers & Store Colleagues unable to book Bra & Suit fit appointments both Online and In-Store | Review the alerting mechanism to identify issues across stores and websites when there is an issue Booking service application | Problem identification & Alerting | Assist/ Biju George | 09/07 - Required alerts are configured to identify such issues in both Dot Com and Stores. 02/07 - There is an existing new relic alert configured indicating API call failures across instore and online. As this is an email alert and due to unavailability of resources, no actions were taken on this alert. We have agreed to configure the below alerts: 1. Creation of a pager duty alert to ensure effective actions are taken. 2. Feasibility of configuring alerts based on booking volume threshold. | Assist app |  | NA | 2024-09-07 | Closed |  |  |  | Gokul | 2025-02-10 | 457 | >60 | July | 2024 | #VALUE!
Infosec & Tech Risk | Infosec & Tech Risk | 90099341 | 2024-07-02 | Customers & Store Colleagues unable to book Bra & Suit fit appointments both Online and In-Store | Review the new policy introduced to create Y account to maintain security regulations. When is the policy due to go live? Agree on a process to inform the relevant account owners. | Solution & Recovery | Cyber Sec/Manideepak G | 30/07 - Pushpa shared the Epic ID - WPTS-21144 and Jira Story ID - WPTS-21145 to track this action with product team. 25/07: Have followed up with Manideepak on the status of Jira reference. 17/07 - Outcome of the call on 16/07 is that the existing accounts with set to expire in 3 months will be extended to 6 months with config changes from AD (Active Directory) team. During this 6 months the automated process will be build to send notifications to owners, asking to reset the password. Incase, if the automation will not complete by the 6 months, AM (Access Management) team will reach out to the owners based on the latest list by then and will be notified on the actions that needs to be done. Have asked a backlog to Manideepak, with which this action will be tracked by the product team 15/07 - Manideepak said that the 1st scenario will take time and is worked upon, while for the 2nd scenario Deepak (access mgmt) spoke to Farid and understood that a viable option of asking Account owners if they are fine to own or providing reason for exception, so that CyberSec can approve to have the account password as "Never Expire". Deepak to setup a call with required stakeholders by 17th. 13/07 - Have checked with Manideepak on the status of the discussion on the various scenarios. 02/07 - A detailed discussion needs to be carried out to ensure the below options to avoid any production impact due to expired password scenarios: 1.Automatic update of the password every 3 months and notify the account owner. 2.Until the above is accomplished, reminder emails should be sent across the account owners to notify them to reset the password before 10, 20 days of expiry using Power automate. | Infosec & Tech Risk |  | NA | 30/07/24 | Closed |  | WPTS-21145 |  | Gokul | 2025-02-10 | 457 | >60 | July | 2024 | #VALUE!
Customer Channels | Selling Experience | 90099341 | 2024-07-02 | Customers & Store Colleagues unable to book Bra & Suit fit appointments both Online and In-Store | Currently, booking app is running with Y account of Assist app, devise a plan to implement a permanent fix by reinstating the Booking app Y account | Permanent Fix | Assist/ Biju George | 15/07 - Biju confirmed that Yaccount has been changed and no further issues observed, hence closing the action. 13/07 - Have checked with Biju if the Yaccount has been changed for the Assist App. 09/07 - A change has been raised to change the Y account for Booking service on 11th July. 02/07 - A work order was raised to reset the password for Booking app. Tech teams are in process of planning the deployment to introduce the Booking app Y account into Booking service. | Assist app |  | NA | 15/07/24 | Closed |  |  |  | Gokul | 2025-02-10 | 457 | >60 | July | 2024 | #VALUE!
GTS | Digital Workplace Services | 90099341 | 2024-07-02 | Customers & Store Colleagues unable to book Bra & Suit fit appointments both Online and In-Store | Validation of all relevant Y accounts created before the introduction of this new policy to ensure the “password never expire” field is set to True. | Problem avoidance | Deepak/ | 02/07 - 16 Y accounts were identified where “Password Never Expire” set as False. Access Management team have set the flag to True for all the Y accounts to ensure no further production impact. | Access Management |  | NA |  | Closed |  |  |  | Gokul | 2025-02-10 | 457 | >60 | January | 1900 | #VALUE!
GTS | Operations | 90099341 | 2024-07-02 | Customers & Store Colleagues unable to book Bra & Suit fit appointments both Online and In-Store | There was an initial confusion to understand the impacted functionality. Therefore, agree with Service desk to capture appropriate information from the store colleagues regarding the issue whilst on a call | Problem identification & Alerting | Jaya Mistry | This will be agreed with Service desk lead – Jaya Mistry | Service Desk |  | NA |  | Closed |  |  |  | Gokul | 2025-02-10 | 457 | >60 | January | 1900 | #VALUE!
Customer Channels | Selling Experience | 90099341 | 2024-07-02 | Customers & Store Colleagues unable to book Bra & Suit fit appointments both Online and In-Store | Update appropriate escalation and support contacts in Contact Repository for Assist App | Supplier and support involvement | Assist/ Biju George | 11/07 - Biju confirmed that the shift details are updated and the Manager details are also updated now. 09/07 - Followed up with Biju and he is still working on updating the contact repo with the Latest details. 02/07 - Contact Repo link has been shared and asked to update the Assist details | Assist app |  | NA | 2024-11-07 | Closed |  |  |  | Gokul | 2025-02-10 | 457 | >60 | July | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90067277 | 2024-06-28 | Central issue at BlueYonder impacting Foods and C&H planning activities | Review the existing alerting and enhance as required | Problem identification & Alerting | Ganesh Regoubady (BY TAM) | 08/07 – Ganesh confirmed that the existing alerting have been enhanced and the actions can be closed 28/06 – Ganesh to share the updates of the actions in the BY Root cause document 24/06 - Network logging and monitoring gaps were identified. Some observability improvement made on 18 June | BY Team |  | NA | 2024-08-07 | Closed |  |  |  | Gokul | 2025-02-10 | 461 | >60 | July | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90067277 | 2024-06-28 | Central issue at BlueYonder impacting Foods and C&H planning activities | BY to have a stringent change process followed to avoid such outages | Problem avoidance | Ganesh Regoubady (BY TAM) | 08/07 – It has been confirmed that an extensive testing will be done before implementing any change within BY infrastructure which could potentially impact their customers including Customer. 28/06 – Ganesh to share the updates of the actions in the BY Root cause document | BY Team |  | NA | 2024-08-07 | Closed |  |  |  | Gokul | 2025-02-10 | 461 | >60 | July | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90067277 | 2024-06-28 | Central issue at BlueYonder impacting Foods and C&H planning activities | Explore alternate options for a quick recovery or a work around | Solution & Recovery | Ganesh Regoubady (BY TAM) | As BY is SaaS platform, it was advised that the decision to invoke DR will be solely will be with them. In case the incident recovery is likely to take a longer period, then they would be invoking DR process | BY Team |  | NA | 28/06/24 | Closed |  |  |  | Gokul | 2025-02-10 | 461 | >60 | June | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90067277 | 2024-06-28 | Central issue at BlueYonder impacting Foods and C&H planning activities | Ensure BY has a proper testing and impact assessment is performed in the lower environments before any changes | Impact analysis | Ganesh Regoubady (BY TAM) | It has been confirmed by BY that they are doing required testing in the available environments and sending appropriate communications to the stakeholders. If any changes could potentially impact Customer, relevant communications are already being sent for proactive notification. | BY Team |  | NA | 28/06/24 | Closed |  |  |  | Gokul | 2025-02-10 | 461 | >60 | June | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90067277 | 2024-06-28 | Central issue at BlueYonder impacting Foods and C&H planning activities | As this was a Blue Yonder outage, they were sending comms but this lacked an ETA for recovery time and did not state when the next update would be. Ensure BY comms has the approximate ETA mentioned for next updates and Service Restoration | Business & IT Communication | Ganesh Regoubady (BY TAM) | 30/07 - Ganesh confirmed that the action taken has been completed. 08/07 – Ganesh confirmed that BY management is working on revisiting the comms | BY Team |  | NA | 30/07/24 | Closed |  |  |  | Gokul | 2025-02-10 | 461 | >60 | July | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 90079822 | 2024-06-27 | Intermittent issues with click and collect kiosks and tablets at stores | Did we perform Performance testing of the change with the additional logging? Performance testing was not carried out. Lessons learnt – will be communicated to the team. Valli and Rohith and they will be part of the technical and change review process | Problem avoidance | Valli and Rohith | Performance testing was not carried out. Lessons learnt – will be communicated to the team. Valli and Rohith and they will be part of the technical and change review process | Click & Collect |  | NA | 27/06/24 | Closed |  |  |  | Rehan | 2025-02-10 | 462 | >60 | June | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 90079822 | 2024-06-27 | Intermittent issues with click and collect kiosks and tablets at stores | There was no memory crunch apart from the log limit on the node server was breaching 1mb. As the pods were restarting this naturally caused spikes in CPU and memory and led us into the wrong areas of investigation. | Root cause | Valli and Rohith | NA/06: Issuesprogress | Click & Collect |  | NA | 27/06/24 | Closed |  |  |  | Rehan | 2025-02-10 | 462 | >60 | June | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 90079822 | 2024-06-27 | Intermittent issues with click and collect kiosks and tablets at stores | It was found that multiple developers carried out various changes in DEV which were combined into one production change – how can we keep track of historical developments that have been brought together under one release. | Problem avoidance | Valli and Rohith | 07/08: We have agreed to have two reviews - ne peer and one technical architect review. These have now been implemented for any changes within C&H team. | Honeywell | Strategic | NA | 2024-07-08 | Closed |  |  |  | Rehan | 2025-02-10 | 462 | >60 | August | 2024 | #VALUE!
GTS | Operations | 90079822 | 2024-06-27 | Intermittent issues with click and collect kiosks and tablets at stores | CR was approved via the four wall auto approval process and did not come to the CAB – Priya to suggest improvements to make these types of changes more visible for review. | Problem avoidance | Priyadharshini Somasundaram | 15/07 Priya advises that the four wall auto process has been reiterated to Rohith to ensure they are more vigilant when approving such changes and Priya will plan for estate wide comms. | SIAM |  | NA | 15/07/24 | Closed |  |  |  | Rehan | 2025-02-10 | 462 | >60 | July | 2024 | #VALUE!
GTS | Enterprise Integration | 90073897 | 2024-06-26 | Carrier label printing issue at Donington on 17/06 | There is a scenario of Mule thread starvation (no. of resources available to process new requests) resulting in slow response for Sorted API calls (carrier label printing) and subsequently affecting other flows including Mule to WMS Database. Identify the cause behind thread starvation in Mule layer resulting in slow message processing. | Root cause | Rajasekar S/ Sivasubramani Pappusamy | 14/08: Siva confirmed that Disabling audit was deployed overnight and hence closing the action. 07/08: Testing has been completed in non prod to disable the audit, it is being planned to be deployed by 14th August in prod. 23/07: Simulation of the actual production issue scenario in non prod is in progress. 26/06 : Auditing is configured across all Mule layer, a detailed performance testing is being performed with increased volume of message requests to identify the options for thread optimisation. | Mule |  | NA | 14/08/24 | Closed |  |  |  | Gokul | 2025-02-10 | 463 | >60 | August | 2024 | #VALUE!
C&H and Intl | C&H and Intl supply chain | 90073897 | 2024-06-26 | Carrier label printing issue at Donington on 17/06 | Monitor the benefit of load distribution to a different Mule server | Solution & Recovery | Murali Srinivasan/ Sivasubramani Pappusamy | 22/07 - Issue recurrences has been significantly reduced and there is a way to mitigate the issue without OMS / Sorted (DC operations) impact. 26/06 - No further issues observed and therefore, closing the action. 20/07: Siva updated that the load distribution is done to the second mule server instance and is active for more than 4-5 weeks and no issues observed. Have asked him for other benefits of it. 01/07: There have been no further instances of carrier label printing issue after the load distribution of database flows to a different Mule server. Monitoring is in place. | Mule/ WMS |  | NA | 22/07/24 | Closed |  |  |  | Gokul | 2025-02-10 | 463 | >60 | July | 2024 | #VALUE!
GTS | Enterprise Integration | 90073897 | 2024-06-26 | Carrier label printing issue at Donington on 17/06 | The auditing of the high NFR is causing load on the mule queues, therefore we plan on disabling the auditing for high NFRs with no messaging interfaces to reduce the load on the Mule audit queues. | Permanent fix | Rajasekar S/ Sivasubramani Pappusamy | 14/08: Siva confirmed that Disabling audit was deployed overnight and hence closing the action. 07/08: Testing has been completed in non prod to disable the audit, it is being planned to be deployed by 14th August in prod. 23/07: Non prod testing completed for removing audit (2 high NFR interfaces). Awaiting confirmation and slot from CD team to move to PRod 01/07: Team have identified 2 high no messaging interfaces like I809 or I810 which are traceable in other integration layers. Therefore, we will be disabling the Mule audit alone. nearly 2 M audits are there for CD for these interfaces. There is a plan to disable auditing at the earliest and changes in progress. Once the root cause is ascertained, we will enable auditing for high NFR | Mule |  | NA | 14/08/24 | Closed |  |  |  | Gokul | 2025-02-10 | 463 | >60 | August | 2024 | #VALUE!
Group Platforms | Finance | 90068324 | 2024-06-26 | Food RDC Good Receipting missing in SAP for depot date 8th Jun | Currently there are 2 flows are being routed via WIAS , Cutover procedure is amended to capture the instruction of holding both the flows in WIAS for any SAP PO outages by SAP Tech | Problem avoidance | Pawankumar M | SOP is updated | Service Lead |  | NA | 22/07/24 | Closed |  |  |  | Gokul | 2025-02-10 | 463 | >60 | July | 2024 | #VALUE!
Group Platforms | Finance | 90068324 | 2024-06-26 | Food RDC Good Receipting missing in SAP for depot date 8th Jun | During SAP SP Exit activity, SAP Process Orchestration (PO) and Queue manager were down. Ideally these messages should have been held in WIAS as part of cutover. Message Count Reconciliation will be carried out by SAP Tech between held systems and SAP as part of post implementation checks on future major outages | Problem avoidance | Pawankumar M | SOP is updated | Service Lead |  | NA | 24/07/24 | Closed |  |  |  | Gokul | 2025-02-10 | 463 | >60 | July | 2024 | #VALUE!
Customer Channels | Selling Experience | 90087203 | 2024-06-26 | Blank Home Page served to customers on desktop and mobile web | Investigate what triggered the web app swap | Root cause | Nigel Magnay | 22/07: Validated and confirmed bot the events are not related to change 16/07: The timing of the web app swap correlates to the occurrence of the 2 byte response. This needs to be investigated further to understand if it was the cause of the 2 byte response | Web app | Tactical | NA | 22/07/23 | Closed |  |  |  | Kavitha | 2025-02-10 | 463 | >60 | July | 2023 | #VALUE!
Customer Channels | Selling Experience | 90087203 | 2024-06-26 | Blank Home Page served to customers on desktop and mobile web | Investigate if any other changes were going on at same time as the incident | Root cause | Nigel Magnay | 22/07: Validated and confirmed this not related to change 16/07: 1. Investigate environmental changes e.g. traffic spike leading to auto-scaling - Nigel to look at Azure scaling 2. Review deployments – Nigel to look at deployments | Web app | Tactical | NA | 22/07/23 | Closed |  |  |  | Kavitha | 2025-02-10 | 463 | >60 | July | 2023 | #VALUE!
Customer Channels | Selling Experience | 90087203 | 2024-06-26 | Blank Home Page served to customers on desktop and mobile web | Investigate whether an Akamai 2 byte response has occurred in other areas | Impact analysis | David Raine | 04/09: Further correlation cannnot be done. Hence we are closing this actions 15/08: David and Nigel attempt to correlate Akami requests with origin responses (if requests make it that far into Azure) 22/07: David will look at the New Relic dataset to see if content length > 1 byte and < 10 bytes. This will help determine whether or not a 2 byte response has occurred anywhere else (i.e. not just on Home Page) or in the past The action owner is out of office until 22nd July. | Akamai | Tactical | NA | 2024-04-09 | Closed |  |  |  | Kavitha | 2025-02-10 | 463 | >60 | September | 2024 | #VALUE!
Customer Channels | Selling Experience | 90087203 | 2024-06-26 | Blank Home Page served to customers on desktop and mobile web | Microsoft to provide information about the request that was cached- A ticket has been raised with Microsoft in order to provide information about the request that was cached. (There is a concern that this could be time critical | Root cause | Luke Sparkes Nigel Magnay | 23/08: Microsoft applied a fix to our subscription on the 5th Aug -- this has resolved the issue, not re-occured for a month. Microsoft provided RCA, Azure had race condition when unpacking the app zip. Fix was Azure-backend rollback of our subscription. No further action required. 12/08: Microsoft were due to share RCA (root cause analysis) today, however we have received it yet . The RCA is being chased with Microsoft. Also, Monitor for reoccurrence of issue since Microsoft applied patch. 05/08: Microsoft agreed Azure behaviour is unexpected by applying a patch to our subscription (in their backend). 22/07: Microsoft is perusing an alternative hypothesis: "Origin serving ‘old’ versions, this was detected 24hrs after this incident occurred" Serving the old origin version DID happen, but doesn't align time-wise with the most recent examples of 2 byte responses (eg 12th July). Microsoft have found evidence that the old version of our code does exist on our base instances (inwwwroot). This should never get served because we use WEBSITE_RUN_FROM_PACKAGE Azure setting where our latest oynx deployment .zip package is mounted from /home/data/sitePackages to wwwroot (docs of how it should work). Our incident investigation found examples where that mounting-over-wwwroot failed..Microsoft are working on RCA why it failed. 09/07;A ticket has been raised with Microsoft in order to provide information about the request that was cached. (There is a concern that this could be time critical | Cloud Ops team | Tactical | NA | 2024-02-09 | Closed |  |  |  | Kavitha | 2025-02-10 | 463 | >60 | September | 2024 | #VALUE!
Customer Channels | Selling Experience | 90087203 | 2024-06-26 | Blank Home Page served to customers on desktop and mobile web | There was no significant order drop but it would be good to understand if there was any financial impac | Impact analysis | Jack Tye | 22/07: Jack confirmed that no order impact, therefore no financial impact- 17/07: Elaine has followed up and awaiting response | WCS | Tactical | NA | 22/07/24 | Closed |  |  |  | Kavitha | 2025-02-10 | 463 | >60 | July | 2024 | #VALUE!
Customer Channels | Selling Experience | 90087203 | 2024-06-26 | Blank Home Page served to customers on desktop and mobile web | Caching and header mitigations | Root cause | David Raine and Nigel Magnay | 15/08: Agreed that we would keep the HP origin max-age TTL header at 0 seconds as that helps find issues and no change is required 22/07: Investigations is still ongoing 16/07: David and Homepage team/Nigel will discuss and see if any additional protection can be put in place | Akamai | Tactical | NA | 15/08/24 | Closed |  |  |  | Kavitha | 2025-02-10 | 463 | >60 | August | 2024 | #VALUE!
Customer Channels | Selling Experience | 90087203 | 2024-06-26 | Blank Home Page served to customers on desktop and mobile web | Alerts to improved for the below scenarios 1 NR Synthetic alerting to be improved so that problems with the Home Page are identified. 2 Alerting for drop in traffic When caching was in place, there was not a lot of traffic at origin. Now caching has been reduced, alerts need to be set up to monitor traffic drops. Agreed that this will be done in Akamai (David) and also New Relic (Nigel) 3 David suggested that it would be useful to have visual integrity alerting on content that is not persoanlised e.g. Customer logo, header/footer etc. Nigel to investigate | Problem identification & Alerting | Syed Ibrahim Sulthan / David Raine /Nigel Magnay | 23/07: New Relic synthetic alert has been created for Akamai home page url. Jira back log has been created to configure the alerts for the other 2 scenarios to improve the alerting 16/07: Alerting to be improved | Akamai | Tactical | NA | 15/08/24 | Closed |  |  |  | Kavitha | 2025-02-10 | 463 | >60 | August | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90069233 | 2024-06-26 | Intermittent carrier label printing issues at C&H Bradford DC | Ensure the relevant flow diagram is available across the support teams to identify the critical systems involved in the flow and facilitate the root cause and recovery actions | Solution & Recovery | Vivek Kumar | 26/06: There is an existing flow diagram to highlight the different layer involved in the carrier label printing process – KNAPP WMS, Mule, Network VIP, Carrier Gateway & Sorted. | Service lead | Tactical | NA | 26/06/24 | Closed |  |  |  | Saloni | 2025-02-10 | 463 | >60 | June | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90069233 | 2024-06-26 | Intermittent carrier label printing issues at C&H Bradford DC | Agree with DC operations to inform relevant service leads to expedite the incident recovery and reduce MTTR | Issue handling/Management | Vivek Kumar | 08/07: Service lead Vivek has agreed with Bradford site operations to inform the oncall service lead during an issue/ 26/06: There were some initial delays in engaging Customer Tech teams as site operations had reached out to Sorted. Therefore, Vivek Kumar will agree with DC ops to ensure we are informed of the issue irrespective of the tech teams responsible for the cause. | Service lead | Tactical | NA | 2024-08-07 | Closed |  |  |  | Saloni | 2025-02-10 | 463 | >60 | July | 2024 | #VALUE!
Customer Channels | Service Experience | 90069233 | 2024-06-26 | Intermittent carrier label printing issues at C&H Bradford DC | Ensure the contact repository tool is updated with relevant contact details for Carrier Gateway team | Supplier and support involvement | Vijesh Mehta | 15/07: The contact details have been updated in contact repository 26/06: There were some challenges in identifying the correct support contact for Carrier Gateway as the details were not updated in Contact Repository. Teams are in process of updating the SPOC details. | Carrier Gateway | Tactical | NA | 15/07/24 | CLosed |  |  |  | Saloni | 2025-02-10 | 463 | >60 | July | 2024 | #VALUE!
GTS | Enterprise Integration | 90069233 | 2024-06-26 | Intermittent carrier label printing issues at C&H Bradford DC | Review the alerting mechanism in Mule and explore options to improve for proactive issue identification | Problem identification & Alerting | Sivasubramani Pappusamy | 12/09: Mule team have checked with their architects and confirmed that for WMS -> Sorted flows, as these are https calls and live calls, alerts in Mule layer is not feasible in New Relic environment as there will be multiple alerts receieved resulting in file system constraints in the software. However, once this is moved to Dynatrace, alerting will be enabled. This needs further exploring. In the interim, we have an alert set up in WMS when there are continous failures whilst reaching to Sorted for 10 mins - this will enable proactive issue identification. 31/07: Due to ongoing issues, the team are not performing any changes int the Mule layer. Therefore, this action has been kept lower in the priority as the incdent is less likely to recur. ETA : 31st August have been provided to complete this action. 26/06: For this flow, this is a live traffic flow configured from Mule into Carrier gateway aka, https flow. Therefore, the log file size is huge and there is no possibility to configure an alert at that level. However, the teams will explore the feasibility of creating a dashboard highlighting the number of successful and failed messages in Mule audit logs. Based on the dashboard creation, a threshold will be set on the number of failed messages followed by creation of an alert | Mule | Strategic | NA | 2024-12-09 | Closed |  |  |  | Saloni | 2025-02-10 | 463 | >60 | September | 2024 | #VALUE!
Customer Channels | Service Experience | 90069233 | 2024-06-26 | Intermittent carrier label printing issues at C&H Bradford DC | Review the alerting mechanism in Carrier Gateway and explore options to improve for proactive issue identification | Problem identification & Alerting | David Jose | There is an existing alert to highlight if there is no traffic flow in Carrier Gateway layer. However, as the issue was intermittent and albeit there were some successful traffic coming into Carrier Gateway, therefore, no alerts were triggered. | Carrier Gateway | Tactical | NA | 26/06/24 | Closed |  |  |  | Saloni | 2025-02-10 | 463 | >60 | June | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 90069233 | 2024-06-26 | Intermittent carrier label printing issues at C&H Bradford DC | Configure alerts in network layer to proactively identify issues with F5 health check failure. | Problem identification & Alerting | Kamalakkanan Kanniappan | 16/10: Alerting has been configured to identiy F5 health check failures. Non prod testing has confirmed that the alert configuration is successful 17/09: This is still pending and Suganya will get us an update 07/09: While the VIP goes Offline / health monitor is down. Alert has been created , need to do testing in non-prod f5 (Tentative :17 -Sep- 24) 08/08: Kamal has asked his team where we are with health check failure alerting – 26/08 as we are carrying out testing 07/09: While the VIP goes Offline / health monitor is down. Alert has been created , need to do testing in non-prod f5 (Tentative :15 -Sep- 24) 31/07: Due to multiple network related issues, Kamal had been focusing on mitigations., therefore, we still await updates. However, there had been no further occurrence of F5 health checks failures impacting critical applications. 12/07: There is no material update on the alert configuration to identify issues with F5 health check failures. We need further updates from 08/07 - Network team are working on creating the alert to identify issues with F5 health check failures - the correct thresholds need to be set and we are awaiting feedback from Kamal 26/06: Feasibility is being checked and it requires time. | Network | Tactical | NA | 16/10/24 | Closed |  |  |  | Saloni | 2025-02-10 | 463 | >60 | October | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 90069233 | 2024-06-26 | Intermittent carrier label printing issues at C&H Bradford DC | Identify the reason behind the 50-50 distribution of the Mule traffic on the network VIPs. | Root cause | Rajeshkumar Singarajan | 08/07: The split is 50/50 between prod and dr of azure not SP and SW. Kamal has advised thatroot cause is inconclusive. 26/06: Ideally, the Mule traffic is configured to connect to Carrier Gateway through network VIP in Stockley Park. If there are any issues with the SP VIP or it is unavailable, the traffic will be routed through the network VIP in Swindon. This needs further investigation. | Network | Tactical | NA | 2024-08-07 | Closed |  |  |  | Saloni | 2025-02-10 | 463 | >60 | July | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 90069233 | 2024-06-26 | Intermittent carrier label printing issues at C&H Bradford DC | Identify the root cause behind the health check failure on SP VIP which impacted the traffic flow between Mule and Carrier Gateway | Root cause | Rajeshkumar Singarajan | 08/07: Kamal has advised thatroot cause is inconclusive. 26/06: There is an existing investigation ongoing with Microsoft by reviewing additional packet capture logs to identify the root cause. | Network | Tactical | NA | 2024-08-07 | Closed |  |  |  | Saloni | 2025-02-10 | 463 | >60 | July | 2024 | #VALUE!
Group Platforms | Finance | 90073599 | 2024-06-24 | Czech Republic and Greece colleagues were unable to access e-SAP from the DC and Head office | What caused the change in file format on the host file? | Root cause | SAP Basis team | 15/07- We do not have sufficient logs to prove that the hosts file format was changed, and no manual change has been made in the hosts file by SAP Basis team in the eSAP DMZ router server on 17th June. Howeevr for the future re-occurence the file format will be checked as a step1 - and this is now added to the SOP aswell for reference 10/07 - This is being further investigated by Dinesh and team as Robert the key SME is on a long leave 24/06- The root cause for the change is file format remains inconclusive as the product team did not perform any recent changes at the server or application level. We suspect recent network changes which could have impacted the file format. SAP team will do final validations along with Network teams to ascertain the actual RCA | SAP Basis | Strategic | NA | 15/07/24 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 465 | >60 | July | 2024 | #VALUE!
GTS | Digital Workplace Services | 90073599 | 2024-06-24 | Czech Republic and Greece colleagues were unable to access e-SAP from the DC and Head office | What is the permanent fix? Can DMZ servers use the internal AD DNS for name resolution, is there a security risk? | Solution & Recovery | AD/NOC and cyber | Once we identified the file format issue, it was corrected and the DNS entries created on AD as a work around were removed for security compliance. | Active Directory | Tactical | NA | 24/06/24 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 465 | >60 | June | 2024 | #VALUE!
Group Platforms | Finance | 90073599 | 2024-06-24 | Czech Republic and Greece colleagues were unable to access e-SAP from the DC and Head office | Do we have the right alerting for the authentication failure in eSAP? | Problem identification & Alerting | Robert Kenndy/SAP Basis | 15/07 - Logs are captured in SAP router but alerting via the router logs is not possible as it is a on-prem server. 10/07 - WE wait udpdates from the SAP basis team 24/06- Logs are captured in SAP router but alerting via the router logs is a challenge. Teams will further explore for any feasible option on the alerting | SAP Basis | Tactical | NA | 15/07/24 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 465 | >60 | July | 2024 | #VALUE!
Group Platforms | Finance | 90073599 | 2024-06-24 | Czech Republic and Greece colleagues were unable to access e-SAP from the DC and Head office | Review and update the SOP to validate the file format whenever we see an authentication issue within the application | Solution & Recovery | SAP Basis | 11/07 -SOP has been updated to check on the file format as well whenever we see a similar issue in future and the remediations steps are also captured. 24/06- We identified the incorrect file format issue only during our root cause investigations. The product team have been asked to update/amend their SOP to validate the file format. | SAP Basis | Tactical | NA | 2024-10-07 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 465 | >60 | July | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90073503 | 2024-06-20 | Issues with hanging operations at Castle Donington | Identify any critical tables that requires gather instead of manually performing gather stats for individual database schemas (a combination of tables) to reduce the recovery time. | Problem avoidance | Kunal Chichkar | 20/06: We already have a daily job scheduled at 18:00 to execute gather stats on the critical tables. | WMS | Strategic | NA | 20/06/24 | Closed |  |  |  | Kavitha | 2025-02-10 | 469 | >60 | June | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90073503 | 2024-06-20 | Issues with hanging operations at Castle Donington | Create a SOP to document the recovery steps performed to resolve the issue. | Solution & Recovery | Kunal Chichkar | 22/06: SOP has been documeted to recover this issue quicker in future | WMS | Tactical | NA | 22/06/24 | Closed |  |  |  | Kavitha | 2025-02-10 | 469 | >60 | June | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90073503 | 2024-06-20 | Issues with hanging operations at Castle Donington | Review the threshold of the existing alerts for both hanging and boxed queue | Problem identification & Alerting | Kunal Chichkar / Pavankumar Chikkeri Nagaraj, | 12/07: Alerting have been reviewed and configured 22/06: A Critical alert for message pile is already configured by the integration services team based on message age as well as message pile up count. However the threshold for these reviewed. | WMS | Tactical | NA | 2024-12-07 | Closed |  |  |  | Kavitha | 2025-02-10 | 469 | >60 | July | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90073503 | 2024-06-20 | Issues with hanging operations at Castle Donington | Why did the database stats go to stale status? | Root cause | Kunal Chichkar | 22/06: Team reveiwed the AWR report and identified a QL ID for the session which processes WCS to WMS messages for hanging queue.This SQL ID had few execution plans present in database and DB was switching the plans regularly causing performance degradation. Team now identified a best execution plan and have pinned the profile which will stop switching of execution plan | WMS | Tactical | NA | 22/06/24 | Closed |  |  |  | Kavitha | 2025-02-10 | 469 | >60 | June | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 90059839 | 2024-06-19 | Czech Republic colleagues are unable to access e-SAP from the DC and Head office | Validate the resilience configuration for other critical VPN connection serving through the secondary DIA circuit. | Problem avoidance | Kamalakkan Kanniappan | 08/07: Everything has now been reviewed with Vodafone and the secondary DIA has been appropriately configured. 19/06: This is a long term action. Speak to Kamal if a JIRA backlog can be raised | Network | Strategic | NA | 2024-08-07 | Closed |  |  |  | Saloni | 2025-02-10 | 470 | >60 | July | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 90059839 | 2024-06-19 | Czech Republic colleagues are unable to access e-SAP from the DC and Head office | Agree with Czech stakeholders to ensure resilient links are configured to mitigate impact | Problem avoidance | Kamalakkan Kanniappan | 12/12: Closed with backlog NETSEC-2049 14/11: Czech is now on FGT and Suganya to check/or provide backlog 17/09: Once we move to FGT we can configure resiliance. This is being planned. 05/09: Czech is currently running with PA On-Prem Active-Active setup in Stockley Park. We are aiming to migrate from PA to FGT cloud by 15th Sept. 08/08: Kamal to follow up with his team 08/07: Discussed with Kamal and this task has not been started yet. 19/06: Kamal will discuss with Jan Kadlec (Czech Tech colleague) to derive a plan. | Network | Strategic | NA | 2024-12-12 | Closed |  | NETSEC-2049 |  | Rehan | 2025-02-10 | 470 | >60 | December | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 90059839 | 2024-06-19 | Czech Republic colleagues are unable to access e-SAP from the DC and Head office | Agree with business stakeholders to perform regular failover testing of critical DIA links before PEAK. | Problem avoidance | Kamalakkan Kanniappan | 08/08 – This activity has now been added to continuous improvement as part peak priorities. 08/07: Failover testing to be completed before peak. 19/06: An exercise will be performed after discussing with business to perform regular failover testing to ensure the network configuration between primary and secondary network links are inline | Network | Strategic | NA | 2024-08-08 | Closed |  |  |  | Rehan | 2025-02-10 | 470 | >60 | August | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 90059839 | 2024-06-19 | Czech Republic colleagues are unable to access e-SAP from the DC and Head office | Agree on a periodical review of network configuration to ensure alignment between primary and secondary DIA links | Problem avoidance | Kamalakkan Kanniappan & Vodafone | 08/08: Kamal advised that this action was to be noted for document purpose only and Kamal has recorded this and will regularly work with VF 08/07: Full review of confgs across estate to be completed before peak. 19/06: Customer network team and Vodafone will jointly agree on the frequently to review the network configuration to avoid any further issues. | Network | Strategic | NA | 2024-08-08 | Closed |  |  |  | Rehan | 2025-02-10 | 470 | >60 | August | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 90059839 | 2024-06-19 | Czech Republic colleagues are unable to access e-SAP from the DC and Head office | Did we receive an alert indicating that the Czech tunnels were unavailable. Review the process of improving alert handling to identify the issue proactively. | Problem identification & Alerting | Kamalakkan Kanniappan | 08/07: Network team have agreed to validate the tunnels as a post validation step after any activity as alerts are configured and working. 19/06: During the failover activity, multiple alerts were received in the network layer. As per process, Network team had manually acknowledged the alerts and once the failover activity was completed, the relevant alerts were automatically closed. There was an alert triggered indicating that the Czech VPN tunnel was in unavailable state, this was missed by the team whilst handling multiple alerts and existing troubleshooting activities, and therefore, the issue was not identified proactively. It has been agreed to include additional steps to validate that the relevant services are running without any issues after a failover activity. | Network | Tactical | NA | 2024-08-07 | Closed |  |  |  | Saloni | 2025-02-10 | 470 | >60 | July | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 90059839 | 2024-06-19 | Czech Republic colleagues are unable to access e-SAP from the DC and Head office | What caused the IP addresses to go missing after the failover activity for the Czech tunnels | Root cause | Kamalakkan Kanniappan | 19/06: It has been confirmed that after the migration from Palo Alto to FortiGate, there are multiple changes in network configuration introduced in the internet circuits. As there is no practice of comparing the network configuration (IP address) between the primary and secondary DIA circuits before a failover activity, the relevant IP addresses went missing in the secondary DIA circuit | Network | Tactical | NA | 19/06/24 | Closed |  |  |  | Saloni | 2025-02-10 | 470 | >60 | June | 2024 | #VALUE!
Group Platforms | Finance | 90058950 | 2024-06-18 | MP (Merchandise Planning) application was unavailable due to stock data discrepancy | Conduct a workshop to ensure product teams have the required knowledge on the ignio process. | Problem avoidance | Rhamya and Souwmiya | 23/07 - Workshopd has been conducted for a brain storming session for the engineers in the team - the best practices Whilst planning for large activities/migrations and also to ensure there is enough buffer time for job related activites. 15/07 - A Workshop has been planned for 19/07. 25/06- Workshop will be planned this week - spoke to Ramya today 18/06 - The team is planning a workshop to ensure all team member use Ignio for job release and hold and check how efficiently it can be used – Whilst planning for large activities/migrations and also to ensure there is enough buffer time for job related activites – This should be reflected in change implementation plan. | SAP- GMOR | Tactical | NA | 23/07/24 | Closed | NA | NA | NA | Pavithra | 2025-02-10 | 471 | >60 | July | 2024 | #VALUE!
Group Platforms | Finance | 90058950 | 2024-06-18 | MP (Merchandise Planning) application was unavailable due to stock data discrepancy | Review and enhance the SOP/document | Solution & Recovery | Rhamya/Murali | 02/07 - The SOP has been updated rightly with the incident scenario's, workarounds and recovery actions etc. 25/06 - SAP GMOR team is currently working on the Quanterly planning - this action will be handled 18/06 - List the possible incident scenarios in GMOR and their respective workarounds and then these needs to be documented/updated in a common place for future references | SAP- GMOR | Tactical | NA | 2024-02-07 | Closed | NA | NA | NA | Pavithra | 2025-02-10 | 471 | >60 | July | 2024 | #VALUE!
C&H and Intl | C&H Commercial Trading | 90058950 | 2024-06-18 | MP (Merchandise Planning) application was unavailable due to stock data discrepancy | Ensure we have the right stakeholder contact for MP application for effective communication | Issue handling/Management | Ashok | 18/06: It has been agreed to contact the below two POC’s for any critical decisions on MP applications. POC : Hellen Morris; Hellen Edwards – They are the right stakeholders from the planning team | Service Lead | Tactical | NA | 18/06/24 | Closed | NA | NA | NA | Pavithra | 2025-02-10 | 471 | >60 | June | 2024 | #VALUE!
Group Platforms | Finance | 90058950 | 2024-06-18 | MP (Merchandise Planning) application was unavailable due to stock data discrepancy | Enable extra hypercare for touch point data after any activites | Problem avoidance | Rhamya/Murali | 02/07 - Going forward additional checks will be performed on the data touch points and the team has been communicated on the same. 25/06 -SAP GMOR team is currently working on the Quanterly planning - However this will be taken with the team by End of this week 18/06: During any major activities like Csap migration or any SAP related activity, it has been agreed with GMOR SAP team to perform additional validations on the complete data availability and to ensure data integrity within the GMOR layer – This should be updated in the change implementation plan. This needs to be confirmed with the GMOR teams that it has been cascaded. | SAP- GMOR | Tactical | NA | 2024-02-07 | Closed | NA | NA | NA | Pavithra | 2025-02-10 | 471 | >60 | July | 2024 | #VALUE!
Customer Channels | Service Experience | 90051798 | 2024-06-17 | Issues with gift card transactions at store tills | Multiple Pagerduty alerts were received in the SVS layer indicating that is no traffic flow into SVS from POS at 08:42. Review the integration between PagerDuty and Remedy to confirm whether an incident was created and what severity was it defined? | Problem identification & Alerting | Balaji Jaganathan | 11/07: Tech teams have confirmed that there were incidents created in remedy for all the alerts that were triggered: INC000090053602 and INC000090053175 17/06: Awaiting further updates. | SVS | Tactical | NA | 2024-11-07 | Closed |  |  |  | Saloni | 2025-02-10 | 472 | >60 | July | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 90051798 | 2024-06-17 | Issues with gift card transactions at store tills | Review the list of other networks F5 load balancer connecting to Cloud AKS cluster in the estate. | Problem avoidance | Kamalakkan Kanniappan | 08/08: Kamal has the list so we can close. 08/07: Network team is already having the list of other critical F5s and the relevant application details. Awaiting the list from Kamal 17/06: Network team will provide a list of other network VIPs which could potentially get impacted to avoid any recurrence. | Network | Strategic | NA | 2024-08-08 | Closed |  |  |  | Saloni | 2025-02-10 | 472 | >60 | August | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 90051798 | 2024-06-17 | Issues with gift card transactions at store tills | Configure alerts in network layer to proactively identify issues with F5 health check failure. | Problem identification & Alerting | Kamalakkan Kanniappan | 08/08: Cancelled as this is a duplicate of action in row 156 31/07: Due to multiple network related issues, Kamal had been focusing on mitigations., therefore, we still await updates. However, there had been no further occurrence of F5 health checks failures impacting critical applications. 08/07 - Network team are working on creating the alert to identify issues with F5 health check failures - the correct thresholds need to be set and we are awaiting feedback from Kamal 17/06: Feasibility is being checked and it requires time. This action will be dealt with once the root cause is ascertained. | Network | Tactical | NA | 2024-08-08 | Closed |  |  |  | Saloni | 2025-02-10 | 472 | >60 | August | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 90051798 | 2024-06-17 | Issues with gift card transactions at store tills | Root cause behind the F5 health check failure whilst connecting to the application health endpoint | Root cause | Kamalakkanan Kanniappan/ Prasanh Rowlo | 19/02: The root cause could not be determined due to its one off nature and lack of logs. It has been agreed to enable logging if the issue recurs. Therefore, this is being closed 07/10: It has been confirmed that further root cause analysis will be performed after the Golden Quarter. 16/09: We got into a call with Network and SVS business teams and we have partially agreed to perform the failover of retail gift card traffic to Stockley Park with TCP check enabled after store closure. A follow up call will be scheduled between Network and app team to walkthrough the plan. This change will be performed through a change management process and testing will be performed using the test tills to avoid impact. 10/09: MIM and Network team had a call and it is evident that the RCA cannot be done prior to Golden Quarter. However, to ensure resilience, a decision will be taken to failover the SVS traffic to Stockley park with basic check enabled as the issue still exists in SP. A call has been scheduled with Kamal and Customer business teams on 16th Sep. 05/09: An internal call scheduled on Sept 9th for discussion & next action plan. Saloni has spoken to Kamal on 10th Sep, and he will provide his availability to schedule a call with Cloud team. 08/08: Kamal says its concerning as we are still running the retail gift card service from Swindon and we need the root cause, he will follow up with his team 31/07: Due to multiple network related issues, Kamal had been focusing on mitigations., therefore, we still await updates. However, there had been no further occurrence of F5 health checks failures impacting critical applications. 15/07: The root cause investigation is still in progress. 08/07: Network and Cloud team are working with Microsoft and performing multiple triaging actions to identify the root cause. Spoke with Kamal and investigations are ongoing. 17/06: An activity was performed on 18/06 to test the Stockley Park F5 health check connection to the Cluster health end point without introducing into production. The issue still exists, and we will agree on further actions on 19th June and if required a case was raised with Microsoft. | Network/ Cloud Ops | Tactical | NA | 19/02/25 | Closed |  |  |  | Saloni | 2025-02-10 | 472 | >60 | February | 2025 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90043777 | 2024-06-14 | Issues with Hanging operations at Castle Donington DC | Review the hotfix developed to allow additional log capture as part of Hanging Optimisation project to fix the Hanging sorter issue. | Permanent Fix | Murali Nasapu/SSI Schaefer | 02/07 - Backlog Id has been shared - Q2 -JDATE-10370 25/06 - Awaiting backlog ID from Murali Nasapu 14/06 - As part of this incident, the hotfix was removed to restore services. There is an ongoing analysis to identify the issue from the logs captured and SSI was able to replicate the issue. Once the issue is identified, SSI will develop a new fix as part of the project. Awaiting the Product backlog id. | Service lead - CD | Tactical | NA | 2024-02-07 | Closed | NA | JDATE-10370 | NA | Pavithra | 2025-02-10 | 475 | >60 | July | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90043777 | 2024-06-14 | Issues with Hanging operations at Castle Donington DC | Identify why the hotfix had resulted in memory constraint in the WCS layer | Root cause | Sabrina Muntean | As part of this incident, the hotfix was removed to restore services. There is an ongoing analysis to identify the issue from the logs captured and SSI was able to replicate the issue. Once the issue is identified, SSI will develop a new fix as part of the project. Awaiting the Product backlog id. | SSI Schaefer | Tactical | NA | 2024-11-06 | Closed | NA | NA | NA | Pavithra | 2025-02-10 | 475 | >60 | June | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90043777 | 2024-06-14 | Issues with Hanging operations at Castle Donington DC | Follow the standard change management process with appropriate documentation and highlight the risk of incapable test regions | Solution & Recovery | Murali Nasapu | The hotfix implemented on 23rd May did not follow the standard change management process and therefore, no change request was raised. It has been agreed that going forward all changes will need to undergo the usual CAB process through a formal change request. | Service lead - CD | Tactical | NA | 2024-11-06 | Closed | NA | NA | NA | Pavithra | 2025-02-10 | 475 | >60 | June | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90043777 | 2024-06-14 | Issues with Hanging operations at Castle Donington DC | Are there any proactive alerts configured to identify the memory issue? | Problem identification & Alerting | Murali Nasapu | 30/07 - Additional alerting has been set-up to identify the memory issue. 25/06 - Awaiting response from Murali Nasapu 14/06 - as the infrastructure on which WCS application is hosted is under TCS scope, we have agreed to liaise with the Linux team to configure alerts on the WCS application server, to identify memory issues proactively. | Service lead - CD | Tactical | NA | 30/07/24 | Closed | NA | NA | NA | Pavithra | 2025-02-10 | 475 | >60 | July | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 90062069 | 2024-06-14 | Secondary (active) network firewall in Stockley Park was unavailable | Create a document highlighting the impact statement during such firewall issues | Impact analysis | Kamalakkan Kanniappan | 31/07: This action is not achievable through the product teams as there is no E2E architectural diagram across the estate. Therefore, this is more of a strategic actions and needs to be tracked under leadership. 08/07: Kamal advised that the application teams need to provide their end to end flows of infrastructure. Only then can NOC team know how the appication is served via the different firewalls. 14/06: We have agreed with Network team to provide the list of critical applications that they refer during a firewall change etc to ensure a clear understanding of the impact and appropriate communication to stakeholders. Once provided, MIM team to integrate this into AIM tool for future references. | Network | Strategic | NA | 31/07/24 | Closed |  |  |  | Saloni | 2025-02-10 | 475 | >60 | July | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 90062069 | 2024-06-14 | Secondary (active) network firewall in Stockley Park was unavailable | Did we receive an alert when the active firewall went into hung state | Problem identification & Alerting | Kamalakkan Kanniappan | 31/07: We have confirmed that an email was receivied systemically. 08/07: Kamal to confirm if the email alert has been integrated into netcool. 14/06: As the active firewall was in hung state but reachable, no alerts were triggered. The issue was identified whilst proactively monitoring the firewall debugging purposes for a separate issue. It has been confirmed that there are existing DNS IP ping alerts configured which triggers an email alert when there is an issue with internet services connecting through SP. There is a defined threshold set beyond which an alert gets triggered. We have agreed with Network team to integrate this email alert into Netcool to avoid any manual intervention. We are also awaiting details on the threshold set for this alert. | Network | Tactical | NA | 31/07/24 | Closed |  |  |  | Saloni | 2025-02-10 | 475 | >60 | July | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 90062069 | 2024-06-14 | Secondary (active) network firewall in Stockley Park was unavailable | Follow up with Fortinet to identify why the debug command had resulted in a spike in CPU utilisation in active firewall | Root cause | Kamalakkan Kanniappan | 18/07: We have confirmed with Fortinet that Whenever a new configuration change or any type of update package is received in the FortiGate, the OS will signal the IPS engine to always ‘reload’ the engine configuration. In some cases, this engine configuration reload is absolutely necessary (e.g. if rule is added/deleted). However, in the case of Malicious URL DB or a FortiSandbox Block list change, this reload is not required. In circumstances where number of sessions is large, and/or when the firewall is processing many policies; and/or when configuration changes or AV/FSA update is too frequent – this can cause the IPS engine to become unnecessarily loaded, resulting in an observable CPU ‘spike’. At times this CPU spike would result in traffic ‘dropping’, or IPS engine crashes. 08/07: We are no longer running debugs. Investigations continue with the more recent spike issue (July) 14/06: Investigations are underway with vendor Fortinet | Network | Tactical | NA | 18/07/24 | Closed |  |  |  | Saloni | 2025-02-10 | 475 | >60 | July | 2024 | #VALUE!
Foods | Foods Supply Chain | 90049399 | 2024-06-11 | Under allocation of foods ambient orders at Bradford and Milton Keynes DCs | Identify what caused the issue with Gzipping in Quantum | Root cause | Shravan | 25/06 - We belive that as the data fix files and the network schedule file was processed at the same time - the supply chain file might have got corrupted. We are unable to prove this but this is the closest probable scenario. 11/06 - The actual root cause on what caused the issue is Gzipping is uncertain as issue is not static and no error logs observed. However, it has been agreed to check on the historical data on the last re-occurrence of any related problem to ascertain the cause. | Foods | Tactical | NA | 25/06/24 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 478 | >60 | June | 2024 | #VALUE!
Foods | Foods Supply Chain | 90049399 | 2024-06-11 | Under allocation of foods ambient orders at Bradford and Milton Keynes DCs | Do we have the right alerting to identify the data discrepancy in the source file (Relex/Quantum) ? | Problem identification & Alerting | Foods | 10/05 - The Script is deplyed and it is into production working as expected 25/06 - A Script is being deployed to perform the recon to identify the data discrepancy between SCRD and Quantum. -ETA - 30th June 11/06 -We have the right alerting between SCRD and Quantum. However since the Gzipping issue happened at a file processing level, it wasn’t captured. A Script is being deployed to identify the data discrepancy - Approx ETA for completion - 30th June | Foods | Tactical | NA | 2024-10-07 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 478 | >60 | July | 2024 | #VALUE!
Foods | Foods Supply Chain | 90049399 | 2024-06-11 | Under allocation of foods ambient orders at Bradford and Milton Keynes DCs | Configure alerts to notify Gzipping/file formatting issues within Quantum before loading the file into the database | Problem identification & Alerting | Sharvan/Naveen | A Script will be developed to compare the gzip file with the original archive file for extra validation in Quantum - in the interim we have manual hypercare in place to compare and validate the order volumes | Foods | Tactical | NA | 2024-11-06 | Closed | NA | Backlog created- FSORP-21256 | NA | Saloni | 2025-02-10 | 478 | >60 | June | 2024 | #VALUE!
Foods | Foods Supply Chain | 90049399 | 2024-06-11 | Under allocation of foods ambient orders at Bradford and Milton Keynes DCs | Do we have the right overnight monitoring/Hypercare in place for the order allocations? | Problem identification & Alerting | Quantum team | We have a recon between ASO & WMS. When there is a change in order volume – A threshold validation will be done on the variance and sev1 will be raised immediately if there are any discrepancy. Support engineers are aligned with the process. Note: As we are aiming to migrate Quantum orders into Relex by Sep’24, We may see some discrepancy with the order volume in Q. Additional checks are agreed within the team, to address the scenario | Foods | Tactical | NA | 2024-11-06 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 478 | >60 | June | 2024 | #VALUE!
Foods | Foods Supply Chain | 90049399 | 2024-06-11 | Under allocation of foods ambient orders at Bradford and Milton Keynes DCs | Agree a process to invoke contingency during a major incident scenario | Issue handling/Management | Promoth Kumar | We have the right process in place to decide on contingency. Once the Service leads or SME’s are planning to invoke contingency an approval will be secured from Daniel Maddox /Terrance Banyard | Foods | Tactical | NA | 2024-11-06 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 478 | >60 | June | 2024 | #VALUE!
Foods | Foods Supply Chain | 90049399 | 2024-06-11 | Under allocation of foods ambient orders at Bradford and Milton Keynes DCs | Review the efficient ways to address the duplicate PO scenario | Problem avoidance | Quantum team | It has been agreed with the team to ensure extra validations are performed before re-triggering the data from source (Quantum/ Relex). Lessons learnt and this step will be documented for future benefit aswell. | Foods | Tactical | NA | 2024-11-06 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 478 | >60 | June | 2024 | #VALUE!
Foods | Foods Supply Chain | 90049399 | 2024-06-11 | Under allocation of foods ambient orders at Bradford and Milton Keynes DCs | Build a report with ASO/WMS for product and line level reconciliation. | Problem avoidance | Foods | This action is being tracked via another Sev1 PIR “90046807 - Bradford Food Overallocation” | Foods | Tactical | NA | 2024-11-06 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 478 | >60 | June | 2024 | #VALUE!
Foods | Foods Supply Chain | 90046807 | 2024-06-10 | Bradford ambient DC was unable to pick due to over allocation in WMS | Alerting is in place and the issue here happened after the checks that are in place – in Relex they did spot the overallocation. Review with foods and WMS actions that are carried out once an issue is spotted. | Problem identification & Alerting | Vinoth Purushothaman | 17/06: Alerts are in place for failures and SOPs are updated. No further action needed. As part of action to create a new dashboard, new Sev-1 alert will be configured to notify the users for mismatches in the data between ASO & WMS. No further action needed on this action and it can be closed. | Foods | Tactical | NA | 17/06/24 | Closed |  |  |  | Saloni | 2025-02-10 | 479 | >60 | June | 2024 | #VALUE!
Foods | Foods Supply Chain | 90046807 | 2024-06-10 | Bradford ambient DC was unable to pick due to over allocation in WMS | Investigate whether the JAXB initialisation error has been caused by the change (ALCS upgrade to JAVA 17 from JAVA 11) – pause further upgrades until he cause is established. | Root cause | Vinoth Purushothaman | 16/07: Anbarasi advised the fix has been deployed (last week) and is working. 17/06: Team working on the fix and it is planned to deploy before 5th Jul. Jira Link : FSCLT1-5457 14/06: Plan is to schedule a call with Vinoth and co to get progress updates on all these actions | Foods | Tactical | NA | 16/07/24 | Closed |  | FSCLT1-5457 |  | Saloni | 2025-02-10 | 479 | >60 | July | 2024 | #VALUE!
Foods | Foods Supply Chain | 90046807 | 2024-06-10 | Bradford ambient DC was unable to pick due to over allocation in WMS | Update the recovery SOP to handle the JAXB initialisation error. | Solution & Recovery | Vinoth Purushothaman | 16/07: SOP has been updated and the team has been eduacted to know which end point has tO be triggered. 17/06: In Progress. SOP will be updated along with the change planned on JAXB code fix. Jira Link : FSCLT1-5457 ETA – 5th Jul 14/06: Plan is to schedule a call with Vinoth and co to get progress updates on all these actions | Foods | Tactical | NA | 16/07/24 | Closed |  | FSCLT1-5457 |  | Saloni | 2025-02-10 | 479 | >60 | July | 2024 | #VALUE!
Foods | Foods Supply Chain | 90046807 | 2024-06-10 | Bradford ambient DC was unable to pick due to over allocation in WMS | We have the NDC ambient dashboard which we use for daily checks to compare ASO/WMS - this is not working in PROD and an incident is open due to a middleware issue | Problem identification & Alerting | Vinoth Purushothaman | 13/08: NDC Dashboard is working fine for lines count and singles count. We can close this action 18/07: ASO/WMS have compeleted the work on this but still it is not reflecting properly due to server issues, teams are chasing WINTEL, other teams for the same 16/07: Anbarasi has a back log for creating alert and the team is working on creating the alert. ETA is August. 20/06: Aso and wms working on creating the alert mechanism to get the alert for any count mismatch between aso and wms after Q and relex order completion. Work is in progress, however, manual hypercare is in place. 17/06: New report is planned to build and it will be tracked under FSCLT1-5471. Due to issues in on-prem server and it is part of SP exit, existing dashboard will not be used. This action is critical therefore, will be tracked until completion. 14/06: Plan is to schedule a call with Vinoth and co to get progress updates on all these actions | Foods | Tactical | NA | 13/08/24 | Closed |  |  |  | Saloni | 2025-02-10 | 479 | >60 | August | 2024 | #VALUE!
Foods | Foods Supply Chain | 90046807 | 2024-06-10 | Bradford ambient DC was unable to pick due to over allocation in WMS | Build a report with ASO/WMS for product and line level reconciliation. If there is a mis-match we can quickly ascertain where the mismatch is with specific product and line – this will help with a much timelier impact assessment and creation of a specific recovery plan – plan timelines or provide a backlog. | Impact analysis | Puviyarasu/Shahul Hameed | 12/11: This dashboard is now complete and is available for use, if there is any mismatch, PCM and support will get an alert and they can take the necessary next steps. 31/10: WMS team have confirmed that their work is completed with the report configuration. There is a plan to introduce the report in prod by ASO team by next week. ETA: 08/11 08/10: ASO and WMS teams have completed the development work for the reconciliation report and we aim to implement by 22/10. 10/09: From ASO pre-requisite work has been done and now further effort is needed from WMS team 20/08: Work is in progress , ETA is october 2024. Created new Feature for this work FSCLT1-5574 now to track. 18/07: FSCLT1-5471 is created and it will be picked in Sprint 3 and 4, ETA Aug'24 16/07: From ASO and WMS side the dashboard is working properly. Team is now working on the reconciliation report. 17/06: New report is planned to build and it will be tracked under. FSCLT1-5471 ETA – by end Jul’24 14/06: Plan is to schedule a call with Vinoth and co to get progress updates on all these actions | Foods | Strategic | NA | 2024-12-11 | Closed |  | FSCLT1-5574 |  | Saloni | 2025-02-10 | 479 | >60 | November | 2024 | #VALUE!
Foods | Foods Supply Chain | 90046807 | 2024-06-10 | Bradford ambient DC was unable to pick due to over allocation in WMS | If any dips/increases are spotted in the allocation, check with operations what the threshold should be before we need to be concerned so we can prioritise our recovery. | Issue handling/Management | Tamil/Puviyarasu | 08/10: Puvi to provide backlog number FSCLT1-5837 16/07: Teams required NGFOA team to set this once the team has rolled out everything to relex within November.We are discussing with Architect on the same( Relex have the contigency order proposal file to compare with the actual allocation and trigger alert). Awaiting a backlog 17/06: Teams are in discussion with In Progress with Logistic users, and business to identify the mismatch threshold to define the criticality of the incident 14/06: Plan is to schedule a call with Vinoth and co to get progress updates on all these actions | Foods | STrategic | NA | 2024-08-10 | closed |  |  |  | Saloni | 2025-02-10 | 479 | >60 | October | 2024 | #VALUE!
Foods | Foods Supply Chain | 90046807 | 2024-06-10 | Bradford ambient DC was unable to pick due to over allocation in WMS | Analyse whether any upstream automated reconciliations we can do so that we can spot potential issues much earlier in the flow - plan timelines or provide a backlog. | Problem identification & Alerting | Tamil/Puviyarasu | 08/10: The upstream reconciliation report will be created after rolling out all NDC orders to Relex only. Backlog: FSCLT1-5837 18/07: Q functionality will not be required in future as Ambient rollout will be completed. We need backlog id or a tentative ETA for the decommission. There is a manual reconciliation/hypercare done on a daily basis to identify issues. 16/07: We are awaiting for Quantum decommission and once we move fully to Relex the reconciliantion can be done. Puvi is going to start the conversation with the architects this week. 17/06: A further discussion needs to happen with Solution architects to develop automatic reconciliations 14/06: Plan is to schedule a call with Vinoth and co to get progress updates on all these actions | Foods | Strategic | NA | 2024-08-10 | Closed |  | FSCLT1-5636 |  | Saloni | 2025-02-10 | 479 | >60 | October | 2024 | #VALUE!
Foods | Foods Supply Chain | 90046807 | 2024-06-10 | Bradford ambient DC was unable to pick due to over allocation in WMS | We don’t have a backup facility to manage the picking in WMS – we are building this - provide a backlog. | Solution & Recovery | Jaychandran Krishna | 17/06: It is part of GLASS NDA program and Backlog details cant be shared. This can be taken out of this PIR action list. 14/06: Plan is to schedule a call with Vinoth and co to get progress updates on all these actions | Foods | Strategic | NA | 17/06/24 | Closed |  |  |  | Saloni | 2025-02-10 | 479 | >60 | June | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 90033215 | 2024-06-07 | Unplanned power outage at Castle Donington DC | Actions to be agreed to raise a risk | Root cause | Mark Davies | 21/08: A risk has been raised - 1596187411 | CD IT | Strategic | NA | 21/08/24 | Closed | 1596187411 |  |  | Rehan/Kavitha | 2025-02-10 | 482 | >60 | August | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 90042330 | 2024-06-05 | 35 BP stores unable to access Customer applications on honeywells | Going forward, segregate any future deployments and target only stores that are relevant. | Problem avoidance | Rav Dale | 27/06: The team to ensure that any future deployments are only targeted as per the rollout. | TPM - Platform & Store Ops | Strategic | NA | 27/06/24 | Closed |  |  |  | Saloni | 2025-02-10 | 484 | >60 | June | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 90042330 | 2024-06-05 | 35 BP stores unable to access Customer applications on honeywells | Go back to Honeywell and ask if 5ghz is disabled in the config why was it deployed as enabled | Root cause | Rav Dale | 27/06: We have used the same honeywell utility for a number of years to generate our configuration, various device level settings have keys which are either set to certain values, or they could be set to enabled or disabled. The config file deployed as part of this change was set as : 5Ghz - Disabled, however, when deployed for other config settings, this WIFI 5Ghz setting was applied (you would only expect this to happen when set to enabled). Since this issue we have questioned the Honeywell team about why this occurred, they have now advised us that we should no longer be using this utility as it is old, and advised us to use another utility to set our config, we were frustrated we were not informed by Honeywell that we should not to use the old utility until after the issue. With the new utility, a configuration setting can only applied as enabled, therefore, there is no longer the option for disabled, and this type of issue will no longer occur. | TPM - Platform & Store Ops | Tactical | NA | 2024-01-07 | Closed |  |  |  | Saloni | 2025-02-10 | 484 | >60 | July | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 90042330 | 2024-06-05 | 35 BP stores unable to access Customer applications on honeywells | Going forward – a different mechanism will be used where we wont have values set to disabled, we just won’t have the value. | Problem avoidance | NOTE | 05/06: Agreed on the call that different mechanism will be used where we wont have values set to disabled, we just won’t have the value. | TPM - Platform & Store Ops | Tactical | NA | 2024-05-06 | Closed |  |  |  | Saloni | 2025-02-10 | 484 | >60 | June | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 90042330 | 2024-06-05 | 35 BP stores unable to access Customer applications on honeywells | NOC to check switch and router up times to see if there was a separate fault or did stores restart their routers to resolve the honeywell issue? | Root Cause | Rajesh | 01/07: Considering the reboots done for the routers, there won’t be enough logs available to validate this from network end. | Network | Tactical | NA | 2024-01-07 | Closed |  |  |  | Saloni | 2025-02-10 | 484 | >60 | July | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 90042330 | 2024-06-05 | 35 BP stores unable to access Customer applications on honeywells | WhSmith was covered in the fix’s 5ghz enablement at AP level – Nick to be given a list of WHS store by Rav to check the status of each store to assess if any clean up needs to be done. | Permanent Fix | Nick Baldwin | 01/07: Team validated and confirmed that the Whsmith stores have 5Ghz configs 27/06: Details have been shared with Store infra, Awaiting updates from Infra to share the back log details so that team can validated and perform the cleanup as part of the product backlog. | Network | Tactical | NA | 2024-01-07 | Closed |  |  |  | Saloni | 2025-02-10 | 484 | >60 | July | 2024 | #VALUE!
GTS | ETP- Cloud operations / Frameworks | 90035888 | 2024-06-03 | Store user manager application issue | Divide the vulnerability list Qualys to prod and non prod after downloading – can we ask qualiys to divide the non prod and prod before we get it Prasant – talk to Chintan | Problem avoidance | Prasanth Rowlo | 17/07 - Prasanth has advised that after in depth analysis - this will not be possible 25/06 - Prasnath has said that it is not possible to divide it ourselves but we need to check with Qualys | Cloud Ops |  | NA | 17/07/24 | Closed |  |  |  | Rehan | 2025-02-10 | 486 | >60 | July | 2024 | #VALUE!
GTS | ETP- Cloud operations / Frameworks | 90035888 | 2024-06-03 | Store user manager application issue | Explore if we can modify the non-prod script to reject any prod servers | Problem avoidance | Prasanth Rowlo | 17/07 - Prasanth has advised that after in depth analysis - this will not be possible 25/6 - This is in progress to see if this is possible | Cloud Ops |  | NA | 17/07/24 | Closed |  |  |  | Rehan | 2025-02-10 | 486 | >60 | July | 2024 | #VALUE!
GTS | Digital Workplace Services | 90035888 | 2024-06-03 | Store user manager application issue | Implemented compulsory peer to peer review process, so we can continuing with remediations immediately | Problem avoidance | All | 16/06 - This has been implemented. | DWS |  | NA | 16/06/24 | Closed |  |  |  | Rehan | 2025-02-10 | 486 | >60 | June | 2024 | #VALUE!
GTS | Digital Workplace Services | 90035888 | 2024-06-03 | Store user manager application issue | Revisit targeted communication DL’s for prod deployments | Business & IT Communication | Prasanth Rowlo | 25/06 - Prasanth advises that we have reviewed the DL list | Cloud Ops |  | NA | 25/06/24 | Closed |  |  |  | Rehan | 2025-02-10 | 486 | >60 | June | 2024 | #VALUE!
GTS | Digital Workplace Services | 90035888 | 2024-06-03 | Store user manager application issue | Check if we can expire the PIM connection once engineer has finished his work | Problem avoidance | Prasant Rowlo | 25/06 - Prasnath has said that it is not possible to expire the PIM. | Cloud Ops |  | NA | 25/06/24 | Closed |  |  |  | Rehan | 2025-02-10 | 486 | >60 | June | 2024 | #VALUE!
GTS | Digital Workplace Services | 90035888 | 2024-06-03 | Store user manager application issue | SQL 2005 DB – No support – do we need to migrate/upgrade to a better solution? | Supplier and support involvement | Rajamani Perumal | 29/01: Rajamani provided backlog ID as this work is ongoing to look for a solution - WPS-402 | DWS |  | NA | 29/01/25 | Closed |  |  |  | Rehan | 2025-02-10 | 486 | >60 | January | 2025 | #VALUE!
GTS | Digital Workplace Services | 90035888 | 2024-06-03 | Store user manager application issue | One Identity is coming in as a store level setup in 3-4 months. Rajamani to confirm on it | Permanent Fix | Rajamani Perumal | 21/06 Perumal advises that One identity system will be deployed for Retail beginning of next year | DWS |  | NA | 21/06/24 | Closed |  |  |  | Rehan | 2025-02-10 | 486 | >60 | June | 2024 | #VALUE!
GTS | Digital Workplace Services | 90035888 | 2024-06-03 | Store user manager application issue | Apply for an exception for the birthday attack vulnerability | Problem avoidance | Rajamani Perumal / InfoSec | 29/01: Rajamani provided backlog ID as this work is ongoing to look for a solution - WPS-402 03/12: Followed up 15/07 Perumal has said that this is now with the infra and he will give Rehan a contact 21/06 - Perumal advises that he is yet to raise exception, need to check with right people for more information | DWS |  | NA | 29/01/25 | Closed |  |  |  | Rehan | 2025-02-10 | 486 | >60 | January | 2025 | #VALUE!
Customer Channels | Selling Experience | 90019318 | 2024-05-31 | Customer.com Store finder not working because Bing Maps is down | How can we improve the alerting? | Problem identification & Alerting | Hemant Goyal/ Sumitro Chakravarty | 02/07 - For the fuzzy search, a fix has been identified and it has been deployed in Prod. 17/06 - Geocoder has 2 API’s- exact search and Fuzzy search. We found that alerts were set up for exact search only and not set up for fuzzy search which was mainly used in checkout - Team is working on getting this sorted 02/06 -1 . New Relic did not trigger an alert even though 1 in 3 requests were failing for the Geocoder API . To be investigated 2. Downstream systems were impacted but no alerts were triggered. WCS team to review whether an alert should have been triggered in Checkout | .com team | Tactical | NA | 2024-02-07 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 489 | >60 | July | 2024 | #VALUE!
Customer Channels | Selling Experience | 90019318 | 2024-05-31 | Customer.com Store finder not working because Bing Maps is down | What would be the Backup solutions if Bing Maps is down | Solution & Recovery | Ramachandrarao RVS and Hemant Goyal | 02/07 -we have short term solution planned in next sprint - via the backlog- LDS-808 and for the Long term solution - LDS-812 25/06- Awaiting backlog ID from Muralidharan Venkatarathinam 17/06 - The single api solution has been rejected after discussions with Matt E , the suggestion is to keep the API’s separate to allow flexibility. For short term we have leveraged Apigee caching. however this needs some additional work which teams pick up in coming sprints. In long term, this api would move into address domain and then they can plan a strategic solution for this. 02/06 - Use the data to make the decision regarding what the best backup solution is: 1. Caching in Apigee as short term solution 2. Single API as longer term solution (as in new world Apigee will not be used) | .com team | Strategic | NA | 2024-02-07 | Closed | NA | short term -LDS-808 and for the Long term solution - LDS-812 | NA | Saloni | 2025-02-10 | 489 | >60 | July | 2024 | #VALUE!
Customer Channels | Selling Experience | 90019318 | 2024-05-31 | Customer.com Store finder not working because Bing Maps is down | What is the process to log incidents with Microsoft ? | Supplier and support involvement | Ramachandrarao RVS | 17/06 - It has been agreed with Ms to create the ticket as a severity C and in order to increase it to A and call the unified support number or reach out the engineer if he is already assigned and engaged. also The hotline is available 24/7 to call in as well as having the option to send an email to the afterhours email address for support 02/06 -Ram to talk to Microsoft about the contract and discuss whether we can raise incidents directly as a severity 2 or 1 | .com team | Tactical | NA | 17/05/24 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 489 | >60 | May | 2024 | #VALUE!
Group Platforms | HR | 90021007 | 2024-05-30 | My HR application was inaccessible on 24/00 | Is there a DR scope for My HR? | Solution & Recovery | Kirsten Walker/ Mudassar Kazmi | It has been confirmed that there is a failover/DR option at Oracle. We never had a failover instance. However, the DR testing has been proved and relevant artifacts are present. | My HR | Tactical | NA | 30/05/24 | Closed |  |  |  | Saloni | 2025-02-10 | 490 | >60 | May | 2024 | #VALUE!
Group Platforms | HR | 90021007 | 2024-05-30 | My HR application was inaccessible on 24/01 | Improvise Stakeholder communication during Major incidents. | Business & IT Communication | Kirsten Walker/ Mudassar Kazmi | We are aware that the delay in sending stakeholder comms was due to Logistics issue, however, it has now been concluded that the relevant service lead is completely aware of the process, templates, timelines to send comms in future scenarios | My HR | Tactical | NA | 30/05/24 | Closed |  |  |  | Saloni | 2025-02-10 | 490 | >60 | May | 2024 | #VALUE!
Group Platforms | HR | 90021007 | 2024-05-30 | My HR application was inaccessible on 24/02 | Review the change management process | Solution & Recovery | Kirsten Walker | We have an agreed cadence on quarterly patches deployed in non-prod on 1st Friday every month and prod on 3rd Friday every month. The issue was not caused due to an Oracle change, this was an unplanned outage. Therefore, no further actions required. | My HR | Tactical | NA | 30/05/24 | Closed |  |  |  | Saloni | 2025-02-10 | 490 | >60 | May | 2024 | #VALUE!
Group Platforms | HR | 90021007 | 2024-05-30 | My HR application was inaccessible on 24/03 | Was there a proactive alert at Oracle which identified the issue? If not, feasibility of configuring one. | Problem identification & Alerting | Mudassar Kazmi | Oracle proactively communicated an issue on non-prod and test environment through an alert – therefore there are no further concerns on proactive notification from Oracle. | My HR | Tactical | NA | 30/05/24 | Closed |  |  |  | Saloni | 2025-02-10 | 490 | >60 | May | 2024 | #VALUE!
Group Platforms | HR | 90021007 | 2024-05-30 | My HR application was inaccessible on 24/04 | Agree with Oracle on preventive measures to remediate a similar issue in future without causing an outage. | Problem avoidance | Kirsten Walker/ Mudassar Kazmi | 14/06: Oracle is implementing additional, more sensitive monitors, to catch and address this scenario quicker. New monitoring mechanism has been deployed in order to automatically detect and alarm on packet corruption. 07/06: There had been no further updates from Oracle. Kirsten Walker - head of product continues to chase. ETA: 17/06 We have agreed in the call to post these questions to Oracle and await their updates. There is no defined ETA yet. | My HR | Tactical | NA | 17/06/24 | Closed |  |  |  | Saloni | 2025-02-10 | 490 | >60 | June | 2024 | #VALUE!
Group Platforms | HR | 90021007 | 2024-05-30 | My HR application was inaccessible on 24/05 | Liaise with Oracle to identify the issue with their networking infrastructure causing the outage and the recovery steps performed to resolve the issue. | Root cause | Kirsten Walker/ Mudassar Kazmi | 14/06: Oracle confirmed that a subset of the infrastructure supporting network services encountered a period of degraded performance, introducing latency which lead to the observed impact. Oracle identified that this specific infrastructure encountered an intermittent bit-flip scenario. A bit flip is a rare phenomenon where a single binary digit (bit) changes its value from 0 to 1 or vice versa. This will affect packet data and cause it to fail and drop. 07/06: There had been no further updates from Oracle. Kirsten Walker - head of product continues to chase. ETA: 17/06 We have agreed in the call to post these questions to Oracle and await their updates. There is no defined ETA yet. | My HR | Tactical | NA | 17/06/24 | Closed |  |  |  | Saloni | 2025-02-10 | 490 | >60 | June | 2024 | #VALUE!
Foods | Foods Commercial Trading | 90018353 | 2024-05-24 | 20 Foods UPC’s missing in CSSM | FMD should be reconfiguring its application to request real time information rather than extracts – this to be handled as part of to sap decoupling – long term – raise a risk in the meantime | Permanent Fix | Srikanth Kathula | 17/06 -SAP Decoupling teams product hierarchy solution has to be brought live to fix this issue - Meanwhile teams have raise a Risk ID for the interim. Risk ID 2168 | FMD | Strategic | NA | 18/06/24 | Closed | Risk ID 2168 | NA | NA | Saloni | 2025-02-10 | 496 | >60 | June | 2024 | #VALUE!
Foods | Foods Commercial Trading | 90018353 | 2024-05-24 | 20 Foods UPC’s missing in CSSM | Communicate and guide the business users on how to create hierarchies and add products. | Problem avoidance | George/Lisy | 25/06 - Galileo team has been already communicated the cutoff and the gap between both the activities will be addressed | Service Owner | Tactical | NA | 25/06/24 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 496 | >60 | June | 2024 | #VALUE!
GTS | Enterprise Integration | 90018353 | 2024-05-24 | 20 Foods UPC’s missing in CSSM | As a temporary fix, ES can plan to delete the data extract entry from our collection after SAP sends the data, so that system can generate a new data extract when consumer hits ES data extract. Next Steps: ES will plan to add changes in our extractor. When SAP sends data through I0160 Interface ES extractor will delete the entry from data extract collection so that new consumer can get an updated data extract. | Problem avoidance | Senthil Kumar | A change has been deployed to address this issue : [MFS-9283] Product Hierarchy Data extractor Fix - Jira App | ES support | Tactical | NA | 17/05/24 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 496 | >60 | May | 2024 | #VALUE!
GTS | Enterprise Integration | 90018353 | 2024-05-24 | 20 Foods UPC’s missing in CSSM | Find out what other application made a call to ES for the extract. | Problem avoidance | Abdus/Hisham | 15/07 - This change has been deployed and it is working as expected. - Going forward whenever, A data is fetched from ES it will generate a live report rather then providing the recently fetched data. 11/07 - This action is no more needed as we have a permanent to be deployed tonight (Where ES will always generate a new file/data 02/07 - Hisham and team are still working on to get the final list of applications which uses ES extract. 25/05 - Hisham is working on the list which uses ES for the data extract 17/06 - follow-up has been made with the PM, awaiting updates | ES support | Tactical | NA | 15/07/24 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 496 | >60 | July | 2024 | #VALUE!
GTS | Enterprise Integration | 90018353 | 2024-05-24 | 20 Foods UPC’s missing in CSSM | Can we stop other applications from making the call to ES so that we prioritise FMD or reset after the last request? | Problem avoidance | Senthil Kumar | A change has been deployed to address this issue : [MFS-9283] Product Hierarchy Data extractor Fix - Jira App | ES support | Strategic | NA | 17/05/24 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 496 | >60 | May | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 90018353 | 2024-05-24 | 20 Foods UPC’s missing in CSSM | We also got an alert at 02:19 to say UPC’s were dropped – however CSSM team need to change their process to escalate the issue appropriately before business hours so we can proactively communicate with the business (if its multiple UPC’s) – check how the severity and criteria works. | Problem identification & Alerting | Valli/Bharat | The team has been provided additional instructions and trainings on the incident handling | CSSM | Tactical | NA | 29/05/24 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 496 | >60 | May | 2024 | #VALUE!
Group Platforms | Finance | 90018353 | 2024-05-24 | 20 Foods UPC’s missing in CSSM | Look to see if we can we automate a daily reconciliation for whether UPC’s are active in sap but dropped in CSSM? | Problem identification & Alerting | Karthik (SAP) Bharat (CSSM) | 10/05 - This action will further be tracked via SBM-5298 02/07 - This is being planned for Q2 to set-up an alert in SAP for the reconsilation - Karthik from SP will provide a backlog for the same 25/06 - Had a call with the Bharath and Karthik - From the CSSM end we do have the right alerting in place and from SAP - Karthik has agreed to enable additional alerting at SAP level before the data is sent to CSSM. Backlog will be shared by Karthik by EOD today. 17/05 - Karthick is yet to provide his inputs on the recon from SAP CSSM has confirmed that they have the right alerting in place - We need to check with SAP for the automated Recon feature in SAP | SAP and CSSM | Strategic | NA | 15/07/24 | Closed | NA | NA | SBM-5298 | Saloni | 2025-02-10 | 496 | >60 | July | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 90004445 | 2024-05-22 | Stores reporting latency in honeywell notifications from Click and Collect application | Review the communication DLs to ensure timely updates to the stakeholder community during a major incident. | Business & IT Communication | Valliammai Ramasamy | 18/06: The relevant stakeholder have been added to be included during future MIs. 10/06: Service leads are trying to collate a list of key stakeholders to be added across all areas. ETA: 17/06 Valli will speak to Hisham Khalid to identify the key business stakeholders to be included in tech comm | Service lead | Tactical | NA | 18/06/24 | Closed |  |  |  | Saloni | 2025-02-10 | 498 | >60 | June | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 90004445 | 2024-05-22 | Stores reporting latency in honeywell notifications from Click and Collect application | Based on SLO's defined, we need to understand the available support capabilities and subscriptions utilized with the respective vendors for each applications / products. | Solution & Recovery | Maebh Booth | 17/07: A backlog has been raised as the teams are held up with multiple actions critical for Golden QUarter - CRSO 1529 10/06: Valli has confirmed that there is a potential call scheduled with the product teams to identify the SLOs. SLOs are to be agreed before actioning this item | Senior head of Engineering | Strategic | NA | 17/07/24 | Closed |  | CRSO 1529 |  | Saloni | 2025-02-10 | 498 | >60 | July | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 90004445 | 2024-05-22 | Stores reporting latency in honeywell notifications from Click and Collect application | Review the product SLO's of all store ops products based on business requirements - which includes vendor involvements, timely response / notifications as part of product features and identify a solution to mitigate further risk. | Solution & Recovery | Maebh Booth | 17/07: A backlog has been raised to deal with this action - CRSO 1468 10/06: Valli has confirmed that there is a potential call scheduled with the product teams to identify the SLOs. A full review of all products using notifications will be performed to identify SLOs, and ensure that we have expected behaviour defined. These will then have alerting set up to monitor adherence to the SLOs. | Senior head of Engineering | Strategic | NA | 17/07/24 | Closed |  | CRSO 1468 |  | Saloni | 2025-02-10 | 498 | >60 | July | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 90004445 | 2024-05-22 | Stores reporting latency in honeywell notifications from Click and Collect application | Review the product SLOs of click and collect application based on the business requirements and identify a suitable solution to mitigate further risk | Solution & Recovery | Valliammai Ramasamy | 17/07: A backlog has been raised to deal with this action - CRSO 1468 10/06: Valli has confirmed that there is a potential call scheduled with the product teams to identify the SLOs. A call will be scheduled with the Product team to agree SLOs for notification arrival for the Click and Collect product | Service lead | Strategic | NA | 17/07/24 | Closed |  | CRSO 1468 |  | Saloni | 2025-02-10 | 498 | >60 | July | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 90004445 | 2024-05-22 | Stores reporting latency in honeywell notifications from Click and Collect application | Improvement on Google engagement and support during major incidents. Review the support wrap with Google and plan an approach considering PEAK. | Supplier and support involvement | Sarah Ensor | 07/06: The Retail project has now been moved to Customer tenant which mean during a future incident, teams will have premium support with Google 04/06: We have agreed we need to move the existing project into the existing Customer account, Phil Torkington is leading this. This will give us better visibility and the correct level of support from Google. Google have agreed to this, so it's just the action to move it across. ETA: 14/06 There were initial challenges in engaging Google or receiving significant updates as the project had a free subscription. There is an existing Customer account with enhanced support, a case was raised through it and response times were slightly improved. Overall, it was not a good experience with Google, and we need further discussions or explore options from the below: Options to move the existing project from basic to Premium support. Options to move the project account to existing Customer account with enhanced support. Review support wrap with Google, we have enhanced support now, considering PEAK, consider moving to Premium support. Move the Retail project to Customer account | Senior head of TPM | Tactical | NA | 2024-07-06 | Closed |  |  |  | Saloni | 2025-02-10 | 498 | >60 | June | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 90004445 | 2024-05-22 | Stores reporting latency in honeywell notifications from Click and Collect application | Address the gap in impact assessment. Create a dashboard to highlight the response times and correlate the metrics with C&C portal, backend API, & android app. | Problem identification & Alerting | Usman Ahmed/ Rohith Ravindran | 15/07: We have a story in current sprint "https://jira.marksandspencer.app/browse/CRSO-1468" to rework the notifications solution options, we will be updating any dashboards as we upgrade the implementation of notifications , either use a new approach or move to token based approach 22/05: There is an existing new relic dashboard however, the data is historic and will not help in efficient impact assessment. Although the issue was identified on 16/05, due to gap in understand the scale of impact, the issue was highlighted to MIM on 17/05. Engineering team to amend our applications to ensure ids are included that allows correlation between the sending and the arrival of the notifications. Engineering team to create a new dashboard to use this correlation and add alerting. | Honeywells | Tactical | NA | 15/07/24 | Closed |  | CRSO-1468 |  | Saloni | 2025-02-10 | 498 | >60 | July | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 90004445 | 2024-05-22 | Stores reporting latency in honeywell notifications from Click and Collect application | Plan the way forward to ensure service continuity after 30th June and mitigate further risks? Analyse the best possible approach for this functionality as a permanent solution. | Permanent Fix | Usman Ahmed/ Rohith Ravindran | 06/06: Googlr has confirmed that they have fine tuned our exisiting projects with topic based approach to send messages with low latency. Ideal way is to use token based approach, however, there is no SLOs agreed at Google. As Google has fine tuned the impacted projects, there are no further actions required 24/05: Google has confirmed that they launched a new feature for the topic based approach to optimise throughput and not latency - there are no issues with the topic based approach at our end. Therefore, Google has enabled some optimization for projects 645452263013 and 62277339341 and remove the temporary exemption next week to bring the latency to the tolerable level. We are awaiting the date to lift up the exemption and make the optimisations permanent so that we can enforce hypercare monitoring to idenifiy any issues proactively. Valli and Rohith are following up with Google 22/05: A follow up call to be scheduled with engineering community to confirm if the token-based approach is the desired solution or it needs further investigation for a different approach. Although, there is time until 30th June, this action is being prioritised to ensure no impact to services. | Honeywells | Tactical | NA | 2024-07-06 | Closed |  |  |  | Saloni | 2025-02-10 | 498 | >60 | June | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 90004445 | 2024-05-22 | Stores reporting latency in honeywell notifications from Click and Collect application | Explore the feasibility of notifying to all consumers when there is a fundamental change from a third party? | Problem avoidance | Sarah Ensor | 18/07: Sarah has confirmed that all people have the right level of access already, and for Store Ops, they added people post the incident last time. 15/07: Sarah has confirmed acoss all portfolios apart from Customer Engagement, and Store Ops. There is no action so far, and we believe both Customer Engagement & Store Ops will be set up for alerts from Firebase, but we are awaiting confirmation. 17/06: Sarah is continously following up on the relevant stakeholders to be added for Google comms when there is a change in their features. She is OOO until 26/06. ETA: 30/06 07/06: Sarah has sent an email today and awaiting on responses - asked across all of D&T, to get a view of all the names needed to be in firebase for service notifications. This will take a week to completed. ETA: 17/06 04/06: Sarah is still trying to get the list of names to be added in the stakeholder list for Google communication where there is new feature launch or amendment in exisitng feature. ETA: 14/06 Google have confirmed that they send notifications of upcoming changes at least a month in advance, depending on the service, the notifications go to the registered email address on that service. We need to get a list of names that should be included and add them to the service so that we don’t have single points of failure. | Senior head of TPM | Tactical | NA | 18/07/24 | Closed |  |  |  | Saloni | 2025-02-10 | 498 | >60 | July | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 90004445 | 2024-05-22 | Stores reporting latency in honeywell notifications from Click and Collect application | Work with Google to identify why the overall latency charts in FCM portal were showing a flat line unlike previous days indicating some issues with reporting. | Root cause | Rohith Ravindran | 25/06: Google have confirmed that Topic messages goes through a different funnel than messages delivered to single devices, so they're not current reflected in Google Cloud dashboard. Therefore, unless we move to token based approach, the dashboard will not reflect the latency in an appropriate manner. 10/06: Rohith and Usman had been following up with Google primarily on the topic/token based approach, this has now been concluded that Google has fine tuned our existing topic based approach to facilitate sending message with low latency. They are now going to discuss further on the dashboard issue on the day. ETA: 17/06 We are still awaiting RCA from Google on this sudden change in latency and issues with dashboard. | Honeywells | Tactical | NA | 25/06/24 | Closed |  |  |  | Saloni | 2025-02-10 | 498 | >60 | June | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 90004445 | 2024-05-22 | Stores reporting latency in honeywell notifications from Click and Collect application | Follow up with Google to understand what has changed in the topic-based approach causing latency in receiving Honeywell notification from 16/05. Agree with Google on proactive notification if there are any changes in their policies or documents. | Root cause | Usman Ahmed/ Rohith Ravindran | 24/05: Google has confirmed that they launched a new feature for the topic based approach to optimise throughput and not latency - there are no issues with the topic based approach at our end. Therefore, Google has enabled some optimization for projects 645452263013 and 62277339341 and remove the temporary exemption next week to bring the latency to the tolerable level. Tech team will review with Google on their document regarding the topic-based solution only addressing the message throughput and not latency. We will ask google to confirm when this became the preferred approach to understand if we have process improvements to make during initial build, or a review process that is needed regularly to re-assess 3rd party guidelines for exiting tech integrations. Actions have been agreed for both of these scenarios. We have agreed with Phil Torkington to speak to James Grainger (Account Director, Google) and based on Google’s availability, Rohith Ravindran to schedule a call to speed up this action. | Honeywells | Tactical | NA | 24/05/24 | Closed |  |  |  | Saloni | 2025-02-10 | 498 | >60 | May | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 90008993 | 2024-05-20 | Sign in Pages not Loading on UK Website and Mobile Apps | Stores Experience as a result of the holding page was degraded. Action to improve the incident management process and engagement of correct people to assess impact to retail. | Supplier and support involvement | Aadil/Maebh | 04/09: Process has been agreed and closed 03/09: Mutliple follow ups have been made, we haven't received any updates on the progress of the actions 07/08: Aadil is out of office, awaiting further updates. 17/07: Awaiting further updated from Maebh 10/07 (TW): Checking with Kavitha/Maebh if call was scheduled. 13/06 – Maebh out of office. Contacted Stuart Brown, but this action does not yet have an update. Follow up on return of Maebh. 06/06: Aadil will discuss with Maebh once she is back from holiday | Service owner/Head of Engineering | Strategic | NA | 2024-04-09 | Closed |  |  |  | Kavitha | 2025-02-10 | 500 | >60 | September | 2024 | #VALUE!
Customer Channels | Customer Engagement | 90008993 | 2024-05-20 | Sign in Pages not Loading on UK Website and Mobile Apps | Identity Team to raise a jira ticket to Assess the feasibility of doing local Customer Auth token refresh | Problem avoidance | Simon Attard/ Priyabharath | 27/06: Team assess the feasibitlity of doing local Customer Auth token refresh under the product back log - CIAM-1026 06/06: To be discussed and confirm the backlog details with Priyabhrath once he is back from his holiday | Indentity team | Strategic | NA | 27/06/24 | Closed |  | CIAM-1026 |  | Kavitha | 2025-02-10 | 500 | >60 | June | 2024 | #VALUE!
Customer Channels | Customer Engagement | 90008993 | 2024-05-20 | Sign in Pages not Loading on UK Website and Mobile Apps | Review & Circulate Incident Management Document/SLA Matric | Supplier and support involvement | Aadil | 04/07: The incident management document and SLA matric has been reviewed and will be published to wider audience 13/06 – Awaiting latest version of SLA Matrix from online ops hub - Once shared this will be circulated. Incident management document still under review. 06/06: To be discussed with SIAM team and will be published | Service Management | Tactical | NA | 2024-04-07 | Closed |  |  |  | Kavitha | 2025-02-10 | 500 | >60 | July | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 90008993 | 2024-05-20 | Sign in Pages not Loading on UK Website and Mobile Apps | On Boarding document for engineering to be updated to advise new team members to request access to tech ops channel | Supplier and support involvement | Maebh Booth | 18/09 - Update from Steve W/Maebh/Ben that this action will be followed up through the operational stability workstream and can be closed off here. 04/9 – Received an update from Maebh advising that the target date for this action is 06/09/24 03/09: Mutliple follow ups have been made, we haven't received any updates on the progress of the actions 07/08: Aadil is out of office, awaiting further updates. 10/07 (TW): Checking with Kavitha/Maebh if call was scheduled. 10/07: Requested update from Maebh and she has advised that she will provide a ticket for this action to track 04/07: Spoken to Maebh, requested confirmation whether she would be the correct single point of contact for this action or whether it will be a different Technology Lead 06/06: Aadil will discuss with Maebh once she is back from holiday | Heads of Engineering | Strategic | NA | 17/10/24 | Closed |  |  |  | Kavitha | 2025-02-10 | 500 | >60 | October | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 90008993 | 2024-05-20 | Sign in Pages not Loading on UK Website and Mobile Apps | Add Risk to risk register regarding availability of Operational Akamai resources | Supplier and support involvement | Aadil | 05/06: Risk has been raised for mitigating the Operational Akamai resources. Sharepoint Risk ID 2166 & Portfolio Risk Spreadsheet Row 499 06/06: Aadil to raise a risk after discussing with Stuart Brown | Service Management | Tactical | NA | 2024-05-06 | Closed | 2166 |  |  | Kavitha | 2025-02-10 | 500 | >60 | June | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 90008993 | 2024-05-20 | Sign in Pages not Loading on UK Website and Mobile Apps | Schedule a training session for Akamai so that the identity team will have the capability of applying relevant changes for their service if required | Problem avoidance | David R | To be scheduled w/c 10 June 2024 when David R. returns from annual leave. Work item raised and placed on team’s backlog (DSDS-2292 Identity team training) 06/06: Session will be arranged once David R is back from holidays. | Identity Team/Akamai Team | Tactical | NA | 27/06/24 | Closed |  | DSDS-2292 |  | Kavitha | 2025-02-10 | 500 | >60 | June | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 90008993 | 2024-05-20 | Sign in Pages not Loading on UK Website and Mobile Apps | Review Holding Page configuration (Review asset exclusions/Page Exclusions/Dependencies within pages that are linked to Holding page) | Problem avoidance | David R | 06/06: Work item raised and placed on team’s backlog (DSDS-2291 - Review Holding Page Configuration) | Identity Team/Aka mai Team | Strategic | NA | 2024-06-06 | Closed |  | DSDS-2291 |  | Kavitha | 2025-02-10 | 500 | >60 | June | 2024 | #VALUE!
Customer Channels | Customer Engagement | 90008993 | 2024-05-20 | Sign in Pages not Loading on UK Website and Mobile Apps | Identity team to circulate RCA once provided by Cloud Entity | Root cause | Identity Tea | Identity Team provided RCA document 21/05. On May 18th, 2024, starting at 9:15 am GMT, the Cloudentity SaaS environment experienced a full outage due to the expiration of the cloudentity.io domain. The registration of the cloudentity.io domain, provided by their vendor Network Solutions, expired resulting in a complete service outage. The expiration was not detected in time due to outdated payment and contact information | Identity Team | Tactical | NA | 22/05/24 | Closed |  |  |  | Kavitha | 2025-02-10 | 500 | >60 | May | 2024 | #VALUE!
Customer Channels | Customer Engagement | 90008993 | 2024-05-20 | Sign in Pages not Loading on UK Website and Mobile Apps | Regular reviews against 3rd parties and update our processes accordingly. | Supplier and support involvement | Darren Gibson | 17/10: Its has been agreed to close this action.As there is no response from Darren on these action its not progressed further and hence we are close it off from the tracker 23/07 - Rehan spoke to Darren whom advised that he will be replying to the email 07/08 – Rehan requests an update from Darren 08/08 – Rehan sends a reminder for an update on the action to Darren 16/09 - Kavitha requests an ETA for the action from Darren 03/09: Mutliple follow ups have been made, we haven't received any updates on the progress of the actions 07/08: Aadil has been following up with Darren every week, awaiting updates from Darren 10/07: Further follow up was made, awaiting updates 04/07: Followed up with Daren for updates, awaiting details 06/06: Aadil to discuss with Daren | Leadership team | Strategic | NA | 17/10/24 | Closed |  |  |  | Kavitha | 2025-02-10 | 500 | >60 | October | 2024 | #VALUE!
Customer Channels | Customer Engagement | 90008993 | 2024-05-20 | Sign in Pages not Loading on UK Website and Mobile Apps | Review standard contract process to ensure we are clear about SLAs and their review process | Supplier and support involvement | Darren Gibson | 17/10: Its has been agreed to close this action.As there is no response from Darren on these action its not progressed further and hence we are close it off from the tracker 23/07 - Rehan spoke to Darren whom advised that he will be replying to the email 07/08 – Rehan requests an update from Darren 08/08 – Rehan sends a reminder for an update on the action to Darren 16/09 - Kavitha requests an ETA for the action from Darren 03/09: Mutliple follow ups have been made, we haven't received any updates on the progress of the actions 07/08: Aadil has been following up with Darren every week, awaiting updates from Darren 10/07: Further follow up was made, awaiting updates 04/07: Followed up with Daren for updates, awaiting details 06/06: Aadil to discuss with Daren | Leadership team | Strategic | NA | 17/10/24 | Closed |  |  |  | Kavitha | 2025-02-10 | 500 | >60 | October | 2024 | #VALUE!
Customer Channels | Customer Engagement | 90008993 | 2024-05-20 | Sign in Pages not Loading on UK Website and Mobile Apps | Cloud entity Detection of the incident. Did they detect it or were they only aware through the ticket raised on our end. | Problem identification & Alerting | Cloud entity | 20/05: Cloud entity have confirmed that they did detect the issue on their end and was investigating prior to Customer raising a ticket. | Cloud entity | Tactical | NA | 20/05/24 | Closed |  |  |  | Kavitha | 2025-02-10 | 500 | >60 | May | 2024 | #VALUE!
Customer Channels | Customer Engagement | 90008993 | 2024-05-20 | Sign in Pages not Loading on UK Website and Mobile Apps | App emergency release process to be documented and shared | Problem avoidance | Luke Charman | 05/06 – App team have created a jira ticket to follow this up (12913) | Mobile App team | Tactical | NA | 2024-06-06 | Closed |  | 12913 |  | Kavitha | 2025-02-10 | 500 | >60 | June | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 90008993 | 2024-05-20 | Sign in Pages not Loading on UK Website and Mobile Apps | Review the list of 22 services | Problem avoidance | David R | 15/09: The list of service has been shared and reviewed 03/09: Mutliple follow ups have been made, we haven't received any updates on the progress of the actions 07/08: Aadil has been following up on this actions awaiting further updates to get more clarity of this action 10/07 : Not sure who is scheduling the call, but Tom Wikstol will pick up when David back from AL 22/7. 13/06 – Spoke to David who has reviewed the list of 22 services and will be sharing for wider review 06/06: To be scheduled a call on 10 June 2024 when David R. returns from annual leave. | Akamai Team | Strategic | NA | 16/09/24 | Closed |  |  |  | Kavitha | 2025-02-10 | 500 | >60 | September | 2024 | #VALUE!
Customer Channels | Customer Engagement | 90008993 | 2024-05-20 | Sign in Pages not Loading on UK Website and Mobile Apps | Disaster Recovery plan for scenario where cloud entity is not available | Solution & Recovery | Simon Attard/ Priyabharath | 13/06: Risk number 2155 raised mitigate the DR unavailibilty in cloud 06/06: A disaster recovery document already exists; however, this needs to be re-reviewed in light of the incident and Team will be raising a risk ticket which this action can be followed up through. | Identity Team | Strategic | NA | 13/06/24 | Closed |  |  |  | Kavitha | 2025-02-10 | 500 | >60 | June | 2024 | #VALUE!
Customer Channels | Customer Engagement | 90008993 | 2024-05-20 | Sign in Pages not Loading on UK Website and Mobile Apps | Understand and document the data points that are required to invoke Business Continuity | Solution & Recovery | Himanshu | 06/06: This actions is part of 'Identify critical services where service degradation is not acceptable so actions can be taken accordingly.' and hence close this action | Online Ops Hub | Tactical | NA | 2024-06-06 | Closed |  |  |  | Kavitha | 2025-02-10 | 500 | >60 | June | 2024 | #VALUE!
Customer Channels | Customer Engagement | 90008993 | 2024-05-20 | Sign in Pages not Loading on UK Website and Mobile Apps | Review where Circuit breakers can be introduced that would enable us to improve the customer expereince while loading the website/app when we encounter similar errors. | Solution & Recovery | Jamie Sanson | 06/06: Onyx Auth Web Platform Team advised that sign in loop and resultant blank page fixed through following GITHUB ticket 17499- Complete App Team are following this up through the following GITHUB ticket- 1189 | Mobile App team | Strategic | NA | 2024-06-06 | Closed |  | 17499/1189 |  | Kavitha | 2025-02-10 | 500 | >60 | June | 2024 | #VALUE!
Customer Channels | Customer Engagement | 90008993 | 2024-05-20 | Sign in Pages not Loading on UK Website and Mobile Apps | Identify critical services where service degradation is not acceptable so actions can be taken accordingly | Problem avoidance | Leads of each area | 13/06: Onyx Auth Web Platform Team advised that sign in loop and resultant blank page fixed through following ticket (GIT-HUB 17499) App Team are validating the feasiblity of having the circuit breaker through the following ticket (GIT HUB- 1189) 06/06: Overall ownership needs to be finalised | Team leads | Tactical | NA | 13/06/24 | Closed |  | GIT HUB- 17499/1189 |  | Kavitha | 2025-02-10 | 500 | >60 | June | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 90008993 | 2024-05-20 | Sign in Pages not Loading on UK Website and Mobile Apps | How do we improve testing of the failure scenarios regularly across the systems- testinf scenarios like dependent internal or external services with a focus on slow response times, high error rate or service unavailablilty | Problem avoidance | Maebh | 18/09 - Update from Steve W/Maebh/Ben that this action will be followed up through the operational stability workstream and can be closed off here. 04/9 – Received an update from Maebh advising that the target date for this action is 06/09/24 03/09: Mutliple follow ups have been made, we haven't received any updates on the progress of the actions 07/08: Aadil is out of office, awaiting further updates. 10/07: Requested update from Maebh and she has advised that she will provide a ticket for this action to track 04/07: Spoken to Maebh, requested confirmation whether she would be the correct single point of contact for this action or whether it will be a different Technology Lead0 6/06: Overall ownership needs to be finalised | Team leads | Strategic | NA | 18/09/24 | Closed |  |  |  | Kavitha | 2025-02-10 | 500 | >60 | September | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 90008993 | 2024-05-20 | Sign in Pages not Loading on UK Website and Mobile Apps | Understand the blast radius of dotcom related incidents which impact stores and ensure clear comms are sent out to stores at the earliest | Business & IT Communication | Maebh / Andy R | 18/09 - Update from Steve W/Maebh/Ben that this action will be followed up through the operational stability workstream and can be closed off here. 04/09 – Received an update from Maebh advising that the target date for this action is 06/09/24 03/09: Mutliple follow ups have been made, we haven't received any updates on the progress of the actions 07/08: Aadil is out of office, awaiting further updates. 10/07 – Requested update from Maebh and she has advised that she will provide a ticket for this action to track 04/07 - Spoken to Maebh who has advised that she will check on the outstanding actions 06/06: This is will be reviewed once Maebh is back from holidays | Maebh / Andy R | Strategic | NA | 18/09/24 | Closed |  |  |  | Kavitha | 2025-02-10 | 500 | >60 | September | 2024 | #VALUE!
Customer Channels | Customer Engagement | 90008993 | 2024-05-20 | Sign in Pages not Loading on UK Website and Mobile Apps | Using data and observability metrics more to understand customer impact quickly during an incident. Review current metrics used to assess health of applications | Problem identification & Alerting | Jordan Teri | 05/06 - The feasibility of using data and observability metrics to ascertain the impact will be tracked under the backlog in GITHUB 1190 | Mobile App team | Tactical | NA | 2024-06-06 | Closed |  |  |  | Kavitha | 2025-02-10 | 500 | >60 | June | 2024 | #VALUE!
Customer Channels | Customer Engagement | 90008993 | 2024-05-20 | Sign in Pages not Loading on UK Website and Mobile Apps | Centralised Runbook for key front-end area’s needs to be published detailing the steps that need to be followed during a major incident | Solution & Recovery | Kerem Gudunz | 05/06 - This action will be tracked under the backlog (AMNS-12912) | Mobile App team | Tactical | NA | 2024-06-06 | Closed |  | AMNS-12912 | Open | Kavitha | 2025-02-10 | 500 | >60 | June | 2024 | #VALUE!
Customer Channels | Selling Experience | 90008993 | 2024-05-20 | Sign in Pages not Loading on UK Website and Mobile Apps | Review which stakeholders need to be called out for a major incident | Business & IT Communication | Himanshu/ Steve | 11/07: Tis action will be covered as part of ongoing severity matrix and comms review across business and technology and both Steve/Himanshu advised that this action can be closed off. No Current point of reference/ticket to follow up this action provided. 10/07– Requested update from Himanshu & Steve.No further updates 04/07 - Requested update from Himanshu & Steve. 13/06 – Requested update from Himanshu & Steve. 20/05: Needs to be reviewed with Darren | Business ops/ Head of Engineering | Strategic | NA | 2024-11-07 | Closed |  |  |  | Kavitha | 2025-02-10 | 500 | >60 | July | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 90008993 | 2024-05-20 | Sign in Pages not Loading on UK Website and Mobile Apps | Ensure teams are regularly reviewing pager duty and ensuring correct people are on call and ensuring training for pager duty is available for any team members that require it | Supplier and support involvement | Maebh /Steve/Ben | 18/09 - Selling Experience teams held a session this week to update pager duty across the portfolio. Platform & Store Ops/Customer Engagement will be picking up this activity as part of the Operational Sability workstream 04/9 – Received an update from Maebh advising that the target date for this action is 06/09/24 03/09: Mutliple follow ups have been made, we haven't received any updates on the progress of the actions 07/08: Aadil is out of office, awaiting further updates. 10/07: Requested update from Maebh and she has advised that she will provide a ticket for this action to track 04/07: Spoken to Maebh, requested confirmation whether she would be the correct single point of contact for this action or whether it will be a different Technology Lead 20/05: Needs to be reviewed with Darren | Head of Engineering | Strategic | NA | 18/09/24 | Closed |  |  |  | Kavitha | 2025-02-10 | 500 | >60 | September | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89992934 | 2024-05-15 | Peterborough (Outlet) DC colleagues were unable to access JDA WMS application | Based on action one we may be able to create an alert based on stale connections. | Problem avoidance | Nandhakumar Saravanan | 14/06: Alerting is not feasible for this scenario 05/06: Action owners are out of office, be back by 10/06 21/05: Followed up with Nadha, awaiting updates | WMS | Strategic | NA | 14/06/24 | Closed |  |  |  | Saloni | 2025-02-10 | 505 | >60 | June | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89992934 | 2024-05-15 | Peterborough (Outlet) DC colleagues were unable to access JDA WMS application | After any similar change the process needs be revised to ensure we check back with DC and also have JDA support on hyper care – agree process with NOC for post deployment checks. | Problem avoidance | Karthick GC | 14/06: We replicated this in non prod and no issues were observed and we didn't observe any issue during the SP exit the application has been succesfully migrated 05/06: Action owners are out of office, be back by 10/06 22/05: Replicate the scenario in non prod and capture the log to move forward and share the log with BY. Once the log shared, BY can analyse and come back with the findings 21/05: Followed up with Karthick, awaiting updates | WMS | Tactical | NA | 14/06/24 | Closed |  |  |  | Saloni | 2025-02-10 | 505 | >60 | June | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89992934 | 2024-05-15 | Peterborough (Outlet) DC colleagues were unable to access JDA WMS application | How can we clear connections in the applications if a firewall is failed over from one to another. Further follow up with JDA, NW and BY | Problem avoidance | Nandhakumar Saravanan | 14/06: BY has confirmed that this is not feasible and advised to perform an application restart 05/06: Action owners are out of office, be back by 10/06 21/05: Followed up with Nadha, awaiting updates | WMS | Tactical | NA | 14/06/24 | Closed |  |  |  | Saloni | 2025-02-10 | 505 | >60 | June | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89992934 | 2024-05-15 | Peterborough (Outlet) DC colleagues were unable to access JDA WMS application | Ascertain if the clearing of session on the app would have worked – recreate scenario and test. | Problem avoidance | Nandhakumar Saravanan | 14/06: BY has confirmed that this is not feasible and advised to perform an application restart 05/06: Action owners are out of office, be back by 10/06 21/05: Followed up with Nadha, awaiting updates | WMS | Tactical | NA | 14/06/24 | Closed |  |  |  | Saloni | 2025-02-10 | 505 | >60 | June | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 89980920 | 2024-05-13 | Issues with store backstage replenishment | Developers and leads should carefully review changes merged for production and make sure no unwanted changes are going live. Peer to peer reviews should happen by default. Rohith to communicate with team | Problem avoidance | Rohith Ravindran | 25/05 - Rohit has informed the team and those changes have been deployed by 23/05. | C&H CSSM | Strategic | NA | 23/05/24 | Closed |  |  |  | Saloni | 2025-02-10 | 507 | >60 | May | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 89980920 | 2024-05-13 | Issues with store backstage replenishment | If there are releases spanning on multiple products - review the release procedure. | Problem avoidance | Vijay Bhasker and Usman Ahmed | 30/05 - Vijay Baskar confirmed that the release procedure has been reviewed for the releases involving multiple products and the team has been made aware of the procedure. 29/05 - Usman updated that for a specific portfolios all details are updated in Jira and also GitHub is integrated with Jira and suggested to discuss with Vijay Bhasker (TPM) to discuss further and close the action. 25/05 - Have checked with Usman on the status of the action which was assigned during the PIR | C&H Store Ops | Strategic | NA | 30/05/24 | Closed |  |  |  | Saloni | 2025-02-10 | 507 | >60 | May | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 89980920 | 2024-05-13 | Issues with store backstage replenishment | QA to make sure that the testing region is setup similar to the production after deployment and also to do a full end to end sanity check on connected systems even if it is a small change. | Problem avoidance | Janarthanan Ravi | 29/05 - Janarthanan R confirmed that the team is conveyed to make sure that the testing region is setup, similar to the production after deployment and also to do a full end to end sanity check on connected systems, even if it is a small change. Hence closing. 25/05 - Have checked with Janarthanan on the status of the action which was assigned during the PIR | C&H Store Ops | Strategic | NA | 29/05/24 | Closed |  |  |  | Saloni | 2025-02-10 | 507 | >60 | May | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 89980920 | 2024-05-13 | Issues with store backstage replenishment | Check the feasibility of adding logging and alerting if zero picks are generated as part of replenishment. | Problem identification & Alerting | Rohith Ravindran | 14/06 - Rohith shared the CHSA-1868 Jira reference for this activity. 13/06 - Rohith confirmed that this is planned to be implemented by Week commencing 17/06, awaiting change details. 30/05 - Vijay suggested to wait for Rohith to get exact Jira details. Hence, scheduled a call with Rohith on 4/06. 29/05 - Rohith is OOO and have scheduled a call on 30/05 with Vijay Bhasker (TPM) to discuss on this.. 25/05 - Have checked with Rohith on the Jira backlog. 13/05 - Jira backlog number to be assigned | C&H CSSM | Tactical | NA | 14/06/24 | Closed |  | CHSA-1868 | Open | Saloni | 2025-02-10 | 507 | >60 | June | 2024 | #VALUE!
GTS | ETP-On premise services | 90048310/89963305 | 2024-05-02 | DataStage services were unavailable after the RHEL upgrade activity | The ITM - MQ Agent on the primary DS node was not available after the DS RHEL upgrade – what caused the agent to go down? | Root cause | Elizabeth Golder | 04/06: The ITM agent big has been fixed 22/05: There is a bug in ITM agent. IBM have advised to downgrade the agent version. But they won't supply us the media as there is a disagreement on licensing. We have escalated to IBM but can't fix until it is resolved. Requested Elizabeth to raise a risk. 10/05: Followed up awaiting further updates | Unix Team | Tactical | NA | 2024-04-06 | Closed |  |  |  | Saloni | 2025-02-10 | 518 | >60 | June | 2024 | #VALUE!
GTS | ETP-On premise services | 90048310/89963305 | 2024-05-02 | DataStage services were unavailable after the RHEL upgrade activity | What caused the space constraint in the file systems? - | Root cause | Elizabeth Golder | 19/06: The FS growth is something due to DS processing which is under control - for the disk addition issue - it was identified due to an LVM partition table was not updated in kernel and the same has been sorted now and we are good to go for uplift in the next maintenance window in July 04/06: Awaiting further updates from RedHat 28/05 :Space constraint is growth over time it's not a major issue but alerts are in place notify them. We tried to increase the file system on 21/05 under a CR but there was an issue. A case has been raised with RegHaT 10/05: Followed up awaiting further updates | Unix Team | Tactical | NA | 19/06/24 | Closed |  |  |  | Saloni | 2025-02-10 | 518 | >60 | June | 2024 | #VALUE!
GTS | ETP-On premise services | 90048310/89963305 | 2024-05-02 | DataStage services were unavailable after the RHEL upgrade activity | Is there any feasibility to configure alerting for the RSYSLOG service if it’s not capturing log for longer time? | Problem identification & Alerting | Sathish Selvapillai | 18/06:we analysed possible options and there is no direct way to setup alert if the rsyslog is not updating as the deamon is still up and running - as an alternate option we have added additional steps to review the rsyslog configs in rhel8 migration. 10/05: To be tested in CATE to see the possibilities - ETA 30th 02/05:Feasibility to be reviewed. | Unix Team | Tactical | NA | 18/06/24 | Closed |  |  |  | Saloni | 2025-02-10 | 518 | >60 | June | 2024 | #VALUE!
GTS | ETP-On premise services | 90048310/89963305 | 2024-05-02 | DataStage services were unavailable after the RHEL upgrade activity | We agreed a hypercare to validate the Rsys log service during the first instance of the issue, however it was missed, how can we prevent this gap going forward | Problem avoidance | Elizabeth Golder | 10/05: SOP has been amended with additional checks that needs to be performed 02/05;We were monitoring at intervals and hence the miss. The hypercare process will be reviewed to agree better check intervals to prevent gaps in the monitoring. | Unix Team | Tactical | NA | 2024-02-05 | Closed |  |  |  | Saloni | 2025-02-10 | 518 | >60 | May | 2024 | #VALUE!
GTS | ETP-On premise services | 90048310/89963305 | 2024-05-02 | DataStage services were unavailable after the RHEL upgrade activity | What caused third issue at 19:07 with OS level routing? | Root cause | Sathish Selvapillai | 08/05: The new version picked up the layer2 config (internal routing) instead of public routing causing the issue. Technical details - In Red Hat Enterprise Linux8 the use of the global /etc/sysconfig/network file is deprecated, and specifying the gateway should now only be done in per-interface configuration files - Ethernet devices have a default route metric starting at 100, while logical interfaces like bond0 and bond1 start from 300 and onwards. If multiple bond interfaces are being used in the system, it is recommended to set explicit route metrics on each interface. This is because we cannot be certain which bond interface will load first during boot. 02/05: After the upgrade the network routing was changed. There are two interfaces, one for publics traffic and the other for internal. After the upgrade the default routing was set to public, but after some time it switched to internal. The internal route was removed manually and a debugging trace needs to be enabled in the next planned outage to see why it switched. | Unix Team | Tactical | NA | 2024-10-05 | Closed |  |  |  | Saloni | 2025-02-10 | 518 | >60 | May | 2024 | #VALUE!
Customer Channels | Selling Experience | 89956269 | 2024-05-01 | Order Drop on Customer.com Website | Explore feasibility of implementing Oracle recommendation to keep open cursors for frequently executed SQL queries | Problem avoidance | WCS Identity Team | 01/05 - Will be followed up using the specified Jira ticket. | WCS Identity Team |  | NA | 2024-01-05 | Closed |  | CIAM-977 |  | Saloni | 2025-02-10 | 519 | >60 | May | 2024 | #VALUE!
Customer Channels | Selling Experience | 89956269 | 2024-05-01 | Order Drop on Customer.com Website | Explore feasibility of recommendation from Oracle regarding reducing unnecessary sql executions | Problem avoidance | WCS Identity Team | 01/05 - Will be followed up using the specified Jira ticket. | WCS Identity Team |  | NA | 2024-01-05 | Closed |  | CIAM-977 |  | Saloni | 2025-02-10 | 519 | >60 | May | 2024 | #VALUE!
Customer Channels | Selling Experience | 89956269 | 2024-05-01 | Order Drop on Customer.com Website | High active session count was observed in Context Management Table, however we couldn't indetify the reason behind the increase in number of active session, hence the root cause is inconclusive. | Root cause | WCS Identity Team | 01/05- High active session counts were observed on the context management table,however we cannot determine the cause for increase in the active sessions. Hence RC is inconclusive. Orcale has given some recommedation to implement to avoid any impact to DB during such scenario's which is being tracked by another action with HCL to implement under the JIRA _ CIAM-977 | WCS Identity Team |  | NA | 2024-01-05 | Closed |  | CIAM-978 |  | Saloni | 2025-02-10 | 519 | >60 | May | 2024 | #VALUE!
foods | Foods Supply Chain | 89970025 | 2024-04-30 | Delay in the Foods final order flow | Ensure we remove the inbound Maersk file processing to a separate interface (bridge) at OT end | Permanent Fix | Opentext (OT) | 30/04 - The cause of the issue was that the Maersk file and FFO files were being processed inthe same interface. The Maersk file processing has been moved to a separate interface at OT’s end. | Opentext Vendor |  | NA | 30/04/24 | Closed |  |  |  | Gokul | 2025-02-10 | 520 | >60 | April | 2024 | #VALUE!
GTS | Enterprise Integration | 89970025 | 2024-04-30 | Delay in the Foods final order flow | Explore the feasibility to convert the proactive alert from OT to a Sev 1 Remedy ticket | Problem identification & Alerting | Venkat/Integration | 14/06 - With available OT alerts, Sev 1 incidents can be raised. However, alerts will be finalized after the contract upgrade with OT in July. Hence, closing this action and this will be tracked in SOP action related to this incident. 12/06 - Alerts have been addressed and are being sent by OT, Integration team is checking if they can be created as Sev 1 incidents. 10/06 - Call has been scheduled on 12/06 to discuss further on these alerts with OT. 04/06 - OT has responded with some available data, however internally they are checking on few others. 31/05 - It was discussed with OT to provide additional details in the existing alerts and OT is exploring the same. Followup call to be scheduled on 05/06 based on everyone's availbality. 30/05 - As the existing alerts from OT are not having much information to interpret the impacted services, call has been scheduled with OT on 31/05 to revisit them. 25/05 - Followup call to be scheduled for 30/05, based on everyone's availability. 21/05 - Integration team to check on existing alerts and followup call scheduled on 24/05. 20/05 - Call scheduled by Naveen to discuss on various actions on 21/05 16/05 - In the PIR reveiew meeting Gokul advised that the ownership of who will own the incident one the alert is triggered is under discussion - meeting to be scheduled. 12/05 - Venkat will discuss with Foods team and finalize on the ticket assignment. 30/04 - If integration team is unable to set up alerts, then OT to be reached out for feasibility of revising the alert as required by Integration team | B2B MQFTE Team | Tactical | NA | 14/06/24 | Closed |  |  |  | Gokul | 2025-02-10 | 520 | >60 | June | 2024 | #VALUE!
Foods | Foods Supply Chain | 89970025 | 2024-04-30 | Delay in the Foods final order flow | Review the recipients for the proactive alert from OT | Problem identification & Alerting | Andrew G/Lisy | 31/07: Lisy confirmed that as part of OT premium support, this is being requested. Also, it is being discussed in premium workshop. Hence closing this action. 23/07: Andrew confirmed that this shall we discussed with Lisy and closed. 18/07: OT confirmed that the mail id "grp-ms-ot-commsnotification@mnscorp.onmicrosoft.com" has been been configured for alerting. 16/07: We await OT to configure the alerting at their end. 12/07 - Based on Ivan's request, a single mail id has been shared with him for configuration and awaiting update. 10/07 - Lisy had shared mails IDs to Ivan on 03/07 and I have followed-up with Ivan today on the action. 02/07 - OT has been asked if the mail ID is added to the alerts, if there is no response. Call to be scheduled. 04/07 to discuss with OT along with other actions for OT. 27/06 - Single mail ID with all required teams has been created and shared with OT for proactive alerts. 25/06 - The list of mail ids is yet to be finalized, call to be scheduled based on the SAP availability on 26th or 27th. 19/06 - OT said that only 1 mail id can be configured to receive the alerts as part of the existing contract. Hence, Lisy to work on creating a single mail id including all the required recipients. 10/06 - Call has been scheduled on 12/06 to discuss further on these alerts with OT. 04/06 - OT has responded with some available data, however internally they are checking on few others. 31/05 - It was discussed with OT to provide additional details in the existing alerts and OT is exploring the same. Followup call scheduled on 05/06. 30/05 - As the existing alerts from OT are not having much information to interpret the impacted services, call has been scheduled with OT on 31/05 to revisit them. 25/05 - Followup call to be scheduled for 30/05, based on everyone's availability. 21/05 - Integration team to check on existing alerts and followup call scheduled on 24/05. 20/05 - Call scheduled by Naveen to discuss on various actions on 21/05 16/05 - The ownership of which team will action the ticket when it is raised via the alert is under discussion - meeting 20/05 14/05 - Andrew suggested to discuss with Integration team. | FITS | Tactical | NA | 31/07/24 | Closed |  |  |  | Gokul | 2025-02-10 | 520 | >60 | July | 2024 | #VALUE!
foods | Foods Supply Chain | 89970025 | 2024-04-30 | Delay in the Foods final order flow | Review and remedy any issues with existing alerts for supplier ASN’s not flowing for 30 mins from GIST and OT | Problem identification & Alerting | Saravanan Jeyabalan/FITs | 20/05 - SCLT3-2429 - "Source Level Missing ASN Alerting Analysis" has been created to track this alert creation, with this closing the action. 14/05 - Saravanan update that they are in discussion with Lisy and Product Owner (Richard Spencer). He also added that a common alert for Supplier ASN and not specific to any specific source . Our product Owner has not agreed to create alert for each ASN Source as it will end up in creating multiple false alerts. | FITS |  | NA | 20/05/24 | Closed |  | SCLT3-2429 | open | Gokul | 2025-02-10 | 520 | >60 | May | 2024 | #VALUE!
Group Platforms | Finance | 89970025 | 2024-04-30 | Delay in the Foods final order flow | Review which alerts are already in place and review if we can create an alert to notify of dashboard mismatches and lack of orders. | Problem identification & Alerting | Karthikeyan M/SAP B&M | 11/06 - Satya confirmed that the alerts are available. Reconfirmed that those alerts to PCM are not raised as incidents to SAP B&M. 04/06 - Karthik confirmed that the SAP outbound alerts have been disabled due to ZP30, it needs to be activated with help on Control M. Karthik M has created a group chat with Satya M. 28/05 - Karthik updated that with the samples, there are alerts to validate the SAP inbound, however for SAP outbound recently were disabled. He is checking on it further. 23/05 - Karthik has got the required samples of the alerts and is analysing them with next update on observations by 24/05. 16/05 - Karthikeyan is working on it. 11/05 - Have checked with Karthikeyan on this action | SAP B&M | Tactical | NA | 2024-11-06 | Closed |  |  |  | Gokul | 2025-02-10 | 520 | >60 | June | 2024 | #VALUE!
GTS | Enterprise Integration | 89970025 | 2024-04-30 | Delay in the Foods final order flow | Explore the feasibility to configure alerts at integration layer if OT inbounds are not received as expected. | Problem identification & Alerting | Venkat/Integration | 14/06 - With available OT alerts, Sev 1 incidents can be raised. However, alerts will be finalized after the contract upgrade with OT in July. Hence, closing this action and this will be tracked in SOP action related to this incident. 10/06 - Call has been scheduled on 12/06 to discuss further on these alerts with OT. 04/06 - OT has responded with some available data, however internally they are checking on few others. 31/05 - It was discussed with OT to provide additional details in the existing alerts and OT is exploring the same. Followup call to be scheduled on 05/06 based on everyone's availbality. 30/05 - As the existing alerts from OT are not having much information to interpret the impacted services, call has been scheduled with OT on 31/05 to revisit them. 25/05 - Followup call to be scheduled for 30/05, based on everyone's availability. 21/05 - Integration team to check on existing alerts and followup call scheduled on 24/05. 20/05 - Call scheduled by Naveen to discuss on various actions on 21/05 16/05 - In the PIR reveiew meeting Gokul advised that the ownership of who will own the incident one the alert is triggered is under discussion - meeting to be scheduled. 12/05 - Team is currently working on OT proactive alert to remedy ticket. | B2B MQFTE Team | Tactical | NA | 14/06/24 | Closed |  |  |  | Gokul | 2025-02-10 | 520 | >60 | June | 2024 | #VALUE!
Foods | Foods Supply Chain | 89970025 | 2024-04-30 | Delay in the Foods final order flow | Only a message pileup alert was sent by OpenText(OT) to integration team with no much information during the issue. Review all of the alerts that exist at OpenText and ensure that they are valid and fit for purpose for Customer | Problem identification & Alerting | Marie/OT | 31/07: Lisy confirmed that as part of OT premium support, this is being requested. Also, it is being discussed in premium workshop. Hence closing this action. 23/07: Andrew confirmed that this shall we discussed with Lisy and closed. 18/07: OT confirmed that the mail id "grp-ms-ot-commsnotification@mnscorp.onmicrosoft.com" has been been configured for alerting (to notify for all MKSPN alert related notifications under ACC scope & handling). This needs to be reconfirmed from Lisy and action can be closed. 17/07: This action is the one where OT have blocked all alerts as they are getting multiple failures due to old messages coming through for redundant suppliers. SAP/RP and CMS are working on this. 12/07 - Based on Ivan's request, a single mail id has been shared with him for configuration and awaiting update. 10/07 - Lisy had shared mails IDs (grp-ms-ot-commsnotification@mnscorp.onmicrosoft.com; grp-b2bgatewaymqftesupport@mnscorp.onmicrosoft.com) to Ivan for the alerts to be sent to on 03/07 and I have followed-up with Ivan today on the action. 01/07 - Lisy has got all the required data from SAP and Masterdata team, will schedule the call with OT to discuss on these. 25/06 - Lisy is working with MasterData and SAP B&M, call to be scheduled based on their availability on 26th or 27th. 19/06 - We had an internal call with Lisy, C&H, MasterData and SAP B&M. But, SAP B&M was busy. Hence, the call would be rescheduled by next week by Lisy. 10/06 - Call has been scheduled on 12/06 to discuss further on these alerts(notifying proactively Customer whenever a pile-up of files generates) with OT. 04/06 - OT has responded with some available data, however internally they are checking on few others. 31/05 - It was discussed with OT to provide additional details in the existing alerts and OT is exploring the same. Followup call to be scheduled on 05/06 based on everyone's availbality. 29/05 - We had a call within Customer across portfolios to understand I078 flow and couple of actions have been agreed and a followup call has been scheduled on 31/05. 20/05 - Gokul advises that Marie from OT is working on it. Gokul will speak to her today and get ETA's on completion of the alert review 16/05 - Marie and her team is working on the alerts. 14/05 - Have sent mail to OpenText to check on the status of the action. | Opentext Vendor | Tactical | NA | 31/07/24 | Closed |  |  |  | Gokul | 2025-02-10 | 520 | >60 | July | 2024 | #VALUE!
foods | Foods Supply Chain | 89970025 | 2024-04-30 | Delay in the Foods final order flow | Review if the parallel processing of 5 files is sufficient for our needs or needs changing to make it more effective. | Problem avoidance | Ivan (CSM-OT) & Foods | 28/05 - OT contract is being revisited. 20/05 - Gokul has sent a followup email to Ivan as Ivan said he would have a meeting and update for 16/5 16/05 - Ivan has a Monthly Review with Customer today and he will keep us posted. 14/05 - Have sent mail to OpenText to check on the status of the action. | Opentext Vendor |  | NA | 20/05/24 | Closed |  |  |  | Gokul | 2025-02-10 | 520 | >60 | May | 2024 | #VALUE!
foods | Foods Supply Chain | 89970025 | 2024-04-30 | Delay in the Foods final order flow | Explore the options on the auto recovery in case of any message pile ups in the interface | Problem avoidance | Ivan (CSM-OT) & OT Integrators | 28/05 - Lisy confirmed that Customer is renegotiating the OT contract, including a review of the SLAs. Hence, closing the action. 20/05 - Ivan has a Monthly Review with Customer today and he will keep us posted. 14/05 - Have sent mail to OpenText to check on the status of the action. | Opentext Vendor | Strategic | NA | 28/05/24 | Closed |  |  |  | Gokul | 2025-02-10 | 520 | >60 | May | 2024 | #VALUE!
foods | Foods Supply Chain | 89970025 | 2024-04-30 | Delay in the Foods final order flow | Review and update the Foods SOP with what service OT manages and monitors for Customer (FFO and ASN’s) | Solution & Recovery | Lisy/Vinoth | 20/05 - A FFO SOP will be created during the "FFO dashboard in Power BI", EPIC ID: FSORP-20668. Hence, closing this action. 16/05 - Naveen B is working on it. 14/05 - Vinoth is OOO, hence reached out to Lisy. 30/04 - To include both inbound and outbound impacts | FITS |  | NA | 20/05/24 | Closed |  | FSORP-20668 |  | Gokul | 2025-02-10 | 520 | >60 | May | 2024 | #VALUE!
GTS | Enterprise Integration | 89970025 | 2024-04-30 | Delay in the Foods final order flow | Only a message pileup alert was sent by OpenText(OT) to integration team with no much information during the issue. Based on the finalized alert configuration by OT, the Integration SOP for OT services. | Solution & Recovery | Venkat/Integration | 31/07: DL has been sent to OT and we are getting alerts, it will be updated in the SOP. Alerts improvement is also in discussion as part of Premium support workshop. 23/07: Once OT alerts are finalized, Venkat to update the SOP and this action can be closed.. 18/07: OT confirmed that the mail id "grp-ms-ot-commsnotification@mnscorp.onmicrosoft.com" has been been configured for alerting (to notify for all MKSPN alert related notifications under ACC scope & handling). This needs to be reconfirmed from Lisy and Venkat to update the SOP and this action can be closed. 12/07 - Based on Ivan's request, a single mail id has been shared with him for configuration and awaiting update. 10/07 - Lisy had shared mails IDs to Ivan for the alerts to be sent to on 03/07 and I have followed-up with Ivan today on the action. 01/07 - Lisy has got all the required data from SAP and Masterdata team, will schedule the call with OT to discuss on these. 25/06 - Lisy is working with MasterData and SAP B&M, call to be scheduled based on their availability on 26th or 27th to finalize on the receipients. 14/06 - SOP will be updated once the contract upgrade with OT is done and the alerts are raised as Sev 1 incidents. 10/06 - Call has been scheduled on 12/06 to discuss further on these alerts with OT. 04/06 - OT has responded with some available data, however internally they are checking on few others. 31/05 - It was discussed with OT to provide additional details in the existing alerts and OT is exploring the same. Followup call to be scheduled on 05/06 based on everyone's availbality. 30/05 - As the existing alerts from OT are not having much information to interpret the impacted services, call has been scheduled with OT on 31/05 to revisit them. 25/05 - Followup call to be scheduled for 30/05, based on everyone's availability. 21/05 - Integration team to check on existing alerts and followup call scheduled on 24/05. 20/05 - PIR audit - Venkat to schedule a call 12/05 - Team is working on alerting, once it is done. SOP will be updated with them as well. 30/04 - To include both inbound and outbound impacts | B2B MQFTE Team | Tactical | NA | 31/07/24 | Closed |  |  |  | Gokul | 2025-02-10 | 520 | >60 | July | 2024 | #VALUE!
foods | Foods Supply Chain | 89970025 | 2024-04-30 | Delay in the Foods final order flow | Ensure the right SME from OT are joining the Customer MIM bridges on a timely manner | Solution & Recovery | Marie/OT | 30/04 - Marie (OT) agreed on the same | Opentext Vendor |  | NA | 30/04/24 | Closed |  |  |  | Gokul | 2025-02-10 | 520 | >60 | April | 2024 | #VALUE!
GTS | Operations | 89970025 | 2024-04-30 | Delay in the Foods final order flow | Review the impact for all portfolios except foods due to OT issues | Supplier and support involvement | Gokul/MIM | 12/06 - Lisy confirmed that we can close this action. 10/06 - Have scheduled a call with Lisy to discuss on this action 04/06 - Needs to be discussed with Lisy and close this action. 28/05 - Got confirmation from Service LEads of Selling and Service Experience, Customer Engagement,Platform and Store Ops. Awaiting to confirm from List and close the action. 20/05 - HR and property Service Leads confirmed that there is no impact to them, I am checking with other portfolios. 16/05 - Most of the portfolios have reverted stating there is no impact, following up with the rest. 07/05 - Have sent mail to all service lead other than Foods to understand if there are any impacts and getting responses | Service Management | Strategic | NA | 2024-12-06 | Closed |  |  |  | Gokul | 2025-02-10 | 520 | >60 | June | 2024 | #VALUE!
foods | Foods Supply Chain | 89970025 | 2024-04-30 | Delay in the Foods final order flow | Review the process followed to raise a Sev1 with OT | Issue handling/Management | Marie/OpenText (OT) | 16/05 - Marie has stated as below are the parameters or criteria that the Production Support Team follows when raising an issue to the highest severity/Severity 1 Urgency is High and Impact is High A Managed Service Customer has a large number of its trading partners affected with extreme impact. •work around available or alternate method of transacting •Critical component outage without Customer workaround •Customers are unable to transact 14/05 - Have sent mail to OpenText to check on the status of the action. | Opentext Vendor |  | NA | 16/05/24 | Closed |  |  |  | Gokul | 2025-02-10 | 520 | >60 | May | 2024 | #VALUE!
foods | Foods Supply Chain | 89970025 | 2024-04-30 | Delay in the Foods final order flow | Review the Service Wrap with OT | Supplier and support involvement | Andrew G | 20/05 - Customer is renegotiating the OT contract, including a review of the SLAs. Hence, Andrew confirmed that the aciton can be closed. 14/05 - Followed up with Andrew on the status of the action. | FITS |  | NA | 20/05/24 | Closed |  |  |  | Gokul | 2025-02-10 | 520 | >60 | May | 2024 | #VALUE!
GTS | ETP-On premise services | 89955164 | 2024-04-26 | Store colleagues unable to book in parcels on the collection app | ControlM outages – Can this be done in active-active mode. (This has been done before) | Problem avoidance | Satya Malayandi | 13/05: In this is scenarioc control-m cannot be made available on secondary as we had required Control-M DB outage. We have not run Control-M DB in secondary until.Team will check the whether the failover has been tested if not can that be performed. 10/05: Awaiting further updates | SMT tools | Strategic | NA | 27/06/24 | Closed |  |  |  | Saloni | 2025-02-10 | 524 | >60 | June | 2024 | #VALUE!
Customer Channels | Service Experience | 89955164 | 2024-04-26 | Store colleagues unable to book in parcels on the collection app | Incident reporting process for web engg applications by retail Ops | Issue handling/Management | Arthi | 27/06: Its has been agreed communicate over a group chat. Retail ops have added the .COM SM where any collection app related issue will be reported. 28/05: Discussion are ongoing with relavent stakeholder there is delay in response as one stakeholder (Katie) was out of office. 21/05:Arthi is laising with Retail ops and is aimed to close this action by end of this week 10/05: Awaiting further updates | Service management | Tactical | NA | 27/06/24 | Closed |  |  |  | Saloni | 2025-02-10 | 524 | >60 | June | 2024 | #VALUE!
Customer Channels | Service Experience | 89955164 | 2024-04-26 | Store colleagues unable to book in parcels on the collection app | Alert in store Collection App on the traffic | Problem identification & Alerting | Vijesh Mehta | 21/05: Alerting has been configured under the JIRA reference- EG-6632 10/05: This action to taken as part of next sprint 15/05 | Store collection app |  | NA | 21/05/24 | Closed |  | EG-6632 |  | Saloni | 2025-02-10 | 524 | >60 | May | 2024 | #VALUE!
GTS | Enterprise Integration | 89955164 | 2024-04-26 | Store colleagues unable to book in parcels on the collection app | Alerts or audits in integration layer EM/B2B layer | Problem identification & Alerting | Mukundan Rajagopalan | 10/05: We have alerts configured for this flow/queues, however auditing is not feasible in EM. | Enterprise Middleware Team |  | NA | 2024-10-05 | Closed |  |  |  | Saloni | 2025-02-10 | 524 | >60 | May | 2024 | #VALUE!
Customer Channels | Service Experience | 89955164 | 2024-04-26 | Store colleagues unable to book in parcels on the collection app | Sterling support included this transaction in Standard Operating Procedures (SOP) for ControlM outages, ensuring manual triggers are initiated as necessary. | Solution & Recovery | Vipin / Rajeev | 26/04: This action has been closed | Order management system |  | NA | 26/04/24 | Closed |  |  |  | Saloni | 2025-02-10 | 524 | >60 | April | 2024 | #VALUE!
Customer Channels | Service Experience | 89955164 | 2024-04-26 | Store colleagues unable to book in parcels on the collection app | An alert has been implemented by Sterling support to flag instances where ready to collect transaction not picked to execute from OMS to CollectionDB | Problem identification & Alerting | Vipin / Rajeev | 26/04: This action has been closed | Order management system |  | NA | 26/04/24 | Closed |  |  |  | Saloni | 2025-02-10 | 524 | >60 | April | 2024 | #VALUE!
Customer Channels | Service Experience | 89961127 | 2024-04-26 | Order Drop on Customer.com Website | Investigate what caused the Vnet routing change on EU North | Root cause | Aadil Kasmani | We need to understand what caused the VNet routing change so that we can be sure this problem will not occur again. One of the engineers in another team managed to recreate the issue. Aadil will set up a call with the engineer and Microsoft in order to triage the issue | Service Management |  | NA | 2024-02-05 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 524 | >60 | May | 2024 | #VALUE!
Customer Channels | Service Experience | 89961127 | 2024-04-26 | Order Drop on Customer.com Website | Certificate renewal/selfsigned certs | Problem avoidance | Tom Peasgood and David Raine | 17/05 - All the self -signed certificates needs to be pinned as akamai Akamai does not trust a self-signed cert without pinning -but the issue is that brightcloud does not have support for this built-in, so we have not updated pipelines accordingly.WE have a backlog opened with Brightclouds to have it all addressed. 26/04 -Experience Layer team will discuss with David Raine how to get self-signed certificates which do not need to be pinned to Akamai | Expereince Layer team |  | NA | 17/05/24 | Closed | NA | https://github.com/DigitalInnovation/brightcloud/issues/1047 | NA | Saloni | 2025-02-10 | 524 | >60 | May | 2024 | #VALUE!
Customer Channels | Service Experience | 89961127 | 2024-04-26 | Order Drop on Customer.com Website | Alerting | Problem identification & Alerting | Dan Tailby David Raine | 13/05 - This is a Long term actions, teams will continue to track this further via a backlog https://jira.marksandspencer.app/browse/BASKET-918 26/04: 403 alerts Dan will add a 403 alert for the Basket team . (Anything above the‘normal’ threshold will alert) this will give early warning of issues. Akamai datacentre down There was a “data centre down” Akamai alert that triggered when there were problems with the certificate. David will route this to the supergraph team/Experience layer so that they are aware when their origins are unreachable. | Akamai |  | NA | 13/05/24 | Closed | NA | BASKET-918 | open | Saloni | 2025-02-10 | 524 | >60 | May | 2024 | #VALUE!
Customer Channels | Service Experience | 89961127 | 2024-04-26 | Order Drop on Customer.com Website | Akamai knowledge | Issue handling/Management | David Raine Wain Glaister | 17/05- All the relevant access were provided to the teams and the requried trainings are provided aswell. Frequent trainings will be provided going forward. 26/04 -Akamai self-serve Carrying out GTMs in Akamai and throttling etc should be selfserve within the Dev Ops teams. David will provide training on GTM, throttling , Cache keys to share the knowledge . He will also provide Akamai access to anyone who needs it . Out of hours support for Akamai/cascading of decisions Dev Ops teams were not aware that they would have to carry out certain Akamai functions (GTM etc) both in hours and out of hours. Wain will discuss this further with Steve Warren /senior leadership. | Akamai |  | NA | 17/05/24 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 524 | >60 | May | 2024 | #VALUE!
Customer Channels | Service Experience | 89961127 | 2024-04-26 | Order Drop on Customer.com Website | Raising of incidents via Pager Duty/Remedy | Problem identification & Alerting | Aadil Kasmani and Dan Tailby Tom Peasgood | 09/06 - The pager duty and remedy integration has been established. Team is getting the required alerts via PD 13/05 - Queue was existing for the team on Remedy, however, it is setup under the old product team name. Queue name has been corrected now and Aadil will be checking on the integration setup with pager duty and will confirm back when it is working. ETA - 15/05 26/04: Aadil and Dan will investigate whether there is an easy way to get information from Pager Duty. Tom will check whether there is integration with Remedy | Service Management | Tactical | NA | 2024-09-06 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 524 | >60 | June | 2024 | #VALUE!
GTS | ETP- Cloud operations / Frameworks | 89949184 | 2024-04-17 | Central network connectivity issue impacting various cloud based applications | Feasibility on receiving notifications/alerts from MS during such backend host updates | Problem avoidance | Andrei Simonescu (Microsoft) | 17/04: Microsoft have confirmed that not all minor changes on the MS environment can be communicated as there could be many during the day. Also Microsoft confirmed that there is no way that the updates they do can be carry out in a controlled manner with Customer fully aware unless we move to dedicated infrastructure. | Microsoft Vendor |  | NA | 17/04/24 | Closed |  |  |  | Saloni | 2025-02-10 | 533 | >60 | April | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89949184 | 2024-04-17 | Central network connectivity issue impacting various cloud based applications | Convert email alert to remedy alert to entire NOC– Mahendran Pradeep 18/04. Ask Pradeep if alert can go to mobile. | Problem identification & Alerting | Mahendran Mahalingam (NOC)/Gokul (MIM) | 22/05: Vendor recommended firewalls have been upgraded with the bug fix, hence closing 20/05: Gokul to follow up with network team 13/05: Have followed up with Mahendran, most of the alerts are configured, he is reconfirming if all are configured. 26/04: Have asked Mahendran to confirm if all alerts are configured. 17/04: Most of alerts were configured the same day. | Network |  | NA | 22/05/24 | Closed |  |  |  | Saloni | 2025-02-10 | 533 | >60 | May | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89949184 | 2024-04-17 | Central network connectivity issue impacting various cloud based applications | Write up the recovery scenario so that all NOC engineers know what to do. | Solution & Recovery | Mahendran Mahalingam | 02/05 - Team is made aware of this and SOP updated. 26/04: Have asked the status of this action to Mahendran. | Network |  | NA | 2024-02-05 | Closed |  |  |  | Saloni | 2025-02-10 | 533 | >60 | May | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89949184 | 2024-04-17 | Central network connectivity issue impacting various cloud based applications | Do we have any proactive alerts configured in PA firewall to notify our network teams on any interface changes at Palo Alto | Problem identification & Alerting | Mahendran Mahalingam | 17/04: Alerts are already in place to notify the network team | Network |  | NA | 17/04/24 | closed |  |  |  | Saloni | 2025-02-10 | 533 | >60 | April | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89949184 | 2024-04-17 | Central network connectivity issue impacting various cloud based applications | Can we have a risk raised until we get a permanent fix? | Solution & Recovery | Mahendran Mahalingam | 14/05 - Risk 2133 has been raised until we have a permanent fix. 26/04: Have asked the status of this action to Mahendran. | Network |  | NA | 14/05/24 | Closed |  |  |  | Saloni | 2025-02-10 | 533 | >60 | May | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89949184 | 2024-04-17 | Central network connectivity issue impacting various cloud based applications | We cannot automate the firewall “failover/isolation no because backend FW itself is healthy. NOC to investigate alternatives. Can the load balancer monitor and take action after aged out logs? | Root cause | Mahendran Mahalingam | 02/05 - We have checked internally and confirmed that there is no option to automate the firewall failover. 26/04: Have asked the status of this action to Mahendran. | Network |  | NA | 2024-02-05 | Closed |  |  |  | Saloni | 2025-02-10 | 533 | >60 | May | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89949184 | 2024-04-17 | Central network connectivity issue impacting various cloud based applications | NOC to improve and advise on more thorough health checks. So, we don’t depend so much on MS notifications to detect a potential issue | Solution & Recovery | Mahendran Mahalingam | 02/05 - Team has been made aware of this and SOP updated. 26/04: Have asked the status of this action to Mahendran. | Network |  | NA | 2024-02-05 | Closed |  |  |  | Saloni | 2025-02-10 | 533 | >60 | May | 2024 | #VALUE!
Customer Channels | Service Experience | 89944603 | 2024-04-16 | Telephony issues in ROI and UK stores | NLP team to provide a full written explanation of what was required by Twilio, what was done by the NLP team to fulfil this request and what caused the issue. Also investigate why ROI stores were fully impacted and UK stores intermittently impacted. This statement will also include granular detail of the discussions held prior to the change with Cyber and NOC teams. | Root cause | Chris McGrath/NLP team | Background: Twilio are expanding the Interconnect media services (with new IPs) for calls in all regions. Twilio also are expanding the RTP port range to 10000-60000 UDP (Twilio are doing that to be able to support more traffic per IP. The more ports you have you can support more calls. As Twilio mentioned in the change log They are making this change to improve the flexibility , reliability and scalability of voice products.) This change improves the flexibility, reliability, and scalability of our Voice products. Twilio are using the new new Media Service and expanded port ranges listed below for all Voice Interconnect traffic. 2. Technical Impact: In order to enable these new Media Services: The new IP addresses must be whitelisted on the Customer perimeter Palo Alto Firewalls. Enable the changes on the Customer Twilio Console Voice Configuration General/ Enable New Voice Media IP Ranges settings - toggle/option button with the new IP addresses in listed. 3. Impact if not done: Any new Interconnect connections created after November 16, 2023 will be configured to use the new IP and port ranges. Failure to do so may cause one-way audio and dropped calls. 4. What Caused the Issue????? The Ip's must be whitelisted in all interconnect platforms. These 4 Ip's did not allow the traffic as the new Ip Ranges from Twilio were not allowed. 185.168.95.200 legacy pool only 185.168.95.201 legacy pool only 185.168.95.232 legacy pool only 185.168.95.233 legacy pool only This caused one way communication to happen. To resolve this, we need to add the new Ip Range to mitel and sabio firewall. 168.86.128.0/18 UDP port range: 10000-60000 (expanding from 10000-20000) why ROI stores were fully impacted and UK stores intermittently impacted. Twilio suspect that at this point would be that have different network paths for each country. Prashant also mentioned that Irish calls go via Mitel which might have something to do with this. Once the ip's were whitelisted, the twilio Team was notified about this and they asked us to toggle the new ip's. once we toggled the new ip's it caused one way traffic to happen and the calls were impacted. 5. Discussions held prior to the change with Cyber and NOC teams. Nlp Team Action: Nlp Team had a call with Angelos from twilio to confirm what are the ip's required to whitelist. After getting the Ip's, Nlp Team raised a tufin request 3125 to implement the change on feb 28th. On march 18 it cleared cyber approval and went for implementation. With Cyber Team, Nlp Team had discussed that it was additional ip's that were required to be whitelisted to improve flexiblity. | NLP Team |  | NA | 2024-10-05 | Closed |  |  |  | Saloni | 2025-02-10 | 534 | >60 | May | 2024 | #VALUE!
GTS | Operations | 89944603 | 2024-04-16 | Telephony issues in ROI and UK stores | Change management team to go through the change process end to end with the NLP team | Problem avoidance | Priyadharshini Somasundaram | 08/05: A change management process was conducted for NLP team | Service Management |  | NA | 2024-07-05 | Closed |  |  |  | Saloni | 2025-02-10 | 534 | >60 | May | 2024 | #VALUE!
GTS | Operations | 89944603 | 2024-04-16 | Telephony issues in ROI and UK stores | NLP team have now been advised to call out all recent changes when in an incident scenario. | Problem avoidance | Rehan Siddiqui | 17/04: Agreed on the call | Service Management |  | NA | 17/04/24 | Closed |  |  |  | Saloni | 2025-02-10 | 534 | >60 | April | 2024 | #VALUE!
Customer Channels | Service Experience | 89944603 | 2024-04-16 | Telephony issues in ROI and UK stores | NLP team to provide a proposal to improve testing of these changes especially with regards to calling stores after a change to ensure all is well. | Problem avoidance | Chris McGrath/NLP team | 19/06: Team will action this under the product back log to identify and implement the testing stragery 21/05: Chris is out of office, team to discuss further once he is back next week 10/05: Discussions are underway, awaiting further updates | NLP Team | Strategic | NA | 19/06/24 | Closed |  | Riceh -577 |  | Saloni | 2025-02-10 | 534 | >60 | June | 2024 | #VALUE!
Customer Channels | Service Experience | 89944603 | 2024-04-16 | Telephony issues in ROI and UK stores | Propose tools that will automate the alerting of issues regarding being unable to make or receive calls. Chris to advise the results of any business cases for the deployment of these tools proposed to Customer – this automation will reduce the dependency on having to make test calls three times a day to find any potential issues. | Problem avoidance | Chris McGrath/NLP team | 19/06: Team will action this under the product back log to identify and implement the automation tool 21/05: Chris is out of office, team to discuss further once he is back next week 10/05: Discussions are underway, awaiting further updates | NLP Team | Strategic | NA | 19/06/24 | Closed |  | Riceh -578 |  | Saloni | 2025-02-10 | 534 | >60 | June | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89942250 | 2024-04-16 | Delay in D&F batch impacting ordering and allocations for C&H DC's | What was causing the memory spike since the migration? | Root cause | Ganesh Regoubady (BY TAM) | 30/04 -There is no evidence to compare against the data point before the migration. The server is hosted in BY Azure like the earlier one before migration. This means that if there is any event when the servers are identified to be faulty then new virtual machines are assigned. In this case the issue was with the memory parameter of the database server. This required tuning or upliftment in the memory. We choose to uplift the memory since it was the quickest approach to solve the criticality. 17/04 -BY to check with the project/migration team if any logs exist before the migration and after the migration to identify a trend. Also to analyse if new migrated servers are having defect/issues | BY Team |  | NA | 30/04/24 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 534 | >60 | April | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89942250 | 2024-04-16 | Delay in D&F batch impacting ordering and allocations for C&H DC's | Check on why the Swap memory was not working as expected on 11/04 | Root cause | Ganesh Regoubady (BY TAM) | 30/04 -Memory swap is not a preferred approach. When it happens there needs to be appropriate action taken. Although new knew it, there were BY internal discussion to fine tune parameters in DB side to address the issue. Before we could conclude on the approach to be taken, the event happened on the day when the database server had low memory leading to performance challenges and slowness. The recommendation received from Red hat vendor is to tune the database and they have not pinpointed any particular action leading to the issue since memory swap is expected to cause such disruption. 17/04 -A sev 1 case has been raised with Vendor Redhat for further investigations. | BY Team |  | NA | 30/04/24 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 534 | >60 | April | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89942250 | 2024-04-16 | Delay in D&F batch impacting ordering and allocations for C&H DC's | Review the memory utilisation continuously for next few days and discuss on the upcoming SLA review calls. | Problem avoidance | BY Team – DBA Team | 30/04 - This under constant review and we will be sharing available memory graph during monthly SLA review. There is one shared during the SLA review meeting for the month of March 2024. 17/04 -Proactively check the trend after the memory uplift (11/04) – to identify any abnormal memory spike’s | BY Team |  | NA | 30/04/24 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 534 | >60 | April | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89942250 | 2024-04-16 | Delay in D&F batch impacting ordering and allocations for C&H DC's | Ensure BY team communicate with D&F team whenever any abnormalities are observed | Solution & Recovery | BY Team – DBA Team | A process has been agreed to immediately inform our D&F team whenever BY identifies any memory/CPU issues which iwill potentially affect the batch | BY Team |  | NA | 16/04/24 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 534 | >60 | April | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89942250 | 2024-04-16 | Delay in D&F batch impacting ordering and allocations for C&H DC's | Do we have the right alerting in place to notify on the memory spike in BY and D&F. | Problem identification & Alerting | BY Team – DBA Team | Alerting is in place at BY and check points are available at D&F - the incident was picked up through alerting. | BY Team |  | NA | 16/04/24 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 534 | >60 | April | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89942250 | 2024-04-16 | Delay in D&F batch impacting ordering and allocations for C&H DC's | Review the BY engagement process - There was a delay in engaging BY initially during the incident. | Issue handling/Management | D&F team and BY | A new process has been agreed with BY – where D&F can raise a Sev1 for any delays in D&F batch immediately and BY MIM team will join our call to assess the impact and will further include their tech teams for triaging. | D&F and BY team |  | NA | 16/04/24 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 534 | >60 | April | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89942250 | 2024-04-16 | Delay in D&F batch impacting ordering and allocations for C&H DC's | Why did not we consider the usage of contingency- by use day-1 data for the C&H orders? | Solution & Recovery | D&F team/ Allen Eapachen | Contingency was not invoked in this scenario as the issue was with the database performance, thus even if we would have invoked contingency the order processing would have been slow. | TCS D&F team |  | NA | 16/04/24 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 534 | >60 | April | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89942250 | 2024-04-16 | Delay in D&F batch impacting ordering and allocations for C&H DC's | Review and document the potential impacts when there is a delay in D&F. | Impact analysis | Shanmugaganathan Murugan | 30/04 - SOP has been updated and all the team members are appraised on the same 16/04 -The impacts to TMS, Beam were highlighted on the call while the CD MI reports impact was not highlighted | TCS D&F team |  | NA | 30/04/24 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 534 | >60 | April | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89942250 | 2024-04-16 | Delay in D&F batch impacting ordering and allocations for C&H DC's | Ensure we get accurate communications out to the logistics team on frequent interval during such incidents. | Business & IT Communication | Vivek Kumar/Nandakumar Sivalingam | It has been agreed with WMS team to communicate to the comms every 30 mins during the incidents | Service Lead (C&H) |  | NA | 16/04/24 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 534 | >60 | April | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89934699 | 2024-04-12 | C&H Bradford DC colleagues were experiencing issues on their pick stations | How can these manual error be prevented during a change? | Problem avoidance | Michael William | 29/05 - Knapp has updated all their Knowledge articles and documents are shred to all the relevant teams. Also relevant trainings has been given on the same. 15/05 - Knapp continues to work on the preventive measure. 09/05- Problem Owner yet to update on the Problem action 30/04 - Yet to get an update from the problem owner 15/04 -Teams will be provided another set of training on the do’s and don’t’s during the patching activity also Knapp team is working to explore the ways for automatic failover | Bradford Product team | Tactical | NA | 29/05/24 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 538 | >60 | May | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89934699 | 2024-04-12 | C&H Bradford DC colleagues were experiencing issues on their pick stations | Review the alerting in SRC to notify on the incorrect/change in configuration | Problem identification & Alerting | Lukasz (Knapp) | 02/05 - Alerting on SRC is not feasible as it is a legacy compoment, however on-site team has been trained on what to do and what to check. 30/04 - Yet to get an update from the problem owner 15/04 -Though we have the right alerting in place on all the other servers, There was a delay in identifying the cause of the issue as the issue was on the SRC DB sever and SRC is a legacy component. Knapp will review the feasibility for extra alerting on the SRC configurations. | KNAPP (3rd Party) |  | NA | 2024-02-05 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 538 | >60 | May | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89934699 | 2024-04-12 | C&H Bradford DC colleagues were experiencing issues on their pick stations | Review the change process – Ensure we have a reference change tracked in Customer environment as well for an enhanced hypercare | Problem avoidance | Michael William | A process has been agreed to create and record CR’s in BMS helix tool for Customer review and reference | Bradford Product team |  | NA | 2024-12-04 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 538 | >60 | April | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89934699 | 2024-04-12 | C&H Bradford DC colleagues were experiencing issues on their pick stations | 30/04 - Usually Fulfilment team does the proposition movement and it is decided based on the issue (volume of orders impacted) 15/04 -Ensure we cascade the right information on the bridge call to the MIM’s for the right communication (eg. There was a confusion on the prop movement | Issue handling/Management | Vivek kumar | There was a confusion on the Prop movement information provided on the MIM bridge. Vivek will liaise with the fulfilment team to get to know the exact process behind the proposition movement | Service Lead (Bradford) |  | NA | 30/04/24 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 538 | >60 | April | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89934699 | 2024-04-12 | C&H Bradford DC colleagues were experiencing issues on their pick stations | Ensure timely engagement of Knapp on the call for the recovery actions to be discussed? | Supplier and support involvement | Lukasz (Knapp) | Since we did not have Knapp on the MIM bridge we had to relay on their hourly comms for the recovery actions and next steps. Knapp has agreed to join MIM bridges during any such Sev 0 incidents at the site. POC for escalations will be : Lukasz : lukasz.szczytowski@knapp.com | KNAPP (3rd Party) |  | NA | 2024-12-04 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 538 | >60 | April | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89934699 | 2024-04-12 | C&H Bradford DC colleagues were experiencing issues on their pick stations | Devise a SOP/Runbook/Document prepared with the right steps on the recovery and have it circulated with Knapp engineers and Hotlines. | Solution & Recovery | Lukasz (Knapp) | 02/05 - Internal database knowledge document has been updated with additional information (extra checks) and all relevant teams informed. 30/04 - Yet to get an update from the problem owner 15/04 -Database knowledge document at the site has been updated for the engineers to refer, however Hotline technicians are yet to be updated. | KNAPP (3rd Party) |  | NA | 2024-02-05 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 538 | >60 | May | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89934699 | 2024-04-12 | C&H Bradford DC colleagues were experiencing issues on their pick stations | Review the upcoming major changes to ensure we have extra hypercare’s during such critical changes. | Problem avoidance | Michael William | 13/05 - A change process has been agreed within the teams, going forward a CR ticket will be raised while 3rd party is performing any changes in production. There is an next outage planned on 04th May on the backup systems at the site. Teams will make sure we have a CR raised in our system, ensure we have the engineers and hotline tech’s trained with the right knowledge. | Bradford Product team |  | NA | 13/05/24 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 538 | >60 | May | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89740877 | 2024-04-10 | Barnstaple-1805 store hard down due to BT Both links down | BT to investigate and report the detailed root cause of the issue why both links went down at same time. | Root cause | BT | When the custom cipher configuration was removed, the health check was successful, and the AKS cluster started receiving traffic. However, it was discovered that the MyAccount application has dependencies on the custom ciphers. As a result, the application started failing when the custom cipher configuration was removed. | NOC |  | NA | 2024-10-04 | Closed |  |  |  | Saloni | 2025-02-10 | 540 | >60 | April | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89740877 | 2024-04-10 | Barnstaple-1805 store hard down due to BT Both links down | There was a challenge in engaging BT during the weekend. Agree with BT to address single store circuit issues | Solution & Recovery | BT/Rajesh | 02/05 - Rajesh update that NOC will continue to follow the SLA agreed with BT and away on any migration plans for non-SLA circuits. 16/04: Rajesh is working with the project team on this to get an update. 10/04: Follow ups being carried out with BT to agree on a way forward to address single store circuit issues in a timely manner. | NOC |  | NA | 2024-02-05 | Closed |  |  |  | Saloni | 2025-02-10 | 540 | >60 | May | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89740877 | 2024-04-10 | Barnstaple-1805 store hard down due to BT Both links down | As Barnstaple store is still under the SDIA (Store Direct Internet Access) configuration, issues were identified after provisioning the 4G solution. What is the plan to convert the remaining SDIA stores to DPDIA (Digital Perimeter Direct Internet Access) during the hard down scenarios. | Solution & Recovery | Suganya C | 09/05: SDWAN migration for pending stores is ebing done as part of the backlog NKB-2240. 16/04: Team is working on it. 10/04:As part of SDWAN migration, stores are converted to DPDIA configuration, ie, if the stores goes hard down, there is no additional activity required after provisioning the 4G cradle point as the traffic gets resolved through Digital perimeter. However, since this store has not been migrated yet and it falls under the SDIA configuration, additional IP whitelisting had to be performed to mitigate the impact as the traffic was hitting the store local firewall. There is a plan to migrate the remaining 40 stores to SDWAN through RIT team. Work with RIT team to get the list of stores scheduled and the respective ETAs . | NOC |  | NA | 2024-09-05 | Closed |  |  |  | Saloni | 2025-02-10 | 540 | >60 | May | 2024 | #VALUE!
GTS | Enterprise Technology Platform | 89740877 | 2024-04-10 | Barnstaple-1805 store hard down due to BT Both links down | Ensuring senior stakeholders from TCS and Customer leadership team are apprised for such critical & escalated incident. | Issue handling/Management | Rajesh | 09/05: NOC team agreed that they would engage service management to make some process and ensure the leadership team to be available on top of escalated incident . 16/04 Rajesh is working with the project team on this to get an update. 10/04: This has been agreed. We would engage service management to make some process and ensure the leadership team to be available on top of escalated incident | NOC |  | NA | 2024-09-05 | Closed |  |  |  | Saloni | 2025-02-10 | 540 | >60 | May | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89740877 | 2024-04-10 | Barnstaple-1805 store hard down due to BT Both links down | Perform testing to improve the performance on 4G/5G solution as the click and collect app was not working on 4G/5G cradlepoint. | Solution & Recovery | Rajesh | 09/05: SDWAN migration for pending stores is ebing done as part of the backlog NKB-2240. 16/04 Rajesh is working with the project team on this to get an update. 10/04: As mentioned in action 3, as this store has not been migrated to SDWAN yet, therefore, is a SDIA configured store, the Ips were hitting the store’s local firewall to access the application. Therefore, once the Ips were whitelisted, it restored the application access. This issue will be addressed once the store has been migrated to SDWAN | NOC |  | NA | 2024-09-05 | Closed |  |  |  | Saloni | 2025-02-10 | 540 | >60 | May | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89740877 | 2024-04-10 | Barnstaple-1805 store hard down due to BT Both links down | During the store hard down, DN engineer was not available to the store. Agree a plan with DN to timely visit the store to install the 4G solution as there was a delay of 12 hrs. In addition, DN engineer should equipped with all the require cables to provide the access to the NOC if required. | Solution & Recovery | Rajesh | 16/08: Kamal confirmed that the DN SOPs are sent 08/08: Kamal advised that the document has been shared and completed however he would still like to confirm. 12/07: SOPs are being created however, we await an ETA from the team 09/07 - Rajesh updated that it is still being worked upon and will try to send to Laura within 12th July 24/06 - SOP is about to be shared with Laura on 30th and it needs to be followed by DN. 10/06 - Rajesh updated that the feedback from Ian has been addressed in SOP and is being reviewed. 21/05 - Rajasekar K updated that NOC team is still working on the SOP. 14/05 - NOC team is working on the SOP based on Ian's feedback. 02/05 - Ian has provided feedback on the SOP and team is working on it. 16/04 Rajesh is working with the project team on this to get an update. 10/04: DN engineer didn’t turn up with proper console accessories which delayed on remote troubleshooting, Therefore, a SOP has been created to detail the E2E instructions to be followed by DN in such scenarios. The SOP document is pending review with Ian. Once this is reviewed, it will be shared to Laura to be sent to DN team | NOC | Strategic | NA | 16/08/24 | Closed |  |  |  | Gokul | 2025-02-10 | 540 | >60 | August | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89740877 | 2024-04-10 | Barnstaple-1805 store hard down due to BT Both links down | Instructions to DN were not clear to recover the store. Provide clear instructions to DN team to collect the cradlepoint from the store once the network has been stable and monitored enough for a week. | Solution & Recovery | Rajesh | 10/08 - As this document to be shared is similar to other documents which he is checking, so closing the action. 08/08: Action can be closed as the update is the same as row 351 09/07 - Rajesh updated that it is still being worked upon and will try to send to Laura within 12th July 02/07 - It is still being reviewed internally and possibly will be shared with Laura on 03/07 24/06 - SOP is about to be shared with Laura on 30th and it needs to be followed by DN. 10/06 - Rajesh updated that the this SOP can be added to the 4G SOP and will get it reviewed by Ian. 21/05 - Rajasekar K updated that NOC team is still working on the SOP. 14/05 - NOC team is working on the SOP based on Ian's feedback. 02/05 - Ian has provided feedback on the SOP and team is working on it. 16/04 Rajesh is working with the project team on this to get an update. 10/04: The SOP in action 6 will details the collection instruction to be followed by DN in future scenarios | NOC | Tactical | NA | 2024-10-08 | Closed |  |  |  | Gokul | 2025-02-10 | 540 | >60 | August | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89740877 | 2024-04-10 | Barnstaple-1805 store hard down due to BT Both links down | There are existing stores running on superfast broadband EBB circuit which don’t have any define SLA delaying the restoration of store link. Agree on a plan with BT to speed up the migration from EBB to BB1 across all the stores in the estate | Solution & Recovery | Manish Rai/ Suganya C | 10/06 - There is no reference for this as it is floodgate WAN expansion program, Jira story not created as implementation manage by RIT. Hence, closing the action. 21/05 - Manish updated that the Floodgate WAN expanssion project is planned to complete in Q1'25 and it is in progress, have asked Manish to share the Jira log reference. 02/05 - Checking with Manish for backlog reference. 16/04 - Flood gate migration project in progress for the mitigation and expected to complete by Q1 FY25. for all the store which are running on superfast Broadband EBB circuit. 10/04: The project team are working with BT to secure the list of all stores pending migration to BB1 circuits and the ETAs, There is another project – Floodgate migration which will convert the BB1 stores to Btnet stores (Enterprise circuits) which will fix these issues permanently. However, this migration is being performed with a limited number of stores in a phased manner due to budget constraints. Work with Manish Rai to get the list of all stores pending migration from BB1 to Btnet and their respective ETAs.24/4 - | NOC | Strategic | NA | 2024-10-06 | Closed |  |  |  | Saloni | 2025-02-10 | 540 | >60 | June | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89740877 | 2024-04-10 | Barnstaple-1805 store hard down due to BT Both links down | There was a challenge in diagnosing the actual issue whilst the NOC teams were troubleshooting as the physical link was up and problem was with radius authentication on the backend. Create a SOP to detail the logical steps to troubleshoot instead of sending engineer onsite performing the checks which delays issue resolution. | Solution & Recovery | Nick Baldwin, BT – Ravi Komalram, Nidhi | 16/08: Kamal confirmed that the SOP to detail the steps for triaging DSL issues SOPs are sent. 08/08: Kamal to get an update by 16th August 12/07: A SOP to detail the steps for triaging DSL issues is currently being worked upon by Nick. This will take time, however, work is in progress. ETA: 30/07 09/07 - Have reached out to Nick to understand the latest on the SOP and if needed will speak with Kamal to assist here based on the response from Nick 25/06 - Nick is working on the SOP, but it needs to be prioritized. We have a scheduled a call with NOC team to discuss on all open problem actions by 27/06. 10/06 - Rajesh is checking with Nick on the latest status of the SOP. 21/05 - Rajasekar K updated the Nick is still working on the SOP. 14/05 - Nick is still working on the SOP. 02/05: Nick updated that he is working on the SOP for diagnosing xDSL issues and will let us know once this is done. 16/04 Will chweck with the user again tomorrow as unable to get an update. 10/04: Due to a knowledge gap, the investigations relied on Nick which delayed the issue identification. Therefore, Nick will create a SOP document detailing the troubleshooting steps for the NOC engineers to follow during future scenarios. In addition, BT will also create a design document facilitating the clear understanding of the issue across the engineers. 24/4 - Nick, have started a document on xDSL fault diagnoses. This needs some more work.But Nick has no update BT creating the Design document | NOC | Tactical | NA | 16/08/24 | Closed |  |  |  | Gokul | 2025-02-10 | 540 | >60 | August | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89740877 | 2024-04-10 | Barnstaple-1805 store hard down due to BT Both links down | During hard down scenarios, explore the feasibility for an alternate solution to provision two cradlepoint routers to improve the performance. | Solution & Recovery | Darren Coughlan, Shantanu Krishna Mahato | 25/06 - Manish Rai shared the EPIC ID, NKB-2213 with which the team is working on this project. 10/06 - Rajesh updated that there is no reference for this currently and needs to be added as a service improvement. 20/05 - Floodgate WAN expansion project is planned to complete in Q1'25 and it is in progress. 24/04 - This is on next sprint we have planned, we need to work on techincal specs and already the physical stuff done, next sprint we are in plan to deliver this. 16/04 - Flood gate migration project in progress for the mitigation and expected to complete by Q1 FY25. for all the store which are running on superfast Broadband EBB circuit. 10/04: The feasibility to provision two cradlepoints will be added into the improvement backlog and need to work with Architect for the testing and rollout plans. | NOC | Strategic | NA | 25/06/24 | Closed |  | NKB-2213 | open | Saloni | 2025-02-10 | 540 | >60 | June | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89740877 | 2024-04-10 | Barnstaple-1805 store hard down due to BT Both links down | Prepare a inventory with the number of available cradle point and deploy in store. If required, devise a strategic plan to buy more to have permanent setup in critical store during the peak trading. | Solution & Recovery | Suganya C/ Suganya B | 09/05 - Team is working with Jira reference. NKB - 2408. 02/05 - Suganya B updated that there are potential a mix of devices here. Unless Brooklands has had the original 4G device replaced it was on an older CB850 which is so long ago which is not on the Cradlepoint sales or management systems anymore. She confirmed with Ian that the Problem action can be closed. 16/04: Team is working on it. 10/04:This need to be added as service improvement backlog and actioned – to be actioned before PEAK | NOC |  | NA | 2024-02-05 | Closed |  | NKB - 2408 |  | Saloni | 2025-02-10 | 540 | >60 | May | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89740877 | 2024-04-10 | Barnstaple-1805 store hard down due to BT Both links down | Explore the feasibility of auto disabling unwanted traffic in a 4G solution for SDWAN stores | Solution & Recovery | Suganya C | 25/06 - Suganya C shared the EPIC ID - NKB-2176 with which the team is working on it. 10/06 - Rajesh updated there is no reference for this currently and needs to be added as a service improvement. However will reconfirm from Suganya C. 21/05 - Suganya C agreed to share the Jira reference. 02/05 - This need to be added as service improvement backlog and actioned. Awaiting Jira ID. 16/04: Team is working on it. 10/04: To ensure better performance at stores, check the options to disable non critical traffic after a 4g cradlepoint router has been enabled | NOC | Strategic | NA | 25/06/24 | Closed |  | NKB-2176 | Open | Saloni | 2025-02-10 | 540 | >60 | June | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89740877 | 2024-04-10 | Barnstaple-1805 store hard down due to BT Both links down | Currently EBB circuits having Ip address in same range and therefore, the BT system assumes the IP for BB1 migration which caused the issue. Discuss with BT to have separate range of IP address until all the migration of all stores | Problem avoidance | Manish Rai | 10/06 - As BT confirmed in April, they have escalated their core team to ensure that there is no conflict with the existing IP address. 21/05 - Manish updated that the Floodgate WAN expanssion project is planned to complete in Q1'25 and it is in progress, have asked Manish to share the Jira log reference. 02/05 - Manish Rai informed that the ticket is currently with BT and will move to Vodafone since this is a part of floodgate project for WAN migration. Awaiting further project details. 16/04: Already raised with BT to arrange the discussion with technical team to check the feasiblity to have 2 different range of IP address on primary and secondary link,escalated to Service Manager Nidhi and Ravi in BT. 10/04: This will be checked with BT for further inputs and actions. | NOC | Strategic | NA | 2024-10-06 | Closed |  |  |  | Saloni | 2025-02-10 | 540 | >60 | June | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89740877 | 2024-04-10 | Barnstaple-1805 store hard down due to BT Both links down | Whilst troubleshooting, Network team can raise a log with Juniper to analyse the SRX switches etc to help facilitate the analysis to identify the issues. Ex - (PPOE killing session command to be removed from SRX while testing) | Problem identification & Alerting | Balamurali | 20/05: SOP is updated with the same 16/04: Followed up with Bala. 10/04: NOC will ensure this point is added in our SOP to raise and engage the TAC team pro-actively. | NOC |  | NA | 20/05/24 | Closed |  |  |  | Saloni | 2025-02-10 | 540 | >60 | May | 2024 | #VALUE!
GTS | ETP- Cloud operations / Frameworks | 89934681 | 2024-04-09 | Issues in accessing MyAccount features | Since the change from http to tcp, the health check is performed on the Azure layer not the Kubernetes Layer so this needs to be reverted ultimately. | Permanent Fix | Emmnauel George | 17/06: The changes have been implemented in production and checks have confirmed that no further issues observerd. 04/06: There are some network issues encountered, therefore, the production deployment is yet to be planned. ETA: 15/06. 20/05: The health check changes were tested successfully by Cloud Ops team in DR on 14/05. Discussions are underway with Hisham and Aadil to identify a suitable window to deploy these changes in production. approx ETA: 28/05 13/05: The health change change is planned along with cipher change on DR on 13/05. Based on the results, this will be implemented in prod. ETA: 21/05. | Cloud Ops | Tactical | NA | 17/06/24 | Closed |  |  |  | Saloni | 2025-02-10 | 541 | >60 | June | 2024 | #VALUE!
Customer Channels | Service Experience | 89934681 | 2024-04-09 | Issues in accessing MyAccount features | Review the cipher configuration currently in place and is it in line with other clusters. This is one of the few clusters that has this configuration in place to only accept certain ciphers. | Permanent Fix | Emmanuel George/ Aravind R | 17/06: The changes have been implemented in production and checks have confirmed that no further issues observerd. 04/06: There are some network issues encountered, therefore, the production deployment is yet to be planned. ETA: 15/06. 20/05: The customer cipher config changes were tested successfully by Cloud Ops team in DR on 14/05. Discussions are underway with Hisham and Aadil to identify a suitable window to deploy these changes in production. approx ETA: 28/05 13/05: Cloud Ops have successfully reproduced the issue in non-prod environment and as a permanent fix the custom cipher config needs to be updated with all the Microsoft approved list of cipher along with existing custom list of ciphers. We have established this fact by testing this in non prod to resolve the issue. Plan is to implement this change in both prod & DR cluster and discussion is in progress with application team to finalize the window and implementation plan. The DR testing is planned on 13/05. Based on the DR testing results, prod deplyment date will be finalised. ETA: 21/05 | Cloud Ops/ App team | Tactical | NA | 17/06/24 | Closed |  |  |  | Saloni | 2025-02-10 | 541 | >60 | June | 2024 | #VALUE!
GTS | ETP- Cloud operations / Frameworks | 89934681 | 2024-04-09 | Issues in accessing MyAccount features | Review the process of making production changes on the Kubernetes environment | Problem avoidance | Prasanth Rowlo | 22/05: The Dotcom fesk clusters are reviewed to assess the handling of deployments and explore alternative deployment methods. It has been identified that a central image/configuration deployment model may not be suitable for the Dotcom fesk clusters due to the presence of customized configurations that need to be managed at the cluster level. Additionally, the implementation of changes on both DR (Disaster Recovery) and Prod (Production) clusters simultaneously, especially in the aftermath of an incident at one location, has the potential to result in a complete outage of the application. This poses a significant risk to our resiliency and business continuity, potentially leading to a disruption in service. These observations highlight the need to carefully evaluate deployment strategies and consider alternative approaches to ensure the stability and reliability of the Dotcom fesk AKS clusters. However, in the modernisation initiative of Cloud, its been considered to standardise the environment for platform clusters. 20/05: Prashant had a discussion with Sam Clement and gone through the various attributes - awaiting technical points from him to update here. | Cloud Ops | Tactical | NA | 22/05/24 | CLosed |  |  |  | Saloni | 2025-02-10 | 541 | >60 | May | 2024 | #VALUE!
GTS | ETP- Cloud operations / Frameworks | 89934681 | 2024-04-09 | Issues in accessing MyAccount features | Observability Dashboards for Cloud ops team | Problem identification & Alerting | Emmanuel George | 13/05: Nginx observability dashboard is in place now | Cloud Ops |  | NA | 13/05/24 | Closed |  |  |  | Saloni | 2025-02-10 | 541 | >60 | May | 2024 | #VALUE!
Customer Channels | Service Experience | 89934681 | 2024-04-09 | Issues in accessing MyAccount features | Alerting for Akamai – monitoring dashboards, traffic | Problem identification & Alerting | Application teams - PDP, HP, MYA | 14/05: The alerts have been configured and tested successfully, | App team |  | NA | 14/05/24 | Closed |  |  |  | Saloni | 2025-02-10 | 541 | >60 | May | 2024 | #VALUE!
Customer Channels | Service Experience | 89934681 | 2024-04-09 | Issues in accessing MyAccount features | Alerting for Returns – errors and drop in traffic | Problem identification & Alerting | Aravind R | 07/05: The Alerts have been created in the Returns layer when there is an error or drop in traffic. Aravind has confirmed that the alerts are getting triggered as expected. | Returns team |  | NA | 2024-07-05 | Closed |  |  |  | Saloni | 2025-02-10 | 541 | >60 | May | 2024 | #VALUE!
Customer Channels | Service Experience | 89934681 | 2024-04-09 | Issues in accessing MyAccount features | Alerting for myAccount – errors and drop in traffic | Problem identification & Alerting | Ashok kumar Vallinayagam | 14/05: The alerts have been configured and tested successfully, | My Account team |  | NA | 14/05/24 | Closed |  |  |  | Saloni | 2025-02-10 | 541 | >60 | May | 2024 | #VALUE!
GTS | ETP- Cloud operations / Frameworks | 89934681 | 2024-04-09 | Issues in accessing MyAccount features | RCA – more actions will be created depending on the RCA and recommended permanent fix from Microsoft | Root cause | Emmanuel George | Microsoft is implementing backend network changes to accept traffic only using the approved list of ciphers. This change is part of Microsoft's security and compliance measures to ensure a secure and standardized network environment. The FESK AKS cluster has custom configurations for allowed ciphers, which doesn’t include all the approved ciphers as per Microsoft's standards which caused the isue. | Cloud Ops team |  | NA | 13/05/24 | Closed |  |  |  | Saloni | 2025-02-10 | 541 | >60 | May | 2024 | #VALUE!
GTS | Digital Workplace Services | 89934337 | 2024-04-08 | SALINA WiFi network connectivity issues across various DC's due to CRL expiry | There was a delay in identifying the issue, how can we improve the triaging to identify the issue and mitigate them sooner. F15F7:F14 | Solution & Recovery | MuthuNagappan Subramanian | 11/04: The SOP has been updated We observed KDC (Key Distributed centre) authentication error. When the logs were validated, team couldn’t find any issues related to KDC. Hence, we initially thought that issue not related to AD which delayed the identification of the issue. Hence AD team will update the SOP to adding the list of components to validated when we encounter the KDC error. | Active Directory |  | NA | 2024-12-04 | Closed |  |  |  | Saloni | 2025-02-10 | 542 | >60 | April | 2024 | #VALUE!
GTS | Digital Workplace Services | 89934337 | 2024-04-08 | SALINA WiFi network connectivity issues across various DC's due to CRL expiry | Root CRL Expiry (expires every 6 months), however the expiry of root CRL was notified as the automated script failed. | Problem avoidance | MuthuNagappan Subramanian | Incorrect date was keyed in whilst running the script and hence due to incorrect date the script failed. In addition, the script was pointing to a decommissioned SMTP server (which is responsible for triggering the email notification) and now it has been corrected. | Active Directory |  | NA | 2024-08-04 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 542 | >60 | April | 2024 | #VALUE!
GTS | Digital Workplace Services | 89934337 | 2024-04-08 | SALINA WiFi network connectivity issues across various DC's due to CRL expiry | Review other scripts/jobs depending on the decommissioned SMTP server. | Problem avoidance | MuthuNagappan Subramanian / Messaging | 11/04: Team has revalidated and confirmed the SMTP server was not decommissioned and hence there is no action is requried. | Active Directory |  | NA | 2024-11-04 | Closed |  |  |  | Saloni | 2025-02-10 | 542 | >60 | April | 2024 | #VALUE!
GTS | Operations | 89934337 | 2024-04-08 | SALINA WiFi network connectivity issues across various DC's due to CRL expiry | Explore the option to add the CRL in the Certificate Management Dashboard for tracking | Problem identification & Alerting | MuthuNagappan Subramanian / Priya (Certificate management) | 12/04: The CRL expiry has being configured in Certificate dashboard for tracking 11/04: All the requirement has been shared with Certificate management awaiting further updates on the configuration | Active Directory/ Certificate management |  | NA | 2024-12-04 | Closed |  |  |  | Saloni | 2025-02-10 | 542 | >60 | April | 2024 | #VALUE!
GTS | Digital Workplace Services | 89934337 | 2024-04-08 | SALINA WiFi network connectivity issues across various DC's due to CRL expiry | Proactive alerting/notification thar can configured to notify the Root CRL expiry | Problem identification & Alerting | MuthuNagappan Subramanian | Calendar invite has been configured to remind the CRL renewal every six nothing. Additional alerting cannot be configured as the servers is powered off all the time will be powered only when the certificate is renewed. | Active Directory |  | NA | 2024-08-04 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 542 | >60 | April | 2024 | #VALUE!
GTS | Digital Workplace Services | 89934337 | 2024-04-08 | SALINA WiFi network connectivity issues across various DC's due to CRL expiry | Explore the options to configure the alert when the CRL is expired based the available errors in CS servers | Problem identification & Alerting | Gounalane, Subhapriya | 11/04: Alerts has been confirgured however it can be tested only when CRL expires | Active Directory |  | NA | 2024-11-04 | Closed |  |  |  | Saloni | 2025-02-10 | 542 | >60 | April | 2024 | #VALUE!
GTS | Digital Workplace Services | 89934337 | 2024-04-08 | SALINA WiFi network connectivity issues across various DC's due to CRL expiry | Can this certificate renewal be automated? | Problem avoidance | MuthuNagappan Subramanian | Cannot be automated as it needs to be renewed physically on the server due to security compliance | Active Directory |  | NA | 2024-08-08 | Closed |  |  |  | Saloni | 2025-02-10 | 542 | >60 | August | 2024 | #VALUE!
GTS | Digital Workplace Services | 89934337 | 2024-04-08 | SALINA WiFi network connectivity issues across various DC's due to CRL expiry | Review and update the root CRL renewal SOP | Problem avoidance | MuthuNagappan Subramanian | 11/04: This action is complete and SOP has been updated in the sharepoint | Active Directory |  | NA | 2024-11-04 | Closed |  |  |  | Saloni | 2025-02-10 | 542 | >60 | April | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89934337 | 2024-04-08 | SALINA WiFi network connectivity issues across various DC's due to CRL expiry | What is the plan to remove old HHTs in Castle Donington DC which is depending on the CRL and radius servers for authentication | Problem avoidance | Murali Srinivasan | Project team is already working on moving the old HHTs to Android HHTs, hence no additional action required | Service lead - CD |  | NA | 2024-08-08 | Closed |  |  |  | Saloni | 2025-02-10 | 542 | >60 | August | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89934337 | 2024-04-08 | SALINA WiFi network connectivity issues across various DC's due to CRL expiry | What is the plan to remove old HHTs in Milton Keynes DC which is depending on the CRL and radius servers for authentication | Problem avoidance | Sakthi Santhosh Nagarathinam | 22/04: The aim is to roll out the andriod devices by 28th May, and this will be tracked under the product backlog WC 18 | WMs - Foods |  | NA | 22/04/24 | Closed |  | WC-18 |  | Saloni | 2025-02-10 | 542 | >60 | April | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89934337 | 2024-04-08 | SALINA WiFi network connectivity issues across various DC's due to CRL expiry | Do we have any old HHTs in other C&H DCs as well if yes what is the plan to remove them? | Problem avoidance | Colin/ Murali Srinivasan | 10/04: There are around 444 old HHTs across DCs, however there is plan in place to replace the 50% of the 444 HHTs in Q1 and remaining all by Q4 2024/25 as it dependent on budgeting this is tracked under the JIRA backlog - [WC-18] HHT Replacement - Jira App (marksandspencer.app) Hemel=78,Hydepark=27,Ollerton=95(Q1),Stoke=13,Swindon=1,Thorncliffe=159 (Q1),WelhamGreen=26 Westthrouck=45 | Service Lead (C&H) |  | NA | 2024-10-04 | Closed |  | WC-18 |  | Saloni | 2025-02-10 | 542 | >60 | April | 2024 | #VALUE!
GTS | Digital Workplace Services | 89934337 | 2024-04-08 | SALINA WiFi network connectivity issues across various DC's due to CRL expiry | Feasibility of having common runbook for any issues with SALINA | Solution & Recovery | NOC | 16/04: Its has been understood the having a common runbook is not feasible. As the requriment and scenarios changes. SOP for the individual team to handle their issue are updated To be discussed with network team. | Active Directory/ Network |  | NA | 2024-12-04 | Closed |  |  |  | Saloni | 2025-02-10 | 542 | >60 | April | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89934337 | 2024-04-08 | SALINA WiFi network connectivity issues across various DC's due to CRL expiry | How to identify validity of the certificate on HHTs? | Solution & Recovery | Murali/Micheal Arundel | 10/04: There is process inplace and its documented in the CDIT process documents and Murali will notify the team to follow the step to verify the certificate expiry going forward. | CD- Service lead |  | NA | 2024-10-04 | Closed | ` |  |  | Saloni | 2025-02-10 | 542 | >60 | April | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89934337 | 2024-04-08 | SALINA WiFi network connectivity issues across various DC's due to CRL expiry | Explore the feasibility of having backup network when SALINA is unavailable across C&H and Foods DC | Solution & Recovery | Network | 10/05: Spoke to Rajesh and understood that this should given as a new requirement from product team to network to understand the feasibility and configuring additonal network 16/04: A call to be scheduled to discuss further | Network |  | NA | 2024-10-05 | Closed |  |  |  | Saloni | 2025-02-10 | 542 | >60 | May | 2024 | #VALUE!
GTS | Digital Workplace Services | 89934337 | 2024-04-08 | SALINA WiFi network connectivity issues across various DC's due to CRL expiry | Explore options to reduce the dependency on the CRL renewal on AD SME team as it onsite renewal activity in Stockley park. | Problem avoidance | Muthu/Farid. | 18/06: A AD resource for onsite has been inducted and KT is i progress, mean while team can guide MHM or any Infra person to perform the acitivity in the DC incase of any issue. 21/05: Team is inprogress of securing an AD resource onsite and KT will given once thats complete. Meanwhile discussion needs to taken on interim solution, however Farid is ooo. will discuss further once he is back. Also note, Offshore is having knowledge on how perform the activity on non-prod, however prod CRL renewal needs to done on physical server. 08/05: The required steps to perform the renewal activity has been clearly documented and team is working on identifying a resource to begin the KT. However Farid is in vacation and will be back on 16/05 as we complete dependency on the resource to KT as this is a activity needs a physical presence at the site 16/04: A call to be scheduled to discuss further | Active Directory | Strategic | NA | 18/06/24 | Closed |  |  |  | Saloni | 2025-02-10 | 542 | >60 | June | 2024 | #VALUE!
Foods | Foods Supply Chain | 89928907 | 2024-04-08 | Issue with the Relex batch processing | Explore the feasibility to configure alerts when any jobs have been disabled/deleted after any change as part of their post implementation checks | Problem identification & Alerting | Tommi (Relex) | 02/07 - Tamil updated that, this is Relex SaaS issue, Its a One off Issue and it has not recurred, The server move happened manually and now agreed no Manual deployments. 19/06 - Tamil is working with Accenture and next update is expected by 25/06 as they are busy in planning activities. 14/06 - Tamil would be checking with Accenture on this and let us know. 01/06 - Have scheduled a call with Matt on 06/06 to understand on the status of Alert from Relex based on his availability. 25/05 - Matt has agreed to raise this with Relex in their review call. Awaiting details of when is it. 21/05 - Matt is OOO until 23/05, however followed up with him on the latest. 14/05 - Matt updated that he has chased Relex for confirmation of the new alerts they've put in. 03/05 - Have checked with Matt White on this. 28/04: Have sent mail to Promoth asking the status of the action. 19/04: Have checked with Promoth on the latest | Relex | Tactical | NA | 2024-02-07 | Closed |  |  |  | Saloni | 2025-02-10 | 542 | >60 | July | 2024 | #VALUE!
Foods | Foods Supply Chain | 89928907 | 2024-04-08 | Issue with the Relex batch processing | Agreed with Relex to join the Customer MIM bridges for faster triaging and recovery | Supplier and support involvement | Paul (Relex) | Agreed on the PIR call. | Relex |  | NA | 2024-08-04 | Closed |  |  |  | Saloni | 2025-02-10 | 542 | >60 | April | 2024 | #VALUE!
Foods | Foods Supply Chain | 89928907 | 2024-04-08 | Issue with the Relex batch processing | There were no Customer change reference for the Relex hardware replacement. Agree within the FOA team to a raise a Information change, whenever there are Relex changes which could potentially impact Customer | Supplier and support involvement | Promoth/Matt | 16/04: In the call, multiple changes and their processes were agreed. 15/04: change process walkthrough scheduled on 16/04. | Foods product team |  | NA | 17/04/24 | Closed |  |  |  | Saloni | 2025-02-10 | 542 | >60 | April | 2024 | #VALUE!
GTS | Operations | 89928907 | 2024-04-08 | Issue with the Relex batch processing | Conduct a workshop to walkthrough the standard change process with the FOA Team | Supplier and support involvement | SIAM Change Management | 16/04: In the call, multiple changes and their processes were agreed. 15/04: change process walkthrough scheduled on 16/04. | SIAM |  | NA | 17/04/24 | Closed |  |  |  | Saloni | 2025-02-10 | 542 | >60 | April | 2024 | #VALUE!
Foods | Foods Supply Chain | 89928907 | 2024-04-08 | Issue with the Relex batch processing | Review the supplier communication process and agree with the relevant portfolio stakeholders | Business & IT Communication | Promoth/Matt | 28/05 - Lisy informed that On call FCS has to be informed, who inturn will inform the suppliers. Hence closing the action. 25/05 - Have requested Matt to check with Lisy if Joey is busy. 21/05 - Matt is OOO until 23/05, however followed up with him on the latest. 14/05 - Matt updated that "comms provided to Suppliers were considered fine on that day, and he has picked up with Joey to determine if there's more we should do on this." 03/05 - Have checked with Matt on this 28/04: Have sent mail to Promoth asking the status of the action. 19/04: Have checked with Promoth on the latest 08/04: During this incident, OFP banner was updated, but, other supplier comms is to be agreed | Foods product team | Tactical | NA | 28/05/24 | Closed |  |  |  | Saloni | 2025-02-10 | 542 | >60 | May | 2024 | #VALUE!
Foods | Foods Supply Chain | 89928907 | 2024-04-08 | Issue with the Relex batch processing | Ensure timely engagement of the impacted downstream product teams - BEAM team during such issues, | Supplier and support involvement | Promoth Kumar | 03/05 - Promoth confirmed that it is conveyed to the team. 28/04: Have sent mail to Promoth asking the status of the action. 19/04: Have checked with Promoth on the latest | Foods product team |  | NA | 2024-03-05 | Closed |  |  |  | Saloni | 2025-02-10 | 542 | >60 | May | 2024 | #VALUE!
Foods | Foods Supply Chain | 89928907 | 2024-04-08 | Issue with the Relex batch processing | Review the existing SOP document to assess the actual impact statement during an incident | Impact analysis | Promoth Kumar | 03/05 - Promoth confirmed that the SOP is reviewed to include all the impacts. 28/04: Have sent mail to Promoth asking the status of the action. 19/04: Have checked with Promoth on the latest | Foods product team |  | NA | 2024-03-05 | Closed |  |  |  | Saloni | 2025-02-10 | 542 | >60 | May | 2024 | #VALUE!
Digital & Data | Digital & Data | 89928907 | 2024-04-08 | Issue with the Relex batch processing | As part of recovery, list down the BEAM interfaces and ETA details along with the path where the files must be placed manually for the FFO when there is a delay in the batch completion. | Solution & Recovery | Ranadip/Saranya M | 12/05 - Saranya has the list of list down the BEAM interfaces and ETA details along with the path where the files must be placed manually for the FFO when there is a delay in the batch completion. 03/05 - Saranya confirmed that he is working on this. 26/04: Ranadip has escalated it to Deepa. 19/04: Followed up with Saranya | BEAM |  | NA | 2024-09-05 | Closed |  |  |  | Saloni | 2025-02-10 | 542 | >60 | May | 2024 | #VALUE!
Digital & Data | Digital & Data | 89928907 | 2024-04-08 | Issue with the Relex batch processing | Are there any alerts configured to check for file availability and to process all Day-1 files? If not, explore the feasibility to configure an alert | Problem identification & Alerting | Ranadip/Saranya M | 20/05 - Saranya has explained that when our process runs 30 mins before that the Relex file should arrive. If the file is not there and the process will fail and an incident will be raised and we will ask Relex. There is alerting in place to say the file has not arrived and the batch fails. 12/05 - Team is still checking on the feasibility of the alerts if the file is not received. 03/05 - Saranya confirmed that he is working on this. 26/04: Ranadip has escalated it to Deepa. 19/04: Followed up with Saranya | BEAM |  | NA | 20/05/24 | Closed |  |  |  | Saloni | 2025-02-10 | 542 | >60 | May | 2024 | #VALUE!
GTS | Enterprise Integration | 89928907 | 2024-04-08 | Issue with the Relex batch processing | To create a SOP detailing the steps to rerun OTS reports when the latest data is available on the same day. | Solution & Recovery | Sreeraj | 29/04: Sreeraj confirmed that the SOP is done and shared within their team 26/04: Have checked with Sreeraj on the status of SOP. 19/04: Followed up with Sreeraj who is working on the SOP | Integration Services |  | NA | 29/04/24 | Closed |  |  |  | Saloni | 2025-02-10 | 542 | >60 | April | 2024 | #VALUE!
Foods | Foods Supply Chain | 89928907 | 2024-04-08 | Issue with the Relex batch processing | During FFO delays, involve DS to hold the relevant jobs within 04:45 to avoid any cascading impact to the OTS reports generation. | Solution & Recovery | Tamil | Agreed on the PIR call. | Foods product team |  | NA | 2024-08-04 | Closed |  |  |  | Saloni | 2025-02-10 | 542 | >60 | April | 2024 | #VALUE!
Foods | Foods Supply Chain | 89928907 | 2024-04-08 | Issue with the Relex batch processing | To create a SOP detailing the various impacts in case of delay in generating the OTS reports | Impact analysis | Tamil | 30/04: SOP has been created and shared with the system 26/04: Have followed up with Tamil on the backlog and status of the action. 16/04: Tamil updated that the team has picked up in this Sprint starting 17th | Foods product team |  | NA | 30/04/24 | Closed |  |  |  | Saloni | 2025-02-10 | 542 | >60 | April | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89929555 | 2024-04-05 | CD experiencing Metapack call failures at SYW for AnPost orders | Speak to the relevant product teams to ensure they raise e-comm incidents especially relating to those that directly impact customer orders at the correct priority and how ascertain how they are manage these going forward | Issue handling/Management | Mark Davies | 15/05: There is a weekly incident meeting with the incident team onsite about incidents. From there the actions are raised. Going forward the incident team have been retrained on how to raise the incidents correctly. | CD WMS Devops |  | NA | 15/05/24 | Closed |  |  |  | Saloni | 2025-02-10 | 545 | >60 | May | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89929555 | 2024-04-05 | CD experiencing Metapack call failures at SYW for AnPost orders | F5 HW and SW is out of support – the F5 software can be upgraded to allow it to become back in+F121to support - this needs to be planned. | Problem avoidance | Rajesh/Ian | 15/05: There is a risk number for this as the upgrade will not be feasible for now - risk number 2132 | NOC |  | NA | 15/05/24 | Closed |  |  |  | Saloni | 2025-02-10 | 545 | >60 | May | 2024 | #VALUE!
GTS | Enterprise Technology Platform | 89929555 | 2024-04-05 | CD experiencing Metapack call failures at SYW for AnPost orders | Record the resolution steps to ensure all NOC members have visibility of this 24/7 in case of a recurrence | Problem avoidance | Rajesh | 15/05: These steps were done at the time and recorded | NOC |  | NA | 15/05/24 | Closed |  |  |  | Saloni | 2025-02-10 | 545 | >60 | May | 2024 | #VALUE!
GTS | Enterprise Technology Platform | 89929555 | 2024-04-05 | CD experiencing Metapack call failures at SYW for AnPost orders | F5 HW and SW is out of support and this issue can reoccur as we have no current root cause - Raise a high priority risk | Root cause | Rajesh | 15/05: Risk number 2132 | NOC |  | NA | 15/05/24 | Closed |  |  |  | Saloni | 2025-02-10 | 545 | >60 | May | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89929555 | 2024-04-05 | CD experiencing Metapack call failures at SYW for AnPost orders | The route to metapak will be changing to bypass the B2B gateway in azure and will go directly from WMS via internet to metapak – Dean to confirm. Will the F5 load balancer still be part of this route? When are the changes due to take place> | Problem avoidance | Dean Worswick | 15/07 - Since the WMS desptacher upgrade the route has now change and bypasses the B2B gateway, 15/05: Not been able to get to working on this as we are still tackling issues in Donington. w information should be provided by the architects. Quayle, Alastair should be able to provide this info. | CD WMS Devops | Strategic | NA | 15/07/24 | Closed |  |  |  | Saloni | 2025-02-10 | 545 | >60 | July | 2024 | #VALUE!
GTS | Enterprise Technology Platform | 89929555 | 2024-04-05 | CD experiencing Metapack call failures at SYW for AnPost orders | Key training gaps to be addressed in the NOC BAU team Rajesh/Ian | Issue handling/Management | Rajesh/Ian | 15/05 - There is a short term and long term ongoing training plan and a meeting will be setup for Friday weekly to provide updates on the maturity and implementation of this plan. | NOC |  | NA | 15/05/24 | Closed |  |  |  | Saloni | 2025-02-10 | 545 | >60 | May | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89925701 | 2024-04-04 | Internet connectivity issues across multiple DCs after Palo Alto license expiry | What caused the gap/miss in the PA license renewal on a timely manner? | Root cause | Ravikumar chinnardurai/NOC | There was a delay in permanent License renewal due to few commercial reasons. Alternatively, we had to raise for a temporary license, 2 weeks before the license actual expiry (31/03) causing the last minute confusion. Preventive actions have been agreed on the same below. | Network |  | NA | 2024-04-04 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 546 | >60 | April | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89925701 | 2024-04-04 | Internet connectivity issues across multiple DCs after Palo Alto license expiry | Review the existing alerting and process for any critical license expiry. | Problem identification & Alerting | Rajesh/NOC | 29/05 - All the critical certs have been added to the central tracker 17/05 - The request has been raised to add these certs to the central inventory 09/05 - Waiting latest update from the problem Owner 04/04 - Though we have an inventory in place which lists the existing licenses along with it expiry dates. However, there is no process of alerting the team, when nearing the license expiry. Teams will agree on a process to configure the right alerting, update the SOP’s and plan the right hypercares during any such critical license expiry. | Network | Strategic | NA | 29/05/24 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 546 | >60 | May | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89925701 | 2024-04-04 | Internet connectivity issues across multiple DCs after Palo Alto license expiry | Review the list of applications utilizing Palo Alto licenses to ensure we do efficient impact analysis during the MI. | Impact analysis | Janani/Rajesh | 17/05 - During the incident teams did not have any visibility what sort of security feature has to be disabled and impact that it would cause - all of the details are now recorded and the impacts are documented for future reference 04/04 -Network project team will work on a list of applications still using via PA and those will be considered during the next renewal. Also NOC will consolidate and update their SOP’s on the steps of recovery/impact mitigation. | Network |  | NA | 17/05/24 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 546 | >60 | May | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89925701 | 2024-04-04 | Internet connectivity issues across multiple DCs after Palo Alto license expiry | Ensure we have the right SME’s from NOC to address the issue on a timely manner. | Solution & Recovery | Rajesh/NOC | 17/05 - Lot of KT sessions and other handover planned by project team (ongoing), thus whoever from NOC joining can effectively work on this type of incidents 04/04 -There was a delay in engaging the right SME from NOC, which eventually delayed the recovery. Noc team to update the SOP with the right steps on the recovery and would conduct few brainstorming sessions within the team, so that all the engineer have the expertise to direct us on the right investigations | Network |  | NA | 17/05/24 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 546 | >60 | May | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89925701 | 2024-04-04 | Internet connectivity issues across multiple DCs after Palo Alto license expiry | Prioritize the next PA license renewal. | Permanent Fix | Ravikumar chinna durai/Janani/Rajesh and Rajasekaran | 30/04 - PA license has been renewed for next one year. 23/04 - Palo Alto has shared the license keys for both Bom1 and Bom2. Franklin from network team will apply it on 23/04 . 15/04 - PA license has been renewed upto - 26th April - teams are working with PA to get it renewed for 1 year. | Network |  | NA | 30/04/24 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 546 | >60 | April | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89925701 | 2024-04-04 | Internet connectivity issues across multiple DCs after Palo Alto license expiry | Ensure we migrate Global protect 7050 devices to ZPA migration before 15th April. | Permanent Fix | Ravikumar chinna durai/Janani/Rajesh and Rajasekaran | 02/05 - All of the 7050 devices has been upgraded to Zscalar and All the Colleagues in Welham green has been trained on the accessibility. 23/04 - All the devices have been configured with the ZPA configurations and has been sent to Welham Green DC. NOC will conduct a Training/KT to the WG colleauges today. 10/04 - The plan has been devised and it is expected to be implemented by 17/04 21/03 - Though all the user machines have been migrated to ZPA we have few devices used by the DCs using GP via PA firewall. ZPA project team (Networks) have devised a plan to get all the devices migrated to Zscalar within 10th April. – This action needs to be followed-up on priority as well. | Network |  | NA | 2024-02-05 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 546 | >60 | May | 2024 | #VALUE!
Customer Channels | Service Experience | 89933591 | 2024-04-03 | Connectivity issue with Eagle Eye services for mobile coupons | To revisit the New Relic alert for the transaction failures | Problem identification & Alerting | Laura | New Relic alerts were set up. | Service Lead |  | NA | 2024-03-04 | Closed |  |  |  | Saloni | 2025-02-10 | 547 | >60 | April | 2024 | #VALUE!
Customer Channels | Service Experience | 89920510 | 2024-04-03 | Staff discount/ pension leavers card not scanning on tills | Explore an option within CDCS to force download the correct extract file on the tills without having to restart the tills. | Solution & Recovery | Balaguru Subramaniam/ Balaji Jaganathan | 07/10: Chris has confirmed that a combined decision was made to not move forward with the suggested recommendation, as this is not the priority of the team. 05/10: It has been confirmed that the file download is controlled by the CDCS application, and Beanstore cannot manage this schedule. POSTEAM has proposed a solution to trigger the file download in CDCS on an ad-hoc basis. However, this will require configuration changes. Further discussions are ongoing to assess the risk profile of these changes and determine whether it is feasible to implement them before the Golden Quarter. 10/09: Awaiting further update from Chris Etherington. A decision will be made on the priority of this request provided we receive an update from Flooid 20/08: POS Client’s currently set to check and download the latest CDCS file on its schedule. If we must force an update, existing file had to be deleted and POS must be restarted. It will force to POS to go and download the file from CDCS again. This action will now be verified with Flooid if this service/function can be triggered adhoc (action item 6). Item 6 or 7 are to meet the same outcome through two different methods. 31/07: The product is still under Payment Foundations group. Therefore. Chris has raised the query with the POS team, to see if this is possible within the current architecture setup. As this action is more of a wishlist item provided during the PIR, Chris will check with architectures/ senior engineer the real feasibility of executing this action. ETA: 10th Sep 15/07: Chris confirmed the staff discount product is currently not having a product manager nor it has been tagged to any portfolio, Chris will be liasing with Daniel Louden to devise a plan on this action. ETA: 26th July 25/06: Saloni is awaiting an update from Daniel Louden to schedule a call to discuss on the feasibility of force downloading the extract file without restarting the tills. 14/06: Saloni has spoken to Daniel Louden to identify the ownership of CDCS application after the restructuring. Identify a suitable window to discuss on this action. 20/05: Balaji has advised that this has not been prioritised after the re-org in payments by Product owner - Chris Etherington. Also there are discussions on going for CDCS app to be moved out of payments. Until that's confirmed this won't be prioritised. Chris is on leave next two weeks, returning on 31/05, plan is to speak to Daniel Louden (Chris's manager) to identify the ownership. Follow up continues with Balaji Jaganathan. PM has followed up on 20/05 and awaiting a response and ETA. A call to be scheduled on 21/05. | POS. CDCS | Strategic | NA | 2024-07-10 | Closed |  |  |  | Saloni | 2025-02-10 | 547 | >60 | October | 2024 | #VALUE!
Customer Channels | Service Experience | 89920510 | 2024-04-03 | Staff discount/ pension leavers card not scanning on tills | Explore the feasibility to implement an automatic adhoc process to update the tills without having to restart the tills. | Solution & Recovery | Balaguru Subramanian | 14/05: POS architect team has confirmed that there is no way to create an automatic adhoc process to update tills without a restart Flooid code. This logic has to be handled in CDCS code(jar) in tills which is being further worked upon by Payment FOundation team - Balaji Jaganathan Teams to liaise with Flooid for further progress | POS |  | NA | 14/05/24 | Closed |  |  |  | Saloni | 2025-02-10 | 547 | >60 | May | 2024 | #VALUE!
Group Platforms | HR | 89920510 | 2024-04-03 | Staff discount/ pension leavers card not scanning on tills | Agree a process with Colleague services team for an improved communication in terms of highlighting the issue whilst understanding the scale of impact for faster resolution. | Problem identification & Alerting | Valliamai Ramasamy/ Mudassar Kazmi | 07/05: Valli has confirmed that they have agreed a process to facilitate immediate updates within the service leads. In parallel, Colleague services customer care team will update Mudassar as soon as they have identified an issue based on the number of calls. Agree a process with Colleague services team for an improved communication in terms of highlighting the issue whilst understanding the scale of impact for faster resolution. | Service leads |  | NA | 2024-07-05 | Closed |  |  |  | Saloni | 2025-02-10 | 547 | >60 | May | 2024 | #VALUE!
Customer Channels | Service Experience | 89920510 | 2024-04-03 | Staff discount/ pension leavers card not scanning on tills | There was no authorised change request raised to perform the URL change in CDCS. Review the change management process within CDCS. | Issue handling/Management | Kanan Oza | It has been agreed with the CDCS team to ensure that a CR is being raised for any changes implemented on production and follow the standard change management process before its deployment. This will include validations/ post implementation with the POS team to confirm the change to be successful | CDCS |  | NA | 22/04/24 | Closed |  |  |  | Saloni | 2025-02-10 | 547 | >60 | April | 2024 | #VALUE!
Customer Channels | Service Experience | 89920510 | 2024-04-03 | Staff discount/ pension leavers card not scanning on tills | Review the data contract in CDCS to identify the mandatory fields and explore the feasibility of configuring a validation/ alerting mechanism within CDCS during a file format issue scenario | Problem identification & Alerting | Kanan Oza | 22/04: The data contracts between the teams have been agreed upon and relevant changes implemented in Dev. These changes will be tested and planned for a go-live in upcoming sprints(target go-live date not planned yet) under PFOUND-627 & PFOUND-628 CDCS team will collaborate with the My Discount team to identify the mandatory fields in the discount eligible employee extract and configure a validation check if there are any format issues/ mismatch on the mandatory fields before sending the file to the tills. | CDCS |  | NA | 22/04/24 | Closed |  | PFOUND-627 PFOUND-628 |  | Saloni | 2025-02-10 | 547 | >60 | April | 2024 | #VALUE!
Customer Channels | Service Experience | 89920510 | 2024-04-03 | Staff discount/ pension leavers card not scanning on tills | Review the local test database at POS and SCOT tills to ensure the attributes are fundamentally like-to-like in nature. | Problem avoidance | Seevaratam Sivasurath | 22/04: The relevant team have been made aware to not modify the data whilst testing. A step will be added in the confluence page to refresh the data before testing There were 2 card test scenarios within POS: 1. Staff discount card with a Sparks id – which tested fine. 2. Old staff discount card without a Sparks id – during the testing, it was not realised that this card had a Sparks id associated to it. The teams did not refer to the local POS database to verify the card before testing. Also, during the SCO tills testing, there were some manual amendments done on the database which is not as part of best practices. | POS |  | NA | 22/04/24 | Closed |  |  |  | Saloni | 2025-02-10 | 547 | >60 | April | 2024 | #VALUE!
Group Platforms | HR | 89920510 | 2024-04-03 | Staff discount/ pension leavers card not scanning on tills | Review the test cases, types of cards to be considered within the POS and SCOT layer to identify this issue during the testing phase. Analyse the test results thoroughly before proceeding with the go live | Problem avoidance | Seevaratam Sivasurath/ Mahesh Ramasamy | 22/04: The test scope along with test data is available in POS: https://confluence.marksandspencer.app/pages/viewpage.action?pageId=229391630. The teams will now collaborate in analysing the test cases and document the results. The staff discount card used whilst testing was linked to a Sparks id and therefore, they were scanned successfully on the test tills. Due to insufficient test cases scenarios, there was no testing performed for a Staff discount card without any link to a Sparks id. Teams will document the test cases to be used for future instances. | POS / My Discount |  | NA | 22/04/24 | Closed |  |  |  | Saloni | 2025-02-10 | 547 | >60 | April | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89931618 | 2024-04-03 | Czech and Greece colleagues unable to access eSAP | To help with future fault finding we need to review the service and create a consolidated list of services provided by Fortigate and raise a risk highlighting the lack of control/centralised service design and transition document and support wrap. Start the process also of creating centralised service design and transition document and support wrap. Create prechecks and post checks to be carried out in any future migrations. | Solution & Recovery | Janani M | 29/05: Risk#2145has been rasied to mitiagte the Janani advises that we need a separate service and transition resource to get the run book ready containing all the services that will get affected during the change. Risk to be raised | Network | Strategic | NA | 2024-03-06 | Closed | 2145 |  |  | Saloni | 2025-02-10 | 547 | >60 | June | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 89918599 | 2024-04-02 | C&H SSI application inaccessible | Feasibility of configuring 2 IP addresses for SSI application to establish resilience during such scenarios to remediate the stakeholder impact. | Permanent Fix | Kumarjit David | 03/04: Back log has been created to track this action by product teams 02/04:This needs further discussion. | Akamai |  | NA | 2024-04-04 | Closed |  | DSDS-2223 | Open | Saloni | 2025-02-10 | 548 | >60 | April | 2024 | #VALUE!
C&H and Intl | C&H Commercial Trading | 89918599 | 2024-04-02 | C&H SSI application inaccessible | Review the stakeholder communication | Business & IT Communication | George Loizou | 08/05: we will continue to use the C&H BU DLs but the business will ensure they are up to date 11/04: A survey needs to be taken to decide the best approach. 02/04: Service leads will liaise with the buying stakeholdersto improve the communication channel either by setting up a separate DL for heads of BU for frequent updates during incidents. | C&H SSI |  | NA | 2024-08-05 | Closed |  |  |  | Saloni | 2025-02-10 | 548 | >60 | May | 2024 | #VALUE!
C&H and Intl | C&H Commercial Trading | 89918599 | 2024-04-02 | C&H SSI application inaccessible | Conduct process awareness / Knowledge workshopswithin the application teams | Problem avoidance | Naresh Mandapu | 08/05: This action has been closed. 11/04: A session has been planned with in next 2 weeks 02/04: A knowledge sharing session should be conducted to ensure the ground level engineers are up to date with the different elements within an application. | C&H SSI |  | NA | 2024-08-05 | Closed |  |  |  | Saloni | 2025-02-10 | 548 | >60 | May | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89918599 | 2024-04-02 | C&H SSI application inaccessible | The propagations of DNS changes took 1 hrs as the TTL set to ‘3600s’ (approx.) Can this reduced so that any future changes can be propagated sooner. | Solution & Recovery | Mahendran Mahalingam | 16/04: A back log to be raised to priortise and close this action 02/04: There is an option to reduce the TTL parameter to 30s for each Cnames, A records. This needs further discussion within Network teams SMEs as it requires a DNS change | Network |  | NA | 2024-08-05 | Closed |  |  |  | Saloni | 2025-02-10 | 548 | >60 | May | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89918599 | 2024-04-02 | C&H SSI application inaccessible | There was delay in understanding the number of ‘A records’ and ‘cNames’ that was dependent on the IP changes, how can we address the knowledge to reduce the restoration time | Solution & Recovery | Rajeshkumar Singarajan | 02/04: This can be addressed through - Implement extensive checks within Network layer before deleting a public IP address ( below) | Network |  | NA | 2024-02-04 | Closed |  |  |  | Saloni | 2025-02-10 | 548 | >60 | April | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89918599 | 2024-04-02 | C&H SSI application inaccessible | Implement extensive checks within Network layer before deleting a public IP address | Problem avoidance | Rajeshkumar Singarajan | 02/04: It has been agreed NOC should use the MX toolbox portal to fetch the DNS namesassociated to a particular IP address and perform necessary actions in collaboration with the respective portfolio team before taking any action on the IP address. | Network |  | NA | 2024-02-04 | Closed |  |  |  | Saloni | 2025-02-10 | 548 | >60 | April | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89918599 | 2024-04-02 | C&H SSI application inaccessible | Feasibility of implementing a validation mechanism within Muzirisin case of an incorrect IP scenario. | Problem avoidance | Rajeshkumar Singarajan | 08/05: Team is still working on this action, considering its completely new automation requirement team will raise a a back log to track it- CNWK-2132 12/04: Network team is working with Platfrom to understand the feasiblity 11/04: Followed up on the action awaiting further updates | Network |  | NA | 2024-08-05 | Closed |  | CNWK-2132 |  | Saloni | 2025-02-10 | 548 | >60 | May | 2024 | #VALUE!
C&H and Intl | C&H Commercial Trading | 89918599 | 2024-04-02 | C&H SSI application inaccessible | Review the SOP document by the engineeringexpert to ensure appropriate details are updated to avoid such scenarios. | Problem avoidance | Ashok/Meenakshi | 11/04: The SOP has bee created. | C&H SSI |  | NA | 2024-11-04 | Closed |  |  |  | Saloni | 2025-02-10 | 548 | >60 | April | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 89918599 | 2024-04-02 | C&H SSI application inaccessible | Feasibility of configuring an alert to proactively identify these issues before being reported by colleagues resulting in a significant impact. | Problem identification & Alerting | David Raine | 03/04: https://jira.marksandspencer.app/browse/DSDS-2222 has been created to track this | Akamai |  | NA | 22/04/24 | Closed |  | DSDS-2222 | Open | Saloni | 2025-02-10 | 548 | >60 | April | 2024 | #VALUE!
Digital & Data | Digital & Data | 89913334 | 2024-03-26 | Bigdata platform issues impacting the EIH data availability | How did Cloudera identify the latency issue before the EIH Platform team concluded? Review and adopt the actions taken by Cloudera to identify the issue without relying on Cloudera for further occurrences. | Solution & Recovery | Munesh Patil | 06/05: The recovery steps have been document and will be utilised for future instances. Outside of this incident, Platform team will adopt to new learnings and techniques from cloudera. 15/04:Munesh advised to assign the action to Zeeshan, we need to ensure the EIH support team are adopting new troubleshooting strategies and learnings from our vendors. The less we rely on 3rd party support vendors like Cloudera, is a measure of success within our own teams. Check with Zeeshan on a SOP creation to document the ways forward whilst triaging an issue. Cloudera compared the query profiles – one with normal execution time and the problematic run. EIH platform team to collaborate with Cloudera and adopt these actions to ensure prior identification. | EIH Platform team |  | NA | 2024-07-05 | Closed |  |  |  | Saloni | 2025-02-10 | 555 | >60 | May | 2024 | #VALUE!
Digital & Data | Digital & Data | 89913334 | 2024-03-26 | Bigdata platform issues impacting the EIH data availability | Review the escalation proess within Cloudera | Supplier and support involvement | Munesh Patil | 15/04: Munesh needs to be involved for timely escalation for future scenarios EIH platform team escalated to Cloudera at 13:15, and a response was received from the first level engineer at 13:50. Address the delay in the acknowledgement of the case and assign a second level engineer. | EIH Platform team |  | NA | 15/04/24 | Closed |  |  |  | Saloni | 2025-02-10 | 555 | >60 | April | 2024 | #VALUE!
Digital & Data | Digital & Data | 89913334 | 2024-03-26 | Bigdata platform issues impacting the EIH data availability | Why was there a delay from EIH platform to escalate to Cloudera | Supplier and support involvement | Zeeshan Khan | 06/05: Data Platform has confirmed that they had undrgone the first level of troubleshooting which takes time (apprx 1 hour). Also, this will be raised with Cloudera in Bi-weekly catchup call with them how to speed up the process to get the blacklined engineer( This is Cloudera's internal process that initial support engineer needs to follow) during severity 1 issue Even though a case was raised with Cloudera, it was escalated only at 13:15. | EIH Platform team |  | NA | 2024-07-05 | Closed |  |  |  | Saloni | 2025-02-10 | 555 | >60 | May | 2024 | #VALUE!
Digital & Data | Digital & Data | 89913334 | 2024-03-26 | Bigdata platform issues impacting the EIH data availability | Explore the feasibility of configuring alerts within the EIH platform to proactively identify these issues. | Problem identification & Alerting | Zeeshan Khan/ Cloudera | 31/07: The teams have confirmed that as EIH is in the decommissioning path, no further efforts will be spent to review or configure any more alerts in the platform. EIH is getting decommissioned on 14th Aug. 22/07: The relevant resource is currently OOO. We have reached out to Platform lead to help coordinate in identifying the root cause. 12/07: From cloudera side there is no option to setup alert on CPU utilization. From Linux side we had requested Linux Monitoring team to give us the Server level dashboard . They have provided the access to that citirx dashboard that we are exploring it. 25/06: We have now escalated this to Customer - Munesh Patil and awaiting further updates. If there is no response received, a further follow up to be made 17/06: the teams had been busy whilst coordinating the EDW SP to SW migration. This has now been escalated to Customer POC to get better traction. Follow up call scheduled on 18/06 28/05: Teams are currently working on job migration for an upcoming SP exit activity planned on 1st June, therefore, this will be picked up next week, ETA 7th June. 20/05: Zeeshan will speak to Remedy team in accordance with Linux team to configure a sev2 alert when the CPU spikes to 70%. Also, explore feasibility to configure Sev3 alerts at a 60% utilisation. As we are still investigating root cause, this steps is to ensure we proactively identify issues before causing an impact. 06/05: Zeeshan and team are discovering the possibilities how to setup alert for CPU part from application itself. Linux team has already setup the CPU alerts from their end and Platform teams receive the INC once the CPU threshold which is 85% breached. In this scenario, the CPU utilization had not breached and therefore, no incident was triggered. There is an existing dashboard within the platform to identify critical issues. However, in this case, there was a latency in the Impala service on three problematic servers – however, no alerts were triggered. Review the existing platform alerts for CPU and memory spike along with Cloudera and look at the feasibility of configuring additional alerts. | EIH Platform | Tactical | NA | 31/07/24 | Closed |  |  |  | Saloni | 2025-02-10 | 555 | >60 | July | 2024 | #VALUE!
Digital & Data | Digital & Data | 89913334 | 2024-03-26 | Bigdata platform issues impacting the EIH data availability | Why was the issue not identified within the platform proactively before being highlighted by the DataOps team? | Problem identification & Alerting | Munesh Patil/ Zeeshan Khan | 20/05: A SOP has been created to document the required steps to troublshoot a query slowness issue to identify the cause of the problem. There are different Layers in this platform. Platform team (Amnomix) own the application layer, and didn't receive any alerts from application during the issue window. There were no alerts on problematic host in Cloudera Dashboard. In the Cloudera application there is no mechanism to monitor the query slowness like if any query taking more than an hour so alerts should be triggered. The query slowness needs to be reported by end user if any because query slowness is related with many aspects like number of records being fetched, Partitions, Table size ,number of parallel queries running, Statistics updated or not etc. Still, We will raise this with Vendor to check is there any way to monitor the query slowness even though there are no alerts on Cloudera Platform/ Impala service. Identify the rationale within the platform to conclude that it was healthy. Review the E2E system resources as an action to investigate platform issues. | EIH Platform |  | NA | 20/05/24 | Closed |  |  |  | Saloni | 2025-02-10 | 555 | >60 | May | 2024 | #VALUE!
Digital & Data | Digital & Data | 89913334 | 2024-03-26 | Bigdata platform issues impacting the EIH data availability | Review the stakeholder communication across different portfolio channels | Business & IT Communication | Timothy Barrett | 27/05: Tim has spoken to the stakeholders in terms of EIH related communicated, however, this platform is due to be decommissioned and will be replaced by BEAM, we have confirmed that stakeholder comms are predefined in BEAM environmenet 15/04: Follow-on calls now need to take place between Timothy and service leads to define communication plans for critical solutions (though due to the migration programme, the key focus here will be BEAM). A meeting has been scheduled on Monday to discuss on facilitating the communication between the portfolio channels. This will get improved once we have a clear understanding on the impact. | Data Ops manager | Tactical | NA | 27/05/24 | Closed |  |  |  | Saloni | 2025-02-10 | 555 | >60 | May | 2024 | #VALUE!
Digital & Data | Digital & Data | 89913334 | 2024-03-26 | Bigdata platform issues impacting the EIH data availability | Support coverage during off business hours – Cloudera, EIH platform, Data Ops team | Supplier and support involvement | Munesh Patil | 15/04, EIH Platform: For future SEV 1, Platform Related issues on EIH, Munesh will be added to the existing escalation process for EIH. My numbers are 07900052222 or 07939141631. This will give the opportunity to assess the situation and current challenges in real time and help the team triage in a timely manner. There was a massive challenge in getting appropriate traction from EIH platform and Cloudera. EIH platform/ Amnomics - The issue was highlighted at 09:30, however, there was a delay in engaging the right person from EIH Platform (Amnomics). Review the escalation policy within Amnomics. It has also been agreed that MIM will give a call out to Munesh Patil in case of these issues. Cloudera – Liaise with Cloudera to improve the out of office hours support. There were some challenges in getting the appropriate engineer on the call with the right expertise and the escalation process within Cloudera – to be addressed in the next weekly review. | EIH Platform team |  | NA | 15/04/24 | Closed |  |  |  | Saloni | 2025-02-10 | 555 | >60 | April | 2024 | #VALUE!
Digital & Data | Digital & Data | 89913334 | 2024-03-26 | Bigdata platform issues impacting the EIH data availability | Review the KPI/ SLOs for the adhoc/ self-service queries with the business users from EIH & BEAM | Impact analysis | Timothy Barrett | There are no SLOs for self service reports. | Data Ops manager |  | NA | 15/04/24 | Closed |  |  |  | Saloni | 2025-02-10 | 555 | >60 | April | 2024 | #VALUE!
Digital & Data | Digital & Data | 89913334 | 2024-03-26 | Bigdata platform issues impacting the EIH data availability | Effective impact assessment | Impact analysis | Timothy Barrett | 15/04: There are two critical processes - ISCV and Core Workflow. There is an exisiting Operations Guide in place for each of these to understand the impact statement. However, as EIH only holds the dataset, there are slight challenges in understanding the impact to the critical reports. At present, the EIH platform only provides the datasets without any visibility of the self-service reports potentially impacted. The EIH datasets are currently being migrated to BEAM. A meeting is scheduled with Louis and Sathish to agree on a plan. | Data Ops manager |  | NA | 15/04/24 | Closed |  |  |  | Saloni | 2025-02-10 | 555 | >60 | April | 2024 | #VALUE!
Digital & Data | Digital & Data | 89913334 | 2024-03-26 | Bigdata platform issues impacting the EIH data availability | If the issue still exists after the restart, perform live testing with the same query liaising with NOC and Linux to check the backend logs | Root cause | Zeeshan Khan/ Jafar Sadiq/ Rajesh | 15/04/2024: From platform side, the services on node hlxp0hd004,hlxp0hd005 and hlxp0hd006 were stopped. The teams decided to reboot 1 server first and start the impala service on it. Also, the teams had successfully did the reboot of servers on hlxp0hd004 and hlxp0hd005 and started the impala services. They have not found any issue on those 2 servers. The same was done for server hlxp0hd006 and the CPU was spiking again once they started impala service and that was impacting other 2 good servers as well. So, the problematic server was identified which is hlxp0hd006 and raised it with Linux team. This is a collaborative action and will be carried out once we had completed the above 4 actions. | EIH Platform/ Linux/ Network |  | NA | 15/04/24 | Closed |  |  |  | Saloni | 2025-02-10 | 555 | >60 | April | 2024 | #VALUE!
Digital & Data | Digital & Data | 89913334 | 2024-03-26 | Bigdata platform issues impacting the EIH data availability | Once we receive a confirmation from HP, explore the feasibility of performing a full hard restart of one of the problematic servers and monitor the Impala service performance | Root cause | Zeeshan Khan/ Ranadip Saha | 15/04/2024: From platform side, the services on node hlxp0hd004,hlxp0hd005 and hlxp0hd006 were stopped. The teams decided to reboot 1 server first and start the impala service on it. Also, the teams had successfully did the reboot of servers on hlxp0hd004 and hlxp0hd005 and started the impala services. They have not found any issue on those 2 servers. The same was done for server hlxp0hd006 and the CPU was spiking again once they started impala service and that was impacting other 2 good servers as well. So, the problematic server was identified which is hlxp0hd006 and raised it with Linux team. As the storage element is associated with these servers, therefore, the teams will identify a non-critical window to restart one of the problematic servers. Plan is to run the same query on the | EIH Platform/ Data Ops |  | NA | 15/04/24 | Closed |  |  |  | Saloni | 2025-02-10 | 555 | >60 | April | 2024 | #VALUE!
GTS | Enterprise Technology Platform | 89913334 | 2024-03-26 | Bigdata platform issues impacting the EIH data availability | Review the CPU utilisation across the three problematic servers to conclude whether the increase in CPU had caused the issue or not | Root cause | Sathish Selvapillai/ Jafar Sadiq | 15/04: This has been completed and bigdata application related process was consuming CPUs., its part of their daily run Teams will review the NMON reports to analyse the CPU utilisation during the issue. | Linux team |  | NA | 15/04/24 | Closed |  |  |  | Saloni | 2025-02-10 | 555 | >60 | April | 2024 | #VALUE!
GTS | Enterprise Technology Platform | 89913334 | 2024-03-26 | Bigdata platform issues impacting the EIH data availability | Analyse the hardware component of these 3 problematic servers | Root cause | Sathish Selvapillai/ Jafar Sadiq | 20/05: HP has confirmed that there are no hardware issues on the server. Also, as part of RCA, all 3 problematic servers were rebooted followed by a restart of Impala service. It was observed that the CPU had spiked for only one server. Therefore, Linux team have requested EIH platform team to schedule a call with Cloudera and this is being addressed in another "Root cause " action. 15/04: HPE Investigated the logs and found no issues with the hardware as such - a further query raised and waiting for an update., all 3 nodes were restarted as per the req from app team. We are awaiting feedback from HP to conclude the hardware health. It is anticipated that there are no issues with the hardware as we have multiple servers residing on the same hardware rack. | Linux team |  | NA | 20/05/24 | Closed |  |  |  | Saloni | 2025-02-10 | 555 | >60 | May | 2024 | #VALUE!
Digital & Data | Digital & Data | 89913334 | 2024-03-26 | Bigdata platform issues impacting the EIH data availability | Root cause of the issue | Root cause | Zeeshan Khan | 31/07: To identify the root cause regarding the 3 impacted server, Linux team suggested to perform Powerdrain and ILO reset activity. This activity can only be performed by bringing down all the 3 servers at once. As EIH is currently migrated to SW and from 23/07, onwards team have initiated the activity of stopping all the jobs from stockley park platform and soon this will be decommissioned. The teams will no longer be spending efforts in triaging the root cause. EIH is getting decommissioned on 14th Aug. 22/07: The relevant resource is currently OOO. We have reached out to Platform lead to help coordinate in identifying the root cause. 12/07: Linux team has recommended to upgrade the Firmware on those impacted server 004-005-006 . This activity was schedule on one of the servers on 17-06-2024 but due to package mismatch the activity got postponed. Team is checking the feasibility to accommodate this change. 25/06: We have now escalated this to Customer - Munesh Patil and awaiting further updates. If there is no response received, a further follow up to be made 17/06: the teams had been busy whilst coordinating the EDW SP to SW migration. This has now been escalated to Customer POC to get better traction. Follow up call scheduled on 18/06 28/05: Teams are currently working on job migration for an upcoming SP exit activity planned on 1st June, therefore, this will be picked up next week, ETA 7th June. 20/05: Linux team advised that the issue needs further discussion with Cloud Era, Platform team and Linux teams. A call will be scheduled by Zeeshan to investigate further, ETA: 24/05. 15/04/2024: From platform side, the services on node hlxp0hd004,hlxp0hd005 and hlxp0hd006 were stopped. The teams decided to reboot 1 server first and start the impala service on it. Also, the teams had successfully did the reboot of servers on hlxp0hd004 and hlxp0hd005 and started the impala services. They have not found any issue on those 2 servers. The same was done for server hlxp0hd006 and the CPU was spiking again once they started impala service and that was impacting other 2 good servers as well. So, the problematic server was identified which is hlxp0hd006 and raised it with Linux team. Cloudera suspects an issue with the CPU utilisation resulting in the latency of the Impala service. We have agreed multiple actions to identify the root cause of the incident. | EIH Platform | Tactical | NA | 31/07/24 | Closed |  |  |  | Saloni | 2025-02-10 | 555 | >60 | July | 2024 | #VALUE!
GTS | Enterprise Technology Platform | 89849978 | 2024-03-25 | Issues with EDW data refresh, reporting and queries on new HP EDW system | Schedule weekly calls with the business stakeholders for keeping them updated on the incident status. | Solution & Recovery | Karthick Chandra | We have agreed with the project team to schedule weekly calls to update the finance business on the latest progress and actions being taken to resolve the issue. | Project team |  | NA | 2024-08-04 | Closed |  |  |  | Saloni | 2025-02-10 | 556 | >60 | April | 2024 | #VALUE!
Digital & Data | Digital & Data | 89849978 | 2024-03-25 | Issues with EDW data refresh, reporting and queries on new HP EDW system | Review the scope of improvement on the stakeholder communication | Issue handling/Management | Timothy Barrett | As the post implementation hypercare was limited to the individual impacted users, the relevant business stakeholders were not kept informed on the issue. Therefore, it has been agreed to reach out to the relevant business SPOCs and service leads to ensure effective communication is sent. | Data Ops |  | NA | 2024-08-04 | Closed |  |  |  | Saloni | 2025-02-10 | 556 | >60 | April | 2024 | #VALUE!
Digital & Data | Digital & Data | 89849978 | 2024-03-25 | Issues with EDW data refresh, reporting and queries on new HP EDW system | Review the scope of improvement to anaylse the impact statement in a timely manner in future scenarios. | Impact analysis | Timothy Barrett | As part of post implementation checks, the project team had been addressing issues with the individual users which resulted in a lack of understanding of the scale of impact. We have agreed to check with the end user community in case an issue is highlighted after a migration activity to determine the appropriate severity of the impact. | Data Ops |  | NA | 2024-08-04 | Closed |  |  |  | Saloni | 2025-02-10 | 556 | >60 | April | 2024 | #VALUE!
GTS | Enterprise Technology Platform | 89849978 | 2024-03-25 | Issues with EDW data refresh, reporting and queries on new HP EDW system | Review the overall migration process if there is a possibility of sustaining the old platform and move the production load in batches on the new platform. | Problem avoidance | Karthick Chandra | 22/04: As part of SP exit, project team will work with the portfolio teams and business stakeholder to walkthrough the overall migration process, test scenarios, implementation plan, lessons learnt to ensure the upcoming migrations is seamless. This is a lesson learnt and during future platform changes, the teams should consider migrating the production load (database replication, ETL jobs, a group of self-service reports etc) in batches to monitor the performance before decommissioning the old platform. Engage a third-party COE team to monitor the testing before productionising the platform | Project team |  | NA | 22/04/24 | Closed |  |  |  | Saloni | 2025-02-10 | 556 | >60 | April | 2024 | #VALUE!
GTS | Enterprise Technology Platform | 89849978 | 2024-03-25 | Issues with EDW data refresh, reporting and queries on new HP EDW system | Review the level of testing performed before migrating the EDW DB from PDOA to HP solution? Explore the scope of improvement in testing scenarios before any future platform changes? | Problem avoidance | Karthick Chandra | 22/04: As part of SP exit, project team will work with the portfolio teams and business stakeholder to walkthrough the overall migration process, test scenarios, lessons learnt to ensure the upcoming migrations is seamless. The solution was tested with the peak load and no issues with concurrent (parallel) reports were identified. Also, the system resource – CPU, memory utilization seemed normal in HP. However, the I/O in PDOA was better than HP – this was ruled out during testing due to the available system resources – lessons learnt. Tech teams to explore other testing options (concurrent load run etc) before making any platform changes in future. Review the test cases to get a production like load testing. | Project team |  | NA | 22/04/24 | Closed |  |  |  | Saloni | 2025-02-10 | 556 | >60 | April | 2024 | #VALUE!
Digital & Data | Digital & Data | 89849978 | 2024-03-25 | Issues with EDW data refresh, reporting and queries on new HP EDW system | Once we are confident with the above test results, agree on eliminating the MQT optimisation implemented on the reports. | Solution & Recovery | Timothy Barrett | The action has been suspended, as the current infrastructure is pretty unstable and multiple optimisations are performed which included MQT optimisations. Therefore, this fine tuning will remain as it is to enhance the performance. | Data Ops |  | NA | 22/04/24 | Closed |  |  |  | Saloni | 2025-02-10 | 556 | >60 | April | 2024 | #VALUE!
Digital & Data | Digital & Data | 89849978 | 2024-03-25 | Issues with EDW data refresh, reporting and queries on new HP EDW system | Perform effective testing after parameter change has been deployed. | Solution & Recovery | Ashish Ranjan/ Piyush Sahoo | Test the parameter change with multiple combination of reports – reports with no optimisation, reports not hitting MQT etc. This will help in gaining confidence on the effectiveness of the change. | Data Ops |  | NA | 2024-02-04 | Closed |  |  |  | Saloni | 2025-02-10 | 556 | >60 | April | 2024 | #VALUE!
GTS | Enterprise Technology Platform | 89849978 | 2024-03-25 | Issues with EDW data refresh, reporting and queries on new HP EDW system | Implement the parameter change suggested by IBM on the SW database at 18:00 , 25/03. | Solution & Recovery | Badrinarayana Muvalla | This is an online change and the tech teams have been aligned to perform the relevant checks before applying the change - Completed | Project team |  | NA | 2024-02-04 | Closed |  |  |  | Saloni | 2025-02-10 | 556 | >60 | April | 2024 | #VALUE!
GTS | Enterprise Technology Platform | 89908543 | 2024-03-25 | Multiple BT hosted stores were hard down | BT to provide a full root cause report and attend a follow up PIR to explain their conclusions. | Root cause | Neil Volan (BT) | Update 16/04:There was a process error (human) which led to some IP addresses being missed on the range. There is now increased peer to peer verification at BT’s end to prevent a recurrence. Update 11/04:Investigations identified an issue with the application of IP address ranges within the BT network as the result of a planned network outage. A review is underway to identify the reasons for the error in the application of the IP Addresses. As part of this review measures will be identified to ensure consistency and robust security practices across the network infrastructure Update 28/03: BT have internally escalated and feel that due to the b/h the document will be published on Tues 2/4 | BT Vendor |  | NA | 16/04/24 | Closed |  |  |  | Saloni | 2025-02-10 | 556 | >60 | April | 2024 | #VALUE!
GTS | Enterprise Technology Platform | 89908543 | 2024-03-25 | Multiple BT hosted stores were hard down | BT to advise what alerting they have that would have proactively alerted them to an issue after their core network change and explain what incident communication process they have in place to advise their customers of outages. | Problem identification & Alerting | Neil Volan (BT) | Update 15/05: Neil to check who in Customer is registered for an outage notification. Update 16/04 There is no alerting at a single circuit level and this is a volume based product hence alerting not feasible by BT. Major system outages are communicated via email notifications. No one from Marks and Spencer is currently signed up for these notifications. To be added to the notifications we need to contact broadband.eco.admin@bt.com - Ian and Kamal aware and they will add whoever requires it. | BT Vendor |  | NA | 16/04/24 | Closed |  |  |  | Saloni | 2025-02-10 | 556 | >60 | April | 2024 | #VALUE!
GTS | Enterprise Technology Platform | 89908543 | 2024-03-25 | Multiple BT hosted stores were hard down | What is the official provision for BT overnight support and review if the overall support wrap is fit for purpose. | Solution & Recovery | Neil Volan (BT) | 15/05 - The echat is available but not fit for purpose as the updates are very generic. Nothing can be done to resolve this as this is a contractual level of support. BBOne is supported 24/7 via eChat – reiterate this to the NOC team and see if they are aware and plus know how to access/use it. | BT Vendor |  | NA | 15/05/24 | Closed |  |  |  | Saloni | 2025-02-10 | 556 | >60 | May | 2024 | #VALUE!
GTS | Enterprise Technology Platform | 89908543 | 2024-03-25 | Multiple BT hosted stores were hard down | The BT portal was not working when the incident started preventing us from logging the issue – how is the portal supported out of hours, what was the issue with it and how was it resolved? | Issue handling/Management | Neil Volan (BT) | 16/04:The Portal was not working due to a BT issue, causing the fault diagnostics not to run, this then prevented the fault being raised. The e-chat team can raise faults manually in cases like these as a workaround. | BT Vendor |  | NA | 16/04/24 | Closed |  |  |  | Saloni | 2025-02-10 | 556 | >60 | April | 2024 | #VALUE!
GTS | Enterprise Technology Platform | 89908543 | 2024-03-25 | Multiple BT hosted stores were hard down | Ascertain if changes made by BT are communicated to Customer even if they are more wider changes, if so, who is on the DL list? | Business & IT Communication | Neil Volan (BT) | 16/04: PEW updates are communicated to simon.hockaday@marks-and-spencer.com There was no PEW for this as it was deemed it would not affect BT customers. BT have committed that even if a pew will not cause customer impact they will publish a PEW. | BT Vendor |  | NA | 16/04/24 | Closed |  |  |  | Saloni | 2025-02-10 | 556 | >60 | April | 2024 | #VALUE!
GTS | Enterprise Technology Platform | 89908543 | 2024-03-25 | Multiple BT hosted stores were hard down | Confirm if we need to raise a fault on each circuit – its challenging to do so on a widespread issue | Issue handling/Management | Alan Gardner (BT) | 16/04: We don’t have to raise a fault on each circuit but please use 5 different sites (raise a minimum of 5 faults) to at least provide an idea of the nature of the issue. | BT Vendor |  | NA | 16/04/24 | Closed |  |  |  | Saloni | 2025-02-10 | 556 | >60 | April | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89908543 | 2024-03-25 | Multiple BT hosted stores were hard down | The solar winds tool is working slowly impeding live monitoring and this is being investigated by the NOC team. | Problem identification & Alerting | Rajesh Kumar Singarajan (NOC) | 15/05 - We are moving to a hybrid version of solar winds and will be operational in a few weeks. The new env is already up and runnimng. Closed confirmed by Kamal | Network |  | NA | 15/05/24 | Closed |  |  |  | Saloni | 2025-02-10 | 556 | >60 | May | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89908543 | 2024-03-25 | Multiple BT hosted stores were hard down | The NOC Team is not utilising the new tooling like Fortimanager to understand the estate. Training to maximise the potential of the tool is required. Fortinet to help develop and teach the best reporting methods. | Solution & Recovery | Rajesh Kumar Singarajan (NOC) | 08/07: Trainin contInues and kamal advises action can be closed. 03/06 - Rehan called kamal for an update on the training. Kamla advised that we should keep this open for three months and ask Avik for sporadic updates. 15/05 - There is a short term and long term ongoing training plan and a meeting will be setup for Friday weekly to provide updates on the maturity and implementation of this plan. | Network | Strategic | NA | 2024-08-07 | Closed |  |  |  | Saloni | 2025-02-10 | 556 | >60 | July | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89908543 | 2024-03-25 | Multiple BT hosted stores were hard down | We require a central repository where all stores and their components can be recorded and kept up to date. The commodity WAN register is the nearest thing but its managed by RIT – how do we get it into something like PowerBI? The tool should have centralised mapping of up to date store/RIT/network components. Agree initial scope and long-term owner. | Issue handling/Management | Simon H | 05/09: Data asset register dashboard has been built in Power Bi with all the store & Device details. Agreed this can be closed 05/09: Data asset register dashboard has been built in Power Bi with all the store & Device details. Review in-progress Update 08/08: Kamal to follow up with Simon H. Update 08/07: The portal has been created but we need to discuss how to make it operational Update 15/05: A central finops portal is being ceated that will have all this information along with circuit dashboard (power BI) work ongoing - update in one month | Network | Strategic | NA | 17/09/24 | Closed |  |  |  | Rehan | 2025-02-10 | 556 | >60 | September | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89908543 | 2024-03-25 | Multiple BT hosted stores were hard down | Can we deploy 4G in a timelier manner – create business case to buy more, and also prioritise/feasibility analysis based on coverage where we deploy ready to be used. Revisit where we have 4G routers and if required do we have the capability to turn them own remotely? How do we provide support through 4G routers in future? | Issue handling/Management | Ian Kirk | 18/05: Kamla has advised that there is already a process in place where every engineer carries a 4G router and this will be deployed if both links are down. To be able to improve this process will require resource and funding which given the current changes pending is not possible. | Network |  | NA | 18/05/24 | Closed |  |  |  | Saloni | 2025-02-10 | 556 | >60 | May | 2024 | #VALUE!
Customer Channels | Service Experience | 89908543 | 2024-03-25 | Multiple BT hosted stores were hard down | Work with business on their ability to be able to run operations offline (offline work book – e.g.: fridge monitoring manually, legal requirements) | Solution & Recovery | Laura Whittle | 14/05: As this is a long term action: A backlog has been created to address this: RETAILSL-90 | Network |  | NA | 14/05/24 | Closed |  | RETAILSL-90 |  | Saloni | 2025-02-10 | 556 | >60 | May | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 89908543 | 2024-03-25 | Multiple BT hosted stores were hard down | Work with business on their ability to be able to run operations offline (offline work book – e.g.: fridge monitoring manually, legal requirements) | Solution & Recovery | Valliammai Ramasamy | Update: Valli advised us of the backlog that has been raised - Retail SL-90 | Network |  | NA | 14/05/24 | Closed |  |  |  | Saloni | 2025-02-10 | 556 | >60 | May | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89908543 | 2024-03-25 | Multiple BT hosted stores were hard down | NOC fault finding training/SOP’s and KB articles to be created | Solution & Recovery | Rajesh Kumar Singarajan/Ian Kirk | 15/05: The NOC team are going through weekly training on various technologies including this. | Network |  | NA | 15/05/24 | Closed |  |  |  | Saloni | 2025-02-10 | 556 | >60 | May | 2024 | #VALUE!
Digital & Data | Digital & Data | 89902881 | 2024-03-22 | Colleagues were unable to run reports through Business Objects | Create a SOP detailing steps to abide by the industry level best practices whilst deploying a project/service/application | Solution & Recovery | Arghya Shankar Monal | 15/04: A confluence page has not been created to detail tge steps and direction to move all storage account to a private end point. https://confluence.marksandspencer.app/display/ADE/Future+plan+and+prerequisites+fir+creating+blob+storage+NSG 08/04: Arghya had a discussion with the internal team and finalized all new storage account creation would have a Private endpoint created . Already this process is being followed for few recent months . Would still create a confluence page on this. A SOP is being created to refer to during any future migration/activities. | Data Platform |  | NA | 15/04/24 | Closed |  |  |  | Saloni | 2025-02-10 | 559 | >60 | April | 2024 | #VALUE!
Digital & Data | Digital & Data | 89902881 | 2024-03-22 | Colleagues were unable to run reports through Business Objects | Perform an E2E review of the NSG rule set across different layers within the Business Objects services/application to ensure they are pointed to the correct endpoints. | Problem avoidance | Prashant Rowlo & Arghya Shankar Mondal | 29/05: A call was scheduled with Cloud and Data team to identify any other NSG rules with public end points in Buisness Object. It has now been concluded there are no other rules which needs amendment - therefore, the actions is being closed. 20/05: PM had a call with Arghya (Data) and Prashanth (Cloud) and Data team confirmed that there are no other end points which needs to be pointed to private end point. However, we have requested for further validations through a call with both teams. 02/05: Additional details were requested by Cloud team to investigate further. This has been shared by Data team and we await further update. ETA: 16/05. 20/04: This is a long term activity to review all cloud endpoint across Data layer. ETA: 02/05. 15/04: A work order has been created to review all the endpoints with Cloud team within the data portfolio. 08/04: The teams are internally working to review the endpoints. We have requested the Data dev team to raise a backlog and track this through closure. This action requires collaboration between the Cloud Ops and BO team to review all the rules set within the BO layer ensuring they are configured appropriately to avoid any further incidents | Data Platform & Cloud Ops | Strategic | NA | 29/05/24 | CLosed |  |  |  | Saloni | 2025-02-10 | 559 | >60 | May | 2024 | #VALUE!
Digital & Data | Digital & Data | 89902881 | 2024-03-22 | Colleagues were unable to run reports through Business Objects | Create the private endpoint to point the Business Objects application storage account. | Permanent Fix | Arghya Shankar Mondal | 20/05: The deployment was completed on 14/05 and Data team had tested in lower environment and confirmed that the BO storage account is now pointing to a private endpoint which means the issue is fixed permanently. 13/05: The network piece of work is completed on 09/05, the teams are in progress of deploying the change into prod. ETA: 14/05 07/05: Data team has raised a CR, however, there is a piece of work to be implemented by NOC and they are awaiting updates. ETA of change deployment: 08/05 22/04: The testing is completed in non prod. A CR will be raised to deploy the change into production. 15/04: The teams are planning to deploy the private end point on non prod environment on 18/04, once this is proven successful, it will be deplpyed in prod. 08/04: After discussion it has been agreed to do it in non prod environment first before going to implement in prod after testing . ETA for implementation in non prod : This week . Discussions are underway with the architects | Data platform |  | NA | 20/05/24 | Closed |  |  |  | Saloni | 2025-02-10 | 559 | >60 | May | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89900521 | 2024-03-21 | Fire incident at Bradford C&H DC impacting site operations | The PSU’s we have do not match the product recall. We need if ask Zebra of our PSU needs to be added to their list. We will send the specific details to zebra and can send then the cable if needed | Root Cause | Colin Haworth | 20/04 - Customer procured printers and psu’s from 2010 from various companies but not directly from Zebra. Zebra should have told all their suppliers who sell their products about the recall and then the suppliers should have told us. We only found out by chance as we googled the part number. We are now part of the Zebra communication lists, which was an action they took as part of the PIR and we now buy from DN who are an approved supplier and we also have direct support with Zebra with our device serial numbers all registered with them. 03/04 - Yet to get an update on these actions | Product Owner |  | NA | 20/04/24 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 560 | >60 | April | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89900521 | 2024-03-21 | Fire incident at Bradford C&H DC impacting site operations | How do we ensure we are on Zebra’s recall notification list? What happens if the suppliers goes out of business? | Problem avoidance | Colin Haworth | 17/05- Customer procured printers and psu’s from 2010 from various companies but not directly from Zebra. Zebra should have told all their suppliers who sell their products about the recall and then the suppliers should have told us. We only found out by chance as we googled the part number. We are now part of the Zebra communication lists, which was an action they took as part of the PIR and we now buy from DN who are an approved supplier and we also have direct support with Zebra with our device serial numbers all registered with them. 13/05 - We are yet to hear back from Zebra 23/04/2024 - Colin is still discussing on this with the relevant teams and we are waiting feedback from Zebra 03/04 - Yet to get an update on these actions | Product Owner |  | NA | 17/05/24 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 560 | >60 | May | 2024 | #VALUE!
GTS | Digital Workplace Services | 89900521 | 2024-03-21 | Fire incident at Bradford C&H DC impacting site operations | How do we manage a product recall process? | Problem avoidance | David Bruce/Promode/Sathish | 23/04 - Warehouse Colleague Product related equipments are dealt by both JohnAriss/Colin Haworth - they work with the Vendors accordingly 03/04 - Yet to get an update on these actions | WPT |  | NA | 20/04/24 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 560 | >60 | April | 2024 | #VALUE!
GTS | Operations | 89900521 | 2024-03-21 | Fire incident at Bradford C&H DC impacting site operations | In the PIR it was reported that the communication from Tech to Business Continuity wasn’t as timely as it could have been. Business Continuity Teams to be added too all MIM comms. | Business & IT Communication | Saloni Chowdhury | This has been completed. | MIM |  | NA | 22/03/24 | Closed |  |  |  | Saloni | 2025-02-10 | 560 | >60 | March | 2024 | #VALUE!
C&H and Intl | C&H commercial Trading | 89900521 | 2024-03-21 | Fire incident at Bradford C&H DC impacting site operations | Who do BCP communicate to in D&T? – who receive the BC comms in Tech | Business & IT Communication | John Frost | BCP team communicates with the D&T on-call incident manager as designated in the weekly on call rota | Product Owner |  | NA | 20/04/24 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 560 | >60 | April | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89900521 | 2024-03-21 | Fire incident at Bradford C&H DC impacting site operations | Agree the process model for the hardware during a sev 0 situation | Issue handling/Management | Martin/Nanda/ RIT/NOC | 13/05 - A process has been agreed within the relevant teams 03/04 - Yet to get an update on these actions | Service Lead |  | NA | 13/05/24 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 560 | >60 | May | 2024 | #VALUE!
Customer Channels | Service Experience | 89883764 | 2024-03-15 | Sparks pay payment failures | Review SLA on getting Worldline incident’s RCA and mitigation steps | Root cause | Gary Allenby | 11/04: RCA has been published by the Worldline 19/03: Escalation have been made to get the root cause details from Worldline | Payments Foundation |  | NA | 16/04/24 | Closed |  |  |  | Saloni | 2025-02-10 | 566 | >60 | April | 2024 | #VALUE!
Customer Channels | Service Experience | 89883764 | 2024-03-15 | Sparks pay payment failures | Communicate to Sparkspay product team on progress with Worldline tickets | Business & IT Communication | Priyabrata Sahu | 19/03: Team has agreed to communicate going forward in addition a request have been raised with Worldline to get Sparkspay email group subscribed to any change management/incident notifications to avail real time notification in event of incidents or in-advance alerts for any planned maintenance activities. | Payments Foundation |  | NA | 15/03/23 | Closed |  |  |  | Saloni | 2025-02-10 | 566 | >60 | March | 2023 | #VALUE!
Customer Channels | Service Experience | 89883764 | 2024-03-15 | Sparks pay payment failures | Add an alert for Sparkpay team on WL transactions failures (online & in-store) | Problem identification & Alerting | Kanan Oza | 16/04: Since there was an alert existing for the same problem identification. team have modified its SLA 21/03: A backlog PFOUND-599 has been raised to track this action 19/03 This action is inprogress | Payments Foundation |  | NA | 16/04/24 | Closed |  | PFOUND-599 |  | Saloni | 2025-02-10 | 566 | >60 | April | 2024 | #VALUE!
Customer Channels | Service Experience | 89895108 | 2024-03-14 | Store colleagues unable to access Travel Money application (Customer Bank) | A. Engage Customer Honeywell teams on ability for Essiell to have a Honeywell to test future change requests | Problem avoidance | Laura Whittle/Valliammai Ramasamy | 14/05 - Valli has created a backlog for this action retailsl - 91, hence closing it. 28/04 - It is still being discussed with Chris by Valli 09/04: Discussion is still in progress between Laura, Valli and the teams 03/04: Valli updated that discussion is still in progress 25/03: Valli is working with RIT team on it | Service Lead |  | NA | 14/05/24 | Closed |  | retailsl - 91 |  | Saloni | 2025-02-10 | 567 | >60 | May | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 89895108 | 2024-03-14 | Store colleagues unable to access Travel Money application (Customer Bank) | In the interim, Customer Colleague Devices team to offer support to test any future changes with Essiell prior to deployment for the Honeywell devices only. | Problem avoidance | Valliamai Ramasamy | NA/03: Colleaguesprogress | Service Lead |  | NA | 14/03/23 | Closed |  |  |  | Saloni | 2025-02-10 | 567 | >60 | March | 2023 | #VALUE!
Customer Channels | Service Experience | 89895108 | 2024-03-14 | Store colleagues unable to access Travel Money application (Customer Bank) | Full Root Cause Analysis (RCA) to be shared to stakeholders across JV. | Root cause | Jamie Donbroski | 09/05 - Chris confirmed that this action can be closed. 25/04: Chris has followed up with the action owners. 19/04: Have checked with Chris F on this action. 09/04: No response to Chris mail from the Action owners 03/04: Chris has followed up with the action owners 25/03: Chris Fenwick is tracking currently with MSB | Customer Bank product team |  | NA | 2024-09-05 | Closed |  |  |  | Saloni | 2025-02-10 | 567 | >60 | May | 2024 | #VALUE!
Customer Channels | Service Experience | 89895108 | 2024-03-14 | Store colleagues unable to access Travel Money application (Customer Bank) | Re-engage Customer Bank operational and product teams on the need to advise all IT related changes to change management process | Supplier and support involvement | Mickey Jones | 14/06 - Valli confirmed that Customer Bank operational and product teams have been made aware on the need to be aware of all IT related changes. 31/05 - Call is scheduled on 04/06 to discuss on the change management. 29/05 - Have reached out to Mickey and Siu to check on their availability to discuss on change management. 22/05 - We have asked to arrange a meeting with Chris Fenwick, Customer Bank and our change team - agree the process and close action. 21/05 - Chris has reached out to Mickey on this Separately as well. 20/05 - we have followed up again with Chris Fenwick 14/05 - Followed up with action owner in mail. 09/05 - Followed up with HSBC. 25/04: Chris has followed up with the action owners. 19/04: Have checked with Chris F on this action. 09/04: No response to Chris mail from the Action owners 03/04: Chris has followed up with the action owners 25/03: Chris Fenwick is tracking currently with MSB | Customer Bank product team | Tactical | NA | 14/06/24 | Closed |  |  |  | Saloni | 2025-02-10 | 567 | >60 | June | 2024 | #VALUE!
Customer Channels | Service Experience | 89895108 | 2024-03-14 | Store colleagues unable to access Travel Money application (Customer Bank) | Share the current Customer Bank incident management playbook for the JV | Supplier and support involvement | Mickey Jones / Siu Mak | 20/05 - Chris confirmed that the playbook is shared and the action can be closed.https://confluence.marksandspencer.app/display/CET/Incident+Management+Process 14/05 - Followed up with action owner in mail09/05 - Followed up with HSBC. 25/04: Chris has followed up with the action owners. 19/04: Have checked with Chris F on this action. 09/04: No response to Chris mail from the Action owners 03/04: Chris has followed up with the action owners 25/03: Chris Fenwick is tracking currently with MSB | Customer Bank product team |  | NA | 20/05/24 | Closed |  |  |  | Saloni | 2025-02-10 | 567 | >60 | May | 2024 | #VALUE!
Customer Channels | Service Experience | 89895108 | 2024-03-14 | Store colleagues unable to access Travel Money application (Customer Bank) | Continue to workshop the current Customer Bank incident management playbook and support wrap for Travel Money to ensure alignment and closedown of 11.1 Internal Audit action. | Supplier and support involvement | Mickey Jones / Siu Mak & Priya Sahu | 28/03: Priya confirmed that the internal audit call went fine on the 27/03 and all good, hence closing the action. 25/03: Internal audit action call is on the 27/03 | Customer Bank product team |  | NA | 28/03/24 | Closed |  |  |  | Saloni | 2025-02-10 | 567 | >60 | March | 2024 | #VALUE!
Customer Channels | Service Experience | 89895108 | 2024-03-14 | Store colleagues unable to access Travel Money application (Customer Bank) | Once playbook agreed, James Taylor and Darren Gibson to review and approve and arrange suitable cascades to technology partners across JV. | Problem avoidance | James Taylor | 14/06 - Valli confirmed to close the action as the process document has been sent. 28/05 - Have sent a mail copying Darren to help on this. 22/05 - Sent mail to James Taylor (Customer Bank) sharing the playbook to be reviewed with Darren Gibson. 20/05 - Chris confirmed that the playbook is shared with Customer, waiting for confirmation to share with James and Darren for their reviwal and approval. 14/05 - Followed up with Chris in mail 09/05 - Followed up with HSBC. 25/04: Chris has followed up with the action owners. 19/04: Have checked with Chris F on this action. 09/04: No response to Chris mail from the Action owners 03/04: Chris has followed up with the action owners 25/03: Chris Fenwick is tracking currently with MSB | Customer Bank product team | Tactical | NA | 14/06/24 | Closed |  |  |  | Saloni | 2025-02-10 | 567 | >60 | June | 2024 | #VALUE!
Customer Channels | Service Experience | 89895108 | 2024-03-14 | Store colleagues unable to access Travel Money application (Customer Bank) | Future change roadmap to be shared by Essiell and Customer Bank to ensure all technology stakeholders are aware of confirmed and unconfirmed activity to enable change management | Business & IT Communication | Mickey Jones / Jamie Donbroski | 14/06 - Valli confirmed that Essiell and Customer Bank will be updating Customer on all the changes done at their end. 31/05 - Call is scheduled on 04/06 to discuss on the change management. 29/05 - Have reached out to Mickey and Siu to check on their availability to discuss on change management. 21/05 - Chris has reached out to Mickey on this Separately as well. 14/05 - Followed up with action owner in mail. 09/05 - Followed up with HSBC. 25/04: Chris has followed up with the action owners. 19/04: Have checked with Chris F on this action. 09/04: No response to Chris mail from the Action owners 03/04: Chris has followed up with the action owners 25/03: Chris Fenwick is tracking currently with MSB | Customer Bank product team | Tactical | NA | 14/06/24 | Closed |  |  |  | Saloni | 2025-02-10 | 567 | >60 | June | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89893425 | 2024-03-12 | Support centre and store colleagues reported that they were unable to view product images on the website | What was the reason behind several cnames being filtered and not allowed by the DNS filter on the FortiGate? | Root cause | Kamal/Ian Kirk | 18/05 - Fortinet is a new technology where our associates are veing trained and there will be difference, this has been put down to learning | Network |  | NA | 18/05/24 | Closed |  |  |  | Saloni | 2025-02-10 | 569 | >60 | May | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89893425 | 2024-03-12 | Support centre and store colleagues reported that they were unable to view product images on the website | The test plan that was at hand was followed but did not include observing of images were visible on the website via the internal network. Add today’s impacts to the test plan for large scale changes – .com plus /assist (Ensure that the test team do more in depth functional testing with .com plus and assist and the website) | Problem avoidance | Kamal/Ian Kirk | 04/04: while the test plan is pretty comprehensive, its not going tp be possible to test the hundreds, possibly thousands of applications, especially considering that this was not an issue externally and only manifested as an issue internally, and the apps affected were not Day 1 | Network |  | NA | 2024-04-04 | Closed |  |  |  | Saloni | 2025-02-10 | 569 | >60 | April | 2024 | #VALUE!
GTS | Operations | 89893425 | 2024-03-12 | Support centre and store colleagues reported that they were unable to view product images on the website | From the MAL extract the day 1 business critical applications and share with network team for them to see the feasibility of accommodating them in their test plan for critical changes | Problem avoidance | Dinesh Maluroutu | 12/12: Dinesh has sent an email to Kamal with the Day 1 and Day 3 critical apps 02/12: Spoke with Dinesh who said he will close today 15/07: Dinesh will extract the day 1 applications and send to NW team and ask them to accomodate testing after network changes - eta eod 16/07 15/05: Dinesh has confirmed he is continuing work on this. 11/04: The list has been extracted but needs to be analysied to identify the most critical applications. | Service Management | Strategic | NA | 2024-12-12 | Closed |  |  |  | Rehan | 2025-02-10 | 569 | >60 | December | 2024 | #VALUE!
Customer Channels | Customer Engagement | 89893425 | 2024-03-12 | Support centre and store colleagues reported that they were unable to view product images on the website | Identify an owner for .com + | Problem avoidance | Hisham/Steve Warren | 04/04: For the selling part of .com+ we have agreed that this will be owned by the “In-store Digital Selling” Product Group, under the engineering leadership of Charly Webster | Network |  | NA | 2024-04-04 | Closed |  |  |  | Saloni | 2025-02-10 | 569 | >60 | April | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89893425 | 2024-03-12 | Support centre and store colleagues reported that they were unable to view product images on the website | Network team to add the website to the test plan, further than the front page | Problem avoidance | Kamal Kanniappan | 18/05 - The test plan cannot be changed as this would crate a much larger over head of effort given the 100's of changes done. Closed as confirmed by Kamal | Network |  | NA | 18/05/24 | Closed |  |  |  | Saloni | 2025-02-10 | 569 | >60 | May | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89893425 | 2024-03-12 | Support centre and store colleagues reported that they were unable to view product images on the website | Identify if we have we have strong SME’s on the FortiGate manager tool (Fortinet is the company). | Solution & Recovery | Kamal Kanniappan | Closed – We are putting more of the NOC team through Fortinet certification | Network |  | NA | 2024-12-03 | Closed |  |  |  | Saloni | 2025-02-10 | 569 | >60 | March | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89893425 | 2024-03-12 | Support centre and store colleagues reported that they were unable to view product images on the website | Understand from Fortinet why the $ had to be removed to allow the cname. | Solution & Recovery | Kamal Kanniappan | 18/05 - Fortinet is a new technology where our associates are veing trained and there will be difference, this has been put down to learning | Network |  | NA | 18/05/24 | Closed |  |  |  | Saloni | 2025-02-10 | 569 | >60 | May | 2024 | #VALUE!
GTS | Operations | 89893425 | 2024-03-12 | Support centre and store colleagues reported that they were unable to view product images on the website | How do we improve the overall support for DNS –– Raise formal risk on the lack of ownership | Problem avoidance | Ian/Sathish/Kamal/Jane | 15/05: It has been confirmed that Venkat in the NOC team has taken ownership of this and will be trained accordingly. | Service Management |  | NA | 15/05/24 | Closed |  |  |  | Saloni | 2025-02-10 | 569 | >60 | May | 2024 | #VALUE!
Foods | Foods Supply Chain | 89884794/89885099 | 2024-03-11 | Delay in Foods Bradford NDC allocation | MS SQL team suggested to enable the Hikari logs when the issue reoccurs. | Problem avoidance | Neethu C/Vivek | 14/05 - Hikari logs have been enabled and further trouleshooting is being done as part the action to restart API server. Hence closing this action. 07/05 - Still no logs have been captured, hence logs are being enabled for 2 more Pods which could be potentially causing the issue. 03/05 - No logs have been captured till now. 30/04: Team is working on this currently and no logs have come till now. 26/04: On 29th Apr, ASO team is planning to enable the Hikari pool logs for WE region, for further analysis, as per recommendation from MS and the logs will be shared to MS for analysis by Cloud Team. 19/04: Have checked with Emmanuel on the latest on this action. 09/04: Captured network trace during the issue doesn't include the timeout errors, hence the issue needs to be reproduced and fresh network trace is needed to analyze further by MS. This has been escalated to MS Account Manager for Traction. 04/04: MS had again asked for specific (network) details with which they would be working with their Network team. 03/04: MS has asked for few more details on the issue and the same has been shared by Cloud Team. 28/03: On 27/03, hikari logs were enabled in WE service PODs, captured required logs and have been shared with MS by cloud team. As the issue persisted, the Service was reverted to NE. 25/03: Anbarasi updated that based on the outcome of testing in non prod, on 27/03 Hikari logs will be enabled in 1 POD(one of the services will be deployed in WE prod) and monitored to decide on further steps. 19/03: Vivek updated that yesterday there were issues in WE, when they tried to move services for one of pod and reverted to NE. 14/03: Plan to revert to WE by early next week | ASO |  | NA | 14/05/24 | Closed |  |  |  | Saloni | 2025-02-10 | 570 | >60 | May | 2024 | #VALUE!
Foods | Foods Supply Chain | 89884794/89885099 | 2024-03-11 | Delay in Foods Bradford NDC allocation | MS asked for JDBC driver version and config details | Problem avoidance | Neethu C | 13/03: The required logs have been shared with MS | ASO |  | NA | 13/03/24 | Closed |  |  |  | Saloni | 2025-02-10 | 570 | >60 | March | 2024 | #VALUE!
Foods | Foods Supply Chain | 89884794/89885099 | 2024-03-11 | Delay in Foods Bradford NDC allocation | Original action: To restart the API server – which will refresh all components under the AKS foods cluster to see if this resolves the delay from West Europe to SQL New action: To bring 50% of the services back to West Europer as we originally had. | Permanent Fix | Neethu C and Emmanuel G/Vivek | 19/06 - CRQ000000203348 has been raised for this activity. 14/06 - Emmanuel confirmed that the app team will do the deployment of all services in West next week, Awaiting the change number. 10/06 - Emmanuel updated that after the timeout deployment changes the POD has been stable since 29/05, where the cluster level settings (for all foods application) has been performed. Cloud team is checking with Foods on bringing all the services back to 50:50 between WE and NE. 28/05 - As part of observations, by 29/05 OSCS service will be deployed in WE (1 POD) new node pool will be enabled and cloud ops are planning to add ingress time out in WE similiar to NE. 22/05 - Application and Cloud team have a call by 23/05 to discuss and decide on this further. 20/05 - Emmanuel updated on that the API restart has been done from the Microsoft side. Our team has hosted a service in DR. For two days it worked fine but then we saw issues. Over the last two weeks we have created a new VM host pool under the exisiting cluster in West Europe and moved three services across. We have monitored and there have been no issues. We now need to talk to the application team about moving back to a 50/50 configurations. EG to schedule meeting for 21/05. 16/05 - No hikari logs got generated so far in ALCS and OSCS in WE until now since the corresponding log capture enabled on 8th May. 14/05 - Still there are delay from West Europe to SQL connectivity, platform team to work with NOC. 07/05 - Still no logs have been captured, hence logs are being enabled for 2 more Pods which could be potentially causing the issue. 03/05 - No logs have been captured till now. 30/04: Team is working on this currently and no logs have come till now. 26/04: On 29th Apr, ASO team is planning to enable the Hikari pool logs for WE region, for further analysis, as per recommendation from MS and the logs will be shared to MS for analysis by Cloud Team. 19/04: Have checked with Emmanuel on the latest on this action. 09/04: Captured network trace during the issue doesn't include the timeout errors, hence the issue needs to be reproduced and fresh network trace is needed to analyze further by MS. This has been escalated to MS Account Manager for Traction. 04/04: MS had again asked for specific (network) details with which they would be working with their Network team. 03/04: MS has asked for few more details on the issue and the same has been shared by Cloud Team. 28/03: On 27/03, hikari logs were enabled in WE service PODs, captured required logs and have been shared with MS by cloud team. As the issue persisted, the Service was reverted to NE. 25/03: Anbarasi updated that based on the outcome of testing in non prod, on 27/03 Hikari logs will be enabled in 1 POD(one of the services will be deployed in WE prod) and monitored to decide on further steps. 19/03: Vivek updated that yesterday there were issues in WE, when they tried to move services for one of pod and reverted to NE. 14/03: Plan to revert to WE by early next week | ASO/Cloud | Tactical | NA | 19/06/24 | Closed |  |  |  | Saloni | 2025-02-10 | 570 | >60 | June | 2024 | #VALUE!
Foods | Foods Supply Chain | 89884794/89885099 | 2024-03-11 | Delay in Foods Bradford NDC allocation | Explore the capability of switching the services between WE and NE simultaneously whenever there are issues at the POD level for the applications which are running in Active-Active without any manual intervention | Problem avoidance | Raguram and Vinoth | 30/04 - Vinoth discussed with Ragu along with cloud team. It is not possible to automatically handle the switching of services and it has to be picked up manually and move pods accordingly based on the performance in the respective regions. Hence closing this action. 19/04: As it is a long term action, Vinoth is working on a backlog. 28/03: Raguram updated that this will be picked in Q1 11/03: Cloud and Application teams to work collaboratively | ASO/Cloud |  | NA | 30/04/24 | Closed |  |  |  | Saloni | 2025-02-10 | 570 | >60 | April | 2024 | #VALUE!
Foods | Foods Supply Chain | 89884794/89885099 | 2024-03-11 | Delay in Foods Bradford NDC allocation | Review the alerts received at the start of the issue especially regarding unresponsive/restart pods, Any other possible alerts can be configured? | Problem identification & Alerting | Vivek/ASO | 19/03: Initial alert was obtained at 2:10, however there was a delay due to Q issue 11/03: POD restarted alerts were received, team to share the time of the alerts. | ASO |  | NA | 19/03/24 | Closed |  |  |  | Saloni | 2025-02-10 | 570 | >60 | March | 2024 | #VALUE!
Foods | Foods Supply Chain | 89884794/89885099 | 2024-03-11 | Delay in Foods Bradford NDC allocation | Delay in preparing the retrigger file to fix the issue– why did it take more than 90 minutes? | Solution & Recovery | Vinoth | It was the first occurrence after the hypercare, template is now prepared and shared among the team | ASO |  | NA | 2024-11-03 | Closed |  |  |  | Saloni | 2025-02-10 | 570 | >60 | March | 2024 | #VALUE!
Foods | Foods Supply Chain | 89884794/89885099 | 2024-03-11 | Delay in Foods Bradford NDC allocation | Plan to segregate Kafka (Message event in cloud) from the WMS integration flow where ASO faced issues on 07th Mar. | Problem avoidance | Vivek/ASO | A change CRQ000000196454 was deployed to avoid any impact to DC operations. | ASO |  | NA | 2024-11-03 | Closed |  |  |  | Saloni | 2025-02-10 | 570 | >60 | March | 2024 | #VALUE!
Group Platforms | Finance | 89933408 | 2024-03-07 | Significant number of duplicate ECS tickets to be printed at stores | Feasibility to amend the design configuration in SAP to rectify the flow of product attribute changes as price changes to the downstream systems | Permanent Fix | Santhanalakshmi Ramachandran | 23/04 - After all the investigations and analysis, it was been confirmed by SAP that "There was no feasibility to amend the design config's in SAP" 20/03 - Architect had suggested to get help from the tech team's (ABAP) help to further analyse respective program to find behaviour of I020 with product change and without price change. ABAP team has been involved for the same 12/03 - SAP team is checking with the Architect. 07/03 - Discussions are underway. | SAP Team |  | NA | 20/04/24 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 574 | >60 | April | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 89933408 | 2024-03-07 | Significant number of duplicate ECS tickets to be printed at stores | Devise an interim solution to avoid the duplicate ticket scenario in ECS | Solution & Recovery | Mark Charlwood | Teams have undertaken the functional testing of the ‘omit from check’ option in the non-production environment. This will inform work (if any) required within the ECS solution. | Product Owner |  | NA | 25/03/24 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 574 | >60 | March | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 89933408 | 2024-03-07 | Significant number of duplicate ECS tickets to be printed at stores | For all future design changes that don’t require immediate batching, is there a feasibility to manually intervene to force a hashcode refresh that includes the design change but doesn’t result in a ticket being batched. Any future price records from SAP that don’t include an actual price change will then be suppressed by ECS. | Problem avoidance | Mark Charlwood | All future design changes that don’t require immediate batching, there is a feasibility to manually intervene to force a hashcode refresh that includes the design change but doesn’t result in a ticket being batched. - This will be the interim solution until we get the permanent fix | Product Owner |  | NA | 25/03/24 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 574 | >60 | March | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 89933408 | 2024-03-07 | Significant number of duplicate ECS tickets to be printed at stores | Apply the ‘omit from check’ option to design changes in ECS. Where there’s a requirement to include changes in the check, ad-hoc batches can be created to force design changes to stores. Where there’s a requirement to include changes in the check, ad-hoc batches can be created to force design changes to stores. | Permanent Fix | Mark Charlwood | The Option "Omit from check" is in place and it will be turned ON/OFF as requried on the business needs | Product Owner |  | NA | 27/03/24 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 574 | >60 | March | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 89933408 | 2024-03-07 | Significant number of duplicate ECS tickets to be printed at stores | Create a framework for Business continuity with all the ticketing scenarios with the valid information before reaching out to Tech/business. This action is to ensure that proper impact is communicated. | Business & IT Communication | Chris Davey/ECS team | 17/06 - This action is part of the tracking and meanwhile the right training has been provided to the associated to convey the right impact to the BC whenever there is a MI. 23/05 - This actions is being tracked in multiple places - Risk, Service design etc within Foods - Problem Manager has requested for a reference Risk_Id/ Backlog to close this action from this tracker. 13/05 - This action is being worked upon within the teams on high priority however this is a long term approach. Contacts for business continutiy has been shared to Chris for further follow-up's. Also yet to get a backlog for this long tern approach 20/03 - Im yet to hear back from the Action owner | Retail OPS | Strategic | NA | 17/05/24 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 574 | >60 | May | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 89933408 | 2024-03-07 | Significant number of duplicate ECS tickets to be printed at stores | Build a UAT environment for testing these scenarios | Solution & Recovery | Mark Charlwood | 03/04 - The testing environment has been enhanced to support this further. 19/03 There is an exisiting non-prod environment, however, the data and config in the non-prod is not like-to-like as production. Therefore, teams will look at the feasibility of refreshing the non-prod before delivering any major change to test the use cases in future. | Product Owner |  | NA | 2024-03-04 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 574 | >60 | April | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89880759 | 2024-03-06 | Colleagues were unable to connect their Customer assets to internet due to a central network connectivity issue | How effectively can the testing be improved? Review the feasible ways to ascertain the right impact before the change. | Impact analysis | Kamal/NOC/Janani | 28/03: In the next CC and DP3p changes, these testing were included and the issues didn't resurface. On the architecture, NOC team have understood the DNS failover. 06/03: During the testing, we did not observe any issues as we did not have a like to like test environment as Prod. To address this gap, NOC will check with the Design architects to have a better understanding on the configurations. Once the Design is understood, we can have the like-to-like test environment for exact results and to ascertain the expected impacts. | Network |  | NA | 28/03/24 | Closed |  |  |  | Gokul | 2025-02-10 | 575 | >60 | March | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89880759 | 2024-03-06 | Colleagues were unable to connect their Customer assets to internet due to a central network connectivity issue | How efficiently can we communicate to the stores before them highlighting the issue to Service desk or Retail stakeholders? Do we have the right monitoring available on the Honeywells? | Problem identification & Alerting | Stores team/NOC | 06/03: We do have the required alerting in place and the issue was identified proactively however, during the incident as the stores support team were on the different project call along with the NOC team it was not communicated in the MIM bridge. Teams have agreed to notify MIM first during such outages and to join the MIM bridges rather than having separate calls. | Network |  | NA | 2024-06-03 | Closed | NA | NA | N/A | Gokul | 2025-02-10 | 575 | >60 | March | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89880759 | 2024-03-06 | Colleagues were unable to connect their Customer assets to internet due to a central network connectivity issue | Review and ensure we have the right MIM engaging process with service Desk. Also review the troubleshooting steps taken from the NOC end when SD reports issues with stores connectivity. | Problem identification & Alerting | SD and NOC | 22/03: NOC team is also made aware of the process to engage MIM for more than 5 store related issues. 06/03: SD : Teams are educated to contact MIM on a timely manner whenever we receive more than 05 calls from stores– Proper trainings are planned for the New joiners as well – Completed NOC : Next level checks to be added - In-progress | Network |  | NA | 22/03/24 | Closed |  |  |  | Gokul | 2025-02-10 | 575 | >60 | March | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89880759 | 2024-03-06 | Colleagues were unable to connect their Customer assets to internet due to a central network connectivity issue | Feasibility of configuring an alerting within Network area to proactively identify the issue when multiple stores lose internet connectivity (wrt to HHT’s and WKS). | Problem identification & Alerting | Kamal/NOC/Janani | 11/06 - Rajesh updated that these products are being explored. Janani also confirmed the same. Hence closing this action. 29/05 - 7 Signal is having limited license, ZDX is still being discussed. 20/05 - Kamal/Rajesh to confirm if the tool is now fit for purpose 09/05: Suganya B updated 7 Signals ((wireless nw performance tool) has been deployed to all the stores successfully in Q4'23. ZDX POC completed and no further comments. To be verified with Rajesh for closing the action. 19/04: Have checked with Suganya on the Jira for the 7 signals. 28/03: Suganya B updated that 7signals is a wireless network perfomance tool, currently team is working on it with a backlog - .While for ZDX, POC is done and team is working on it. 06/03: NOC team is working on a new solution for alerting during such central connectivity issue– Currently we have 2 tools existing (7signals and ZDX) NOC will try exploring ZDX tool for better monitoring. | Network | Tactical | NA | 2024-11-06 | Closed |  |  |  | Gokul | 2025-02-10 | 575 | >60 | June | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 89880759 | 2024-03-06 | Colleagues were unable to connect their Customer assets to internet due to a central network connectivity issue | Standard comms to be agreed when a large scale issue impacts honeywells and all other store apps during different times of the day | Business & IT Communication | Valliamai Ramasamy | 03/04: Valli shared the backlog RETAILSL-89 id. 19/03: Valli is working on it and will share a backlog as the document needs multiple approval after it is updated. 06/03: Valli will update the existing retail document (in the General teams channel) – with the right impact statements and the comms template based on the time of day, so that we can quickly get the store comms out during the such central issue. | Service Lead |  | NA | 2024-03-04 | Closed |  | RETAILSL-89 |  | Gokul | 2025-02-10 | 575 | >60 | April | 2024 | #VALUE!
GTS | Enterprise Technology Platform | 89880759 | 2024-03-06 | Colleagues were unable to connect their Customer assets to internet due to a central network connectivity issue | We should only have SME’s on call rotas – not just anyone to act as a placeholder on the rota, on call person should be experienced with the right knowledge to give the right impact statement | Impact analysis | All | It was agreed on the PIR call, to get the right SME’s on the MIM calls so that we can get the overall impacts consolidated and have the right communications addressed. | All |  | NA | 2024-06-03 | Closed | NA | NA | N/A | Gokul | 2025-02-10 | 575 | >60 | March | 2024 | #VALUE!
GTS | Operations | 89880759 | 2024-03-06 | Colleagues were unable to connect their Customer assets to internet due to a central network connectivity issue | There was challenge in collating the impact during the issue. Create a central outage run book based on major incidents, platforms/portfolio wise – with Impacts consolidated and with a basic template on wider comms. | Issue handling/Management | Gokul/MIM | 27/08 - AIM Tool has the impact assessment for all applications across various periods and product teams are updating it regularly. Product teams are working on various preventive actions including run books based on the major incidents. Basic D&T templates are available for the business comms and are being utilized whenever appropriate. 11/05 - File is ready and internal discussion needs to be done. 07/05 - We have the AIM tool which has the detailed impacts, however for the central issues. I am working to create a file with impacts for last 6 months MI 22/04: Dinesh is working on it 19/04: Internally team is discussing on it 03/04: Team is working on it 06/03: MIM will create a centralized document with the default impacts listed for each critical services as and then a MI occurs. Note: This document will be based out of MIM handled Major incidents and will be updated on a regular interval. | SIAM | Tactical | NA | 27/08/24 | Closed |  |  |  | Gokul | 2025-02-10 | 575 | >60 | August | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 89880759 | 2024-03-06 | Colleagues were unable to connect their Customer assets to internet due to a central network connectivity issue | As per offline discussion, in the event of any Honeywell outages - We have an impact to Customer Bank which was unknown. | Business & IT Communication | Valliamai Ramasamy | 03/04: IM process is agreed and the Valli has shared the document with SD 25/03: Currently in the Customer business and store comms, Customer bank(MSB) DL has been included, in case of the MSB incidents and changes Customer needs to be included. Overall IM process is being setup. 14/03: There was a call on 13th with Customer bank on this issue, but no updates on ownership from Customer yet. There is a PIR scheduled today for another incident 89895108. 06/03: Currently we do not have a stabilized process w.r.t. Customer bank services. However, Customer bank service is a regulated area for financial crime and anti-money laundering thus during any service interruption, we are required to notify Customer Bank IT incident team. – An official process yet to be concluded | Service Lead |  | NA | 2024-03-04 | Closed |  |  |  | Gokul | 2025-02-10 | 575 | >60 | April | 2024 | #VALUE!
GTS | Digital Workplace Services | 89880759 | 2024-03-06 | Colleagues were unable to connect their Customer assets to internet due to a central network connectivity issue | Review the External DNS forwarding configurations in Customer network | Problem avoidance | Muthunagappan Subramaniam | 19/03: Farid updated that "this will remain as is for now as its not causing any issues. We will revisit if and when we move services to the cloud that have to use the ADROOT DNS, and also need to break out to the internet. Even then the zones will primarily run from Infoblox and not the Windows DNS servers and also we are tracking it as part of SP exit work and DNS consolidation and redesign work with network team" 11/03: AD team to review the forwarder configuration for the cloud hosted ADROOT domain controllers. 06/03: As per NOC, ideally external DNS should not be resolving internally between SP and SW rather it should reach the external Azure DNS. AD team to revisit the design architecture of the DNS forwarding process. | Active Directory |  | NA | 19/03/24 | Closed |  |  |  | Gokul | 2025-02-10 | 575 | >60 | March | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89880759 | 2024-03-06 | Colleagues were unable to connect their Customer assets to internet due to a central network connectivity issue | Review the MIM engaging process and the escalation Matrix of Fortigate | Business & IT Communication | NOC | 22/03: NOC team has the escalation matrix for the Fortigate and is available with NOC team and will be shared with MIM team for reference. 06/03: As there was a challenge in getting Vendor Fortigate on the MIM bridge we will have a process agreed to get them on the bridge and Noc should have their escalation Matrix handy | Network |  | NA | 22/03/24 | Closed |  |  |  | Gokul | 2025-02-10 | 575 | >60 | March | 2024 | #VALUE!
Customer Channels | Selling Experience | 89843143 | 2024-03-01 | Sofa and Armchair PDPs showing a 503 error to customers | Discussion around whether the initial customer shouts should have been more fully investigated as this would have uncovered the fact that it was a wider issue, not just specific to one sofa. Elaine to discuss with the business operations team. | Solution & Recovery | Elaine Hawthorn | 11/04: Service lead had a discussion with the business teams and it has been concluded that due to lack of resources over the weekend/oncall hours, they will not be able to carry out more in-depth investigations. Therefore, this is being closed. | Selling Experience |  | NA | 2024-11-04 | Closed |  |  |  | Saloni | 2025-02-10 | 580 | >60 | April | 2024 | #VALUE!
Customer Channels | Selling Experience | 89843143 | 2024-03-01 | Sofa and Armchair PDPs showing a 503 error to customers | Agreed that there should have been wider knowledge about the issues faced with MTM curtains and that this sort of issue should be posted in the Tech Ops Teams channel | Business & IT Communication | Elaine Hawthorn | This has been agreed | Selling Experience |  | NA | 2024-01-03 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 580 | >60 | March | 2024 | #VALUE!
Customer Channels | Selling Experience | 89843143 | 2024-03-01 | Sofa and Armchair PDPs showing a 503 error to customers | The traffic was very low on the Sofa and Armchair pages which meant that the warningthreshold for 503 alerts did not trigger. The threshold was set to 50 and the actual count of errors was 35. The threshold has already been changed to a lower number (30). A new alert has been introduced to highlight when pods are not running. If 3 or more pods are in a pending (i.e. non-running ) state the alert will trigger. | Problem identification & Alerting | Elaine Hawthorn | The alerts have been configured. | Selling Experience |  | NA | 2024-01-03 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 580 | >60 | March | 2024 | #VALUE!
GTS | Enterprise Integration | 89858563 | 2024-03-01 | Multiple foods UPC lines deactivated in SAP causing stock loss in store | What caused the movement of 1 UPC to C&H assortment from Foods in Enterprise Services resulting in £40K stock loss. | Root cause | Sivasubramani Pappusamy | 20/08: MS team have enabled the SSL checks across all the server connection middleware channels. 15/07: Siva has confirmed that there is a certificate renewal activity on 2nd week of August, they are planning to club the JKS checkpoint change with the activity. ETA: 16th August and will be performed by Middleware admin team 25/06: The changes can only be implemented once Donington has attained stability. There are multiple critical changes being deployed to the DC, however, this one being least critical will be deployed once the issue is resolved. 14/06: As the Donington incident is still ongoing, we might need to identify a suitable window to implement thi change. 13/05: The change is ready to be deployed into production, however, due to ongoing CD MI, all changes are held until the issue is resolved. 22/04: There were some issues after changing the properties, Siva is working with admin team. Will target May 1st for Prod 15/04: The JKScheckpoint has been enabled for all Queue managers. However, it needs a parameter change to reflect and it needs to be enabled for one QM one at a time. Due to ongoing SP exit program, the DS team will liaise with middleware admin team to plan the day of deployment. 27/03: From the audit logs, it was identified that the impacted UPC was posted on the year 2023 and it looks like there has been a manual amendment of this UPC on 19/02//2024 which is not ideal. However, due to insufficient logs, the details around the manual amendment could not be identified. To identify these issues, a checkpoint is being tested in the integration environment which will capture the details if there are any manual amendments made on an existing UPC. Once this is tested successfully, the change will be deployed into production. 15/03: From the initial investigation, it seems like there was some manual posting performed which caused the issue. However, further analysis is being performed to avoid the scenario in future. Teams are investigating the log file. There is no change in SAP, it was sent with Foods assortment on 19/02, however, it was moved to C&H in ES, teams are investigating further. | ES support | Strategic | NA | 20/08/24 | Closed |  |  |  | Saloni | 2025-02-10 | 580 | >60 | August | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 89858563 | 2024-03-01 | Multiple foods UPC lines deactivated in SAP causing stock loss in store | Review the alerting mechanism in CSSM and apply thresholds to engage MIM during a major incident. | Problem identification & Alerting | Bharath Murugan | There is an existing alert in CSSM which we received on 21st, 22nd and 23rd. The usual process is to validate in SAP to confirm if they are genuine deactivations | CSSM DevOps |  | NA | 27/02/24 | Closed |  |  |  | Saloni | 2025-02-10 | 580 | >60 | February | 2024 | #VALUE!
Business Process Services | Business Process Services | 89858563 | 2024-03-01 | Multiple foods UPC lines deactivated in SAP causing stock loss in store | Review the deactivation process at business whether the relevant stock/ booked stocks are validated before requesting the deactivation. | Permanent Fix | Samantha Welsh | 31/07: A follow up was done with Samantha Welsh again, as this is a strategic and long term action to agree on a systemic process to perform product deactivation, therefore, will be tracked under a backlog - BPSFOOD1. 15/07: We have now spoken to Joey as an escalation and await further updates from him 08/07: Sam has confirmed that there isa meeting scheduled with the stakeholder on 11th July and we await further updates 25/06: Saloni has followed up with Sam for a backlog id in JIRA to close this action. ETA to provide a backlog id is 30th June 17/06: Saloni has requested Sam to create a backlog id for this action as we have manual checks in place during deactivation/activation process. 29/05/: Sam mentioned that the process is awaiting fund approval and she does not have an ETA. Agreed with her to follow up on 05/06 for an ETA 13/05: Sam has confirmed that as Nat Skinner has left Customer, it took some time to create the working group. The working group has been created and the process is being developed, as this is a strategic action to avoid recurrence in future, PM has been advised to keep the ETA as end of this month. 22/04: Phase change documentation for day parting - this action is depending on the parting changes. 11/04: It is still in progress, working group has been set up by Sam with the business stakeholders to finalise what needs to be done. ETA: 30/04. 15/03: Sam is working with the business teams to set up a working group to improve the deactivation process. | Centralised Ops Trading | Strategic | NA | 31/07/24 | Closed |  | BPSFOOD1 |  | Saloni | 2025-02-10 | 580 | >60 | July | 2024 | #VALUE!
Business Process Services | Business Process Services | 89858563 | 2024-03-01 | Multiple foods UPC lines deactivated in SAP causing stock loss in store | Implement a validation step to confirm the successful reactivation of the UPCs through the extract from FMD and SAP. | Problem avoidance | Prabhuraj Krishnan | 15/03: A report will be generated from SAP for all the deactivation/activation email, and it will undergo a quality check by the senior SME in the team to ensure the request is actioned accordingly before sending a confirmation email to the relevant request owner. | Centralised Ops Trading |  | NA | 15/03/24 | Closed |  |  |  | Saloni | 2025-02-10 | 580 | >60 | March | 2024 | #VALUE!
Business Process Services | Business Process Services | 89858563 | 2024-03-01 | Multiple foods UPC lines deactivated in SAP causing stock loss in store | Upon bulk reactivation of the impacted 75 UPCs, only 36 UPCs had interfaced into CSSM, remaining were not reactivated properly. What caused the issue? How can we improve the reactivation process to reflect correctly in SAP? | Root cause | Prabhuraj Krishnan/ Karthikeyan Mariappan | 27/03: SAP teams had replicated the issue by deactivating/reactivation 80UPCs via a bulk upload and no issues were identified, therefore, the root cause remains UNKNONW. Therefore, it has been agreed with Central Ops team to engage SAP during future bulk deactivation/reactivation to identify the issue (if any). 15/03: Tech teams have tested with 15 UPCs in the lower environment and could not see any issues. However, the plan is to replicate the scenario with bulk deactivation/reactivation of 75 UPCs to identify any issues in the flow. Galileo and SAP teams are jointly investigating. | Centralised Ops Trading/ SAP |  | NA | 27/03/24 | Closed |  |  |  | Saloni | 2025-02-10 | 580 | >60 | March | 2024 | #VALUE!
Business Process Services | Business Process Services | 89858563 | 2024-03-01 | Multiple foods UPC lines deactivated in SAP causing stock loss in store | On 21/02, Galileo team had deactivated 75 UPCs incorrectly for both Ordering & estimation, however, business had requested only for ordering deactivation. Identify options to improve the deactivation process to eradicate manual intervention | Problem avoidance | Prabhuraj Krishnan | 15/03: A report will be generated from SAP for all the deactivation/activation email, and it will undergo a quality check by the senior SME in the team to ensure the request is actioned accordingly before sending a confirmation email to the relevant request owner. Galileo team to look at the feasibility of improving the deactivation process - Peer review to be done by SMEs etc. | Centralised Ops Trading |  | NA | 15/03/24 | Closed |  |  |  | Saloni | 2025-02-10 | 580 | >60 | March | 2024 | #VALUE!
Customer Channels | Customer Engagement | 89874461 | 2024-03-01 | Customer Website not available and no orders placed UK, IE, International | RCA and recommendations for improvement and making the process more robust. | Root cause | IP Twins | Completed 05/03 - The issue was caused by a DNS change made using IP Twins portal and they have investigated and shared the root cause and preventative measures. The issue was caused by a page refresh on the browser resulting in a partial zone file to be updated | IP Twins |  | NA | 2024-05-03 | Closed |  |  |  | Saloni | 2025-02-10 | 580 | >60 | March | 2024 | #VALUE!
GTS | Enterprise Technology Platform | 89874461 | 2024-03-01 | Customer Website not available and no orders placed UK, IE, International | Training of the IP Twins portal and necessary documentation to be provided to the Customer team | Solution & Recovery | Kamal Kanniappan | 15/05: Venkat is now part of the NOC team and is taking up IP Twins work - he is being trained as required. | IP Twins |  | NA | 15/05/24 | Closed |  |  |  | Saloni | 2025-02-10 | 580 | >60 | May | 2024 | #VALUE!
GTS | Enterprise Technology Platform | 89874461 | 2024-03-01 | Customer Website not available and no orders placed UK, IE, International | Review of DNS changes, implementation – Testing, Validation, Reversion etc. As in this case there was no validation of the change and there was no reversion plan for issues impacting large number of records. | Solution & Recovery | Kamal Kanniappan | Update 01/05: The DNS service has now been handed over to the Network portfolio. There is an additional governeance layer to review any DNS changes or modifactions Still awaiting ownership – Jane has confirmed this will sit with Network (previously GSOC) but Ian Kirk needs to assign the team. Sathish is helping with this and once we have owners then they will tell us how long they need to deliver these actions. | IP Twins |  | NA | 2024-01-05 | Closed |  |  |  | Saloni | 2025-02-10 | 580 | >60 | May | 2024 | #VALUE!
Customer Channels | Customer Engagement | 89874461 | 2024-03-01 | Customer Website not available and no orders placed UK, IE, International | Emergency Contact and Escalation process for IP Twins This is needed as currently Customer only have standard support numbers. | Solution & Recovery | IP Twins / Customer | Completed – OOO Escalation number provided by IPT and Customer number whitelisted | IP Twins / Customer |  | NA | 2024-12-03 | Closed |  |  |  | Saloni | 2025-02-10 | 580 | >60 | March | 2024 | #VALUE!
Customer Channels | Customer Engagement | 89874461 | 2024-03-01 | Customer Website not available and no orders placed UK, IE, International | Review Incident engagement process for Customer Bank Bank were doing their own investigation in parallel, and it took a very long time to understand that common issue was impacting both sides. | Solution & Recovery | Priya / Dan (Bank) | 01/05: Priya Sahu advises that a common process has been created with agreed contacts. This process will be shared with all MIM's. | Customer Bank |  | NA | 2024-01-05 | Closed |  |  |  | Saloni | 2025-02-10 | 580 | >60 | May | 2024 | #VALUE!
Customer Channels | Customer Engagement | 89874461 | 2024-03-01 | Customer Website not available and no orders placed UK, IE, International | Review change communication process with Customer Bank | Business & IT Communication | Priya / Siu Mak (Bank) | Priya & Alan have a weekly cadence to discuss any upcoming changes from MSB & MSR. This process enables to bring more transparency, business visibility (& sign-off as required) and comms aligned. | Customer Bank |  | NA | 2024-12-03 | Closed |  |  |  | Saloni | 2025-02-10 | 580 | >60 | March | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89874461 | 2024-03-01 | Customer Website not available and no orders placed UK, IE, International | Ownership of DNS changes and IP Twins Portal, change approval and communication process | Solution & Recovery | Kamal Kanniappan | Update 01/05: The DNS service has now been handed over to the Network portfolio. There is an additional governeance layer to review any DNS changes or modifactions. One engineer was doing the changes and he has been taken under the Network Portfolio Still awaiting ownership – Jane has confirmed this will sit with Network (previously GSOC) but Ian Kirk needs to assign the team. Sathish is helping with this and once we have owners then they will tell us how long they need to deliver these actions. | Network |  | NA | 2024-01-05 | Closed |  |  |  | Saloni | 2025-02-10 | 580 | >60 | May | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89874461 | 2024-03-01 | Customer Website not available and no orders placed UK, IE, International | CMDB for DNS records. This will help identify the owners and understand the impact of any changes to a DNS a record. Not directly related to this incident but called out as a useful information to have. | Impact analysis | Kamal Kanniappan | 01/05: This will be reviewed under the new DDI strategy. Still awaiting ownership – Jane has confirmed this will sit with Network (previously GSOC) but Ian Kirk needs to assign the team. Sathish is helping with this and once we have owners then they will tell us how long they need to deliver these actions. | Network |  | NA | 2024-01-05 | Closed |  |  |  | Saloni | 2025-02-10 | 580 | >60 | May | 2024 | #VALUE!
Customer Channels | Customer Engagement | 89874461 | 2024-03-01 | Customer Website not available and no orders placed UK, IE, International | Review NR alerts and distribution lists for Customer Bank | Problem identification & Alerting | Sumitro / Siu Mak (Bank) | Completed – Customer Bank already get alerts from App Dynamics. DL for New Relic alerts has been updated to include Service Leads. | Customer Bank |  | NA | 2024-12-03 | Closed |  |  |  | Saloni | 2025-02-10 | 580 | >60 | March | 2024 | #VALUE!
Customer Channels | Customer Engagement | 89874461 | 2024-03-01 | Customer Website not available and no orders placed UK, IE, International | 5 preventative measures detailed in the Root Cause section | Problem avoidance | IP Twins | 10/06 - IP Twins confirmed that they have completed the last action. 03/06 - Rehan has sent IP Twins the following regarding task 5 below - I am tracking the completion of this in our problem tracker and need to provide an ETA (I know you have now prioritised this) – what date do you suggest please? Email alerts / record criticality We will implement email alerts sent to all Administrator and Technical users of the portfolio when a zone file update is performed and : - The zone file update covers more than 10 records at once, or - The zone file update covers records marked at critical on the zone file. We will implement a feature allowing to mark/unmark records as critical on the zone file of any domain name. 1/ Alert message on zone file edition (do not refresh) IP Twins have already implemented a message indicating “Caution : Do Not Refresh the Page” while the zone file update is being sent to our master name server.Completed 4/3 2/ Diff comparison with production IP Twins will update the zone edition process by comparing the production zone file and the updated zone file : if the change is greater than 10 records, a pop-up message will be brought, that will (i) alert of the change, (ii) display the requested change, (iii) allow to confirm change and push to production or cancel and revert to the production zone file. Completed 18/3 3/ Alert message on current edition by another user IP Twins will block zone file edition to any user if a user is already working on the zone file of the same domain name. Priority will be given to the user that was first on the zone file, and the second user will be displayed a “read-only” zone file with no modification capabilities. A message will indicate that update is being performed by another user. Completed 18/3 4/ Rollback to last stable version The current UI allows to obtain zone file history and roll back in bulk by duplicating the zone file history. IP Twins will implement a rollback button to ease the process. The rollback will be performed up to the last stable version, i.e. a version with a DNS serial number which was in place for over 24 hours. Completed 18/3 5/ Email alerts / record criticality We will implement email alerts sent to all Administrator and Technical users of the portfolio when a zone file update is performed and : - The zone file update covers more than 10 records at once, or - The zone file update covers records marked at critical on the zone file. We will implement a feature allowing to mark/unmark records as critical on the zone file of any domain name. Estimated change implementation: in progress - 18/05 This has now been confirmed as prioritised by IP Twins. | IP Twins | Strategic | NA | 2024-10-06 | Closed |  |  |  | Saloni | 2025-02-10 | 580 | >60 | June | 2024 | #VALUE!
Customer Channels | Customer Engagement | 89874461 | 2024-03-01 | Customer Website not available and no orders placed UK, IE, International | Revisit Incident Management Process due to change in portfolio boundaries | Solution & Recovery | Hisham / Steve Warren | 08/05: Steve Warren advises that this is being worked as part of the Project Evolution workstream, where we are looking at tactical changes to Incident Management / Service Management. This is starting with an external consultant looking at our maturity. | Service Management |  | NA | 2024-08-05 | Closed |  |  |  | Saloni | 2025-02-10 | 580 | >60 | May | 2024 | #VALUE!
Customer Channels | Customer Engagement | 89874461 | 2024-03-01 | Customer Website not available and no orders placed UK, IE, International | Review of Service Management Function | Solution & Recovery | Hisham / Steve Warren | 08/05: Steve Warren advises that this is being worked as part of the Project Evolution workstream, where we are looking at tactical changes to Incident Management / Service Management. This is starting with an external consultant looking at our maturity. | Service Management |  | NA | 2024-08-05 | Closed |  |  |  | Saloni | 2025-02-10 | 580 | >60 | May | 2024 | #VALUE!
Customer Channels | Customer Engagement | 89874461 | 2024-03-01 | Customer Website not available and no orders placed UK, IE, International | Explore options of DNS monitoring with either existing or new tools | Problem identification & Alerting | Sathish to liaise with Jane Gilmour regarding assigning owners for actions with missing owners. | Still awaiting ownership – Jane has confirmed this will sit with Network (previously GSOC) but Ian Kirk needs to assign the team. Sathish is helping with this and once we have owners then they will tell us how long they need to deliver these actions. | Sathish to liaise with Jane Gilmour regarding assigning owners for actions with missing owners. |  | NA | 2024-08-05 | Closed |  |  |  | Saloni | 2025-02-10 | 580 | >60 | May | 2024 | #VALUE!
Customer Channels | Selling Experience | 89870729 | 2024-03-01 | Customers unable to place orders on the kiosks at Digital Cafe stores | CS will work to allow ‘day part changes’ to be executed via a module to provide validation around this scenarios pre implementation. This will allow it to be tested in test env | Problem avoidance | Jordan/ Counter Solutions | 13/05: The changes have been implemented, product owner is happy with the configuration 22/04: Day part changes taken into CS April sprint, for delivery by 8th May 2024 at latest. 15/04: PM has reached out to Paul Dasan Cutting, he is checking his repository for further updates. 11/04: Laura is OOO, awaiting here response. In progress | Counter Solutions |  | NA | 13/05/24 | Closed |  |  |  | Saloni | 2025-02-10 | 580 | >60 | May | 2024 | #VALUE!
Customer Channels | Selling Experience | 89870729 | 2024-03-01 | Customers unable to place orders on the kiosks at Digital Cafe stores | Counter Solutions have refactored their POST deployment script and included it in our Phase change documentation to utilise this specific authorised script when performing day part changes. | Solution & Recovery | Jordan/ Counter Solutions | 13/05: The changes have been implemented, product owner is happy with the configuration 15/04: PM has reached out to Paul Dasan Cutting, he is checking his repository for further updates. 11/04: Laura is OOO, awaiting here response. In progress | Counter Solutions |  | NA | 13/05/24 | Closed |  |  |  | Saloni | 2025-02-10 | 580 | >60 | May | 2024 | #VALUE!
Infosec & Tech Risk | Infosec & Tech Risk | 89867645 | 2024-02-28 | Issues with C&H SFTP file transfers | Identify the owner of specific VM’s and notify them when a threat is detected to understand the impact and mitigate them | Problem avoidance | Jay Jay Davey | Instead of using product owner tag from VM, communicate to support team under the ‘support group tag’ going forward and loop in service owners and cloud platform team | Info Security |  | NA | 2024-01-03 | Closed |  |  |  | Saloni | 2025-02-10 | 582 | >60 | March | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89867645 | 2024-02-28 | Issues with C&H SFTP file transfers | Revise the product name, product owner, support group etc of the VM’s under C&H portfolio | Problem avoidance | Nirmal Poikaikumaran | 04/04: The action is complete 15/03: Team is planning to move the C&H applications individual VM's | TMS |  | NA | 2024-04-04 | Closed |  |  |  | Saloni | 2025-02-10 | 582 | >60 | April | 2024 | #VALUE!
GTS | ETP- Cloud operations / Frameworks | 89867645 | 2024-02-28 | Issues with C&H SFTP file transfers | Revise the product name, product owner, support group etc for the VM’s across all portfolios | Problem avoidance | Raguram Ramasamy | Agreed to initiate email communication will be initiated to notify the product teams to revise the details in VM of their respective portfolios | Cloud platform |  | NA | 28/02/24 | Closed |  |  |  | Saloni | 2025-02-10 | 582 | >60 | February | 2024 | #VALUE!
Infosec & Tech Risk | Infosec & Tech Risk | 89867645 | 2024-02-28 | Issues with C&H SFTP file transfers | Review the process document of MIM and GSOC engagement | Supplier and support involvement | Jamie Aston | The existing document has been shared with Jamie for review | Info Security |  | NA | 2024-01-03 | Closed |  |  |  | Saloni | 2025-02-10 | 582 | >60 | March | 2024 | #VALUE!
GTS | Operations | 89867645 | 2024-02-28 | Issues with C&H SFTP file transfers | CMDB for the cloud components to be made available with GSOC for reference | Solution & Recovery | CMDB team | This will be a new requirement as the existing CMDB is maintained only for on prem. Discussion are in progress for bring this scope in future | CMDB |  | NA | 2024-01-03 | Closed |  |  |  | Saloni | 2025-02-10 | 582 | >60 | March | 2024 | #VALUE!
GTS | ETP- Cloud operations / Frameworks | 89867645 | 2024-02-28 | Issues with C&H SFTP file transfers | Identify how the ‘ncrack’ was installed in the SFTP VM’s | Root cause | Emmanuel | The source of the ncrack tool couldn’t be identified based on the current logs all we can identify is it was available from 2017 since the VM was built | Cloud platform |  | NA | 2024-01-03 | Closed |  |  |  | Saloni | 2025-02-10 | 582 | >60 | March | 2024 | #VALUE!
GTS | ETP- Cloud operations / Frameworks | 89867645 | 2024-02-28 | Issues with C&H SFTP file transfers | Improve the recovery of the issue and engage respective stakeholders and MIM | Solution & Recovery | Emmanuel | An internal call was initiated to triage and the VM was restarted. Respective stakeholder and MIM was engaged later when it the was related to isolation of VMs by GSOC | Cloud platform |  | NA | 2024-01-03 | Closed |  |  |  | Saloni | 2025-02-10 | 582 | >60 | March | 2024 | #VALUE!
GTS | ETP- Cloud operations / Frameworks | 89867645 | 2024-02-28 | Issues with C&H SFTP file transfers | Liaise with Microsoft to understand if any notification can be enabled. | Problem identification & Alerting | Prashant Rowlo | 22/04: We cannot enable any notification as the VM;s will be in running status and we cannot configure notification 04/04: Case has been raised with Microsoft,awaiting further updates | Cloud platform |  | NA | 22/04/24 | Closed |  |  |  | Saloni | 2025-02-10 | 582 | >60 | April | 2024 | #VALUE!
GTS | Enterprise Integration | 89867645 | 2024-02-28 | Issues with C&H SFTP file transfers | Was there any alerting for message failures/pile ups in middleware as multiple SFTP transfer were impacted ? | Problem identification & Alerting | Sreeraj Cheriyil | 29/02: Since the SFTP VM itself was down, alerts related to message failure or pile ups were not triggered. However, there was an to platform team to notify the issue with the VM’s | MQFTE |  | NA | 2024-01-03 | Closed |  |  |  | Saloni | 2025-02-10 | 582 | >60 | March | 2024 | #VALUE!
GTS | Enterprise Integration | 89867645 | 2024-02-28 | Issues with C&H SFTP file transfers | The disaster recovery wasn’t seamless, how can it be improved? | Solution & Recovery | Kishore | 29/02: The DR is an active-active set up, since both active VM’s were down the failover wasn’t seamless and manual intervention was required. | MQFTE |  | NA | 2024-01-03 | Closed |  |  |  | Saloni | 2025-02-10 | 582 | >60 | March | 2024 | #VALUE!
GTS | Enterprise Integration | 89867645 | 2024-02-28 | Issues with C&H SFTP file transfers | Perform a planned SFTP DR for C&H portfolio | Solution & Recovery | Kishore | 04/04: The DR has been planned for current quarter. Awaiting back log details from the product team -INTSVCS-53919 29/02: Note: Not all the VM have DR set up | MQFTE |  | NA | 2024-08-05 | Closed |  | INTSVCS-53919 |  | Saloni | 2025-02-10 | 582 | >60 | May | 2024 | #VALUE!
Infosec & Tech Risk | Infosec & Tech Risk | 89867645 | 2024-02-28 | Issues with C&H SFTP file transfers | Update the escalation details in Contact repo and set up PagerDuty call for GSOC | Supplier and support involvement | Jamie Aston | 01/02: Pager duty schedule has been created 29/02: Escalation details will be updated in contact repo and until PagerDuty is set up Jamie Aston (Head of info sec) can reach out for any critical issues | Info Security |  | NA | 2024-01-03 | Closed |  |  |  | Saloni | 2025-02-10 | 582 | >60 | March | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89839262 | 2024-02-23 | Intermittent network connectivity issues were observed between Stockley and Swindon data centres | Work with VF to amend the CMDB database to ensure the relevant information is correct for reference during an incident. Create a diagram with NOC and VF with the appropriate information captured to refer during any incident. | Solution & Recovery | Rajesh Kumar Singrarajan | 13/05: NOC are receiving monthly CMDB database from VF, also embeded the circuit info in Solarwinds interfaces where connecting to different type of VF links. | Network |  | NA | 13/05/24 | Closed |  |  |  | Saloni | 2025-02-10 | 587 | >60 | May | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 89839262 | 2024-02-23 | Intermittent network connectivity issues were observed between Stockley and Swindon data centres | Is there a service design document for all the impacted applications | Solution & Recovery | Elizabeth Golder/Valliammai Ramasamy/ Nandakumar Sivalingam | The service design document should be within the produc team and this will be taken up as a project within a product. | Service Leads |  | NA | 2024-08-04 | Closed |  |  |  | Saloni | 2025-02-10 | 587 | >60 | April | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89839262 | 2024-02-23 | Intermittent network connectivity issues were observed between Stockley and Swindon data centres | Feasibility of restoring the resilience in a timelier manner. | Solution & Recovery | Kamalakkan Kanniappan | There were no obvious issues which could have pointed towards the issued component, also it involved VF – third party troubleshooting the link, therefore, it took time to restore the resilience | Network |  | NA | 15/03/24 | Closed |  |  |  | Saloni | 2025-02-10 | 587 | >60 | March | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89839262 | 2024-02-23 | Intermittent network connectivity issues were observed between Stockley and Swindon data centres | Create a network MAP towards the downstream LAN switches. | Solution & Recovery | Kamalakkan Kanniappan | 13/05: Kamal has reviewed the network map and therefore, this action can be closed This is currently in progress. | Network |  | NA | 13/05/24 | Closed |  |  |  | Saloni | 2025-02-10 | 587 | >60 | May | 2024 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89839262 | 2024-02-23 | Intermittent network connectivity issues were observed between Stockley and Swindon data centres | Feasibility of configuring an alert to identify any issues with the traffic through the DEA links before we start seeing the impact. | Problem identification & Alerting | Kamalakkan Kanniappan | 13/05: The network map has been created and alerts have been configured to proactively identify latency issues between the two DEA links and downstreams Once the network map is created (action 2), alerting will be configured to indicate any latencies between the connectivity of SP and SW DEA links and the downstream systems. | Network |  | NA | 13/05/24 | Closed |  |  |  | Saloni | 2025-02-10 | 587 | >60 | May | 2024 | #VALUE!
GTS | Enterprise Technology Platform | 89848633 | 2024-02-23 | Gift card page was unavailable to customers | Web-dns Repository managed DNS Zone need to be migrated to Brightcloud supported – MAPMonkey based solution, DNS zone to production subscription, associated pipelines for consumers to update | Solution & Recovery | Vidhya B | 01/05 - In progress - Vidhya advises thatthe activity hasnt started and its in a backlog - https://github.com/DigitalInnovation/cloud9-terraformers/issues/827 | Cloud Ops team |  | NA |  | Closed |  |  |  | Saloni | 2025-02-10 | 587 | >60 | January | 1900 | #VALUE!
GTS | Enterprise Technology Platform | 89848633 | 2024-02-23 | Gift card page was unavailable to customers | Documentation for the teams to mark new application entries into Web-DNS Repository. and Update the CODE Owners for PR merge to be updated. | Solution & Recovery | Vidhya B | 01/05 - Vidhya advises thatthe activity hasnt started and its in a backlog - https://github.com/DigitalInnovation/cloud9-terraformers/issues/827 | Cloud Ops team |  | NA | 2024-01-05 | Closed |  |  |  | Saloni | 2025-02-10 | 587 | >60 | May | 2024 | #VALUE!
GTS | Enterprise Technology Platform | 89848633 | 2024-02-23 | Gift card page was unavailable to customers | Action to create an automated way to recover removed DNS entries (like GitHub actions) | Solution & Recovery | Vidhya B | Completed | Cloud Ops team |  | NA | 15/02/24 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 587 | >60 | February | 2024 | #VALUE!
Customer Channels | Customer Engagement | 89848633 | 2024-02-23 | Gift card page was unavailable to customers | Identifying the number of customers impacted could not be determined during the incident. Action to create a standard process of collecting customer impact with given time (part of runbook, available in confluence) | Impact analysis | Ram M | 12/05: Alerting has been configured in Newrelic Priya Sahu to check with Ram Meena to see if a systemic solution can be put in place to get abetter impact assessment. | Gift card |  | NA | 2024-09-05 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 587 | >60 | May | 2024 | #VALUE!
Customer Channels | Customer Engagement | 89848633 | 2024-02-23 | Gift card page was unavailable to customers | Add an alert for any active service’s availability status (before hitting to application services, it would check for origin/network layer) | Problem identification & Alerting | Ramesh A | The alert has been configured | Gift card |  | NA | 15/02/24 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 587 | >60 | February | 2024 | #VALUE!
Customer Channels | Service Experience | 89854118 | 2024-02-22 | Customers were receiving an error while accessing order history, returns and account settings pages across platforms. | Set-up a New alert configuration for checking Apdex score condition dropping to 0 | Problem identification & Alerting | .com - Fulfilment Team | A New set-up for alerting has been configured | Service experience - Fulfilment red Team |  | NA | 26/02/24 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 588 | >60 | February | 2024 | #VALUE!
Customer Channels | Service Experience | 89854118 | 2024-02-22 | Customers were receiving an error while accessing order history, returns and account settings pages across platforms. | Adding an additional alert with customer transactional failure rates to indicate on service availability | Problem identification & Alerting | .com - Fulfilment Team | An Additoinal alert has been added to notity on service availability | Service experience - Fulfilment red Team |  | NA | 26/02/24 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 588 | >60 | February | 2024 | #VALUE!
Customer Channels | Service Experience | 89854118 | 2024-02-22 | Customers were receiving an error while accessing order history, returns and account settings pages across platforms. | Action to review PagerDuty setup for Orders & Returns team name, escalation policy (including older team – feskmyaccount) | Issue handling/Management | Prem G | 13/03 - PD and the escalation policy has been reviewd and is set-up accordingly | Service experience - Fulfilment Team |  | NA | 13/03/24 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 588 | >60 | March | 2024 | #VALUE!
Customer Channels | Service Experience | 89854118 | 2024-02-22 | Customers were receiving an error while accessing order history, returns and account settings pages across platforms. | Action to find cause and fix forward of application container restarts increased trend since 11th Feb | Solution & Recovery | Prem G | 13/03 - The cause and the fix has been identified and the fix has been put in place | Service experience - Fulfilment Team |  | NA | 13/03/24 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 588 | >60 | March | 2024 | #VALUE!
Customer Channels | Service Experience | 89854118 | 2024-02-22 | Customers were receiving an error while accessing order history, returns and account settings pages across platforms. | Action to review and replace personal token with generic account credentials | Permanent Fix | Sabareesh | 13/03- Access token has been created using the Y-Account | Service experience - Fulfilment Team |  | NA | 13/03/24 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 588 | >60 | March | 2024 | #VALUE!
Customer Channels | Service Experience | 89854118 | 2024-02-22 | Customers were receiving an error while accessing order history, returns and account settings pages across platforms. | Action to separate code repo for individual application/service | Problem avoidance | Maryam | 13/03- Create a Single repository containing multiple page applications. - Since it is a long term plan - Tech backlog Jira has been created for further tracking | Service experience - Fulfilment Team |  | NA | 13/03/24 | Closed | NA | ACNT-307 | NA | Saloni | 2025-02-10 | 588 | >60 | March | 2024 | #VALUE!
Customer Channels | Service Experience | 89854118 | 2024-02-22 | Customers were receiving an error while accessing order history, returns and account settings pages across platforms. | Action to remove hardcoded value and make it more generic via Github actions | Solution & Recovery | Sabareesh | 13/03 hardcoded value has been removed to avoid security issues | Service experience - Fulfilment Team |  | NA | 13/03/24 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 588 | >60 | March | 2024 | #VALUE!
Customer Channels | Service Experience | 89854118 | 2024-02-22 | Customers were receiving an error while accessing order history, returns and account settings pages across platforms. | Wider scan on any personal token usage on Azure and highlight those code repos with automated reporting | Problem avoidance | Aravind R | 09/05 - This will further tracked via a backlog - https://jira.marksandspencer.app/browse/FULRE-2847 23/04 - Im yet to get a Backlog ID from the action owner 27/03 - To get the wider scan on the all the personal space it a difficult process. Teams will work internally via a JIRA story on alternative options to have this accompolised. Jbacklog ID is yet to be provided. | Service experience - Fulfilment Team |  | NA | 2024-09-05 | Closed | NA | https://jira.marksandspencer.app/browse/FULRE-2847 | NA | Saloni | 2025-02-10 | 588 | >60 | May | 2024 | #VALUE!
Digital & Data | Digital & Data | 89846290 | 2024-02-20 | Issue in EDW prod vs DR database replication impacting critical reports | Review the business comms sent during the issue. | Business & IT Communication | Timothy Barrett | No issues in the comms process, the required user community were kept updated on time. | Data Ops |  | NA | 22/02/24 | Closed |  |  |  | Saloni | 2025-02-10 | 590 | >60 | February | 2024 | #VALUE!
GTS | Enterprise Technology Platform | 89846290 | 2024-02-20 | Issue in EDW prod vs DR database replication impacting critical reports | Review the alerting on the Q replication process for proactive issue identification | Problem identification & Alerting | Saravanan Sundaram Chennakesavan | There are enough alerting mechanism configured between prod and DR databases to identify issues proactively | Database |  | NA | 22/02/24 | Closed |  |  |  | Saloni | 2025-02-10 | 590 | >60 | February | 2024 | #VALUE!
Digital & Data | Digital & Data | 89846290 | 2024-02-20 | Issue in EDW prod vs DR database replication impacting critical reports | Review the critical reports – Power BI, EDW etc which will require attention during these issues. Create a SOP for effective impact mitigation | Impact analysis | Timothy Barrett | We have the list of critical user managed reports which could get impacted during the issue. There is a plan to create a Confluence page and keep it updated as and when the issue recurs. Need the confluence link. 22/04: Asked Tim to provide the Confluence link. | Data Ops |  | NA | 22/04/24 | Closed |  |  |  | Saloni | 2025-02-10 | 590 | >60 | April | 2024 | #VALUE!
GTS | Enterprise Technology Platform | 89846290 | 2024-02-20 | Issue in EDW prod vs DR database replication impacting critical reports | Enable the variable logging mechanism suggested by IBM to capture appropriate logs if the issue occurs again for effective root cause analysis. | Root cause | Saravanan Sundaram Chennakesavan | The database and reporting teams will agree on an appropriate window to enable this logging mechanism and analyse the logs captured, provided there is no performance issues observed. 22/04: Variable logginf mechanism was enabled and team identified a specific table with replication issues. Therefore, the replication was disabled on this particular table which fixed the overall replication issue. | Database |  | NA | 22/04/24 | Closed |  |  |  | Saloni | 2025-02-10 | 590 | >60 | April | 2024 | #VALUE!
Group Platforms | Finance | 89843461 | 2024-02-15 | SAP POSDTA application unavailable | Root cause of the issue. | Root cause | Remko Smit | 04/04: SAP confirmed the root cause as "A network glitch in the hosted environment which led to instability to the POSDTA application - necessitating a restart of the hosts on that day (all within the hosted stack, so in SAP control). " 03/04: We have now received a new RCA as being related to a hyper scalar hosting issue rather than a data spike causing performance issues. We have a session with SAP vendor on 4th April to go through details. 25/03: SAP vendor is working internally on this and a call will be scheduled between Customer and SAP SME on the root cause 19/03: Ben (Head of Technology) has escalated this 11/03: SAP vendor has provided a partial answer. So, Remko has asked for more clarity from them. 05/03: SAP vendor updated that they are checking with their outage team internally on this 28/02: Remko updated that the vendor SAP updated that the POSDTA system was overloaded and that is why the issue happened. However, according to our analysis the number of messages and the workload of the system were comparable to other days - so we are going to ask for clarification. 15/02: We await root cause and resolution details from vendor SAP. | Service Lead |  | NA | 2024-04-04 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 595 | >60 | April | 2024 | #VALUE!
Group Platforms | Finance | 89843461 | 2024-02-15 | SAP POSDTA application unavailable | Is there a resilience or failover option for SAP POSDTA during a major outage? | Solution & Recovery | Gopi Kishan | 19/03: Ben has asked for a backlog to be created with Gopi. 13/03: Ben Dewitt updated that we can ask for a free DR test every year from SAP and it will be planned by late Q1 or in Q2. Awaiting further details. 06/03: Followed up with Gopi for the updates on contract with SAP for SAP POSDTA with VMO 23/02: Gopi responded with the details and we are working with Service Continuity team on the contract for SAP vendor on the SAAS with VMO 22/02: Checked with Gopi and understood that there is DR, but not tested since setting up POSDTA. Hence have asked 1.Is the SAP POSDTA DR hosted internally within Customer or by vendor SAP? 2.During what scenarios, would the DR be invoked ? 3.Is there a SOP detailing all the pre-requisites and the necessary actions to invoke the DR ? 4.How confident are we with the DR environment stability during an Emergency outage at SAP ? if not, when can we plan the DR Test. 15/02: In progress. | Product Manager |  | NA | 20/03/24 | Closed | NA | SPM-23633 | Open | Saloni | 2025-02-10 | 595 | >60 | March | 2024 | #VALUE!
Group Platforms | Finance | 89843461 | 2024-02-15 | SAP POSDTA application unavailable | What caused the overnight GMOR batches to miss their target completion times? | Problem avoidance | Rhammya Somassoudirame | 22/02: Job dependency has been added now to avoid the parallel run of the Ecom extractor. 15/02: There was a parallel job execution in GMOR which was utilizing the same table, however, performing different operations. This caused data corruption in GMOR resulting in the batch delay. Therefore, a job dependency had been added to avoid the parallel run of the Ecom extractor. | SAP BW |  | NA | 22/02/24 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 595 | >60 | February | 2024 | #VALUE!
Group Platforms | Finance | 89843461 | 2024-02-15 | SAP POSDTA application unavailable | There was a challenge in engaging the SME from GMOR during the incident, how can we ensure required SME support are available during out of business hours | Problem avoidance | Rhammya Somassoudirame | 22/02: SOP is ready and there is a review call today and will be published on 23/02. 15/02: Team has created SOP to follow and understand the impact and make decision. | SAP BW |  | NA | 23/02/24 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 595 | >60 | February | 2024 | #VALUE!
Group Platforms | Finance | 89843461 | 2024-02-15 | SAP POSDTA application unavailable | Perform an overall review of the GMOR jobs if any other job dependencies should be created to avoid any further data corruption. | Problem avoidance | Rhammya Somassoudirame | 27/02: The action is complete 22/02: Parallel jobs checking are on track and expected to be completed tomorrow | SAP BW |  | NA | 27/02/24 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 595 | >60 | February | 2024 | #VALUE!
C&H and Intl | C&H commercial Trading | 89833987 | 2024-02-13 | CSSM reference job failure impacting RFID counting in stores | The scenario causing the issue was that two duplicates were created in STIBO and this cannot currently be handled by CSSM. Wasim to propose a solution | Problem avoidance | Wasim Qureshi | 05/03: backlog CHBS-1224 28/02: vendor STIBO team is working on a fix. Guna will share the backlog 24/02: Followed up with Guna 20/02: Wasim has included Gunasekaran K on the fix related updates 13/02: A Fix needs to be developed | Product Manager |  | NA | 2024-05-03 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 597 | >60 | March | 2024 | #VALUE!
C&H and Intl | C&H commercial Trading | 89833987 | 2024-02-13 | CSSM reference job failure impacting RFID counting in stores | Measure the number of failures from the various sources promotion setup (GM central support) PLM, Range Planner dept, Stibo – last 3 months Dec Jan | Problem avoidance | Rohith Ravindran | 03/04: George confirmed that it has been monitored for a week now and this can be closed. 28/03: Fix deplyed in prod by STIBO for color and stroke validation on 21st, which will not allow any color stroke duplicates. This will be monitored by PDX support. 25/03: Have scheduled a call with Guna, Ashok and George by 28th 02/03: RP - Ashok updated that still discussion is ongoing, if the STIBO fix will help RP as well STIBO - ETA as 25th March for a fix, Ashok will check on the backlog 29/02: It was agreed that the upstreams need to fix the issue rather than SAP. Below are the POCs PLM - Ashok confirmed that it will not reoccur mostly RP - Valli will discuss with Ashok and update STIBO - ETA as 25th March for a fix, Ashok may have the backlog 28/02: Scheduled a call with SAP and CSSM on 29th Feb to discuss with the data obtained for last 3 months 24/02: Checked with Rohit on the status of the action 13/02 - Follow up to discuss – what solutions need to be created for the other sources. Stats are needed | C&H CSSM |  | NA | 2024-03-04 | Closed |  |  |  | Saloni | 2025-02-10 | 597 | >60 | April | 2024 | #VALUE!
C&H and Intl | C&H commercial Trading | 89833987 | 2024-02-13 | CSSM reference job failure impacting RFID counting in stores | Review overall workaround process to make it more seamless and less reliant on emails – communication process to be reviewed – especially overnight | Solution & Recovery | Wasim Qureshi | 03/04: George confirmed that it has been monitored for a week now and this can be closed. 28/03: Fix deployed in prod by STIBO for color and stroke validation on 21st, which will not allow any color stroke duplicates. This will be monitored by PDX support. 25/03: Have scheduled a call with Guna, Ashok and George by 28th 12/03: There is a call on 15th with Brands business to understand the existing process and agree on a SOP. 06/03: Guna has shared the problem record 67178 and have scheduled a call by 12th to discuss on it. 28/02: Currently there is a dependancy on business to mitigate the duplicates, Guna is checking further on this 24/02: Followed up with Guna 20/02: Wasim has included Gunasekaran K on the fix related updates | Product Manager |  | NA | 2024-03-04 | Closed |  |  |  | Saloni | 2025-02-10 | 597 | >60 | April | 2024 | #VALUE!
C&H and Intl | C&H commercial Trading | 89833987 | 2024-02-13 | CSSM reference job failure impacting RFID counting in stores | C&H restructure activities. will now include CSSM team as part of post checks | Problem avoidance | Ashok Gunasekaran | 19/02 - Ashok confirmed that CSSM will be involved for the post checks | Service Lead |  | NA | 19/02/24 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 597 | >60 | February | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 89822495 | 2024-02-08 | Store colleagues are unable to launch ECS application via Single sign-On | Document how ECS application single sign on works | Solution & Recovery | Natarajan Ravichandran, Vikram/ Mark | 02/05 - As this is a long term aciton - Teams will work on it internally via a backlog - EP-1755 23/04 - VIkram continues to work on the documentation. 10/04 - ECS team has got the right access from AD via SFAP request to start working on the documentation. Vikram and team will work on it in the upcoming weeks. Approx ETA - 20th April 09/03 - Vikarm is yet to get the Design diagram on the functionality 13/02 - Team has requested for a 2 weeks time to get this action addressed. Next follow-up will be on 20/02. | ECS team |  | NA | 2024-02-05 | Closed | NA | EP-1755 | Open | Saloni | 2025-02-10 | 602 | >60 | May | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 89822495 | 2024-02-08 | Store colleagues are unable to launch ECS application via Single sign-On | Understand if there is any additional validation that can be performed from SAL and document the same | Solution & Recovery | Dhilip Kumar | 19/02 - Relevant documents have been updated and is uploaded in the sharepoint for future references. 15/02 - All the validation steps | Stores Infra |  | NA | 19/02/24 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 602 | >60 | February | 2024 | #VALUE!
GTS | Operations | 89822495 | 2024-02-08 | Store colleagues are unable to launch ECS application via Single sign-On | Identify the enterprise-wide architect | Issue handling/Management | Rehan Siddiqui | 11/04 : Rehan spoke with Saurab Sengupta who advised that as sso is a Microsoft product, then WPT should own this and he suggested that Rehan speak with Promode. 13/02 - As there was lack of ownership on this incident, Rehan from MIM will check with the respective leadership teams on the right approach to identify the correct architect, who can give us the exact architecture of the application with SSO. | MIM |  | NA | 2024-02-05 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 602 | >60 | May | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 89822495 | 2024-02-08 | Store colleagues are unable to launch ECS application via Single sign-On | Collaborate with application, Stores infra, Active directory and Network and document whole architecture of how the single sign on works. | Solution & Recovery | ECS Team | 02/05 - As this is a long term aciton - Teams will work on it internally via a backlog - EP-1755 13/02 - Once we have identified the right architect (as per the above action) we will further follow-up to get the Whole Architecture diagram to understand how SSO works in ECS | TBC |  | NA | 2024-02-05 | Closed | NA | EP-1755 | N/A | Saloni | 2025-02-10 | 602 | >60 | May | 2024 | #VALUE!
GTS | Digital Workplace Services | 89822495 | 2024-02-08 | Store colleagues are unable to launch ECS application via Single sign-On | Summarize the findings of the AD investigations | Root cause | Muthunagappan Subramaniam | 13/02 - All the possible logs have been validated from the AD end, but no abnormalities observed. Active directory team has concluded that it is not an AD specific issue based on their validations. | Active Directory |  | NA | 22/02/24 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 602 | >60 | February | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 89824383 | 2024-02-06 | Store colleagues reporting blank ECS pricing tickets | What was the root cause of the issue | Root cause | Mark Charlwood | Detailed discussions with Mark Charlwood, product owner of the ticketing solution revealed that style override function is cumbersome to use and prone to the user making errors. Work done to make changes to the style override for the deposit return scheme at the time of the issue could have led to the corruption of ECS data. It has been agreed that the issue cannot be replicated, and it is highly unlikely that the root cause for this issue will be found. | Product Owner |  | NA | 2024-06-02 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 604 | >60 | February | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 89824383 | 2024-02-06 | Store colleagues reporting blank ECS pricing tickets | Can changes to the style override be first carried out in a test environment? | Problem avoidance | Mark Charlwood | Update 12/04 - Closed with a low priority backlog in JIRA - https://jira.marksandspencer.app/browse/EP-1836 Currently production and test environments are not in synch and therefore not in a suitable position for testing in a dev environment first. Mark Charlwood has agreed to work with the product team to ensure the test environment matches production and is fit for purpose so we can avoid make live changes in production. | Product Owner |  | NA | 2024-12-04 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 604 | >60 | April | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 89824383 | 2024-02-06 | Store colleagues reporting blank ECS pricing tickets | Improvements need to be made to improve the complexity of the style override function and Mark Charlwood will take this forward outside of the PIR as this is a longer-term action. | Problem avoidance | Mark Charlwood | To be managed outside this PIR. Action 2 suffices to ensure the incident is avoided in future | Product Owner |  | NA | 2024-06-02 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 604 | >60 | February | 2024 | #VALUE!
GTS | Enterprise Technology Platform | 89814764 | 2024-02-05 | Merchandise Planning (MP) application was inaccessible | Ascertain whether the host name be changed when a server moves from on prem to cloud? | Problem avoidance | Elizabeth Golder | Elizabeth advised there are technical reasons to keep the same server name in this case, to prevent changing the config for 200 users, the host name was kept the same. | Service Lead |  | NA | 2024-05-02 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 605 | >60 | February | 2024 | #VALUE!
GTS | Digital workplace Services | 89814764 | 2024-02-05 | Merchandise Planning (MP) application was inaccessible | The decommissioning team is non-technical and would not know whether the host name has been changed or not. Ascertain a way of ensuring that all relevant teams no which servers have moved but retained the same host name. | Problem avoidance | Farid Arab | We now have a list of all servers that have been moved with the same server name and this will be double checked each time a DNS removal change will be raised. | Active Directory |  | NA | 2024-05-02 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 605 | >60 | February | 2024 | #VALUE!
Customer Channels | Selling Experience | 89823312 | 2024-02-05 | Customers unable to load or view Onyx hosted online baskets. | Improve the ways of handling the change to avoid change failure | Problem avoidance | Tawfiq Oladoja/ Richard Day | 05/04: This action have been closed 05/02: Onyx and Price Domain teams to discuss how to handle anything that break the basket. i.e. what sort of error handling should we put in place, what scenarios should we take account of etc. Tawfiq and Richard Day to discuss further | Onyx basket and Price domain teams |  | NA | 2024-05-04 | Closed |  |  |  | Saloni | 2025-02-10 | 605 | >60 | April | 2024 | #VALUE!
Customer Channels | Selling Experience | 89823312 | 2024-02-05 | Customers unable to load or view Onyx hosted online baskets. | Review the system Interdependencies | Problem avoidance | Wain Glaister/Tawfiq Oladoja | 20/02:This is work in progress, an outline process is defined and the team is looking into the best way to implement it as it spans multiple teams.It will be tracked under the back log 05/02: It was agreed that there is a lack of clarity regarding understanding the interdependencies across domains. Note: This issue does not just relate to deployments Tawfiq will review the breaking change process and make sure that people are aware of the standards and that they should be followed. Wain advised that we need to look at things other than testing. i.e. the relationship between graph and domains. Wain and Tawfiq to discuss further (including deprecation of fields) | Onyx basket team |  | NA | 20/02/24 | Closed |  |  |  | Saloni | 2025-02-10 | 605 | >60 | February | 2024 | #VALUE!
Customer Channels | Selling Experience | 89823312 | 2024-02-05 | Customers unable to load or view Onyx hosted online baskets. | The reporting tool was't working as expected what can be done to fix it | Problem identification & Alerting | Wain Glaister | 20/02: This has been fixed and released last week bringing the feature back to its previous capability. 05/02:The reporting tool (graphql-hive) was used to identify redundant fields in Production. This worked correctly and identified breaking changes. However, the usage statistics in the report were incorrect. These stats. have now been removed . Wain is looking at what needs to be done about usage stats e.g. try and fix or do something else. | Onyx Basket team |  | NA | 16/02/24 | Closed |  |  |  | Saloni | 2025-02-10 | 605 | >60 | February | 2024 | #VALUE!
Customer Channels | Selling Experience | 89823312 | 2024-02-05 | Customers unable to load or view Onyx hosted online baskets. | Improvements to be made in testing | Problem identification & Alerting | Jackie Collier Hisham Khalid/ Elaine Hawthorn/ Steve Warren | 05/02:Agreed that testing needs to be improved. Testing within the Price Domain took place . The issue occurred when the Price Domain connected with other domains. At the moment, it is not possible to carry out end-to-end testing across domains Jackie will work with the Onyx Basket team in order to put something in their pipeline to improve testing .- We now have the Basket E2E tests as part of our pipeline - Completed Elaine and Hisham will speak to Steve Warren about testing across domains. | Onyx Basket team |  | NA | 26/02/24 | Closed |  |  |  | Saloni | 2025-02-10 | 605 | >60 | February | 2024 | #VALUE!
C&H and Intl | C&H commercial Trading | 89809846 | 2024-02-05 | Brands articles go live on the website impacted due to missing RRP | RP products scenario - users to be advised not to copy and paste data into price field. Must be typed manually. | Problem avoidance | George Louizou | Done | Service Lead |  | NA | 2024-12-02 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 605 | >60 | February | 2024 | #VALUE!
C&H and Intl | C&H commercial Trading | 89809846 | 2024-02-05 | Brands articles go live on the website impacted due to missing RRP | STIBO - fix is due w/c 12th February after successful testing last week. | Permanent Fix | George Louizou | 03/04: Fix deployed in prod by STIBO for color and stroke validation on 21st, which will not allow any color stroke duplicates. It has been monitored by PDX support. 25/03: Have scheduled a call with Guna, Ashok and George by 28th 12/03: There is a call on 15th with Brands business today. 10/03: Checked with Ashok as George is OOO 23/02: George updated that they've had to make some changes so looks like a new deployment is due early March and let us keep this action open till then 19/02: Followed up with George on the status of the fix 05/02: Awaiting for the fix to be deployed | Service Lead |  | NA | 2024-03-04 | Closed |  |  |  | Saloni | 2025-02-10 | 605 | >60 | April | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 89814960 | 2024-02-01 | Some store colleague accounts were deleted | Review the AD accounts deletion task during any store closure activity | Problem avoidance | Mark Browne/ Sophia Wright | 12/02: Sophia confirmed that she is clear on the process to review the AD accounts deletion during any store closure activity. Hence closing. 01/02: Make sure all the store user accounts are reviewed before placing the accounts for deletion during the store closure process. Ensure we map the retained/active store user accounts to the respective stores before the activity. | Retail team |  | NA | 2024-12-02 | Closed |  |  |  | Saloni | 2025-02-10 | 609 | >60 | February | 2024 | #VALUE!
GTS | Digital Workplace Services | 89814960 | 2024-02-01 | Some store colleague accounts were deleted | What would be the action plan for full recovery – Outlook, Teams, one-drive, access to other applications? | Problem avoidance | Saran/Farid team | 29/02: All corporate devices are equipped with their accounts, hence closing the action 25/02: Followed up with Saran on the latest 15/02: Saran updated that For mailbox and Sharepoint recovery is complete! For surface Go Mary had fixed it and group restore is done by AM team except for Daniel Smith we may need confirmation from user. 09/02: Teams are working on the full recovery for all impacted store colleagues. 01/02: All the deleted accounts have been recreated in AD. However, to recover: Old emails on Outlook: Recover requests are being invoked for each affected user. As of now we have recovered for 5 users and the rest 53 will be done in batches. In-progress. MS Teams old chats/groups – We were unable to get the metadata to recover the one2one chats however we could add the users to their old groups and channels in the backend. In-progress. One-drive – Export the profile URLs from SPO deleted repo and initiate the data copy. In-progress. Access to other applications: Using a few model IDs we will be able to recover their access. In-progress.. | active Directory |  | NA | 29/02/24 | Closed |  |  |  | Saloni | 2025-02-10 | 609 | >60 | February | 2024 | #VALUE!
GTS | Digital Workplace Services | 89814960 | 2024-02-01 | Some store colleague accounts were deleted | Create a playbook, with the steps on the recovery of AD accounts, outlook mailbox, MS Teams and One-drive etc in relation to such scenarios (bulk user accounts deletion) | Solution & Recovery | Saran Rajkumar | 25/03: Saran share the backlog WPTC-5193 10/03: Followed up with Saran on the playbook 29/02: Saran is working on the playbook for mailbox and will share it other teams to update it, however in parallel will get the Jira reference ASAP 25/02: Followed up with Saran on the latest 15/02: Saran is still working on it 11/02: Have followed up with Saran on the action 01/02: High level points on recovery actions. | Messaging Team |  | NA | 25/03/24 | Closed |  | WPTC-5193 |  | Saloni | 2025-02-10 | 609 | >60 | March | 2024 | #VALUE!
GTS | Digital Workplace Services | 89814960 | 2024-02-01 | Some store colleague accounts were deleted | Implement an additional process within AD to have a back-up of the accounts before deletion | Solution & Recovery | Farid/AD team | 05/03: Got the Epic reference 29/02: Servers are in build phase, Muthu to share the backlog 24/02: Muthu shared the ERF, waiting for CATE server allocations 19/02: Muthu confirmed that there is a backlog for this long term action, Muthu to share. 12/02: AD team is testing semperis tool in cate, Once that is implemented we can recovery AD faster. 01/02: During any store closure activity, move the users to a new OU via a service request before implementing the account deletion task. Accounts in the new/spare OU will be set as a backup and then will be deleted permanently after a few days of hypercare. This additional process before the deletion of the OU will help to reduce/prevent the impact. Note: The service request will be tagged with the original CR for easy reference. | active Directory |  | NA | 2024-05-03 | Closed |  | WPTS-17000 | Open | Saloni | 2025-02-10 | 609 | >60 | March | 2024 | #VALUE!
GTS | Digital Workplace Services | 89814960 | 2024-02-01 | Some store colleague accounts were deleted | Review the feasibility to get a tool to do the AD recovery quicker. | Solution & Recovery | Farid/Duane | 05/03: Got the Epic reference 24/02: Followed up with Duanne on the link 15/02: Have checked with Duane for the Epic link 12/02: Duane updated that the team is already working on a POC with a tool from Semperis and awaiting for the epic link. 01/02: The plan to get a new tool for AD is in the roadmap and is being worked upon by the teams and it is expected to be brought into production by next financial year. In the interim, we have enabled a recycle bin in the AD to store the recently deleted accounts. This will help us for a quick recovery. | active Directory |  | NA | 2024-05-03 | Closed |  | WPTS-17000 | Open | Saloni | 2025-02-10 | 609 | >60 | March | 2024 | #VALUE!
Group Platforms | Finance | 89817942 | 2024-01-31 | cSAP ECC database running out of memory | Review of the alerting to ensure alerts are appropriately routed to product teams that need to take actions. | Root cause | Mahesh/Jafar | 12/02: Based on discussion with Sathish and Jafar, Mahesh confirmed that for alerting, we are not changing the any process. For any incidents related to OS will have one to one and try to fix the issue accordingly. 07/02: Call is scheduled between Mahesh, Jafar and Sathish at 3 PM today 31/01: Both SAP and Unix team agreed to review together. | SAP/Unix |  | NA | 2024-12-02 | Closed |  |  |  | Saloni | 2025-02-10 | 610 | >60 | February | 2024 | #VALUE!
GTS | Enterprise Technology Platform | 89817942 | 2024-01-31 | cSAP ECC database running out of memory | How can we invoke HA/DR effectively? | Solution & Recovery | Jafar Sadiq | Power HA is available for DB, but as reboot was quicker form of recovery. HA option would have required a comparatively longer outage. | UnixTeam |  | NA | 31/01/24 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 610 | >60 | January | 2024 | #VALUE!
Group Platforms | Finance | 89817942 | 2024-01-31 | cSAP ECC database running out of memory | How quickly, we can get a consolidated Impact during such scenarios? | Impact analysis | Remko Smit | It was agreed to use the AIM tool effectively, however, the issue required an emergency outage, therefore only the critical services were considered | SAP |  | NA | 31/01/24 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 610 | >60 | January | 2024 | #VALUE!
GTS | Enterprise Technology Platform | 89817942 | 2024-01-31 | cSAP ECC database running out of memory | Feasibility checks to increase the OS memory | Problem avoidance | Mahesh/Jafar | 22/02: Swap space uplift done with the change CRQ000000194962 12/02: Mahesh updated that, as per SAP Suggestion we are increasing the SWAP space/Pagin memory from 44 to 244 GB - CR implementation in Progress. 07/02: Call is scheduled between Mahesh, Jafar and Sathish at 3 PM today 31/01: Both SAP and Unix team agreed to review together. | SAP/Unix |  | NA | 22/02/24 | Closed |  |  |  | Saloni | 2025-02-10 | 610 | >60 | February | 2024 | #VALUE!
Group Platforms | Finance | 89817942 | 2024-01-31 | cSAP ECC database running out of memory | Case to be raised with SAP for root cause | Root cause | Mahesh Chedde | 12/02: SAP team have raised OSS message based on that, we have given recommendations. 07/02: Checked with Mahesh on the case with SAP vendor 31/01: IBM vendor has shared the root cause (PMR details) for the memory hike and suggested to engage SAP vendor for further investigation | SAP |  | NA | 2024-12-02 | Closed |  |  |  | Saloni | 2025-02-10 | 610 | >60 | February | 2024 | #VALUE!
GTS | Enterprise Technology Platform | 89817942 | 2024-01-31 | cSAP ECC database running out of memory | To run the DPO (Dynamic Platform optimization) based on the IBM recommendation | Problem identification & Alerting | Sathish Selvapillai/ Jafar | 22/02: DPO done 07/02: CR is raised for 14th - we will implement two actions DPO + Swap space uplift CRQ000000194962 31/01: Currently we are having P10 version of IBM DB server which doesn’t require DPO. However, we will proceed with a DPO as it is a best practice to fragment the memory for quicker accessing of the data | UnixTeam |  | NA | 22/02/24 | Closed |  |  |  | Saloni | 2025-02-10 | 610 | >60 | February | 2024 | #VALUE!
GTS | Enterprise Technology Platform | 89817942 | 2024-01-31 | cSAP ECC database running out of memory | To enable the performance logs when there is a Sev 2 alert for 90% paging space | Problem identification & Alerting | Sathish Selvapillai | Sathish has informed the team | UnixTeam |  | NA | 2024-01-02 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 610 | >60 | February | 2024 | #VALUE!
Customer Channels | Service Experience | 89792763 | 2024-01-31 | CD DC received Ecom nominated orders beyond the cut off time | For any CD planned outage, how can we prevent the recurrence of this issue in future? | Problem avoidance | Srinivasan Natarajan | 21/01: This action is completed 31/01: It has been understood in the PIR call that the delivery calendar can be switched off for NDD & Standard delivery services specific to Castle Donington. However, for the C&C delivery service the delivery calendar is shared across Braford, Thorncliffe and Castle Donington. Going forward delivery date will be switched off for any planned outages | C&H Online Fulfilment operations |  | NA | 21/02/24 | Closed |  |  |  | Saloni | 2025-02-10 | 610 | >60 | February | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89792763 | 2024-01-31 | CD DC received Ecom nominated orders beyond the cut off time | Add a process to validate the orders by ship by date and full fill the orders during any planned outages. | Problem avoidance | Pragadesh | 06/02: WMS consumes only a single date field from middleware which is populated to site users. Hence there is no specific validation that can be introduced advising users to refer an alternate date. Additionally, OMS confirmed over the PIR that going forward Delivery date will be amended instead of Shipment date which will ensure that the orders will not drop beyond their cut off time. As a best practice whenever, there is a long outage planned in site the below step can be included. WMS team to add a step in the cutover to verify if there are open orders with change in proposition against OMS and advise site to pull forward the orders. This can be planned on the outage day. | WMS |  | NA | 2024-06-02 | Closed |  |  |  | Saloni | 2025-02-10 | 610 | >60 | February | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89792763 | 2024-01-31 | CD DC received Ecom nominated orders beyond the cut off time | Discuss and agree whether the preposition can be reverted based on the incident scenarios once the service is restored/impact is mitigated. | Solution & Recovery | MIMs / Service lead | 31/01:Agreed in the call that discussion will be made on reversion of the global preposition in the MIM call and actions will be taken accordingly | CD IT |  | NA | 31/01/24 | Closed |  |  |  | Saloni | 2025-02-10 | 610 | >60 | January | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89792763 | 2024-01-31 | CD DC received Ecom nominated orders beyond the cut off time | Can we change the reference of ‘latest ship date’ to ‘ship date’ in the WMS logic so the shipping calendar can be switched off only for Castle Donington | Permanent Fix | Pragadesh | 20/02:The feasibility of changing the reference of ‘latest ship date’ to ‘ship date’ in the WMS logic so the shipping calendar can be switched off only for Castle Donington is being explored under the back log JDATE-1032206/02: Though OMS feeds 2 types of date, from Middleware WMS receives only 1 date field that is populated to users. Any amendments required needs to be configured in EM/Middleware on which type of date WMS needs to consume. With Dispatcher upgrade scheduled to Go Live on April’24 this change is not appropriate now. Post Dispatcher upgrade and MULE coming into the architecture, a decision can be taken after discussing with OMS, MULE and WMS teams. | WMS |  | NA | 20/02/24 | Closed |  | JDATE-10322 |  | Saloni | 2025-02-10 | 610 | >60 | February | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89792763 | 2024-01-31 | CD DC received Ecom nominated orders beyond the cut off time | During any incident ensure that impact is assessed meticulously and reevaluated throughout the incident so that respective actions can be taken to prevent any additional issue. | Impact analysis | All | 31/01: Agreed in the call that impact to reevaluated and updated in the communications accordingly. | WMS |  | NA | 31/01/24 | Closed |  |  |  | Saloni | 2025-02-10 | 610 | >60 | January | 2024 | #VALUE!
Digital & Data | Digital & Data | 89806638 | 2024-01-30 | A central Azure issue at Microsoft impacting Sorted label printing at CD and Beam Services. | Beam services: Do we have any workaround for the daily sales reports during such MS outages | Problem avoidance | Ranadip/Arup | No workaround exists as these systems are completely on cloud. However, we have the right communication process in place to keep our stakeholders informed about delay. Product teams will internally check on the possible workaround options if any. | Beam team |  | NA | 26/01/24 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 611 | >60 | January | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89789015 | 2024-01-29 | Thorncliffe DC colleagues were intermittently unable to access WMS application on the RDTs impacting the Click & Collect orders | Test and install a second patch supplied by BY to help with root cause analysis. | Root cause | Kunal Chichkar | 11/04 - Kunal confirmed this is deployed in prod two weeks back BY patch was just additional debugging and we have received the same from them and it is tested and ready for deployment. The reason this is yet deployed in production is because of another project go live in Brands for ROI E-COM orders. Once the system is stable with this new changes, the change will be deployed. Abhishek will have the exact date of deployment for the above changes. | C&H Software engineering |  | NA | 2024-11-04 | Closed |  |  |  | Saloni | 2025-02-10 | 612 | >60 | April | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89789015 | 2024-01-29 | Thorncliffe DC colleagues were intermittently unable to access WMS application on the RDTs impacting the Click & Collect orders | Coding changes on the RDT as preventative measures – discuss with engineers and test | Problem avoidance | Abhishek Kumar | Update 11/04 - Fix was deployed on 20th March Additional preventative fix in WMS is also developed and tested and ready for deployment. The reason this is yet deployed in production is because of another project go live in Brands for ROI E-COM orders. Once the system is stable with this new changes, the change will be deployed. Abhishek will have the exact date of deployment for the above changes. | C&H Software engineering |  | NA | 2024-11-04 | Closed |  |  |  | Saloni | 2025-02-10 | 612 | >60 | April | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89789015 | 2024-01-29 | Thorncliffe DC colleagues were intermittently unable to access WMS application on the RDTs impacting the Click & Collect orders | Work on developing a standard environment with agreed production and dev version levels so that testing and deployment can go seamlessly | Problem avoidance | Kunal Chichkar | This has been rectified and we have Non Prod env now which is in Synch with production. So in future env synch should not be an issue. | C&H Software engineering |  | NA | 13/03/24 | Closed |  |  |  | Saloni | 2025-02-10 | 612 | >60 | March | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89789015 | 2024-01-29 | Thorncliffe DC colleagues were intermittently unable to access WMS application on the RDTs impacting the Click & Collect orders | Agree what is the prod level in all DC’s and then get BY and Customer to match their individual dev environment for troubleshooting - provide backlog ID | Problem avoidance | Karthick GC | Update 16/04 - KGC advised that the comparison has been done and only CMS. The CMS environment will be built in Q2 | WMS |  | NA | 22/04/24 | Closed |  |  |  | Saloni | 2025-02-10 | 612 | >60 | April | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 89817622 | 2024-01-29 | Sign in & Log Off Pages Displaying Blank Page | Run Book additions to facilitate quicker decision making on incident scenarios involving Onyx | Solution & Recovery | Prabhat Thapa | Decision to fallback took a while. Run book with set scenarios to assist in coming to quicker decisions regarding what steps to take for critical sev 1 scenarios for Onyx Auth. | Onyx Auth |  | NA | 19/03/24 | Closed |  |  |  | Saloni | 2025-02-10 | 612 | >60 | March | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 89817622 | 2024-01-29 | Sign in & Log Off Pages Displaying Blank Page | MIM Bridge details to be pinned on Tech Ops | Supplier and support involvement | Aadil Kasmani | 29/01: MIM 4 bridge details have been pinned to Tech Ops channel on teams. Also added to description of the channel and notes tab | .com Operations |  | NA | 29/01/24 | Closed |  |  |  | Saloni | 2025-02-10 | 612 | >60 | January | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 89817622 | 2024-01-29 | Sign in & Log Off Pages Displaying Blank Page | Clean up of net storage | Problem avoidance | Runtime Team | 05/04:This actions will be carried under a GITHUB issue reference as Onyx team is not using JIRAhttps://github.com/DigitalInnovation/onyx/issues/14377 04/04: This actions will be carried under a GITHUB issue reference as Onyx team is not using JIRA 06/02- 03/04: Aadil was working on identifying the owners 06/02: This is will be longterm actions awaiting a JIRA backlog | Runtime Team |  | NA | 2024-05-04 | Closed |  |  |  | Saloni | 2025-02-10 | 612 | >60 | April | 2024 | #VALUE!
Customer Channels | Selling Experience | 89817622 | 2024-01-29 | Sign in & Log Off Pages Displaying Blank Page | Wider strategy for browser caching review. | Problem avoidance | Runtime Team | 05/04: Action is out of scope for this PIR closing this action as confirmed by the service lead Aadil and Product teams 04/04: This actions will be carried under a GITHUB issue reference as Onyx team is not using JIRA 06/02- 03/04: Aadil was working on identifying the owners 06/02: This is will be longterm actions awaiting a JIRA backlog | Runtime Team |  | NA | 2024-05-04 | Closed |  |  |  | Saloni | 2025-02-10 | 612 | >60 | April | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 89817622 | 2024-01-29 | Sign in & Log Off Pages Displaying Blank Page | Check LFTP (Used for file transfer to Net Storage) Options that could prevent net storage from having 0 byte file scenario | Problem avoidance | Runtime Team | 05/04:This actions will be carried under a GITHUB issue reference as Onyx team is not using JIRAhttps://github.com/DigitalInnovation/onyx/issues/14377 06/02- 03/04: Aadil was working on identifying the owners 06/02: This is will be longterm actions awaiting a JIRA backlog 29/01: This will add an additional check and prevent a scenario with a 0 byte file. | Runtime Team |  | NA | 2024-05-04 | Closed |  |  |  | Saloni | 2025-02-10 | 612 | >60 | April | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 89817622 | 2024-01-29 | Sign in & Log Off Pages Displaying Blank Page | Push a new build with an amendment so that hash is regenerated for the impacted assets creating a new file on net storage | Permanent Fix | Onyx Auth | 05/02: A new build has been created and deployed | Onyx Auth |  | NA | 2024-06-02 | Closed |  |  |  | Saloni | 2025-02-10 | 612 | >60 | February | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 89817622 | 2024-01-29 | Sign in & Log Off Pages Displaying Blank Page | Verifying Net Storage Assets with non-cached asset versions on Akamai | Problem identification & Alerting | Runtime/Onyx Auth | 05/04:This actions will be carried under a GITHUB issue reference as Onyx team is not using JIRA https://github.com/DigitalInnovation/onyx/issues/9736 29/01:This may take a considerable amount of time. In the mean time inform other Onyx teams of findings so that teams can identify this issue sooner if the issue occurs for them. | Runtime/Onyx Auth |  | NA | 2024-05-04 | Closed |  |  |  | Saloni | 2025-02-10 | 612 | >60 | April | 2024 | #VALUE!
Customer Channels | Selling Experience | 89817622 | 2024-01-29 | Sign in & Log Off Pages Displaying Blank Page | Follow up with Ticket with Akamai regarding net storage | Root cause | Runtime Team | 06/02: 2 request was received at 15:13, the first one failed due time out error,during which the 2nd request was processed resulting in a empty file 29/01: Akamai have updated to advise that during the 15:12 update there were concurrent requests to amend the same file, which resulted in a 409 status code issued for the first request and 0 byte file updated for the 2nd. | Runtime Team |  | NA | 2024-06-02 | Closed |  |  |  | Saloni | 2025-02-10 | 612 | >60 | February | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 89817622 | 2024-01-29 | Sign in & Log Off Pages Displaying Blank Page | Access to cloudlet policy for on call team members | Problem identification & Alerting | Onyx Team | 29/01: Team to have a regular exercise in place to ensure all on call team members have access to relevant Akamai cloudlets policies | Onyx Team |  | NA | 2024-07-02 | Closed |  |  |  | Saloni | 2025-02-10 | 612 | >60 | February | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 89817622 | 2024-01-29 | Sign in & Log Off Pages Displaying Blank Page | Alerting to ensure this issue is detected by the relevant team/Why alerts did not trigger. O | Problem identification & Alerting | Onyx Team | 06/02: The alert was disabled and it has been enabled again 29/01:Alerts did not trigger because during the time window alerting is muted due to daily increase in error rate at 00:30am. Will check if these can be re-enabled/What needs to be done to get these reenabled | Onyx Team |  | NA | 2024-06-02 | Closed |  |  |  | Saloni | 2025-02-10 | 612 | >60 | February | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89806638 | 2024-01-29 | A central Azure issue at Microsoft impacting Sorted label printing at CD and Beam Services. | Why Sorted did not invoke their resiliency by failing over to another available server/host? | Solution & Recovery | Jackie Martin/Sorted | Since all Microsoft Azure regions were impacted, therefore for Sorted to fail over to a different Azure region was impossible. High Availability therefore could not be implemented. | Product team |  | NA | 26/01/24 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 612 | >60 | January | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89806638 | 2024-01-28 | A central Azure issue at Microsoft impacting Sorted label printing at CD and Beam Services. | What are the recommended workarounds during any reoccurrences? | Solution & Recovery | Carrier team | The only recommended workaround is to switch to another carrier service like DPD, Royal Mail etc. However, for ROI, there is only Anpost, there is no other carrier service thus no workaround can be implemented for Anpost services. | Product team |  | NA | 26/01/24 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 613 | >60 | January | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89806638 | 2024-01-27 | A central Azure issue at Microsoft impacting Sorted label printing at CD and Beam Services. | Review how effectively we could implement the workaround of failing over to the other carrier. | Solution & Recovery | Jackie Martin | 02/02 - As all the Axure services were impacted due to the global outage, Sorted were unable to invoke the High availablity. 31/01-Product team to agree with the business on a process for implemented a workaround (failing over to another carrier service) as there are access restrictions and our carrier support team does not work 24*7 - considering all the challenges a process needs to be devised for immediate mitigation | Product team |  | NA | 2024-02-02 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 614 | >60 | February | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89806638 | 2024-01-26 | A central Azure issue at Microsoft impacting Sorted label printing at CD and Beam Services. | Ensure the right communication process is agreed with Sorted. | Supplier and support involvement | Jackie Martin /Nandha/ Sorted | 02/02- Sorted had confirmed that they have have revisited the process with all the Technical Customer Support Team to ensure that communications are sent in a timely fashion . 26/01-During the incident, if Sorted would have communicated to Customer on the global azure outage on time, immediately a workaround would have been initiated to minimize the impact. Need to agree with Sorted on an effective communication process. | Product team |  | NA | 2024-02-02 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 615 | >60 | February | 2024 | #VALUE!
Customer Channels | Service Experience | 89809963 | 2024-01-25 | Issues with card payments at stores and online | We await the root cause report from Worldline | Root cause | Oza kannan/Balaji Jaganathan | Update 19/02: Report received - root cause was human error by World Line: During a Visa change period, Worldpay traffic was required to be moved to a route that would be unaffected by the changes. Worldpay inadvertently moved some traffic to an incorrect route, resulting in the impact to transactions. | Payments foundation |  | NA | 19/02/24 | Closed |  |  |  | Saloni | 2025-02-10 | 616 | >60 | February | 2024 | #VALUE!
Customer Channels | Selling Experience | 89798659 | 2024-01-25 | Issues with Assist app and SPPD application. | Add MIM DL to Akamai incident notification | Supplier and support involvement | David Raine | 29/01: This is complete | Assit app |  | NA | 29/01/24 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 616 | >60 | January | 2024 | #VALUE!
Customer Channels | Service Experience | 89799773 | 2024-01-23 | ROI stores unable to process online returns | Agree that any comms to all the POS related teams should go to one DL rather than treat each smaller team as a separate team. Shikhar to talk to TPM Tayo Oluyinka and create the DL. | Problem avoidance | Shikhar Khanna | 13/02 The DL has been created and has been sent Flooid. | Online returns |  | NA | 13/02/24 | Closed |  |  |  | Saloni | 2025-02-10 | 618 | >60 | February | 2024 | #VALUE!
Customer Channels | Service Experience | 89799773 | 2024-01-23 | ROI stores unable to process online returns | Teams to collaborate on how they would like receive the updates and where the content should be centrally stored. Also, identify a central place where historical roll outs can be stored so that in future, we can refer back to them | Problem avoidance | Shikhar Khanna | 13/02 Teams have been requested to share the release notes and a confluence page had been created where all the releases are being stored. | Online returns |  | NA | 13/02/24 | Closed |  |  |  | Saloni | 2025-02-10 | 618 | >60 | February | 2024 | #VALUE!
Customer Channels | Service Experience | 89799773 | 2024-01-23 | ROI stores unable to process online returns | Analyse the transactional/exceptions data going into New Relic to see if New Relic could be used as a monitoring & alerting tool for a reduction in various types of reductions (such as refund transactions). | Problem identification & Alerting | Shikhar Khanna | 19/02: Back log provided: https://jira.marksandspencer.app/browse/COB-250 13/02 Partly done. Medium term strategy is to map all the scenarios in new relic. The APM agent will be trialled on two non prod till to help map the scenarios. Shikhar to raise a backlog JIRA | Online returns |  | NA | 19/02/24 | Closed |  |  |  | Saloni | 2025-02-10 | 618 | >60 | February | 2024 | #VALUE!
Customer Channels | Service Experience | 89799773 | 2024-01-23 | ROI stores unable to process online returns | Review process to see if it needs to be updated for small changes and see if we need to match it to large changes as much as possible - deploy to all tills in 2-3 stores then monitor. Provide a final approach. | Problem avoidance | Shikhar Khanna | 13/02 - We have now changed the process to carry out the change for a few tills, then a few whole stores, then we roll out if no issues reported here. | Online returns |  | NA | 13/02/24 | Closed |  |  |  | Saloni | 2025-02-10 | 618 | >60 | February | 2024 | #VALUE!
Customer Channels | Service Experience | 89799773 | 2024-01-23 | ROI stores unable to process online returns | Review hypercare process following change deployment to help pick up anything stores raise on the till. | Problem identification & Alerting | Shikhar Khanna | 13/02 Hypercare process in place. You cant do hypercare on the whole estate, this is why its been changed in the action in row 57 | Online returns |  | NA | 13/02/24 | Closed |  |  |  | Saloni | 2025-02-10 | 618 | >60 | February | 2024 | #VALUE!
Customer Channels | Service Experience | 89799773 | 2024-01-23 | ROI stores unable to process online returns | Testing – Sripriya is working on automated regression testing – to systemically pick the top testing scenarios. This in place for UK but ROI is now being worked on. Laura to review scenarios. Sripriya to provide JIRA ID then this can be closed from the PIR. | Problem identification & Alerting | Shikhar Khanna | 13/02 - There was no regression testing plan for ROI but a back log has been raised - RPOS-11009 | Online returns |  | NA | 13/02/24 | Closed |  |  |  | Saloni | 2025-02-10 | 618 | >60 | February | 2024 | #VALUE!
Foods | Foods Commercial Trading | 89802641 | 2024-01-23 | Pricing ops colleagues reported that some homecare products were being traded at the incorrect prices on tills | Create a runbook to recover any pricing and promotion issue for different scenarios across all the systems. | Solution & Recovery | Dhinesh Kumar | 11/04: Team is collarbating with all the upstream and downstream system to create the runbook on different failure scenario which will be closed in the Q1 and will tracked further under the back log- PAP-7198 10/04: Awaiting further updates. 04/04: Team is working on creating a run book based on the sample runbook from POS 20/02: Team is working on it | Pricing and Promotion |  | NA | 2024-11-04 | Closed |  | PAP-7198 |  | Saloni | 2025-02-10 | 618 | >60 | April | 2024 | #VALUE!
Foods | Foods Commercial Trading | 89802641 | 2024-01-23 | Pricing ops colleagues reported that some homecare products were being traded at the incorrect prices on tills | E2E to dashboard to be developed to proactively identify the issue and to understand the impact sooner. | Problem identification & Alerting | David /Promoth | 30/01: PAP-6593 is already exisiting to create the dashboard The design has been picked and aimed to complete in Q1, | Pricing and Promotion |  | NA | 30/01/24 | Closed |  | PAP-6593 |  | Saloni | 2025-02-10 | 618 | >60 | January | 2024 | #VALUE!
Foods | Foods Commercial Trading | 89802641 | 2024-01-23 | Pricing ops colleagues reported that some homecare products were being traded at the incorrect prices on tills | Explore the options to develop a tool to terminate the promotions at mass for both E2E Elimination promotions and normal TPRs | Problem avoidance | David /Promoth | 12/03: The actions is being tracked under a product back log- PAP-6597 20/02: Awaiting further updates from the action owners | Pricing and Promotion |  | NA | 2024-12-03 | Closed |  | PAP-6597 |  | Saloni | 2025-02-10 | 618 | >60 | March | 2024 | #VALUE!
Foods | Foods Commercial Trading | 89802641 | 2024-01-23 | Pricing ops colleagues reported that some homecare products were being traded at the incorrect prices on tills | Enhance the for approval and confirmation processes of ranging and promotion based on existing promotion and ranging of the products | Problem avoidance | Pricing and Ops team / David | 10/04: The stock integrity action is being tracked under - https://jira.marksandspencer.app/browse/FSO-56 04/04: Corporate & Site level promotions submissions business process is aligned to Auto elims process. But it doesn't include Seasonal eliminations, and this will be included once Stock integrity feature( delivered by Retail team) - Awaiting back log details to close this action 20/02: Awaiting further updates from the action owners | Pricing and Promotion |  | NA | 2024-10-04 | Closed |  | FSO-56 |  | Saloni | 2025-02-10 | 618 | >60 | April | 2024 | #VALUE!
Foods | Foods Commercial Trading | 89802641 | 2024-01-23 | Pricing ops colleagues reported that some homecare products were being traded at the incorrect prices on tills | Explore the option to have a view of existing promotions & ranging information for the Pricing and promotion team colleagues when the sets up a new promotion/ranging for any products. | Problem avoidance | David /Promoth | 10/04: The stock integrity action is being tracked under - https://jira.marksandspencer.app/browse/FSO-56 04/04: Corporate & Site level promotions submissions business process is aligned to Auto elims process. But it doesn't include Seasonal eliminations, and this will be included once Stock integrity feature( delivered by Retail team) - Awaiting back log details to close this action 20/02: Awaiting further updates from the action owners | Pricing and Promotion |  | NA | 2024-10-04 | Closed |  | FSO-56 |  | Saloni | 2025-02-10 | 618 | >60 | April | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 89802641 | 2024-01-23 | Pricing ops colleagues reported that some homecare products were being traded at the incorrect prices on tills | Explore the feasibility of aligning the price and promotion processing at ECS and POS to avoid the illegal trading scenario as POS as precedence to prioritize store level prices over others | Problem avoidance | David, Mark & Saurab | 10/04: Mark is out office and will be back on 15th, 09/04: This action is more of new requirement, the current ticket batching design is used by various vendor, discussion to be made on the feasibility of the requrienment with the vendor. 04/04: To be discussed with RET team on this design .In current design RET is not giving precedence to Store level price. It always print the tickets based on the latest price changes from source system. 20/02: Awaiting further updates from the action owners | ECS and POS |  | NA | 15/04/24 | Closed |  |  |  | Saloni | 2025-02-10 | 618 | >60 | April | 2024 | #VALUE!
Foods | Foods Commercial Trading | 89802641 | 2024-01-23 | Pricing ops colleagues reported that some homecare products were being traded at the incorrect prices on tills | E2E elimination promotion set up on 1st Jan (Store level) and deeper cut promotion set up on 18th Jan (Estate level) were overlapping is this an expected scenario | Problem avoidance | Dhinesh Kumar/Moorthy | 20/02:Yes, these prices were set at store level and estate level which was not considering under overlapping scenario according to SAP. There are certain scenarios where if the promotion overlaps it fails to process in SAP. | E2E Elimins |  | NA | 20/02/24 | Closed |  |  |  | Saloni | 2025-02-10 | 618 | >60 | February | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 89803522 | 2024-01-22 | Store colleagues were unable to print price labels as the ECS application was not accessible | On call duty manager for SIT team to always test call functionality prior to be on-call. | Supplier and support involvement | SIT Team | Closed as this is a point of note | SIT |  | NA |  | Closed |  |  |  | Saloni | 2025-02-10 | 619 | >60 | January | 1900 | #VALUE!
Customer Channels | Platform & Store Ops | 89803522 | 2024-01-22 | Store colleagues were unable to print price labels as the ECS application was not accessible | Ensure each change is categorised correctly (INFO). 4 wall or otherwise | Supplier and support involvement | Valli/Alex | Closed as this is a point of note | Stores ops SL |  | NA |  | Closed |  |  |  | Saloni | 2025-02-10 | 619 | >60 | January | 1900 | #VALUE!
Customer Channels | Platform & Store Ops | 89803522 | 2024-01-22 | Store colleagues were unable to print price labels as the ECS application was not accessible | Document the strategy for simplification of POS deployments – risk ID to be provided as this action may take a longer period of time. | Problem avoidance | Subhashish Dasgupta | Risk has been raised in Risk Register. Risk # 2116 | Stores Infra |  | NA | 23/01/24 | Closed | 2116 | NA | N/A | Saloni | 2025-02-10 | 619 | >60 | January | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 89803522 | 2024-01-22 | Store colleagues were unable to print price labels as the ECS application was not accessible | SSI to SIT communication gap –to be addressed by a better handover between platform team and SIT | Problem avoidance | ALL | Closed | SIT |  | NA |  | Closed |  |  |  | Saloni | 2025-02-10 | 619 | >60 | January | 1900 | #VALUE!
Customer Channels | Platform & Store Ops | 89803522 | 2024-01-22 | Store colleagues were unable to print price labels as the ECS application was not accessible | For future SAL deployment testing, set up deployment only on one machine and test prior to proceeding – define the test pipeline for SAL changes. | Problem avoidance | Subhashish Dasgupta | 24/01: SAL implementation plan document has been modified with all necessary checks and a Pilot rollout step to cover things are working fine before full estate rollout. | Stores Infra |  | NA | 24/01/24 | Closed |  |  |  | Saloni | 2025-02-10 | 619 | >60 | January | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 89803522 | 2024-01-22 | Store colleagues were unable to print price labels as the ECS application was not accessible | Remove the option of having an x86 package in MECM – add this to SIT Deployment SOP/check list. | Problem avoidance | Stuart Shale | 06/02: This is action is no longer needed as the initial process gap has been addressed with Store infra, however Stuart will perform the validation before deployment | SIT |  | NA | 2024-06-02 | Closed |  |  |  | Saloni | 2025-02-10 | 619 | >60 | February | 2024 | #VALUE!
Customer Channels | Platform & Store Ops | 89803522 | 2024-01-22 | Store colleagues were unable to print price labels as the ECS application was not accessible | Add a precheck within each new SAL package to systemically prompt when it checks the version of the operating system – it should systemically stop deployment if the OS versions don’t match. | Problem avoidance | Subhashish Dasgupta | 23/01: As discussed with Packaging team, there is an option already available in SCCM/MECM where we can make a check in the requirement settings to choose specific client platform ( win7/Win10) before deployment. However, Packaging team is going to add platform specific restrictions to the installer which will be an added security to prevent this issue in future on any manual / Human errors. This requirement has been taken into packaging team’s backlog for development for future SAL packages. | Stores Infra |  | NA | 23/01/24 | Closed | NA | RPOS-11004 |  | Saloni | 2025-02-10 | 619 | >60 | January | 2024 | #VALUE!
Customer Channels | Customer Engagement | 89787609 | 2024-01-17 | Few products were not displayed on SRP and PLP pages | Create a Runbook for code reversion | Solution & Recovery | Rob Haley | 07.02: The roll back steps are added in the below link,https://confluence.marksandspencer.app/display/CGE/SCL+Overview 22/01:Rob will document the process of reversion if there is more than 1 PR to revert | Search and Sort Team |  | NA | 2023-07-02 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 624 | >60 | February | 2023 | #VALUE!
Customer Channels | Customer Engagement | 89787609 | 2024-01-17 | Few products were not displayed on SRP and PLP pages | Incident updates | Issue handling/Management | Essam Nabil | 22/01: The Search and Sort team “BAU Support process” is being documented by Essam. It includes details of frequency of updates until the issue is resolved. https://confluence.marksandspencer.app/displ ay/CGE/Business+As+Usual+%28BAU%29+Supp ort+Process | Search and Sort Team |  | NA | 2023-07-02 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 624 | >60 | February | 2023 | #VALUE!
Customer Channels | Customer Engagement | 89787609 | 2024-01-17 | Few products were not displayed on SRP and PLP pages | Contact on-call person via Pager Duty | Issue handling/Management | Hisham Khalid / Elaine Hawthorn | 22/01: Agreed that Service Leads should be able to contact the on-call person via Pager Duty. In order to do this, Service Leads need access to Pager Duty Hisham and Elaine to speak to Steve Warren and Sam Clement about paying for 4 more accounts to access Pager Duty (2 in Selling Experience, 2 in Service Experience | . COM SM |  | NA | 2024-06-02 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 624 | >60 | February | 2024 | #VALUE!
Customer Channels | Customer Engagement | 89787609 | 2024-01-17 | Few products were not displayed on SRP and PLP pages | Improve handover to on-call person and clarify working hours | Problem avoidance | Rob Haley | 22/01: Agreed that the handover to the on-call person needs to be improved (e.g. Rob was on-call and was aware of what was going on but was not aware of the detail) | Search and Sort Team |  | NA | 13/02/24 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 624 | >60 | February | 2024 | #VALUE!
Customer Channels | Customer Engagement | 89787609 | 2024-01-17 | Few products were not displayed on SRP and PLP pages | Any change relating to the Bloomreach Full Feed should be validated after the Full Feed has run in Production | Problem avoidance | Bloom reach team | 22/01: Has been agreed in call and its closed | Bloom reach team |  | NA | 17/01/24 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 624 | >60 | January | 2024 | #VALUE!
Customer Channels | Customer Engagement | 89787609 | 2024-01-17 | Few products were not displayed on SRP and PLP pages | Improve communication between Search and Sort team and wider teams . Search and Sort team can post in Tech Ops Teams channel and tag Service Leads. | Business & IT Communication | Hisham Khalid | 13/02: The SL tag has been created. 22/01: The Service Leads will be responsible for informing relevant business stakeholders. Service Leads to set up a tag to be used in Tech ops | . COM SM |  | Na | 13/02/24 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 624 | >60 | February | 2024 | #VALUE!
Customer Channels | Customer Engagement | 89787609 | 2024-01-17 | Few products were not displayed on SRP and PLP pages | Improvements to alerting identified: 1. Alerting will be set up to identify issues before the change gets deployed to Production. Within lower/test environments 2. Add an alert for products failing validation checks in the Full Feed | Problem identification & Alerting | Rob Haley/ Saumya Khandelwal | 13/02: Both alerts have been created, PF the document. :https://confluence.marksandspencer.app/pages/viewpage.action?pageId=213856579 06/02: Alerting scenario 1 is set up successfully 22/01: 1. New Relic alert will be set up to detect significant deviation in the number of products processed by the Bloomreach Full Feed. | Search and Sort Team |  | Na | 13/02/24 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 624 | >60 | February | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89779090 | 2024-01-12 | Performance issues in WMS application at C&H Bradford DC | Workshop with the DC colleagues to re-iterate the process of executing a query to avoid these issues | Problem avoidance | KNAPP (3rd Party) | A workshop was conducted with the DC colleagues with the KNAPP Tech team to remind them to apply filters while executing any queries on the database. | KNAPP (3rd Party) |  | NA | 2024-12-01 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 629 | >60 | January | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89779090 | 2024-01-12 | Performance issues in WMS application at C&H Bradford DC | KNAPP to deploy a fix to prevent the issue recurrence. | Permanent Fix | KNAPP (3rd Party) | A change was deployed on 8th January by KNAPP. This is to ensure whenever a report is extracted with large amount of data, the data will no longer loaded to the KNAPP JBOSS memory responsible for keeping the database stable | KNAPP (3rd Party) |  | NA | 2024-12-01 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 629 | >60 | January | 2024 | #VALUE!
Customer Channels | Selling Experience | 89790541 | 2024-01-12 | Digital cafe stores customers unable to place orders using the kiosks | Seems to be the 2nd instance of this happening in 18 months so review of the cause and mitigation | Problem avoidance | CS (Jordan) | 23/04 - CS has migrated the services to Azure on 17/04 . Testings have proven positive. 12/04 - CS will migrate the remaining 2x services which are on prem to Azure on 16/4, Once migrated post the testing this action will be closed | Counter Solutions - 3rd Party |  | NA | 2024-12-04 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 629 | >60 | April | 2024 | #VALUE!
Customer Channels | Selling Experience | 89790541 | 2024-01-12 | Digital cafe stores customers unable to place orders using the kiosks | What caused the Application Server to failover | Root cause | CS (Jordan) | 12/04 - The RCA is still inconclusive however we See an improvement since CS has started migrating their services to Azure Cloud. 03/03 - Adam is yet to provide a Risk ID - owning to this ACtoin 20/03 - This is due to the underlying issue with the CS-API,We have a risk raised for the same until CS gives us a Valid solution. In the interim we have the digital cafe resilient solution is in place | Counter Solutions - 3rd Party |  | NA | 2024-12-04 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 629 | >60 | April | 2024 | #VALUE!
Customer Channels | Selling Experience | 89790541 | 2024-01-12 | Digital cafe stores customers unable to place orders using the kiosks | Could Customer be recipients of the alerting that comes out of the systems to help with quicker notification | Problem identification & Alerting | Laura and Adam | 12/04 - Customer has been added as the recipients of the alerting 20/03 - This is still being worked upon 12/01: 1.Laura to share MIM number 2.Adam to help provide that DL Also Define who would be the recipients of that alerting output 1.Who to call in case of Incident 2.Who to add to automatic alert | Customer Digital Café product team |  | NA | 2024-12-04 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 629 | >60 | April | 2024 | #VALUE!
Customer Channels | Selling Experience | 89790541 | 2024-01-12 | Digital cafe stores customers unable to place orders using the kiosks | How can we get the Kiosks to recover quickly | Issue handling/Management | Customer – Thea | RDC was raised with Counter Solutions. And it has been addressed. | Customer Digital Café product team |  | NA | 26/02/24 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 629 | >60 | February | 2024 | #VALUE!
Foods | Foods Supply Chain | 89763232 | 2024-01-08 | Missing EOD stock files for Foods Bradford impacting allocation | Review the possibilities of efficient and timely impact assessment in these scenarios. | Impact analysis | Joey Ocansey | 05/03: From WMS perspective, the teams were notified and reiterated on the criticality of the EOD file and in-addition, the control-M job has been configured to fail when the ISM file doesn’t get generated. This will ensure we understand the actual impact upon job failure. 13/02: As there had been no response from the Foods team, an email has been sent with all the actions, also spoke to Jay in person to chase up. Awaiting updates. If the issue was notified, the impact could have been mitigated in Relex & Q. This is an ability to pause the batch. Feasibility of customising a SOP to understand the impact to Q – supplier orders and allocation. Relex – An automated report is in place. | Service Lead |  | NA | 2024-07-03 | Closed |  |  |  | Saloni | 2025-02-10 | 633 | >60 | March | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89763232 | 2024-01-08 | Missing EOD stock files for Foods Bradford impacting allocation | Delay in highlighting the issue from WMS on the disk space alert | Issue handling/Management | Sakthi Santhosh Nagarathinam | The support teams have been advised to ensure that any issues overnight should be communicated via Teams channel along with timely engagement of MIM. | WMS |  | NA | 2024-12-02 | Closed |  |  |  | Saloni | 2025-02-10 | 633 | >60 | February | 2024 | #VALUE!
Digital & Data | Digital & Data | 89763232 | 2024-01-08 | Missing EOD stock files for Foods Bradford impacting allocation | Configure alerts for the missing ISM file in BEAM | Problem identification & Alerting | Arup Neogy/Ranadip Saha | As this is one single file with a combination of BF and MK, therefore, no alerts can be configured. | BEAM |  | NA | 13/02/24 | Closed |  |  |  | Saloni | 2025-02-10 | 633 | >60 | February | 2024 | #VALUE!
Digital & Data | Digital & Data | 89763232 | 2024-01-08 | Missing EOD stock files for Foods Bradford impacting allocation | Configure alerts for the missing ISM file in EDW | Problem identification & Alerting | Gaurav Kothari | As this is one single file with a combination of BF and MK, therefore, no alerts can be configured. Additionally, there is no usage of these files in EDW. | EDW |  | NA | 2024-09-01 | Closed |  |  |  | Saloni | 2025-02-10 | 633 | >60 | January | 2024 | #VALUE!
Foods | Foods Supply Chain | 89763232 | 2024-01-08 | Missing EOD stock files for Foods Bradford impacting allocation | Configure alerts to identify the missing ISM file in Relex | Problem identification & Alerting | James Lewis | 05/03: Pager duty Alerts were already configured in FOA 13/02: As there had been no response from the Foods team, an email has been sent with all the actions, also spoke to Jay in person to chase up. Awaiting updates. This will be picked up with the Project team. | Relex |  | NA | 2024-07-03 | Closed |  |  |  | Saloni | 2025-02-10 | 633 | >60 | March | 2024 | #VALUE!
Foods | Foods Supply Chain | 89763232 | 2024-01-08 | Missing EOD stock files for Foods Bradford impacting allocation | Configure alerts to identify missing ISM file in Q | Problem identification & Alerting | Kalli | 05/03: The task has been added to the Quantum backlog and prioritized. We expect the work to complete by this Feb'24 end. We will find a suitable opportunity to deploy the alert in Production by Mar'24. 13/02: As there had been no response from the Foods team, an email has been sent with all the actions, also spoke to Jay in person to chase up. Awaiting updates. Feasibility study completed. Task (code change) taken up in current sprint (4.2).-FSORP-20984 | Quantum |  | NA | 27/03/24 | Closed |  |  |  | Saloni | 2025-02-10 | 633 | >60 | March | 2024 | #VALUE!
GTS | Enterprise Integration | 89763232 | 2024-01-08 | Missing EOD stock files for Foods Bradford impacting allocation | Investigate why did the inventory balance extract file sent to Q via FSSD DS have the date of 26/12 instead of 25/12. | Solution & Recovery | Venkat Reddy/ Sreeraj Cheriyil | 22/02: The alerts have been created to ensure the issue is identified proactively. A SOP to be put in place when there is an adhoc run of the inventory balance extract file on the same day, the EOD run picks up the next day’s date. Configure alerting if the date is not adhered. | DS support team |  | NA | 22/02/24 | Closed |  |  |  | Saloni | 2025-02-10 | 633 | >60 | February | 2024 | #VALUE!
Foods | Foods Supply Chain | 89763232 | 2024-01-08 | Missing EOD stock files for Foods Bradford impacting allocation | Devise a contingency plan to address the allocation across Q and Relex for a largescale impact. | Solution & Recovery | Promoth Kumar and Andrew Goslin | 05/03: RELEX : Ambient is not live yet. Contingency plan and sop's will be created as part of ambient roll-out. Planned in May'24. Need a backlog QUANTUM: Feasibility of recovering impact to without manual STOs: Bulk upload of STOs in SAP/ASO is the best approach. Once the orders are created and sent to WMS, Q will get the order details in the shipment plan interface at 3 pm. This will update Q's forward view Relex - A forecasted allocation view gets generated in Relex every morning (Day +3). An agreement to execute the contingency plan for Relex, Create a SOP documenting the E2E mitigation plan during these scenarios. Quantum – Feasibility of incorporating a way to recover the impact to Q without raising manual STOs. An option to bulk upload STOs in SAP. How can we determine the expected volume vs the allocated volume to narrow down the impact - over/under allocation. | Foods product team |  | NA | 14/03/24 | Closed |  | FSORP-20885 |  | Saloni | 2025-02-10 | 633 | >60 | March | 2024 | #VALUE!
Foods | Foods Supply Chain | 89763232 | 2024-01-08 | Missing EOD stock files for Foods Bradford impacting allocation | Devise a contingency plan for supplier orders across Q and Relex. | Solution & Recovery | Promoth Kumar and Andrew Goslin | 05/03: Bulk update of PO: OFP team will be requested with a feature requirement to add in the backlog to enable Suppliers/SDPs to bulk update the POs in OFP in case of a major issue 03/02: As there had been no response from the Foods team, an email has been sent with all the actions, also spoke to Jay in person to chase up. Awaiting updates. Q – 28-days order plan. Relex – 28-day order plan. Manually cancel the POs via OFP for Relex and Q – Is there way to enhance the process of cancelling/amending POs? Explore the feasibility of mass PO amendment ability – To be picked as part of PI planning | Foods product team |  | NA | 15/03/24 | Closed |  | FSORP-20984 |  | Saloni | 2025-02-10 | 633 | >60 | March | 2024 | #VALUE!
Foods | Foods Supply Chain | 89763232 | 2024-01-08 | Missing EOD stock files for Foods Bradford impacting allocation | An adhoc FOP was executed to update supplier orders for Quantum products, what is the plan to recover Relex products? | Solution & Recovery | James Lewis | 05/03: This option was discussed in previous incidents. There is no such option to re-run a Relex batch during day time. 03/02: As there had been no response from the Foods team, an email has been sent with all the actions, also spoke to Jay in person to chase up. Awaiting updates. It was advised that a full batch needs to be executed for Relex products. A plan is in place to implement a design change to recover the Relex products. Also define the other scenarios and devise a contingency plan to mitigate impact for Relex products. | Relex Product Team |  | NA | 2024-07-03 | Closed |  |  |  | Saloni | 2025-02-10 | 633 | >60 | March | 2024 | #VALUE!
GTS | Enterprise Integration | 89763232 | 2024-01-08 | Missing EOD stock files for Foods Bradford impacting allocation | There is a dependency between the WMS file generation and the DS output job. There are 2 conditions configured in the DS job – 1. ISM file process completion. 2. Pick face process completion. These conditions were set to OR to start the job in Datastage, therefore, the DS job completed successfully on 24/12. Configure proactive alerts in Datasatge to identify the issue before processing into the downstream systems. | Problem identification & Alerting | Venkat Reddy/ Sreeraj Cheriyil | 24/04: The change was successful 22/04: Teams have have raised CRQ000000199626 for this change and planning to deploy on Wed(24/04) since there is a DS outage tomorrow. 05/04: There were some access issue in the DS non prod environment as it has been recently migrated to Cloud, this has been fixed now. ETA to deploy in prod - 17/04. 14/03: Due to ongoing DS outages, it is taking longer, Sreeraj has confirmed that he will provide an update by 21/03. 12/02: The issue with the WMS job which failed on the day, however, reflected "completed" in control M caused the confusion in DS. This has been sorted now. Additionally, a file watcher job is being configured in DS to ensure successful receipt of the files before processing to the downstream systems It has been agreed to amend the DS job condition to “AND” to ensure both the files are received before the job starts executing. Also, an additional file watcher job will be configured to verify the availability of the files. | DS Support |  | NA | 2024-05-05 | Closed |  |  |  | Saloni | 2025-02-10 | 633 | >60 | May | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89763232 | 2024-01-08 | Missing EOD stock files for Foods Bradford impacting allocation | There is a 70% threshold alert configured for disk space utilization in WMS, however, it reaches to 100% in 5 mins whilst the logs are being written on the server. Review with Blue Yonder on how the files are being written or if there is a feasibility to increase the disk space. | Problem avoidance | Sakthi Santhosh Nagarathinam | 13/02: There had been no further recurrence of the logs filling up the disk space, therefore, this could not be investigated. I have advised Sakthi to raise a backlog as an action item to capture this upon recurrence. CnH-WMS-00192 Tech teams are liaising with Blue Yonder in internal calls to investigate further. | WMS |  | NA | 15/02/24 | Closed |  | CnH-WMS-00192 |  | Saloni | 2025-02-10 | 633 | >60 | February | 2024 | #VALUE!
GTS | Enterprise Integration | 89763232 | 2024-01-08 | Missing EOD stock files for Foods Bradford impacting allocation | The ISM file is generated in WMS and gets transferred to the datastage layer via Middleware. Configure job failure alerts in MS in case of no files available. | Problem identification & Alerting | Rajasekar Subramanium | It is not possible to set any alert from MQFTE end as well | MQFTE |  | NA | 2024-08-01 | Closed |  |  |  | Saloni | 2025-02-10 | 633 | >60 | January | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89763232 | 2024-01-08 | Missing EOD stock files for Foods Bradford impacting allocation | Configure job failure alerts for no disk space scenarios in WMS. Replicate the alerts across all dispatcher sites. | Problem identification & Alerting | Sakthi Santhosh Nagarathinam | 13/02: Tech team worked with Control-M team and configured the ISM job to fail and alert if the job is not successful due to the disk space Tech team will perform a comparison between the other jobs with failure alerts on disk space issue vs the ISM job which did not fail with the disk space issue on 23/12. | WMS |  | NA | 13/02/24 | Closed |  |  |  | Saloni | 2025-02-10 | 633 | >60 | February | 2024 | #VALUE!
Supply Chain | Foods Supply Chain | 89759673 | 2024-01-05 | Allocation variances observed for some CFTO products | Configure alerts that can identify allocation variances for Quantum, Relex and CFTO products which are processed in ASO and affected by the race condition scenario. | Problem identification & Alerting | Santhosh Veeraraghavan | 18/01: Alerts are available and being used 05/01: During the issue, a script was developed to automatically detect the allocation variance for CFTO products and provide the relevant information (products, UPC, quantity etc), to the depots for manual allocation. Tech team will explore the options to configure alerts for Quantum and Relex products. | Foods |  | NA | 18/01/24 | Closed |  |  |  | Saloni | 2025-02-10 | 636 | >60 | January | 2024 | #VALUE!
Supply Chain | Foods Supply Chain | 89759673 | 2024-01-05 | Allocation variances observed for some CFTO products | Identify an approach to fix the race condition issue in ASO. | Permanent Fix | Santhosh Veeraraghavan | 18/01: It will be done as part of Q1 - FSCLT1-5115 05/01: Analysis is in progress. Testing and implementation will be picked up as part of Q1 planning. | Foods |  | NA | 18/01/24 | Closed |  | FSCLT1-5115 | Closed | Saloni | 2025-02-10 | 636 | >60 | January | 2024 | #VALUE!
Supply Chain | Foods Supply Chain | 89759673 | 2024-01-05 | Allocation variances observed for some CFTO products | At the start of the incident, once Tech identified the variance, the impacted depot was asked to manually allocate against the problematic volumes, however, additional information was not initially shared (expected allocation volume). Tech Team has a responsibility to share clear, relevant and actionable information to depots if there is an expectation to ‘act’ upon the information being shared. | Business & IT Communication | Joey Ocansey | This has been agreed and aligned with TEMs, TPMs and Engineering. | Service Lead |  | NA | 2024-05-01 | Closed |  |  |  | Saloni | 2025-02-10 | 636 | >60 | January | 2024 | #VALUE!
Supply Chain | Foods Supply Chain | 89759673 | 2024-01-05 | Allocation variances observed for some CFTO products | Once action 1 is completed, tech teams to effectively monitor the alerts for efficient and appropriate impact assessment. | Impact analysis | Santhosh Veeraraghavan | This has been agreed | Foods |  | NA | 2024-05-01 | Closed |  |  |  | Saloni | 2025-02-10 | 636 | >60 | January | 2024 | #VALUE!
Supply Chain | Foods Supply Chain | 89759673 | 2024-01-05 | Allocation variances observed for some CFTO products | Perform a review of all other multithreading processes within the Foods portfolio and assess if they are at risk of experiencing a ‘Race Condition’ scenario – Based on individual findings, action plans will need to be created accordingly | Problem avoidance | Andrew Goslin | 29/01: Vinoth confirmed that the backlog is created, awaiting for the details 21/01: Followed up with Andrew on the backlog 18/01: Andrew is OOO 05/01: Long term action – requires a backlog | Foods TEM |  | NA | 29/01/24 | Closed |  | FSCLT1-5115 | Closed | Saloni | 2025-02-10 | 636 | >60 | January | 2024 | #VALUE!
Supply Chain | Foods Supply Chain | 89759673 | 2024-01-05 | Allocation variances observed for some CFTO products | There is a fix developed to address the race condition scenario in Quantum. Validation of the fix to confirm its success. | Permanent Fix | Santhosh Veeraraghavan | 20/02: Closing with backlog reference 19/02: The fix for this issue will be picked in the upcoming Sprints, waiting for the backlog reference. 15/02: Checked with Santhosh/Naveen on the status of the fix. 18/01: Validation is in progress and expected to complete in the current sprint with an ETA of 13th Feb 05/01: Replicate the issue for Quantum and confirm if the fix is working. | Foods |  | NA | 20/02/24 | Closed |  | FSCLT1-5115 | Closed | Saloni | 2025-02-10 | 636 | >60 | February | 2024 | #VALUE!
Customer Channels | Selling Experience | 89775205 | 2024-01-04 | Multiple issues impacting the Digital Café stores | Only allow users to enter up to 255 char for a description. Ensure users cannot enter a product description > 255 chars | Problem avoidance | CS (Jordan) | 15/02 - This action has been addressed in the last sprint with dev resource assigned. WC 5/2/24 | Counter Solutions - 3rd Party |  | NA | 15/02/24 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 637 | >60 | February | 2024 | #VALUE!
Customer Channels | Selling Experience | 89775205 | 2024-01-04 | Multiple issues impacting the Digital Café stores | Do not fail whole batch due to handful of products | Problem avoidance | CS (Phil & Jordan) | This action has been addressed in the last sprint with dev resource assigned. WC 5/2/24 | Counter Solutions - 3rd Party |  | NA | 15/02/24 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 637 | >60 | February | 2024 | #VALUE!
Customer Channels | Selling Experience | 89775205 | 2024-01-04 | Multiple issues impacting the Digital Café stores | How do we proactively alert and monitor before failures are raised | Problem identification & Alerting | CS - deliver Customer – E2E Ownership | 15/02 - Teams have agreed with New Relic approach with CS and have reviewed data points to include in monioring. | Counter Solutions - 3rd Party |  | NA | 15/02/24 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 637 | >60 | February | 2024 | #VALUE!
Customer Channels | Selling Experience | 89775205 | 2024-01-04 | Multiple issues impacting the Digital Café stores | Can the 7am batch timeframe be brought forward | Problem avoidance | CS (Phil) | 15/02 - CS confirmed that this will now be run at 5am for the proactive checks | Counter Solutions - 3rd Party |  | NA | 15/02/24 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 637 | >60 | February | 2024 | #VALUE!
Customer Channels | Selling Experience | 89775205 | 2024-01-04 | Multiple issues impacting the Digital Café stores | Make reporting group a mandatory field to reduce future human error. | Problem avoidance | CS (Jordan) | 15/02 -This action has been addressed in the last sprint with dev resource assigned. WC 5/2/24 | Counter Solutions - 3rd Party |  | NA | 15/02/24 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 637 | >60 | February | 2024 | #VALUE!
Customer Channels | Selling Experience | 89775205 | 2024-01-04 | Multiple issues impacting the Digital Café stores | Need to establish an SLA which describes availability for Digital Café | Issue handling/Management | Customer - Laura & Paul DN – Birthe | Example scenarios aligned to SLA's created to share with the business and suppliers. SLA's will be reviewed as part of contract discussions March/April. | Customer Digital Café product team |  | NA | 22/01/24 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 637 | >60 | January | 2024 | #VALUE!
Customer Channels | Selling Experience | 89775205 | 2024-01-04 | Multiple issues impacting the Digital Café stores | Define P categories for estate wide incidents | Impact analysis | Customer - Laura & Paul DN – Birthe | SLA's will be reviewed as part of contract discussions March/April. | Customer Digital Café product team |  | NA | 22/01/24 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 637 | >60 | January | 2024 | #VALUE!
Customer Channels | Selling Experience | 89775205 | 2024-01-04 | Multiple issues impacting the Digital Café stores | CS to speak to devs and understand alerts from Orderly if batches fail. | Problem identification & Alerting | CS (Phil) | Alerts have been discussed and has been documented for further references | Counter Solutions - 3rd Party |  | NA | 26/02/24 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 637 | >60 | February | 2024 | #VALUE!
Customer Channels | Selling Experience | 89775205 | 2024-01-04 | Multiple issues impacting the Digital Café stores | Establish comms mechanism to the business (wider Hospitality stakeholders) during high priority incidents | Business & IT Communication | Customer – Laura & Paul | Wider hospitality stakeholder group created. Standard MIM comms process also followed. | Customer Digital Café product team |  | NA | 22/01/24 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 637 | >60 | January | 2024 | #VALUE!
Customer Channels | Selling Experience | 89775205 | 2024-01-04 | Multiple issues impacting the Digital Café stores | Establish on call rota for alerts and monitoring | Problem identification & Alerting | Customer – Charly | 05/03- A central Rota ha sbeen created for alert moniroting 15/02 -Charly to work out what is involved in getting the Edge Observability Agent onto all 88 kiosks. Also Jordan from CS to check on the Feasibility on the same | Customer Digital Café product team |  | NA | 18/04/24 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 637 | >60 | April | 2024 | #VALUE!
Customer Channels | Selling Experience | 89775205 | 2024-01-04 | Multiple issues impacting the Digital Café stores | CS to redesign API call and communicate workarounds (Long term solution) | Problem avoidance | CS | 19/02 - Options have been agreed to redesign the API calls and few workarounds have been agreed aswell. Teams will now internally work on those provided options to look on the feasibilites and the next steps. AS this is a ling term actions it will further be worked under a problem record 15/02 - Options are being validated | Counter Solutions - 3rd Party |  | NA | 2024-03-04 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 637 | >60 | April | 2024 | #VALUE!
Customer Channels | Selling Experience | 89775205 | 2024-01-04 | Multiple issues impacting the Digital Café stores | CS to implement button on kiosk (Short-term solution) | Problem avoidance | CS | The Kiosk button has been implemented s a short term solution | Counter Solutions - 3rd Party |  | NA | 2024-02-02 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 637 | >60 | February | 2024 | #VALUE!
Customer Channels | Selling Experience | 89775205 | 2024-01-04 | Multiple issues impacting the Digital Café stores | Investigate the build of a publishing workflow to pilot changes. | Problem avoidance | Customer – Charly | This has already been addressed by the previous action (duplicate action) | Customer Digital Café product team |  | NA | 26/02/24 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 637 | >60 | February | 2024 | #VALUE!
Customer Channels | Selling Experience | 89775205 | 2024-01-04 | Multiple issues impacting the Digital Café stores | Standardizing terminology in the Digital Café playbook to support Help Desk calls | Issue handling/Management | Customer – Paul & Thea | Reviewed with stores and helpdesk | Customer Digital Café product team |  | NA | 22/01/24 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 637 | >60 | January | 2024 | #VALUE!
Customer Channels | Selling Experience | 89775205 | 2024-01-04 | Multiple issues impacting the Digital Café stores | Business continuity plan for technology downtime in digital cafes until resilient solution delivered | Issue handling/Management | Customer - Steve Kemp | 18/04 - We have a fall back plan which utilises the black table numbers and the hidden cash till - THis is used as a DR 12/04 - CS have picked this up in their development (April sprint). This will be delivered in May [from May 8th] of which once successfully validated or once we receive a backlog we can close this action | Customer Digital Café product team |  | NA | 18/04/24 | Closed |  | NA | N/A | Saloni | 2025-02-10 | 637 | >60 | April | 2024 | #VALUE!
Customer Channels | Selling Experience | 89775205 | 2024-01-04 | Multiple issues impacting the Digital Café stores | Review alternatives to Orderly | Problem avoidance | Customer – Tony | 26/02 - Reviewing has been given to CS. presented options paper 5/2 (document recorded) 15/02 - Our product teams are reviewing given CS presented options paper 5/2 | Customer Digital Café product team |  | NA | 26/02/24 | Closed |  |  |  | Saloni | 2025-02-10 | 637 | >60 | February | 2024 | #VALUE!
GTS | Digital Workplace Services | 89728098 | 2024-01-04 | Delay in sending the 28DOP to the suppliers | We are not sure what time MP0003 server stopped responding and from when the emails started piling up. What alerting was available on MP0003 and how did support know about the issue? Ascertain if we have appropriate alerting on the post fix server to notify us if emails stop flowing. | Problem identification & Alerting | Saran Rajkumar | 12/02: Saran confirmed that Alerts are working after installing a cert on the email servers. CRQ000000195541 as reference. 05/02: Saran is still working on this 30/10: Followed up with Saran on this action 25/01 - Saran updated that he will come back ASAP on it 19/01 - Followed up with Saran for the status of the automation script 11/01 - Automation script is being worked upon with ETA as 19th 09/01 - Followed up with Saran on the action 04/01 - Manual checks are being done on the post fix server. Systemic alerts are also enabled on the post fix server in vase the queue piles up. Automated scripts will be in place and monitor the queues every 30 minutes - golive 08/01 | Messaging Team |  | NA | 2024-12-02 | Closed |  |  |  | Saloni | 2025-02-10 | 637 | >60 | February | 2024 | #VALUE!
GTS | Digital Workplace Services | 89728098 | 2024-01-04 | Delay in sending the 28DOP to the suppliers | When will the new solution Proof Point be ready? | Permanent Fix | Saran Rajkumar | The target date is end of February 2023. Risk ID 1069 | Messaging Team |  | NA | 2024-04-01 | Closed | 1069 |  |  | Saloni | 2025-02-10 | 637 | >60 | January | 2024 | #VALUE!
GTS | Digital Workplace Services | 89728098 | 2024-01-04 | Delay in sending the 28DOP to the suppliers | The functionalities and policies in the post fix server are not the same as those in the mimesweeper – Info Sec wants a policy and functional comparison between minesweeper and Linux Postfix – Saran to draft a mail | Solution & Recovery | Saran Rajkumar | 11/01 - Saran has sent the comparison mail to Bala 09/01 - Followed up with Saran on the action 04/01 - Manual checks are being done on the post fix server. Systemic alerts are also enabled on the post fix server in vase the queue piles up. Automated scripts will be in place and monitor the queues every 30 minutes - golive 08/01 | Messaging Team |  | NA | 2024-11-01 | Closed |  |  |  | Saloni | 2025-02-10 | 637 | >60 | January | 2024 | #VALUE!
GTS | Digital Workplace Services | 89728098 | 2024-01-04 | Delay in sending the 28DOP to the suppliers | NOTE: All support teams to be made aware to advise and escalate any potential incidents to the relevant channels so that actions can be taken proactively rather than reactively to mitigate impact. | Business & IT Communication | All | Team have been advised on the PIR and to proactively escalate any potential incident and notify relavent stakeholders. | Messaging Team |  | NA | 2024-04-01 | Closed |  |  |  | Saloni | 2025-02-10 | 637 | >60 | January | 2024 | #VALUE!
Customer Channels | Selling Experience | 89723033 | 2024-01-03 | Orders placed in the digital cafes not systemically processing to the kitchens to prepare | Update trouble shooting guide to support incident management in situ | Issue handling/Management | Natasha | The guide has been updated accordingly | Customer Digital Café product team |  | NA | 2024-02-02 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 638 | >60 | February | 2024 | #VALUE!
Customer Channels | Selling Experience | 89723033 | 2024-01-03 | Orders placed in the digital cafes not systemically processing to the kitchens to prepare | QSR to provide root cause following further investigation | Root cause | CS – Phil Swift | 15/02 - Thea from the digital café product team had conduncted a workshop to Counter solutions on 12/02 on the major incident management process wr.t.SLA's 12/12 -What is the SLA to provide incident reports after P1 impact | Counter Solutions - 3rd Party |  | NA | 15/02/24 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 638 | >60 | February | 2024 | #VALUE!
Customer Channels | Selling Experience | 89723033 | 2024-01-03 | Orders placed in the digital cafes not systemically processing to the kitchens to prepare | Investigate error message on screens if the problem with QSR/Kitchen arises again. Evaluate customer journey of error message. | Problem identification & Alerting | CS – Jordan Cope Customer – Paul/ Thea | 15/02 - Thea from the product team has addressed this issue as well on the 12/02 workshop.. These error messages are now being tracked in the RDC board | Counter Solutions - 3rd Party and Customer Digital Café product team |  | NA | 15/02/24 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 638 | >60 | February | 2024 | #VALUE!
Customer Channels | Selling Experience | 89723033 | 2024-01-03 | Orders placed in the digital cafes not systemically processing to the kitchens to prepare | Meeting to review alerts and monitoring of API failures for both incidents. | Problem identification & Alerting | Customer – Adam Smith | 15/02 - We have agreed for the New Relic approach with CS and have reviewed data points to be included in monioring | Customer Digital Café product team |  | NA | 15/02/24 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 638 | >60 | February | 2024 | #VALUE!
Customer Channels | Selling Experience | 89723033 | 2024-01-03 | Orders placed in the digital cafes not systemically processing to the kitchens to prepare | 3rd party representation (QSR) required for MIM’s. | Issue handling/Management | CS - Avalon Smith | 07/01 - CS engineer has spoken and reviewed with QSR and they have confirmed that they are happy to have a representative from QSR join in MIMs when a major incident happens. The representative will be QSR’s VP of Support Solutions . CS to review contract with QSR to understand representation on MIM’s | Counter Solutions - 3rd Party |  | NA | 2024-07-02 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 638 | >60 | February | 2024 | #VALUE!
Customer Channels | Selling Experience | 89723033 | 2024-01-03 | Orders placed in the digital cafes not systemically processing to the kitchens to prepare | What is the root cause for the CS timeout error/ not able to connect to Orderly endpoint. CS to review logs and identify marker. | Root cause | CS – Jordan Cope | The 'root cause' was contained to the CS system exposure, where CS have explained that the latency came from the request, we make to Orderly for stock depletion at the end of a transaction, and the change CS has made now ensures the system is unaffected. Having raised the above with Orderly Senior Management, Orderly have confirmed, having reviewed their application insights with their wider Support team, reviewed and tested the changes CS made, and reviewed the performance of both the stock depletion and transaction completion calls/requests. Orderly, are confident in stating their performance is strong and are at expected levels of performance for the system. | Counter Solutions - 3rd Party |  | NA | 2024-07-02 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 638 | >60 | February | 2024 | #VALUE!
Customer Channels | Selling Experience | 89723033 | 2024-01-03 | Orders placed in the digital cafes not systemically processing to the kitchens to prepare | Decision on store communications approach via Retail comms channel | Business & IT Communication | Customer – Tony Burke | Relevant discussions are done and decision has been made to use the retail comms channel | Customer Digital Café product team |  | NA | 22/01/24 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 638 | >60 | January | 2024 | #VALUE!
Customer Channels | Selling Experience | 89723033 | 2024-01-03 | Orders placed in the digital cafes not systemically processing to the kitchens to prepare | Review stakeholder management comms i.e. wider Hospitality team. | Business & IT Communication | Customer – Laura Whittle | Wider hospitality stakeholder group created. Standard MIM comms process also followed. | Customer Digital Café product team |  | NA | 22/01/24 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 638 | >60 | January | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89753757 | 2024-01-03 | Label printing issues at Ollerton & Stoke DCs | What is our fall back for Ollerton and Stoke? – Other DC’s can use other carriers in the event of an issue. | Problem avoidance | Sam Poultney | 18-01: Currently there is no fallback for both Ollerton and Stoke, however when Ollerton goes live with C&C (w/c 8th Apr) and Mio (Mixed item orders - w/c 11th Mar) Jim Snowden is the Project Manager and DPD vendor will be introduced. Same is expected for Stoke later. | Carrier Team (Customer) |  | NA | 18/01/24 | Closed |  |  |  | Saloni | 2025-02-10 | 638 | >60 | January | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89753757 | 2024-01-03 | Label printing issues at Ollerton & Stoke DCs | Is there any way in which the carrier management team could have proactively spotted this issue - the number if Evri deliveries dropped to 0 – do the CMT have adequate alerting and is it interpreted correctly and quickly? | Problem identification & Alerting | Sam Poultney | 18-01: Yes, Mail alerts are available to the Carrier teams, when Evri deliveries is 0 or in case of any Sorted issue. In the Sorted portal, a ticket reference is also available for these alerts and progress updates | Carrier Team (Customer) |  | NA | 18/01/24 | Closed |  |  |  | Saloni | 2025-02-10 | 638 | >60 | January | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89753757 | 2024-01-03 | Label printing issues at Ollerton & Stoke DCs | Review the current DL Sorted have for stakeholders in Customer who are interested in Sorted incidents and also review the rota for who Sorted should contact at Customer | Supplier and support involvement | Martin Coy/Jackie Martin | 31-01: Martin confirmed that they have agreed for the new rota and contacts 30-01: Followed up with Martin on this action 25-01: There is a call for Martin with Sorted today 18-01: Checked with Martin for update | Service Lead |  | NA | 31/01/24 | Closed |  |  |  | Saloni | 2025-02-10 | 638 | >60 | January | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89753757 | 2024-01-03 | Label printing issues at Ollerton & Stoke DCs | Review how the mule team are supporting us by utilising New Relic and are they experienced enough to interpret the alerts | Problem identification & Alerting | Siva and Kunal/Sai J | 29/02: Sai J and Siva is preparing the checklist for the teams before reaching out to Sorted. It is added to their sprint backlog. 23/02: Followed up with Mule team on the 1 pager guide 19/02: Based on the call it was decided that the WMS Engineering team along with Mule team to prepare a quick guide for label printing issues 15/02: Call is scheduled on 19th to discuss further on this 12/02: Mule team is checking on possibility of usage of the available alerts | WMS and Mule Team |  | NA | 2024-01-03 | Closed |  | CnH-WMS-00196 | Open | Saloni | 2025-02-10 | 638 | >60 | March | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89753757 | 2024-01-03 | Label printing issues at Ollerton & Stoke DCs | Can DC IT teams have access to the New Relic alerting | Problem identification & Alerting | Siva and Kunal/Sai J | 29/02: Sai J and Siva is preparing the checklist for the teams before reaching out to Sorted. It is added to their sprint backlog. 23/02: Followed up with Mule team on the 1 pager guide 19/02: Based on the call it was decided that DC IT teams may not be able to interpret the alerts. Hence WMS Engineering team along with Mule team to prepare a quick guide for label printing issues 15/02: Call is scheduled on 19th to discuss further on this 12/02: Mule team is checking on possibility of usage of the available alerts | WMS and Mule Team |  | NA | 2024-01-03 | Closed |  | CnH-WMS-00196 | Open | Saloni | 2025-02-10 | 638 | >60 | March | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89753757 | 2024-01-03 | Label printing issues at Ollerton & Stoke DCs | During peak trading it took 4 hours to test and deploy the emergency fix – can this be improved upon? | Solution & Recovery | Liam Hogan | 26-01: Liam updated that "No. Due to required risk mitigation steps (issue reproduction, fix analysis and review, unit testing, integration testing and manual testing) and safety protocols currently in place (deployment and regression testing in lower environments prior to Production deployment, deploying the new production instance offline as part of a blue-green deployment followed by customer traffic switch-over) there is no quicker way to provide a service update for this functionality. 18-01: Have sent mail to Liam | Sorted Vendor |  | NA | 26/01/24 | Closed |  |  |  | Saloni | 2025-02-10 | 638 | >60 | January | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89753757 | 2024-01-03 | Label printing issues at Ollerton & Stoke DCs | Can there be a work around or mitigation developed in case the code fails in future from Sorted’s side? | Solution & Recovery | Liam Hogan | 26-01: Liam updated that "No. A critical logic failure in the carrier integration code can render that carrier unavailable. However, an existing feature of the system that can be employed for situations such as this is to allocate_via_service_group, configured with >1 viable carrier service. This strategy will keep allocations moving in such a failure mode. Not directly relevant to the above question however I thought I would mention…. alerting has been configured on Sorted’s side to detect this category of problem sooner. Additional unit testing has also been put in place to prevent this situation. " 18-01: Have sent mail to Liam | Sorted Vendor |  | NA | 26/01/24 | Closed |  |  |  | Saloni | 2025-02-10 | 638 | >60 | January | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89753757 | 2024-01-03 | DC colleagues were unable to print E-com dispatch labels | Liam Hogan from Sorted to provide the root cause in layman’s terms for entry into the PIR | Root cause | Liam Hogan | Complete | Sorted Vendor |  | NA | 2024-03-01 | Closed |  |  |  | Saloni | 2025-02-10 | 638 | >60 | January | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89753757 | 2024-01-03 | DC colleagues were unable to print E-com dispatch labels | What was the description and benefit of the actual change in 2023 | Root cause | Liam Hogan | Complete | Sorted Vendor |  | NA | 2024-03-01 | Closed |  |  |  | Saloni | 2025-02-10 | 638 | >60 | January | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89753757 | 2024-01-03 | DC colleagues were unable to print E-com dispatch labels | Testing for this change did not consider this scenario – action Liam Hogan to review the change plans to see how valid scenarios can be addressed and verified in future. | Problem avoidance | Liam Hogan | Complete - The suite of unit tests for this component were updated accordingly, however no test existed for the scenario which gave rise to the incident. This has now been addressed as part of the correction of error actions for the incident. | Sorted Vendor |  | NA | 2024-03-01 | Closed |  |  |  | Saloni | 2025-02-10 | 638 | >60 | January | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89753757 | 2024-01-03 | DC colleagues were unable to print E-com dispatch labels | Support teams found the issue at 08:07, site reported at 08:30. Teams have now been briefed to raise a log in parallel to their own investigations. | Supplier and support involvement | Nandakumar Sivalingam | Complete | Service Lead |  | NA | 2024-03-01 | Closed |  |  |  | Saloni | 2025-02-10 | 638 | >60 | January | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89753757 | 2024-01-03 | DC colleagues were unable to print E-com dispatch labels | Sorted did not get alerts for this issue at the time. Sorted to review internal alerting for issues such as no service available for a particular carrier – what other indicators are available or need to be developed. | Problem identification & Alerting | Liam Hogan | 09/01 – Complete - The purpose of this review was to identify any way in which the service availability errors could have been detected the moment the incident first occurred. Additional automated monitoring has been configured that traps errors that are emitted from Sorted’s service availability logic for Evri. Any elevation in errors will page the on-call support engineer. | Sorted Vendor |  | NA | 2024-03-01 | Closed |  |  |  | Saloni | 2025-02-10 | 638 | >60 | January | 2024 | #VALUE!
Customer Channels | Selling Experience | 89744704 | 2023-12-20 | WCS Database Unavailable | Jishin and DBA team to review the naming convention to prevent future confusion. Jishin to review where the backups can be stored and what labelling convention should be used. | Problem avoidance | Jishin Jacob | 23/01 - Completed [CM-11095] WCS Live - Oracle Trace Mount Point Creation Update 02/11: We are utilising /backup mount point as DB trace directory for WCS DB. In Customer, we use oracle binary mount point as trace directory as per the standard, however due to high trace file generation, this was routed to /backup since very long time . So, if required we can have a new mount point created with the name ‘oracletrace’ with 500GB size ( Approx cost for 1 TB is £111.30/month) in both primary and standby DB servers. Need platform support help in securing the cost approval. 15/01 - This cost has now been approved and we are waiting for the platform support to provide an appropriate date. Jishin will then provide a CR number after which we can close this action. | Oracle DBA Support |  | NA | 23/01/24 | Closed |  |  |  | Saloni | 2025-02-10 | 652 | >60 | January | 2024 | #VALUE!
Customer Channels | Selling Experience | 89744704 | 2023-12-20 | WCS Database Unavailable | What events actually happened on 13/12 – did the file get fully removed from disk? Jishin to provide Rehan a written summary | Root cause | Jishin Jacob | Update 27/12: CTL-ops team received backup Filesystem usage alert and notified us on Dec 14th 1:30 AM GMT. I checked with the team and found that we did not clear/remove any logs instead compressed large files to bring the usage within threshold. | Oracle DBA Support |  | NA | 27/12/23 | Closed |  |  |  | Saloni | 2025-02-10 | 652 | >60 | December | 2023 | #VALUE!
Customer Channels | Selling Experience | 89744704 | 2023-12-20 | WCS Database Unavailable | Ascertain the reason for deadlocks as the deadlocks is why the log file was filling up quickly | Root cause | Sumitro Chakravarty | 15/01 - Sumitro advised that his team investigated and found that even though there were deadlocks, these deadlocks did not cause a significant increase in tracefile size. The issue was more down to the lack of housekeeping of the logs which has been addressed in other actions. | WCS |  | NA | 15/01/24 | Closed |  |  |  | Saloni | 2025-02-10 | 652 | >60 | January | 2024 | #VALUE!
GTS | Enterprise Technology Platform | 89744704 | 2023-12-20 | WCS Database Unavailable | A log file should be available that shows what files are deleted – as an audit log – Prashant to review if this is already available or possible to set up. | Root cause | Prashant Rowlo | 26/02: The timestamp and user details are now captured as part of the WCS DB audit log. Closed under - CM-11115 19/02: DB linux machines are complete, the remainder ETA is 31/3 Update 03/01 - lan to enable the history in DB linux machines by 31 Jan 2024. Plan to enable the history with timestamp in all prod servers by 31 March 2024 | Cloud Ops team |  | NA | 30/01/23 | Closed |  | CM-11115 |  | Saloni | 2025-02-10 | 652 | >60 | January | 2023 | #VALUE!
Customer Channels | Enterprise Technology Platform | 89744704 | 2023-12-20 | WCS Database Unavailable | Oracle to confirm if the auto restart was not successful as the ASMB was not running or was the restart unsuccessful due to a another reason? | Solution & Recovery | Jishin Jacob | 26/02: The investigations are still onging and requried logs has been shared with Oracle after perfroming a restart as suggested by the vendor and further investigation will be triaged under the product back log - WLCM-2707 15/01 - This test requires a 30 miniute outage and Jishin is working with the platform team to agree a date and time. Update 02/01: We simulated the same scenario in VNP WCS live and DB instance came up in read-write mode as expected. We can start the database via srvctl and sqlplus in Oracle restart environment. During the issue time, DB was brought up via sqlplus, however Oracle restart brings up the DB via srvctl. We verified srvctl configuration but could not find any discrepancies neither Oracle support. Further investigation is in progress with Oracle support. As part of troubleshooting, we will have stop/start WCS live database via srvctl to collect more details. Will follow-up with platform for the same. | Oracle DBA Support |  | NA | 19/02/23 | Closed |  | WLCM-2707 |  | Saloni | 2025-02-10 | 652 | >60 | February | 2023 | #VALUE!
Customer Channels | Selling Experience | 89744704 | 2023-12-20 | WCS Database Unavailable | Why was a running process in production terminated without additional verification? | Solution & Recovery | Prashant Rowlo | Engineers have been briefed to follow standard process for database disk management and to stay within the boundary of responsibility of their team. | Cloud Ops team |  | NA | 20/12/23 | Closed |  |  |  | Saloni | 2025-02-10 | 652 | >60 | December | 2023 | #VALUE!
Customer Channels | Enterprise Technology Platform | 89744704 | 2023-12-20 | WCS Database Unavailable | Alerts should only be routed to the teams who are responsible for taking the action – Prashant to lead a full review of the alerting in his area to ensure alerts are appropriately routed to teams that take actions. | Problem identification & Alerting | Prashant Rowlo | 08/04 - completed 26/02: Awaiting further updates from Cloud team 03/01 - Dotcom database server alerts have been reviewed and changed as required to send tickets directly to respective owners Review of alerts in Non-Dotcom servers is in progress now. - 14 Jan 2024 | Cloud Ops team |  | NA | 2024-08-04 | Closed |  |  |  | Saloni | 2025-02-10 | 652 | >60 | April | 2024 | #VALUE!
Customer Channels | Selling Experience | 89744704 | 2023-12-20 | WCS Database Unavailable | Work with Oracle to understand the behaviour and recreate the scenario in the lower environment e.g: terminating asmb – and observe the result. | Root cause | Jishin Jacob | Recreated same scenario in lower environment. Observed the same error in the alert log and DB instance crashed in VNP WCS live DB but the VNP WCS Live primary DB was auto restarted and came up in read-write mode unlike the primary DB. We are checking this further based on PIR item 6. Closed - moving to action 6 | Oracle DBA Support |  | NA | 2024-02-01 | Closed |  |  |  | Saloni | 2025-02-10 | 652 | >60 | January | 2024 | #VALUE!
Customer Channels | Selling Experience | 89744704 | 2023-12-20 | WCS Database Unavailable | Why is there a frequent increase in file space? Jishin review storage space and see if we can increase it. | Problem avoidance | Jishin Jacob | 02/01: Its due to high trace file generation due to frequent deadlocks. Deadlock count is approximately between 4.5k to 5.5K per day. We will share the deadlocks SQLs to Sumitro for further check. Closed and moving to action 11 | Oracle DBA Support |  | NA | 2024-02-01 | Closed |  |  |  | Saloni | 2025-02-10 | 652 | >60 | January | 2024 | #VALUE!
Customer Channels | Selling Experience | 89744704 | 2023-12-20 | WCS Database Unavailable | Lead root cause investigation of why storage limits are being breached frequently. Review full root cause of all deadlocks. | Root cause | Sumitro Chakravarty | 15/01 - Sumitro advised that his team investigated and found that even though there were deadlocks, these deadlocks did not cause a significant increase in tracefile size. The issue was more down to the lack of housekeeping of the logs which has been addressed in other actions. | WCS |  | NA | 15/01/24 | Closed |  |  |  | Saloni | 2025-02-10 | 652 | >60 | January | 2024 | #VALUE!
Customer Channels | Selling Experience | 89744704 | 2023-12-20 | WCS Database Unavailable | Review how we can limit the size of the trace file logs and ensure it writes to disk up to a limit and then rotates back to the start. | Problem avoidance | Jishin Jacob | 23/01 - Completed - We have limited the trace file growth to 500MB in production servers 02/01: We can set the below parameter to limit the trace file size to 200MB max. This helps to create a new trace file when it reaches 200MB. Implemented in VNP WCS live DB, last week. CR to be raised and deployed in production post confirmation from application team. MAX_DUMP_FILE_SIZE=200MB 15/01 - This was tested and app DBA advised we need to set this to 500 MB. A slot needs to be agreed but this is an online change so no outage required. Waiting for a slot from platform support. | Oracle DBA Support |  | NA | 23/01/24 | Closed |  |  |  | Saloni | 2025-02-10 | 652 | >60 | January | 2024 | #VALUE!
Customer Channels | Enterprise Technology Platform | 89744704 | 2023-12-20 | WCS Database Unavailable | Review engineer’s access levels – Should a sudo ID be used or a name.name to carry out actions? | Solution & Recovery | Prashant Rowlo | 08/04 - Completed 26/02: Awaiting further updates from Cloud team 03/01 - Add name.name accounts into group. Reiterate the account usage practices to the team. Prioritise database servers for personal logins - 31 Jan 2024 | Cloud Ops team |  | NA | 2024-08-04 | Closed |  |  |  | Saloni | 2025-02-10 | 652 | >60 | April | 2024 | #VALUE!
Customer Channels | Selling Experience | 89744704 | 2023-12-20 | WCS Database Unavailable | Review and understand the circumstances where failover should happen, and which conditions were not met in this case. Validate that failover works where the scenarios are valid. Review the overall resilience of the VM and the DB. | Problem avoidance | Jishin Jacob | Update 23/01 - Updated in the backlog ticket : MCIP-3686 to track this further. Update 02/01: The observer will initiate failover to the target standby if and only if ALL of the following conditions are true. •Observer is running – TRUE •observer and the standby both lose contact with the primary - TRUE •observer is still in contact with the standby - TRUE •failover threshold timeout has elapsed - TRUE •durability constraints are met – FALSE During the issue time, all the above conditions were true except one as the logs says standby DB may not be synchronized with primary. As per Oracle support we will have to increase the value of TransportDisconnectedThreshold’. Currently it is 30 seconds which is default value. Further investigation is in progress. Update 15/01: This action will start after action 67 - Jishin to raise a backlog | Oracle DBA Support |  | NA | 23/01/24 | Closed |  |  |  | Saloni | 2025-02-10 | 652 | >60 | January | 2024 | #VALUE!
Customer Channels | Enterprise Technology Platform | 89744704 | 2023-12-20 | WCS Database Unavailable | What were all the ways the incident was detected? Can we see if we can get an alert for the ASMB process and other critical processes not running? | Problem identification & Alerting | Jishin Jacob | Update 11/04 Prashant has raised a CR to capture the command history (with timestamp) for all Oracle databases in .com in Production not just WCS. This has been deployed into production. Update 23/01: Discussed with Prasanth Rowlo and he confirmed they are raising a production change to start capturing the command history along with timestamp this week. Update 02/01: We have 10 critical background processes in Oracle and ASM instances. Process death of any of these processes will cause DB/ASM instance crash immediately. This process death will be captured in the alert log too indicating that which process was terminated. In our case also, we could clearly see that ASMB process was died; but we were not aware of ‘how did ASMB died?”. So, if we enable alerting for these 10 processes; we will get 11 critical alerts (10 process down and 1 DB target down) in case if we bring down the DB or in case of any DB instance crash. However, this won’t help us to avoid the issue or help much unless we check the alert log which we do it anyway. But any alerting or detailed auditing that helps to notify the team in the events of manually process termination/file deletion will help to identify the root cause easily. Jishin to speak with CTL Ops Prashant to see if any alerting can be implented that notify if any processes are being terminated. | Oracle DBA Support |  | NA | 2024-11-04 | Closed |  |  |  | Saloni | 2025-02-10 | 652 | >60 | April | 2024 | #VALUE!
Customer Channels | Selling Experience | 89744704 | 2023-12-20 | WCS Database Unavailable | There was no continual running commentary of the incident – Hisham and Elaine to review how we can summarise in the teams channel regularly | Issue handling/Management | Hishsam/Elaine | 26/02:We agreed to use the Tech Operations channels for providing updates | Service Management |  | NA | 26/02/24 | closed |  |  |  | Saloni | 2025-02-10 | 652 | >60 | February | 2024 | #VALUE!
Customer Channels | Service Experience | 89739134 | 2023-12-14 | Sparks coat promotion cancelled | During the MIM call there was concern about who is responsible for sending the wide Retail business comms – the service lead prepares the store comms and updates the various business Teams groups however not all stakeholders get the communications. Explore a way where all key stakeholders can be made aware of the issue. | Business & IT Communication | Laura Whittle | 19/01: Rehan spoke with Laura who advised that the relevant stakeholders have been added to the Teams service health chat and this satisfies the action. 14/12: Laura to work with various teams and devise a plan | Service leads - Service experience |  | NA | 19/01/24 | Closed |  |  |  | Saloni | 2025-02-10 | 658 | >60 | January | 2024 | #VALUE!
Customer Channels | Service Experience | 89739134 | 2023-12-14 | Sparks coat promotion cancelled | Add the people that are needed to the existing store health chat. | Business & IT Communication | Laura Whittle | 02/01: Completed | Service leads - Service experience |  | NA | 2024-02-01 | Closed |  |  |  | Saloni | 2025-02-10 | 658 | >60 | January | 2024 | #VALUE!
Customer Channels | Service Experience | 89739134 | 2023-12-14 | Sparks coat promotion cancelled | Implement some validation that displays a prompt in the promotions platform (POS staging) to obtain user confirmation that they want to carry out this step. The DDS report is not showing deleted promotions and should be part of the CR being worked on by Seeva. | Problem avoidance | Seeva | 19/12 - Seeva's team has now created a Jira for promotion screen updates and asked team to review it before passing it to Flooid to schedule this work. Showing deletd promotions in the DDS report has already been done. [POSF-223] Promotion Status - Enhancements and additional User confirmation to avoid manual errors | POS |  | NA | 19/12/23 | Closed |  | POSF-223 |  | Saloni | 2025-02-10 | 658 | >60 | December | 2023 | #VALUE!
Customer Channels | Service Experience | 89739134 | 2023-12-14 | Sparks coat promotion cancelled | Try and replicate the steps of what was being done to the promotion yesterday to see if any of these steps can lead to cancellation of the promotion | Root cause | Seeva/Vaishali | NA/12: Coatprogress | POS |  | NA | 14/12/23 | Closed |  |  |  | Saloni | 2025-02-10 | 658 | >60 | December | 2023 | #VALUE!
Customer Channels | Selling Experience | 89739134 | 2023-12-14 | Sparks coat promotion cancelled | Address the gap between Tech and .com comms Discuss with relevant stakeholders between .com and Tech Sathish/Dinesh/Rehan/Hisham | Business & IT Communication | Rehan Siddiqui/Hisham | 19/01: A meeting was held in which we agreed that the reponsibility for MIM comms and business comms will be dealt with on a case by case basis. | Multiple Owners |  | NA | 22/01/24 | Closed |  |  |  | Saloni | 2025-02-10 | 658 | >60 | January | 2024 | #VALUE!
Customer Channels | Customer Engagement | 89739134 | 2023-12-14 | Sparks coat promotion cancelled | Business units should give sufficient notice of promotion changes. Investigate if there is anything we can do to identify the larger categories in advance of the promotions being set and made live. Mhorag/Gill to review the promotions amendment process in line with the Sparks team. | Problem avoidance | Gillian Oconnor | The issue was that the BU missed offer detail from the brief. In final offer testing we identified some lines in the WCS promotion that hadn't been added to the beanstore promotion (set up is done separately for the 2 systems). So we went back to amend the Beanstore promotion. This was the day before the offer went live so last minute pressure was a factor. 2 things to improve: Minimise reliance on BUs to supply stroke/UPC information. We have been working on an automated source since Q2 which enables us get the data ourselves - project is still being worked on and in testing This offer was set up late, so testing and QA checks were late, due to detail being agreed with the BU late and then clash with set up of Black Friday offers, making it a very busy time for offer set up. Unique to 12 days because for other offers we have managed lead times. One for the 12 Days PIR to understand offer agreement deadlines pre Black Friday The above is all being tracked in the 12 days PIR led by the product teams. | Loyalty team |  | NA | 15/01/24 | Closed |  |  |  | Saloni | 2025-02-10 | 658 | >60 | January | 2024 | #VALUE!
Customer Channels | Service Experience | 89739134 | 2023-12-14 | Sparks coat promotion cancelled | What can we do in the next two weeks to protect promotions and to highlight when changes occur? | Problem identification & Alerting | Seeva/Bala | 19/12: Bala confirmed that they have agreed to add the status of promotions which are touched in a day, to business team as part of overnight feed 14/12: Recently changed promotions will be shared with the business teams, who will then be able to verify daily. Use the same DDS group DL | POS |  | NA | 19/12/23 | Closed |  |  |  | Saloni | 2025-02-10 | 658 | >60 | December | 2023 | #VALUE!
Customer Channels | Service Experience | 89739134 | 2023-12-14 | Sparks coat promotion cancelled | Explore an easier and quicker way of obtaining the financial impact to retail/store issues through loss of potential sales. | Impact analysis | Laura Whittle | 19/03: Laura has spoken with the checkou team and they have advised that there are too many variables involved to be able to get a good base line finacial impact - also depending on the issue at hand. Issue therefore closed. 12/03: Laura and I have spoken several times on this and she is looking at options 19/02: Laura will speak to Bala and Sam Clements to see if there are any options. 19/01: Laura advised that she needs to start this but needs to discuss about who are the correct stakeholders. 02/01: Laura advised that she will raise this in a team huddle to see how this action can be started. | Service leads - Service experience |  | NA | 19/03/24 | Closed |  |  |  | Saloni | 2025-02-10 | 658 | >60 | March | 2024 | #VALUE!
GTS | Enterprise Technology Platform | 89731236 | 2023-12-13 | Hardware failure impacting various DC operations and Retail Dashboard report | Did we have the right alerting in place for the memory module? | Problem identification & Alerting | Dharmaraj Balasubramanian | 13/12: An alert was received at 08:15 highlighting the hardware failure and the teams initiated the usual recovery process. It has been confirmed that there’s no feasibility of configuring any intermediate alerts for hardware failures. | Wintel |  | NA | 13/12/23 | Closed |  |  |  | Saloni | 2025-02-10 | 659 | >60 | December | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89731236 | 2023-12-13 | Hardware failure impacting various DC operations and Retail Dashboard report | There was significant delay in the consolidation of list of impacted VM’s. How can this be addressed? | Impact analysis | Dharmaraj Balasubramanian | 13/12:The no.of Vm’s hosts residing on a host is dynamic and it keeps on changing every now and then. Thus we cannot maintain a static repository with the no.of Vm’s as per esxi hosts. During the incident, we had to run a report to get the impacted hosts followed by mapping them with the impacted applications. Therefore, it usually required 10-15 mins of time to get the report of impacted Vm’s | Wintel |  | NA | 13/12/23 | Closed |  |  |  | Saloni | 2025-02-10 | 659 | >60 | December | 2023 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89731236 | 2023-12-13 | Hardware failure impacting various DC operations and Retail Dashboard report | Ensure we send the right communications to the DC’s as soon as we identify any impacted service to the warehouses. | Business & IT Communication | WMS | 13/12: As soon as we got the list of impacted Vm’s. WMS team took the responsibility to communicate to the Dc’s on the incident. | WMS |  | NA | 13/12/23 | Closed |  |  |  | Saloni | 2025-02-10 | 659 | >60 | December | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89731236 | 2023-12-13 | Hardware failure impacting various DC operations and Retail Dashboard report | Ensure we follow the right steps while performing the Cluster restarts. Perform health checks on both the active and passive servers for stability before restarting any server during such hardware failure. | Problem avoidance | Sathish Selvapillai | 21/12: Yes, this has been notified to teams and added in health check process 13/12: During the Cluster restart for Milton Keynes server, the passive server was part of the impacted Vm’s and it was restarted for recovery. But as it was restarted the active server also went for a toil resulting in a downtime on 3 mins for the MK DC. Teams have agreed to have the required steps documented as part of the SOP. | unix |  | NA | 21/12/23 | Closed |  |  |  | Saloni | 2025-02-10 | 659 | >60 | December | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89731236 | 2023-12-13 | Hardware failure impacting various DC operations and Retail Dashboard report | During the incident, it was identified that the CD MQ server was named as Foods PSA. Due to this it was not prioritized as part of the CD operations recovery. Check on the feasibility to extract the dump of the hosts and its associated Vm’s and to send it across to the application teams for validations. Validate the CMDB for the right naming conventions of the Vm’s. Cross -check on the CMDB mapping and Vm servers – On the naming conventions | Problem avoidance | Elizabeth Golder | 28/03: Liz has sent a reminder to all TEMs that the CMDB team are only responsible for maintaining data that is discoverable automatically on the in-scope devices. Anything outside of this like app to server/database/middleware mapping is the responsibility of the application teams. 08/03: Liz confirmed that the team is working on the data 24/02: Followed up with Elizabeth and Infra leads 20/02: Elizabeth confirmed on mail that they will validate the infra data 19/02: It was agreed in the call that CMDB team will be involved to validate the data across the portfolios 15/02: Call scheduled on 16/02 with Elizabeth and Rehan 12/02: Elizabeth will loop me to the mail sent to product teams 05/02: Checked with Elizabeth if she has got the CMDB list and shared with the concerned application teams 18/01: Have followed up with Elizabeth 14/01: Have checked with her on the latest reports and the next steps 11/01: Have followed up with Elizabeth on the report and asked if a backlog can be created 08/01: Elizabeth has got the report from the CMDB to share with all the TEM for them to validate 04/01: Followed up with Elizabeth on the status of the action 21/12: Elizabeth is OOO till 2nd Jan, have reached out to Jafar and awaiting updates 13/12: During the incident, it was identified that the CD MQ server was named as Foods PSA. Due to this it was not prioritized as part of the CD operations recovery. Check on the feasibility to extract the dump of the hosts and its associated Vm’s and to send it across to the application teams for validations. | Service Lead - GTS |  | NA | 28/03/24 | Closed |  |  |  | Saloni | 2025-02-10 | 659 | >60 | March | 2024 | #VALUE!
GTS | Enterprise Technology Platform | 89731236 | 2023-12-13 | Hardware failure impacting various DC operations and Retail Dashboard report | Feasibility to avoid any manual restart of the cluster for swift recovery. | Solution & Recovery | Sathish Selvapillai/ Jafar | 21/12: Redhat also said its up to us to decide on auto start - this is not recommended considering the data loss 13/12: There was a delay in the recovery as most of the clusted in the affected Vm’s required a manual restart. But team did confirm that the design of manual restart is in place purposely to avoid any performance degradations. Still, AIX to double check with Redhat on suggestions or feasibilities to avoid the manual restart of cluster. | Unix |  | NA | 21/12/23 | Closed |  |  |  | Saloni | 2025-02-10 | 659 | >60 | December | 2023 | #VALUE!
GTS | Enterprise Integration | 89731236 | 2023-12-13 | Hardware failure impacting various DC operations and Retail Dashboard report | Ensure we perform the end to end impact analysis as soon as we identify the impacted service. During the incident, few MQ servers were impacted and the cluster restarts were done accordingly later upon investigation teams requested for an outage to restart the mule services and it was not encouraged during an incident. | Impact analysis | Rajasekar Subramanian/Siva | 21/12: Team had revalidated the SOP to follow the steps 13/12: Teams to proactively perform the end-to-end validations of the impact when their service is impacted. Have the right documentation in place to cover the steps accordingly. | Integration Services |  | NA | 21/12/23 | Closed |  |  |  | Saloni | 2025-02-10 | 659 | >60 | December | 2023 | #VALUE!
Foods | Foods Supply Chain | 89721258 | 2023-12-11 | Allocation failures across all Foods depots. | SDP team to follow the usual incident procedure and follow the relevant escalation route. | Problem identification & Alerting | Michael Webb/ Joey/ Matt | 04/01 - We have agreed with SDP team to follow the regular incident process and the escalation matrix during any major issues with allocations. 02/01 - This is yet to be dicussed with the Supply and Demand planners. Previous update 11/12: The other way the impact could have been identified if the SDP team had raised a ticket against each request to share the allocation data. | SDP |  | NA | 2024-04-02 | Closed |  |  |  | Saloni | 2025-02-10 | 661 | >60 | February | 2024 | #VALUE!
Foods | Foods Supply Chain | 89721258 | 2023-12-11 | Allocation failures across all Foods depots. | Arrange a session between FOA Tech and Relex to identify an effective way of working together whilst investigating the issue. | Solution & Recovery | Matt, Joey Ocansey and Andrew | 04/02 - discussion have been made between the accenture team and Matt to address this.. Also a plan has been devised to conclude the working ways after the pogram closer and it will be log term action which will also be addressed 02/01 - PM yet to get an update in the session status.. 11/12: To ensure that the analysis is performed in an efficient manner across the teams, a session will be arranged to understand the E2E technology of the relevant systems involved. | FOA |  | NA | 2024-04-02 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 661 | >60 | February | 2024 | #VALUE!
Foods | Foods Supply Chain | 89721258 | 2023-12-11 | Allocation failures across all Foods depots. | Hypercare monitoring on the knock-on impact or any other issues across any other functionalities in the supply chain estate due to the bug. | Problem avoidance | Andrew Goslin/ Promoth Kumar/James Lewis | 02/01 2024 - Hypercare has been in place thorougout the peak and no issues were observed post that 11/12: This will be performed across all layers Across in Tech – Relex, Quantum etc | Relex |  | NA | 2024-02-01 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 661 | >60 | January | 2024 | #VALUE!
Foods | Foods Supply Chain | 89721258 | 2023-12-11 | Allocation failures across all Foods depots. | It took time to understand the scale of the impact. Configure an alert to identify any products with zero allocation issues? Engagement of Tech in a timely manner for an effective impact analysis and root cause investigation. | Solution & Recovery | Promoth Kumar | 11/12An email notification has been configured which will reflect the total number of products vs the product with missing allocation. This will help to identify the scope of the impact. In future scenarios, tech team should be engaged in a timely manner across FOA tech and Relex to analyse the scope of impact. | Relex |  | NA | 2023-11-12 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 661 | >60 | December | 2023 | #VALUE!
Foods | Foods Supply Chain | 89721258 | 2023-12-11 | Allocation failures across all Foods depots. | Why was the SCRD bug not identified during testing in non-prod. | Problem avoidance | Pushparaj Rajendran | 19/12 - The issue has been replicated in non-prod The scenarios for effective testing has been captured and implemented at supply chain area to ensure all other patterns are captured across the dependent systems. | SCRD |  | NA | 19/12/23 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 661 | >60 | December | 2023 | #VALUE!
Customer Channels | Customer Engagement | 89716033 | 2023-12-08 | Promotional badges still showing on furniture PLPs after promotion has ended | Resolve Certificate error identified in the Delta Feed log - The Certificate error stopped the Full Feed triggering automatically. The certificate error was caused by a connection failure. | Permanent Fix | Saumya Khandelwal | Certificate issue has been resolved by the team | .com |  | NA | 19/12/23 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 664 | >60 | December | 2023 | #VALUE!
Customer Channels | Customer Engagement | 89716033 | 2023-12-08 | Promotional badges still showing on furniture PLPs after promotion has ended | Run Delta Feeds via generic user- Alerting only triggers if the Full Feed Fails. Need to see whether it is possible to trigger an alert if the Full Feed does not start. This will then kick-start the escalation process as per the below actoin | Permanent Fix | Saumya Khandelwal | teams have the right processing checks in place and in case of Feed failures and if they are not triggered on time - Alerting has been set-up | .com |  | NA | 19/12/23 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 664 | >60 | December | 2023 | #VALUE!
Customer Channels | Customer Engagement | 89716033 | 2023-12-08 | Promotional badges still showing on furniture PLPs after promotion has ended | Review of Alerting for Full Feed | Problem identification & Alerting | Saumya Khandelwal | Alerting has been set-up | .com |  | NA | 19/12/23 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 664 | >60 | December | 2023 | #VALUE!
Customer Channels | Customer Engagement | 89716033 | 2023-12-08 | Promotional badges still showing on furniture PLPs after promotion has ended | Previous update Review process of contacting S&S team out of hours | Issue handling/Management | Essam Nabil | 02/01 - Process has been finalized and it has been 22/01 - Teams have agrred to include all incidents and BAUs process to be reviewed, and it is being disucssed across the board. 02/01 - Action owner yet to conclude on the escalation matrix Clarify process for contacting people out-ofhours: • Check out-of-hours rota • Check Pager Duty Integration • Check escalation path if someone cannot be contacted.Need to ensure that S&S team are alerted automatically if the feed does not run. (refer to the above certificate error action) | Search and Sort Team |  | NA | 2024-02-02 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 664 | >60 | February | 2024 | #VALUE!
Customer Channels | Customer Engagement | 89716033 | 2023-12-08 | Promotional badges still showing on furniture PLPs after promotion has ended | Be able to assess full impact early in the incident | Impact analysis | S&S team | 22/01 - The incident process has been defined and default impact statements have been agreed. 02/01 - Action owner yet to update on the below action. Previous update: Team needs to be able to link a technical problem with business impact. This allows the correct severity of incident to be raised and business teams can be given clear guidance on impact. | .com |  | NA | 22/01/24 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 664 | >60 | January | 2024 | #VALUE!
Customer Channels | Customer Engagement | 89716033 | 2023-12-08 | Promotional badges still showing on furniture PLPs after promotion has ended | Investigate why the Full Feed could not be run via the UI - Need to investigate why the Full Feed could not be run via swagger UI. Also need to have this activity as part of a runbook | Problem avoidance | Saumya Khandelwal | Teams had worked on the swagger issue -seems like the issue was not reproducible and as It is a third party tool teams could not explore more on the issue. But they are confident that the issue will not re-occur and it as been stable since the incident. | .com |  | NA | 19/12/23 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 664 | >60 | December | 2023 | #VALUE!
Customer Channels | Customer Engagement | 89716033 | 2023-12-08 | Promotional badges still showing on furniture PLPs after promotion has ended | Cache clear strategy - Need clear strategy for when a cache clear should be carried out. i.e. who can give authorization for this. Given that it is a Sev 1 or 2, it is deemed to be business critical therefore in theory, it should merit a cache clear but the risk of doing this needs to be discussed with the relevant engineering manager before a cache clear is carried out. | Solution & Recovery | Service Leads | 22/01 - This has been taken care by the relevant engineering manager. 02/01 - Action owner yet to conclude on the escalation matrix | .com |  | NA | 22/01/24 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 664 | >60 | January | 2024 | #VALUE!
Customer Channels | Customer Engagement | 89716033 | 2023-12-08 | Promotional badges still showing on furniture PLPs after promotion has ended | Escalation process between Onyx and S&S teams -Need to be clear where to post updates and general commentary during an incident. Elaine to set up a meeting and include Steve Warren , Himanshu Khanna plus Service Leads | Issue handling/Management | Christopher Tomlinson | 22/01- A process has been agreed on the escalation methods. 02/01 - Action owner yet to update the status of the call | .com |  | NA | 22/01/24 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 664 | >60 | January | 2024 | #VALUE!
Customer Channels | Customer Engagement | 89716033 | 2023-12-08 | Promotional badges still showing on furniture PLPs after promotion has ended | Incident communication between business and tech | Business & IT Communication | Elaine Hawthorn | 22/01 - As this issue is a frequent issue the communications are happening as expected on a frequent interval. Thus the communications are inline as requried. 02/01 - Action owner yet to update on the action | .com |  | NA | 22/01/24 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 664 | >60 | January | 2024 | #VALUE!
Customer Channels | Customer Engagement | 89716034 | 2023-12-08 | Promotional badges still showing on furniture PLPs after promotion has ended | Bloomreach Delta Feed - Issues with running the Delta Feeds highlighted the need to check various limits (e.g. Indexing limits/number of products etc) with Bloomreach . Christo to pick up with Bloomreach | Problem avoidance | Christopher Tomlinson | 02/01 - processing checks are in place for the delta feeds now and and we have the processing check for the delta feed that runs frequently during business hours and less frequently during non business hours. | Search and Sort Team |  | NA | 2024-02-02 | Closed | NA | NA | NA | Saloni | 2025-02-10 | 664 | >60 | February | 2024 | #VALUE!
Customer Channels | Selling Experience | 89723808 | 2023-12-08 | Order decline on the Customer Website | Android app start up and sign in journeys need refactoring to rationalise number of API calls, remove duplicates and avoid race conditions | Permanent Fix | Matt Magee | 29/10: The change as implemented to fix the issue | Andriod App |  | NA | 29/01/24 | Closed |  |  |  | Saloni | 2025-02-10 | 664 | >60 | January | 2024 | #VALUE!
Customer Channels | Selling Experience | 89723808 | 2023-12-08 | Order decline on the Customer Website | If we could have identified the DB lock quicker due to App re-tries (started with Apigee platform investigation), Action to look back on the every incoming | Problem identification & Alerting | Sumitro Chakravarty | 12/02: DB restarts has been planned on 14th Feb. further action will be tracked under the product backlog - WLCM-2707 29/10: DBA team has simulated the same scenario in VNP WCS live and the DB instance came up in read-write mode as expected. We can start the database via srvctl and sqlplus in Oracle restart environment. During the issue time, DB was brought up via sqlplus, however Oracle restart brings up the DB via srvctl. DBA team have verified srvctl configuration but could not find any discrepancies and neither could Oracle support. Further investigation is in progress with Oracle support. As part of troubleshooting, an outage is requried to stop/start WCS live database via srvctl to collect more details, the testing is being plan on 19/02 22/01: Followed up with the service lead awaiting further updates this is in progress | WCS Lifecycle |  | NA | 2024-12-02 | Closed |  | WLCM-2707 |  | Saloni | 2025-02-10 | 664 | >60 | February | 2024 | #VALUE!
Customer Channels | Selling Experience | 89723808 | 2023-12-08 | Order decline on the Customer Website | Android batch push throttle (load testing on WCS, Identity APIs) to be determined for future campaigns & Communicate to Marketing Team | Problem avoidance | Kit Barclay | This action is complete | Andriod App |  | NA | 2023-08-12 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 664 | >60 | December | 2023 | #VALUE!
Customer Channels | Selling Experience | 89723808 | 2023-12-08 | Order decline on the Customer Website | The Identity team to make sure that once they are alerted and confirm user impact, they notify the Ops team through the Tech Ops (ReaIT Ops) channel | Problem identification & Alerting | Simon A | This action is complete | Indentity team |  | NA | 2023-08-12 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 664 | >60 | December | 2023 | #VALUE!
Customer Channels | Selling Experience | 89723808 | 2023-12-08 | Order decline on the Customer Website | Android App Improved error handling is required to prevent the continuous re-tries | Permanent Fix | Matt Magee | A risk has been raised again it to mitigate the retry as it is causing wider impact | Andriod App |  | NA | 22/01/24 | Closed | 2106 |  |  | Saloni | 2025-02-10 | 664 | >60 | January | 2024 | #VALUE!
Customer Channels | Selling Experience | 89723808 | 2023-12-08 | Order decline on the Customer Website | Increased frequency of blocking session check in DB from 15 minutes to 5 minutes and reduced threshold from 10 to 5 for now | Problem identification & Alerting | WCS Lifecycle Team | This action is complete | WCS Lifecycle |  | NA | 2023-08-12 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 664 | >60 | December | 2023 | #VALUE!
Customer Channels | Selling Experience | 89723808 | 2023-12-08 | Order decline on the Customer Website | Thread count reaches 80% of maximum, will get an alert | Problem identification & Alerting | WCS Lifecycle Team | This action is complete | WCS Lifecycle |  | NA | 2023-08-12 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 664 | >60 | December | 2023 | #VALUE!
Customer Channels | Selling Experience | 89723808 | 2023-12-08 | Order decline on the Customer Website | Setup an alert for customer session v1 response time at 99th percentile - if this is above 5 secs for 1 minute, it will create an incident | Problem identification & Alerting | WCS Lifecycle Team | This action is complete | WCS Lifecycle |  | NA | 2023-08-12 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 664 | >60 | December | 2023 | #VALUE!
Foods | Foods Supply Chain | 89718748 | 2023-12-07 | Tills trading at reduced prices across the Irish stores | Identify a POC on the ground for stores issues and feedback. (Ireland only) | Business & IT Communication | Joey Ocansey | 18/12: It has been agreed to follow the standard Retail comms process and the usual stakeholder comms. Store comms can be incorporated in valid scenarios. | Foods |  | NA | 18/12/23 | Closed |  |  |  | Saloni | 2025-02-10 | 665 | >60 | December | 2023 | #VALUE!
Customer Channels | Selling Experience | 89718748 | 2023-12-07 | Tills trading at reduced prices across the Irish stores | Ensure SOP for executing Scan and Shop switch off and Switch on is known/circulated + the correct approval/awareness process needed to execute this during trading hrs. (Mobile and Device considerations). Confirm if we can switch off and on Scan and Shop device based on region. | Solution & Recovery | Hisham Khalid/ Ramshankar Ramasamy | 12/01: It has been confirmed that the Scan and Shop device can be turned off provided the store number is known. We have confirmed Scan and Shop (Mobile) app can be switched on and off regionally. 18/12: The feasibility to turn off Scan & Shop – device based on regions is being checked. Note: It was confirmed that only one IE store has the Scan and Shop device. | Scan & Shop |  | NA | 2024-12-01 | Closed |  |  |  | Saloni | 2025-02-10 | 665 | >60 | January | 2024 | #VALUE!
Customer Channels | Service Experience | 89718748 | 2023-12-07 | Tills trading at reduced prices across the Irish stores | Feasibility of manually updating the VOD database or simultaneous updates on VoD and POS. | Problem avoidance | Balaguru Subramanian | 12/02: The change has been deployed into prod successfully. 12/01: The plan to update the VOD prices manually has been developed, testing is ongoing. ETA to deploy in prod - 02/02. 18/12: There is a feasibility of the updating the prices manually in VoD. Testing to be performed and aim to deploy in prod by approx 1st week of Jan 2024. | POS |  | NA | 2024-12-02 | Closed |  |  |  | Saloni | 2025-02-10 | 665 | >60 | February | 2024 | #VALUE!
Customer Channels | Service Experience | 89718748 | 2023-12-07 | Tills trading at reduced prices across the Irish stores | Are there any options for improving the speed and accuracy of in-day correction into POS (SAP data, Validation/comparison with 'reference data/day', execution into POS). Alerting to be configured during an instance of high volume of price changes in POS. | Problem identification & Alerting | Seevaratam Sivasurath | 12/01: Alerts were tested with the valid scenarios in non-prod and confirmed to be working fine. 18/12: Alerting has been configured in POS, testing in progress with the valid scenarios. A sev1 alert will be triggered to VoD and DS team. Vivek and Seeva to work with Richard Wrightwells to design a long-term solution for price and promotion alignment and visibility across systems | POS |  | NA | 2024-12-01 | Closed |  |  |  | Saloni | 2025-02-10 | 665 | >60 | January | 2024 | #VALUE!
Customer Channels | Service Experience | 89718748 | 2023-12-07 | Tills trading at reduced prices across the Irish stores | The shelf edge tickets were not impacted as prices are fed from ES (Enterprise Services) system. Review the possibility of ES sending the feeds to POS – to ensure the prices matches across tills and tickets. | Permanent Fix | Seevaratam Sivasurath | 18/12: As per confirmation, the best solution to avoid these issues in future is to sync the logic behind the data sent to ECS and POS. A backlog RPOS-10857 is raised; however this needs to be prioritized and further discussion to be put forward. | POS |  | NA | 2024-12-01 | Closed |  | RPOS-10857 |  | Saloni | 2025-02-10 | 665 | >60 | January | 2024 | #VALUE!
Foods | Foods Supply Chain | 89718748 | 2023-12-07 | Tills trading at reduced prices across the Irish stores | There was a discrepancy between the prices in POS and ECS system resulting in customer and colleague dissatisfaction. Prioritize the backlog to develop and end to end pricing and promotion dashboard to spot and alert any conflicts. | Solution & Recovery | David Davis/Vivekananda Biradavolu | This is a long pending action and will be prioritized under a backlog | P&P |  | NA | 2023-08-12 | Closed |  | PAP-6593 |  | Saloni | 2025-02-10 | 665 | >60 | December | 2023 | #VALUE!
GTS | Enterprise Integration | 89718748 | 2023-12-07 | Tills trading at reduced prices across the Irish stores | Review the Datastage system logic for Ireland pricing and set the correct priority to ensure these scenarios do not impact all the stores. Also ensure, UK stores are not at a risk of similar issue. | Permanent Fix | Srikanth Kathula | 16/04: CRQ199910 has been approved and the logic was deployed successfully into production on 16/04 - 06:00 BST 11/04: Discussion is still ongoing with POS Team and the teams are clarifying their queries. Planning to get the approval today so that the tech teams will present the CR in cab tomorrow and deploy on Monday. 05/04: The testing is complete, DS team is awaiting the review of the test results and approval from POS team. Sreeraj will chase up with POS, ETA to deploy in prod is 11/04. 14/03: The fix was successfully tested in lower environment, the plan is to deploy into prod on 18/03 12/01: Datastage team confirmed that they are unable to deploy the code fix due to DRS (Deposit Return scheme) changes go live due to its business criticality. However, the plan is to deploy the fix by mid of Feb. 18/12: A logic will be added to the datastage location file creation job to address the scenarios with empty/incorrect pricelist and sales organisation data for IE stores. This will reject any problematic store before generation of the location reference file in datastage and thereby send to POS. Joey, Sreeraj & Vivek to discuss on the different scenarios. Discussions in progress with Foods architect to set the correct priority in the DS logic to arrest such issues efficiently without causing a wider impact. Ireland prices are sent on a country level. Explore the possibility of sending the prices on a store level – Long term | DS Support |  | NA | 16/04/24 | Closed |  |  |  | Saloni | 2025-02-10 | 665 | >60 | April | 2024 | #VALUE!
Business Process Services | Business Process Services | 89718748 | 2023-12-07 | Tills trading at reduced prices across the Irish stores | Find out if there is an emergency POC for Centralised Ops and Masterdata team for an efficient call out process during any MI for out of hours support. | Solution & Recovery | Jaturson & Joey Ocansey | 12/02: The POC/escalation matrix was shared on the newsletter twice through peak - one prior to the incident, and another post the incident as a reminder 18/12: The POC from the Centralised Ops trading team to be shared as part of the newsletter. On the other hand, there is no BSC availability outside of business hours apart from through the Business Continuity Planning (BCP) process. Darren is working with the BCP team to determine what type of incident could be classed as BCP. Joey will check with Remko and Ben on the Master data contacts. | Centralised Ops Trading |  | NA | 13/02/24 | Closed |  |  |  | Saloni | 2025-02-10 | 665 | >60 | February | 2024 | #VALUE!
Group Platforms | Finance | 89718748 | 2023-12-07 | Tills trading at reduced prices across the Irish stores | Explore the feasibility of implementing some sort of restrictions in SAP for incompatible combinations of store attributes. | Problem avoidance | Remko Smit | 12/01: With the enhanced dummy store set up process in place, it will be efficient enough to identify any errors whilst the store is being set up. Therefore, this action has been suspended. 18/12: This action will be picked based on the output of the workshop from Action#1 Validations were performed in SAP and this was confirmed to be a valid scenario for Clonshaugh DC which should have a combination of UK&IE attributes. Review the possibilities of adding a validation step to arrest these scenarios in SAP. – Long term (Backlog to be created once action 1 is completed). | SAP |  | NA | 2024-12-01 | Closed |  |  |  | Saloni | 2025-02-10 | 665 | >60 | January | 2024 | #VALUE!
Business Process Services | Business Process Services | 89718748 | 2023-12-07 | Tills trading at reduced prices across the Irish stores | Enhancements in the store set up process between Centralised Ops (Business extension team) and BSC master data team – Is there a possibility to enhance the initial request process? or introduce automation to eradicate any risk of process error. | Permanent Fix | Jaturson Yogendran | 12/01: The workshop was conducted and here is the conclusion: Normal store set up process – There are enough enhancements in place which will help identify any mismatches before the store set up process. 18/12: A workshop will be conducted in early January to enhance the store set up process through the below means - 1.Standardization - through the (i) mandatory use of a Front Sheet for all requests or (ii) elimination of the Front Sheet entirely and usage of the Site Request Form directly 2.Optimisation - if the Front Sheet is kept, automation to pick all mandatory information from the Front Sheet into the Site Request Form, with potential logic to only accept and save pre-determined use cases 3.Governance - a central owner of the process, who reviews (and potentially channels) all requests, and acts as the final sign-off for store setup. Review the current process and figure out the key attributes responsible (E2E) to set up a store successfully before passing it to Master Data team – Collect the correct level information like Company code, sales org, etc. Implement approval process for the final validation before sending the details to Master data. Review the various combinations for setting up a store. Note: There are no further plans of setting up a dummy store until PEAK. | Centralised Ops Trading |  | NA | 2024-12-01 | Closed |  |  |  | Saloni | 2025-02-10 | 665 | >60 | January | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89710913 | 2023-11-29 | Delay in D&F order processing | Did WMS get delayed order alerts – they already exist – when did they get them and what actions was taken? | Problem identification & Alerting | Nandakumar Sivalingam | 15/12: WMS Team confirmed on that day, they have received null audit mail from DS, so engaged them immediately. 14/12: GC confirmed that there is red/amber alert mail, he is checking what happened on that day. 08/12: As Nandha is OOO, have asked Vivek/GC to update on this action | WMS |  | NA | 18/12/23 | Closed |  |  |  | Saloni | 2025-02-10 | 673 | >60 | December | 2023 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89710913 | 2023-11-29 | Delay in D&F order processing | Inventory Planning Management have taken out the column where a manual order needs to stipulated – manual is default. | Problem avoidance | Allen Eapachen | The action has been discussed and agreed to close in the PIR call | D&F |  | NA | 29/11/23 | Closed |  |  |  | Saloni | 2025-02-10 | 673 | >60 | November | 2023 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89710913 | 2023-11-29 | Delay in D&F order processing | Allen has communicated with Inventory Planning Management on this issue, and the team have been advised to be more vigilant while raising such orders in future | Problem avoidance | Allen Eapachen | The action has been discussed and agreed to close in the PIR call | D&F |  | NA | 29/11/23 | Closed |  |  |  | Saloni | 2025-02-10 | 673 | >60 | November | 2023 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89710913 | 2023-11-29 | Delay in D&F order processing | Implement some validation that displays an error for all custom screens if a mistake is made by an user. Standard BY pages have validation. JIRA backlog shared. | Problem avoidance | Allen Eapachen | Feasibility implementing the validation will explored via the back log -ARCI3018 | D&F |  | NA | 29/11/23 | Closed |  | ARCI - 3018 | Closed | Saloni | 2025-02-10 | 673 | >60 | November | 2023 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89710913 | 2023-11-29 | Delay in D&F order processing | BY got alerts. These jobs run in the SAS cloud. Allen to investigate options to see if BY get an alert, how can we be notified. Ganesh Regoubady from BY has said they will change their SOP to call out to us during job failures and delays – already in place. For data issues they will work on for 30 mins then call out | Problem identification & Alerting | Allen Eapachen | 06/12: BY confirmed that they will give call outs to D&F product team until the alert is setup 05/12: A backlog is created to address this post peak. An automated alert mail will be triggered from ControlM to DL which includes PCM,MIM and D&F devops team when either of the below happens. •If Calculate Plans has not started by midnight UK time. •If all orders have not gone out of D&F by 1:00 AM UK time. Have asked if BY will give a call out to D&F till the alert is configured | D&F |  | NA | 2023-06-12 | Closed |  | ARCI - 3022 | Closed | Saloni | 2025-02-10 | 673 | >60 | December | 2023 | #VALUE!
Customer Channels | Service Experience | 89705822 | 2023-11-29 | CFTO ordering slots not available for customers | What alerting fired on the back of this incident? None, due to nature of the issue, as 21st Dec was still open for slots CFTO orders were still coming through during the incident | Problem identification & Alerting | Rajeev Ekambaram | 15/12: Emma confirmed that this action has been complete 11/12: Have followed up with Emma on the status of the alerts configuration 29/11: 1.To add an alert in OMS to fire if the shipping calendars are switched off covering the CFTO collection dates - Complete 2.To add an alert in WCS to fire when we have continuous/high number of negative responses from the Slot API | WMS Lifecycle Team |  | NA | 15/12/23 | Closed |  |  |  | Saloni | 2025-02-10 | 673 | >60 | December | 2023 | #VALUE!
Customer Channels | Service Experience | 89705822 | 2023-11-29 | CFTO ordering slots not available for customers | What is our plan to switch off ISF over the Christmas & New Year dates? | Problem avoidance | Emma Rotheram & Rajeev Ekambaram | 19/12: on 14th, it has been completed 15/12: Emma updated that team is working on this 11/12: Have followed up with Emma on the status of this action 29/11: Going with the existing method to switch off via the shipping calendar, but wait until CFTO campaign has closed (post 13th/15th Dec). Need to agree this with Chris S from Ops Hub | .com |  | NA | 19/12/23 | Closed |  |  |  | Saloni | 2025-02-10 | 673 | >60 | December | 2023 | #VALUE!
Customer Channels | Service Experience | 89705822 | 2023-11-29 | CFTO ordering slots not available for customers | Are any changes needed to the solution to help prevent such as issue for the next CFTO campaign (2024)? Potential options are… 1.Remain as is and turn off ISF via shipping calendars post campaign close. 2.To create new separate calendars for CFTO specifically or for each of the areas that pick up the node level calendar. Changes would also be needed to the new store set up logic in OMS as well. 3.Remove this capacity concept out of OMS into the Task Domain. | Problem avoidance | Dino Randhawa | 07/02: Dino shared the backlog references The occurrence of duplicate demand quantity reserved during customer order amendment and 17 items were impacted (Bug ID: DNCTA-8757). DNU not triggered as expected for the store change amendment scenarios (Bug ID: DNCTA-8639) 04/01: Dino updated further details, Short-med term i.e. pre peak 2024: One time effort to create a CFTO all day working calendar for all stores in Sterling enabled for Food collection. Code change - currently, when new CFTO stores are enabled, they're not tagged to a calendar, which means they default to the node level (shipping) calendar. This code change will ensure that new CFTO stores default to the CFTO all day working calendar. Longer term: unlikely for peak 2024: Remove the capacity concept out of OMS into Task Domain. He will also share the Jira story reference IDs. 15/12: Emma confirmed that this action has been complete 29/11: PMs to discuss, agree & prioritise which approach to go with | CFTO |  | NA | 15/12/23 | Closed |  |  |  | Saloni | 2025-02-10 | 673 | >60 | December | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89700848 | 2023-11-24 | SAP PO (Process Orchestration) unavailable due to file system space issue | The root cause behind the connectivity issue on the TSM agent could not be ascertained as it is out of support. Devise a plan to upgrade the TDP (Tivoli Data Protect) agent across the estate – starting with SAP. | Problem avoidance | Sailesh K | 27/02: TSM has been upgraded on ISAP and ESAP server. Upgrade is being planned for cSAP. Team will continue to perform the upgraded offline 20/02: CR has been rasied to upgrade SAP TDP this week 11/02: Escalated with Jeeva and Elizhabeth golder for traction 22/01: The plan is still in place 11/12: Followed with Sailesh awaiting updates | Storage |  | NA | 27/02/24 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 678 | >60 | February | 2024 | #VALUE!
GTS | Enterprise Technology Platform | 89700848 | 2023-11-24 | SAP PO (Process Orchestration) unavailable due to file system space issue | As part of the recovery process the archival file system on primary database server was uplifted. Plan to uplift the secondary database server to 499GB | Solution & Recovery | Sathish S | 27/12: The uplift has been completed under the CR#193282 11/12: The uplift has been planned in 3rd week of decemeber | Unix |  | NA | 27/12/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 678 | >60 | December | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89700848 | 2023-11-24 | SAP PO (Process Orchestration) unavailable due to file system space issue | An alert was triggered at 15:20 on 21/11, however, no actions were taken to rectify the issue. Conduct workshops to reiterate the SOP usage across the team. | Solution & Recovery | Sailesh K | 29/12: Workshop has been conducted to walkthrough the SOP 11/12: Followed with Sailesh awaiting updates | Storage |  | NA | 29/12/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 678 | >60 | December | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89700848 | 2023-11-24 | SAP PO (Process Orchestration) unavailable due to file system space issue | Review the database archival log file system capacity to ascertain if an uplift is required | Problem avoidance | Sailesh K | 04/04: All the Database archival log FS are reviewed, Incident and alerting process are already set as expected so there is no need to change the existing process. 27/02: We have round 200 + DB servers and validation is in progress 20/02: Teams are still working on analysis as they have validate multiple server 11/02: Escalated with Jeeva and Elizhabeth golder for traction 22/01: Followed with Sailesh awaiting updates 11/12: Followed with Sailesh awaiting updates | Storage |  | NA | 2024-04-04 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 678 | >60 | April | 2024 | #VALUE!
GTS | Enterprise Technology Platform | 89700848 | 2023-11-24 | SAP PO (Process Orchestration) unavailable due to file system space issue | Review and amend the threshold set for the file system utilization alerts. Also, Increase the severity of the alert. | Problem identification & Alerting | Sailesh and Sathish | 04/04:Existing alerting process was reviewed in all the DB Servers across the estate and validated to ensure we are getting the poper alert and INC raised. 27/02: We have round 200 + DB servers and validation is in progress 20/02: Teams are still working on analysis as they have validate multiple server 11/02: Escalated with Jeeva and Elizhabeth golder for traction 22/01 Followed with Sailesh awaiting updates Review NMON reports for SAP for last week to set lower 1st alert for archivelog file system space utilisation | Storage |  | NA | 2024-04-04 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 678 | >60 | April | 2024 | #VALUE!
GTS | Enterprise Technology Platform | 89700848 | 2023-11-24 | SAP PO (Process Orchestration) unavailable due to file system space issue | Configure alerts on the TSM agents across the estate to identify the permission denied/handshake errors. | Problem identification & Alerting | Sailesh K | 11/04: The alerting for permission denied and password update related issue and ignio alerts across the DB and SAP servers have been reviewed. Alerts are already in place and we have reviewed to ensure its up to date to avoid such production issues in future. 04/04: Configuring alerts for permission denied / handshake errors is in progress we are working on the possibilities of configuring those alerts. 27/02: We have round 200 + DB servers and validation is in progress 20/02: Teams are still working on analysis as they have validate multiple server 11/02: Escalated with Jeeva and Elizhabeth golder for traction 22/01 Followed with Sailesh awaiting updates 11/12: Followed with Sailesh awaiting updates | Storage |  | NA | 2023-11-04 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 678 | >60 | April | 2023 | #VALUE!
GTS | Digital Workplace Services | 89689701 | 2023-11-23 | Power apps hosted applications unavailable due to a central Microsoft issue | Contact Paula Townsend from Commercial to ascertain what the sla’s are for power apps | Supplier and support involvement | Andy Neilson | 22/02: Andy has confirmed that the validation of SLA is might not given/prove any thing instead they should understand will this outage give us an service credits. He will discuss this Paula to understand how this works in new agreement and feed to back service management. Hence closing this action off the tracker as we will once the new agreement is conclude 21/12: Andy has advised that the Engineering team will work from Jan on this 11/12: We have the details of Uptime percentage calaculation of the availabilty but we are yrt to understand further on this. | DWS |  | NA | 2024-09-01 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 679 | >60 | January | 2024 | #VALUE!
GTS | Digital Workplace Services | 89689701 | 2023-11-23 | Power apps hosted applications unavailable due to a central Microsoft issue | A normal Microsoft feedback note here as a closed action – communication was not timely. | Supplier and support involvement | Andy Neilson | 23/11: The action has been closed as agreed in PIR as we do not any expect any response from Microsoft | DWS |  | NA | 23/11/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 679 | >60 | November | 2023 | #VALUE!
GTS | Digital Workplace Services | 89689701 | 2023-11-23 | Power apps hosted applications unavailable due to a central Microsoft issue | How do we monitor the platform as a whole and the individual applications | Problem identification & Alerting | Duane Bergh | 20/02: This is not feasible as they power app platform has 6000+ application from low and critical priorty. Daunae has confirmed the application owner should be supporting the application and they should be responsible for creating the alert. However there will be notification microsoft if there is a issue with platform. Hence closing this action 07/02; Have been following up with Duane but still no updates 22/01- Followed up with Duane no further updates, requested for backlog as it seems to be long term action. 09/01:Followed up with Duane no further updates 21/12: Duane updated that no progress is currently made and the Engineering team will work from Jan on this 11/12: Followed up with Duane awaiting further updates 23/11:Conversation is ongoing with Maebh booth | DWS |  | NA | 20/02/24 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 679 | >60 | February | 2024 | #VALUE!
GTS | Digital Workplace Services | 89689701 | 2023-11-23 | Power apps hosted applications unavailable due to a central Microsoft issue | Work with engineering regarding alerts from Microsoft on power app issues or trigger internal alerts. Can these go straight to owners and MIM etc? Apps should also flag alerts themselves. | Problem identification & Alerting | Duane Bergh | 20/02: 20/02: This is not feasible as they power app platform has 6000+ application from low and critical priorty. Daunae has confirmed the application owner should be supporting the application and they should be responsible for creating the alert. However there will be notification microsoft if there is a issue with platform. Hence closing this action 07/02; Have been following up with Duane but still no updates 22/01: Followed up with Duane no further updates 09/01: Followed up with Duane no further updates 21/12: Duane updated that no progress is currently made and the Engineering team will work from Jan on this 11/12: Followed up with Duane awaiting further updates | DWS |  | NA | 20/02/24 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 679 | >60 | February | 2024 | #VALUE!
GTS | Digital Workplace Services | 89689701 | 2023-11-23 | Power apps hosted applications unavailable due to a central Microsoft issue | When people create apps they need to indicate primary and secondary owners, business criticality and describe the app and its use. We also need a way to quickly identify owners of active apps as opposed to redundant apps. All runbooks and playbooks should be included. | Impact analysis | Rajamani Perumal | 23/11; – this is all being developed in CoE under the JIRA back log- WPTS-9392 | DWS |  | NA | 23/11/23 | Closed | NA | WPTS-9392 |  | Saloni | 2025-02-10 | 679 | >60 | November | 2023 | #VALUE!
Customer Channels | Platform & Store Ops | 89678930 | 2023-11-22 | PLPs and PDPs impacted by Microsoft DNS issue | Review of Onyx /GQL-Mesh alerting | Problem identification & Alerting | Nakul Suneja | 12/12: The error threshold is set to 20%. During the incident the error rate hit was 15.2% (so below threshold and therefore did not alert). There is a concern that if the threshold was reduced to 15%, this would cause a lot of false positives. Whether or not to adjust the threshold will be discussed within the Onyx team 01/12: Nakul is OOO 28/11: Team is working on it. 22/11: There is already a lot of alerting within Onyx. Need to investigate why alerts did not fire, possibly need to adjust the threshold. | Platform & Store Ops |  | NA | 2023-12-12 | Closed |  |  |  | Saloni | 2025-02-10 | 680 | >60 | December | 2023 | #VALUE!
Customer Channels | Platform & Store Ops | 89678930 | 2023-11-22 | PLPs and PDPs impacted by Microsoft DNS issue | Ensure adequate alerting set up for all Onyx front ends | Problem identification & Alerting | Steve Warren and Nakul Suneja | 12/12: Whether or not to add extra logging and alert conditions will be discussed within the Onyx Browse team 11/12: Followed up with Elaine on the status on the action 01/12: Nakul is OOO 28/11: Team is working on it. 22/11: The main front-end area which is live on Onyx is Browse. However, going forward, other teams will move to Onyx and it is essential that adequate client-side alerting is set up to ensure that the alerts capture when the pages do not render properly or are broken. Steve to speak to all relevant teams about this. This alerting will help identify whether the issue falls into severity 1 or 2 territory (and therefore requires formal incident comms etc). Nakul to investigate client-side errors on Browse | Platform & Store Ops |  | NA | 2023-12-12 | Closed |  |  |  | Saloni | 2025-02-10 | 680 | >60 | December | 2023 | #VALUE!
Customer Channels | Platform & Store Ops | 89678930 | 2023-11-22 | PLPs and PDPs impacted by Microsoft DNS issue | Be able to assess full impact early in the incident | Problem identification & Alerting | Steve Warren and Nakul Suneja | 12/12: Alerting is being reviewed by Onyx team 11/12: Followed up with Elaine on the status on the action 01/12: Nakul is OOO 28/11: Team is working on it. 22/11: Refer the above action. Once the client-side alerting has been reviewed/is in place, it will be much easier to identify impact and specifically customer impact which determines whether severity 1 / 2 incident process is followed | Platform & Store Ops |  | NA | 2023-12-12 | Closed |  |  |  | Saloni | 2025-02-10 | 680 | >60 | December | 2023 | #VALUE!
Customer Channels | Platform & Store Ops | 89678930 | 2023-11-22 | PLPs and PDPs impacted by Microsoft DNS issue | Engagement and follow up with Microsoft | Supplier and support involvement | James Cross | 01/12: Added to the runbook for Onyx apps on how/when to interact with Azure support 28/11: Team is working on it. 22/11: The process for engaging Microsoft needs to be documented. 1) Raise support request with MS via their portal and assign a severity that we believe is correct. Note: If no one on the bridge has access to the MS portal, Cloud Ops team can be asked to raise a request 2) MS will review the request and join the bridge if deemed appropriate (i.e. if Marks and Spencer specific issue rather than wider MS issue) 3) If escalation is required, this can be done via the MS Account Manager (Cloud Ops team/Phil Torkington can be asked to assist if this is proving difficult) | Platform & Store Ops |  | NA | 2023-01-12 | Closed |  |  |  | Saloni | 2025-02-10 | 680 | >60 | December | 2023 | #VALUE!
Customer Channels | Platform & Store Ops | 89678930 | 2023-11-22 | PLPs and PDPs impacted by Microsoft DNS issue | Understand cause of server side errors | Problem identification & Alerting | James Cross | 01/12: he only plausible explanation for seeing server side errors after 10:42 is that the issue in Azure caused a knock-on effect that Microsoft didn’t mention in their report of the incident. The vast majority of the errors were for fetching reviews for a product. The PDP and PLP pages were still being rendered and shown to customers during that time, just without any reviews showing. 28/11: Team is working on it. 22/11: Need to understand what caused the service side errors because we could see that they were occurring after Microsoft advised that service had been restored | Platform & Store Ops |  | NA | 2023-01-12 | Closed |  |  |  | Saloni | 2025-02-10 | 680 | >60 | December | 2023 | #VALUE!
Customer Channels | Platform & Store Ops | 89678930 | 2023-11-22 | PLPs and PDPs impacted by Microsoft DNS issue | Inadequate status updates from Microsoft | Supplier and support involvement | Hisham Khalid | 12/12: Hisham confirmed that we have agreed for a proactive updates from Microsoft 11/12: Followed up with Hisham on the status on the action 01/12: Hisham is checking with Microsoft 28/11: Hisham is working on it. 22/11: It was felt that Microsoft did not send out adequate comms about this incident. E.g.teams investigating the incident had to check the service status on the MS website, there was no proactive communication. Hisham to get this raised with our Microsoft Account Manager | Service Lead |  | NA | 2023-12-12 | Closed |  |  |  | Saloni | 2025-02-10 | 680 | >60 | December | 2023 | #VALUE!
Foods | Foods Supply Chain | 89681664 | 2023-11-14 | Quantum User Interface (UI) intermittently unavailable due to a file system space issue | Can we analyse the core dumps with IBM to ascertain any errors or issues? | Root cause | Sathish Selvapillai/ Shravan | 16/02: The recommendation from IBM is not working and their final comment was to upgrade Java which cannot be done for Quantum. It looks like we cannot upgrade to the latest service pack of AIX 7.2, without upgrading Java. There is already a risk raised for AIX 7.3, as it requires the application to have upgraded Java version. We need to add this AIX 7.2 latest service pack as well to the open risk. As Quantum is in the path of decommission, we need to obtain an exception from the security team for not patching Q servers with the latest updates. IBM will not support our servers without upgrading to the latest patch but their out of support date in not yet announced. 01/02 : IBM suggested configuration changes were tested internally. Again test is failing in PT with the same issue. To be discussed with infra team further to decide the way farward. 22/01: IBM has provided few more recommendation,which will be test in upcoming sprint 27/12: The test is failing in PT with the same issue. To be followed up with IBM on next steps 11/12: IBM h shared some recommendation and it will be tested in PT The logs have been shared with IBM for investigations | Quantum |  | NA | 2024-12-02 | Closed | 2103 |  |  | Saloni | 2025-02-10 | 688 | >60 | February | 2024 | #VALUE!
Foods | Foods Supply Chain | 89681664 | 2023-11-14 | Quantum User Interface (UI) intermittently unavailable due to a file system space issue | Do we have a resiliency/DR option for Quantum UI? | Solution & Recovery | Naveen | 21/11: The failover of the Quantum UI to the DR during incidents is not feasible as we may have to move quantum application for a proper DR. As quantum is a legacy application a successful DR is uncertain. Quantum will be decommissioned and replaced with Relex by circa next 1 year. | Quantum |  | NA | 14/11/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 688 | >60 | November | 2023 | #VALUE!
Foods | Foods Supply Chain | 89681664 | 2023-11-14 | Quantum User Interface (UI) intermittently unavailable due to a file system space issue | Do we have the right the alert handling procedures in place? | Problem identification & Alerting | Shravan Madathil | 21/11: Required alerting is in place for Quantum and AIX. However, during the MIM we were working to address the symptom (expanding file system space) rather than fixing the actual problem. | Quantum |  | NA | 21/11/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 688 | >60 | November | 2023 | #VALUE!
Foods | Foods Supply Chain | 89681664 | 2023-11-14 | Quantum User Interface (UI) intermittently unavailable due to a file system space issue | What preventive measures can be taken to avoid such scenarios? | Problem avoidance | Shravan Madathil | 21/11:There is an agreed set of test cases to be performed during every patching. As an additional step, a new test case with the actual load volume will be added for efficient testing and validations. | Quantum |  | NA | 21/11/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 688 | >60 | November | 2023 | #VALUE!
Foods | Foods Supply Chain | 89681664 | 2023-11-14 | Quantum User Interface (UI) intermittently unavailable due to a file system space issue | What is the Root cause of issue? | Root cause | Naveen Kumar Bojjankula | 21/11: During the testing, the Standard testing procedure was followed with 6k UPC’s (Mixture of chilled and Ambient products). However, on Sunday during the weekly job all the UPC’s were ambient UPC’s causing compatibility issues. Also, it is observed that quantum is not compatible with higher java versions and as it is a legacy application, we are not able to drill down on its compatibility issue. As a preventive measure, new test case with significant load volume will be added as part of the standard testing procedure. For the permanent fix, Relex will be replacing quantum in next 9months – 1 year. | Quantum |  | NA | 14/11/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 688 | >60 | November | 2023 | #VALUE!
Foods and C&H international | Foods, C&H supply chain | 89649412 | 2023-11-07 | Quantum Job failure and WMS slowness impacting Bradford NDC allocations | Root cause | Root cause | Foods and WMS | There are two scenarios in this issue: 1.On 27/09, the Foods Critical job “FOP309” failed due to a problematic UPC: Foods Supply chain colleagues had raised a manual purchase order in Quantum with an incorrect (significantly high) order quantity. Due to this the application node went offline whilst processing the UPC resulting in job failure. As there is no restriction within SAP, while raising PO’s these scenarios cannot be prevented. However, there is a standard procedure agreed within the teams to handle the scenario by “re-processing/skipping the problematic UPC” 2.Once the batch was recovered, Bradford DC reported slowness: Owning to the above Job failure, the bradford orders had started interfacing into WMS with a delay at 04:00. In parallel, there was a resource constraint (high CPU utilization) within one of the DB servers in the WMS system. The CPU spike was due to ad-hoc custom reports (10 hours data) generation by a DC colleague via a legacy print server. | Foods and WMS |  | NA | 2023-07-11 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 695 | >60 | November | 2023 | #VALUE!
Foods and C&H international | Foods, C&H supply chain | 89649412 | 2023-11-07 | Quantum Job failure and WMS slowness impacting Bradford NDC allocations | What preventive measures can be taken to avoid the delay in Batch? | Problem avoidance | Foods and WMS | Foods: Whenever a problematic UPC is identified, the UPC will be skipped as per the standard procedure. WMS: DC Colleagues has been communicated not to run the reports on that time. Also, the legacy print server is planned to be migrated to the latest version. (to be planned in Jan’24) | Foods and WMS |  | NA | 2023-07-11 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 695 | >60 | November | 2023 | #VALUE!
Foods | Foods Supply Chain | 89649412 | 2023-11-07 | Quantum Job failure and WMS slowness impacting Bradford NDC allocations | Improve the alerting handling procedure across the product teams | Problem identification & Alerting | WMS/Jishin | Alerting was in place and teams did address the issue as per the alerts. Also, we have agreed with the team to improve the alert handling for faster resolution. | WMS/Oracle DB support |  | NA | 2023-07-11 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 695 | >60 | November | 2023 | #VALUE!
Foods | Foods Supply Chain | 89649412 | 2023-11-07 | Quantum Job failure and WMS slowness impacting Bradford NDC allocations | The decision within the Quantum support to kill the problematic UPC on Quantum took some time which eventually delayed the job recovery. can we revise the SOP’s? | Solution & Recovery | Naveen Kumar Bojjankula | As per the usual process, engineers will restart the quantum services whenever a bad data is identified. But since the node was down engineers were not able to do it at the first place thus the Qlogic rebouncing took some time which further delayed the batch recovery. The SOP has updated on the same | Foods- Quantum |  | NA | 2023-07-11 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 695 | >60 | November | 2023 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89649412 | 2023-11-07 | Quantum Job failure and WMS slowness impacting Bradford NDC allocations | There was delay in identifying the cause for WMS system slowness which further delayed the batch. Ensure that all the engineers educated on the right process and procedures. | Solution & Recovery | Karthick GC | Right after the issue, a workshop was conducted with the engineers to refresh the relevant SOP inorder to ensure timely resolution. | wms |  | NA | 2023-07-11 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 695 | >60 | November | 2023 | #VALUE!
Foods | Foods Supply Chain | 89649412 | 2023-11-07 | Quantum Job failure and WMS slowness impacting Bradford NDC allocations | Agree with the DC colleagues to generate these adhoc reports outside the critical batch window. | Problem avoidance | Jay Krishnan /Thomas Hilliard | 30/11 - DC colleagues have been informed not to generate adhoc reports during the Critical flow window 21/11 - Jay has agreed to inform the bradford ops lead. ETA : 23/11 11/11 - Thomas Hillard is informed on the action, he will comnunicate to the DC colleagues during his nexxt meet with them. ETA - 16/11. An adhoc report generation by a DC colleague in the WMs system during the issue resulted in system resource constraint. DC colleagues needs to be re-iterated not to generate/extract high transactional data reports (eg.10 hours data) rather to use the hourly reports which are available in the relevant sharepoint. | Foods |  | NA | 30/11/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 695 | >60 | November | 2023 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89648657 | 2023-11-03 | HHT issue in Stoke DC | What caused the increase in queue depth within the HHT’s resulting in the issue? | Root cause | Nandakumar/Karthick GC | The cause of the queue depth is attributed to high volume of transactions due to the recent addition of Ecomm orders in Stoke DC. The transactions have been exceeding the queue depth limit of 16kb causing message pile-up’s. | WMS Devops |  | NA | 2023-03-11 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 699 | >60 | November | 2023 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89648657 | 2023-11-03 | HHT issue in Stoke DC | What preventive measures can be taken to make the HHT daemon handle high volume/queue depth? | Permanent fix | Nandakumar/Karthick GC | The Queue size has been increased to 1Mb during the Ecomm orders addition to Stoke DC and to reflect the uplift, the queue has been rebuilt. Also, Vendor BY has provided a new feature within the HHT Daemon to flush out the message pile-up’s as and when the queue depth reaches 1Mb. This will avoid any manual intervention to fix the issue in future. | WMS Devops |  | NA | 2023-03-11 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 699 | >60 | November | 2023 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89648657 | 2023-11-03 | HHT issue in Stoke DC | Feasibility of configuring an alert to proactively identify any HHT issues. | Problem identification & Alerting | Nandha Kumar Saravanan | 21/11 - Testing is in progress. Once the testing is done, after the internal approval, implementation of the alerting will take place 11/10 - Due to the internal change freeze within C&H supply chain, alerting implementation is on-HOLD. Nandhakumar from WMS will work on the alerting once the flag is lifted for the change implementations Alerting was not in place for the HHT daemon in the past and now teams have agreed to put-in the relevant alerting | WMS Devops |  | NA | 30/11/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 699 | >60 | November | 2023 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89648657 | 2023-11-03 | HHT issue in Stoke DC | Ensure the queue rebuilding steps are captured in the cutover plan of any uplifts performed for a site | Problem avoidance | Nandakumar/Karthick GC | The relevant cutover plan has been updated with the right steps including the queue rebuilding steps. Engineers are educated on the right process and procedures to be followed as and when an alert is received. | WMS Devops |  | NA | 2023-03-11 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 699 | >60 | November | 2023 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89648657 | 2023-11-03 | HHT issue in Stoke DC | There was a process gap between the Site and the command centre, as the issue was raised as a Sev2 rather than a Sev1, which delayed the resolution | Solution & Recovery | Nandakumar/Karthick GC | Site had missed to call out the right impact initially and as they have no provision to raise a sev1 in remedy, it was raised as a sev 2 with no proper impact called out. Site has been educated on the right sev1 process. | WMS Devops |  | NA | 2023-03-11 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 699 | >60 | November | 2023 | #VALUE!
Customer Channels | Service Experience | 89650991 | 2023-11-02 | Orders being placed offline & Sterling application unavailable | Enable Splunk Alerts for FRA usage. | Problem identification & Alerting | Rajeev & OMS Support | Splunk Alerts for FRA usage has been enabled | OMS Support |  | NA | 2023-02-11 | Closed |  |  |  | Saloni | 2025-02-10 | 700 | >60 | November | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89650991 | 2023-11-02 | Orders being placed offline & Sterling application unavailable | Review DB alerts to make sure all possible cases are addressed. | Problem identification & Alerting | Vivek & Jishin | 09/11 - Jishin updated that the team has enabled OEM notification for all the possible metrics 07/11 - Jishin updated that RA alert was reviewed and fixed it. Other alerts are being reviewed. | Database |  | NA | 2023-09-11 | Closed |  |  |  | Saloni | 2025-02-10 | 700 | >60 | November | 2023 | #VALUE!
Customer Channels | Service Experience | 89650991 | 2023-11-02 | Orders being placed offline & Sterling application unavailable | Refresh the team’s knowledge on the importance of dropping the restore point after the release activities. | Problem avoidance | Rajeev & OMS Support | Team was made aware on the importance of dropping the restore point after the release activities. | OMS Support |  | NA | 2023-02-11 | Closed |  |  |  | Saloni | 2025-02-10 | 700 | >60 | November | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89650991 | 2023-11-02 | Orders being placed offline & Sterling application unavailable | Investigate if restore point can be dropped automatically after ‘X’ hours. | Problem avoidance | Vivek & Jishin | 24/11 - An alert has been set if any restore points exists longer than 8 hours and have been tested with various scenarios and is working as expected 21/11 - Testing is still in progress and expected to be completed by 23rd EOD 17/11- Alert has been configured and is being tested, by 21 EOD it will be completed and based on the outcome, the action can be closed. 15/11 - DB team is working on instead of creating a job to automatically drop the Restore point, are planning to create an alert notification about the restore point. 13/11 - DB team had a call with sterling support. Most likely they will not be able to create a job to automatically drop the restore points. if it is older than 24 hours rather it will send us an alert to action. So they are working to modify the action. 09/11 - DB team is working with sterling support 07/11 - Jishin updated that this needs to be discussed with sterling support team | Database |  | NA | 24/11/23 | Closed |  |  |  | Saloni | 2025-02-10 | 700 | >60 | November | 2023 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89652851 | 2023-11-01 | Label printing issues at Welham Green DC | Create a SOP documenting the steps for effective log analysis to identify the root cause in a timely manner. | Solution & Recovery | Kunal Chichkar | This has been completed. A SOP has been created | WMS Devops |  | NA | 2023-10-11 | Closed |  |  |  | Saloni | 2025-02-10 | 701 | >60 | November | 2023 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89652851 | 2023-11-01 | Label printing issues at Welham Green DC | Possibility of automating the command execution to avoid any manual errors. | Problem avoidance | Karthick Girichandramohan | A job has been configured on 20/10 which will ensure any files older than 2 days will be automatically moved to an archival folder. | TPM |  | NA | 2023-06-11 | Closed |  |  |  | Saloni | 2025-02-10 | 701 | >60 | November | 2023 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89652851 | 2023-11-01 | Label printing issues at Welham Green DC | Restrict the level of access to critical file directories | Problem avoidance | Kunal Chichkar | 10/11: We cannot restrict access to the offshore team for rpwms user. Below are the list of activities they do on day to day basis which requires rpwms access. Application Health checks will be done by logging into App Server whenever required. Application Appstart and Appstop activities during the Upgrade/Outage Activities. Hyper Care Activities during the Deployment and Outage acticvity. Team will clear the HHT message pile ups. View and validate the Critical file path directories and files. As part of service improvements, team will login into server to write the scripts or run the scripts manually if required Revisit the SUDO RPWMS access for daemon restart. Feasibility of automating the daemon restart. | WMS Devops |  | NA | 2023-10-11 | Closed |  |  |  | Saloni | 2025-02-10 | 701 | >60 | November | 2023 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89652851 | 2023-11-01 | Label printing issues at Welham Green DC | Feasibility of identifying any alerting mechanism during a daemon restart in case of any missing files. | Problem identification & Alerting | Kunal Chichkar | 28/11: In general, any daemon will either fail to start or report it in the log, in case of missing of any mandatory files. But the problem on that specific issue was that the “defaultlabel.xml” is “not a mandatory” file for jrtskdae to start or even to work as usual in most of the cases. It is “only” needed for label printing except for those labels where a custom XML file contained absolutely everything. Hence we have seen that all the standard and custom reports were getting printed fine on that day. This kind of reporting of missing file by the daemons, is true not only for jrtskdae, but for other daemons as well. As this field is not mandatory file for daemon, no alerts cannot be configured by BY. 10/11:BY case: 04946360 The above case is raised with BY to advice if anything product team can do for alerting. We are yet to get any response Kunal will work with Blue Yonder to address this. | WMS Devops |  | NA | 27/11/23 | CLosed |  |  |  | Saloni | 2025-02-10 | 701 | >60 | November | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89656303 | 2023-10-31 | WMS application unavailable at Ollerton DC | We also need a better way of extracting logs from unmonitored assets, as it was a challenge and required manual log trawling. How can we improve the way we capture the session logs for this se | Solution & Recovery | Elizabeth Golder | 13/02: Elizabeth confirmed that this is on Glen's back log to look into but they will not be any were near top of the list, being decided as part of strategy. 08/01: Elizabeth discussing with architecture - Glen and new tools would be for tools and not under Ops scope Infra and Cyber sec team will jointly analyze the possibilities of effectively capturing the logs to ensure easy access whilst investigating during an issue. | Infra & Infosec |  | NA | 19/02/24 | Closed |  |  |  | Saloni | 2025-02-10 | 702 | >60 | February | 2024 | #VALUE!
GTS | Enterprise Technology Platform | 89656303 | 2023-10-31 | WMS application unavailable at Ollerton DC | During the incident recovery, it was advised that the backup file was not available in the TSM server due to an existing certificate issue? How can we address this? | Solution & Recovery | Sailesh Kaluva | The certificate issue was resolved, and the Welham Green file backup process is running as expected. In addition, the critical backup processes are running as expected and have confirmed the primary server backup is successful. IT has also been agreed that the product team will monitor for any critical failures and notify the relevant application team if required. | Backup & Storage |  | NA | 2023-06-11 | Closed |  |  |  | Saloni | 2025-02-10 | 702 | >60 | November | 2023 | #VALUE!
GTS | Operations | 89656303 | 2023-10-31 | WMS application unavailable at Ollerton DC | Include service leads in the Business Continuity texts | Business & IT Communication | Sathishkumar Sheshiah | This has been completed | Service Management |  | NA | 26/11/23 | Closed |  |  |  | Saloni | 2025-02-10 | 702 | >60 | November | 2023 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89656303 | 2023-10-31 | WMS application unavailable at Ollerton DC | Agree on a process to effectively manage the communication to the relevant stakeholders – Brands, Ollerton, Stoke | Business & IT Communication | Martin Coy | 28/11: Martin confirmed that after repeated chasing there is no update from business, so therefore, this is not a priority for business - No change in comms 09/11: Martin advised that the .com business operations are catching up to discuss on the comms process early next week. Martin will feed back to us. ETA: 15/11 Martin will liaise with the ecomm business to agree on an approach to effectively handle the stakeholder communication going forward. | Service Lead |  | NA | 28/11/23 | Closed |  |  |  | Saloni | 2025-02-10 | 702 | >60 | November | 2023 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89656303 | 2023-10-31 | WMS application unavailable at Ollerton DC | DR capability - Ollerton DR has not been tested, plan a DR test after addressing the HA test | Solution & Recovery | Karthick Girichandramohan | 08/01: The DR/HA testing for Ollerton will be covered as part of SP exit program in Q2 24-25 The DR testing is still being planned. Both Karthick GC and Nanda are OOO. Saloni to follow up on 07/12 Application team will lead the DR test planning with help from the Infra teams. If the DR test fails, a risk should be raised. | TPM |  | NA | 2024-08-01 | Closed |  |  |  | Saloni | 2025-02-10 | 702 | >60 | January | 2024 | #VALUE!
GTS | Enterprise Technology Platform | 89656303 | 2023-10-31 | WMS application unavailable at Ollerton DC | Explore options to identify a tool to compare features of the VMs to identify issues in a timely manner. | Solution & Recovery | Elizabeth Golder | 13/02: Elizabeth confirmed that this is on Glen's back log to look into but they will not be any were near top of the list, being decided as part of strategy. 08/01: Elizabeth discussing with architecture - Glen and new tools would be for tools and not under Ops scope 13/11: Awaiting updates from Customer on the go ahead decision Tools and license cost are under evaluation. Will share with Customer for next steps. | Service Lead |  | NA | 19/02/24 | Closed |  |  |  | Saloni | 2025-02-10 | 702 | >60 | February | 2024 | #VALUE!
GTS | Operations | 89656303 | 2023-10-31 | WMS application unavailable at Ollerton DC | Service Transition – Do we have a design document which can highlight that there was no backup available for the site. | Solution & Recovery | Priyadharshini Somasundaram | 27/02: The action will be carried out and tracked under the backlog - MTSM 74 Priya is currently working on draft plan to run through this with Customer... once its finalized we will be planning to send a wider comms | Service Management |  | NA | 27/02/24 | Closed |  | MTSM 74 |  | Saloni | 2025-02-10 | 702 | >60 | February | 2024 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89656303 | 2023-10-31 | WMS application unavailable at Ollerton DC | During the incident, it was identified, that there is no backup available for the Ollerton servers across the web, middleware, and application layers. Devise a plan to build the backup infrastructure for Ollerton | Solution & Recovery | Karthick Girichandramohan | 08/01: The TSM back up for all Ollerton servers enabled on 04/01/2024 and the backup is BAU now. 05/12: The DR testing is still being planned. Both Karthick GC and Nanda are OOO. Saloni to follow up on 07/12 Backup is available for the database. Application team will devise a plan and liaise with the Infra team to implement backup across the Ollerton infrastructure. | TPM |  | NA | 2024-08-01 | Closed |  |  |  | Saloni | 2025-02-10 | 702 | >60 | January | 2024 | #VALUE!
GTS | Enterprise Technology Platform | 89656303 | 2023-10-31 | WMS application unavailable at Ollerton DC | Procure the architectural diagram (infrastructure) across the sites to help lead the investigation. | Solution & Recovery | Elizabeth Golder | 13/02: Elizabeth confirmed that this is on Glen's back log to look into but they will not be any were near top of the list, being decided as part of strategy. 08/01: Elizabeth discussing with architecture - Glen and new tools would be for tools and not under Ops scope There is a structure diagram available in the CMDB, Elizabeth will find out. Explore Dynatrace to address this, if possible. | Service Lead |  | NA | 19/02/24 | Closed |  |  |  | Saloni | 2025-02-10 | 702 | >60 | February | 2024 | #VALUE!
GTS | Operations | 89656303 | 2023-10-31 | WMS application unavailable at Ollerton DC | This change was tracked as part of a standard change and therefore was oversee. Ensure such changes are now tracked in the CAB following the usual Change Management process | Solution & Recovery | Priyadharshini Somasundaram | This is completed. A report is published everyday to highlight any changes within the last 24 hours | Change Management |  | NA | 2023-06-11 | Closed |  |  |  | Saloni | 2025-02-10 | 702 | >60 | November | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89656303 | 2023-10-31 | WMS application unavailable at Ollerton DC | Perform an E2E review of the server build process and ensure it is documented with respective ownership on the steps involved. Peer review to be invoked to avoid manual overseeing. Explore automation feasibility to rule out the manual intervention. | Permanent Fix | Elizabeth Golder | 28/11: A meeting was held - Onprem servers use static instead of DHCP, so it is not possible to discover any static IP addresses. Infoblox automations is not feasible 13/11: Elizabeth has a meeting scheduled with Balaji on 15/11 to discuss on the IP address procurement for further rebuuilds. This action is currently in progress. Elizabeth to include Balaji to determine the possibility of different ways to procure IP addresses. Explore Muziris Portal to request for the build process - Automation | Service Lead |  | NA | 28/11/23 | Closed |  |  |  | Saloni | 2025-02-10 | 702 | >60 | November | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89656303 | 2023-10-31 | WMS application unavailable at Ollerton DC | Perform a detailed build review of all the new servers from the last 6 months | Problem avoidance | Jafar Sadiq | 28/11: Additional review process is in place before the build starts - by the relevant Tech SMEs Detailed review of build process has been done. Evaluating the possibilities of implementing 1. Automation to find Free IP in a specific VLAN 2. Automation to query DNS to find unused hostname in the network 3. Complete Review of ERF & Config sheet by Technology SME or Tower Lead. Upon signoff, build process will be initiated | Linux Team |  | NA | 28/11/23 | Closed |  |  |  | Saloni | 2025-02-10 | 702 | >60 | November | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89656303 | 2023-10-31 | WMS application unavailable at Ollerton DC | Feasibility of configuring an alert to identify the duplicate IP address scenarios How can we effectively identify the issue from the logs? | Problem identification & Alerting | Jafar Sadiq | 28/11: The alerts have been configured for duplicate IP issues. It is feasible to implement alerting for Duplicate IP in the network. Unix team working with Tools to implement alerting | Linux Team |  | NA | 28/11/23 | Closed |  |  |  | Saloni | 2025-02-10 | 702 | >60 | November | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89656303 | 2023-10-31 | WMS application unavailable at Ollerton DC | Create a SOP to document the steps to navigate through the logs while identifying the IP conflict issue. | Solution & Recovery | Jafar Sadiq | SOP has been created and incorporated with Unix SOM in sharepoint location. | Linux Team |  | NA | 2023-06-11 | Closed |  |  |  | Saloni | 2025-02-10 | 702 | >60 | November | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89656303 | 2023-10-31 | WMS application unavailable at Ollerton DC | Configure alerts to proactively identify these data corruption issues? Create a SOP detailing the data corruption scenarios and its fix for faster recovery. | Problem identification & Alerting | Jafar Sadiq | : As confirmed by Redhat, network interruption has led to data corruption in the encountered scenario. We will work on implementing alerting for duplication IP in the network. We can’t set alerting for FS corruption but we will be alerted once Shared FS unmounted or cluster got affected. | Linux Team |  | NA | 2023-06-11 | Closed |  |  |  | Saloni | 2025-02-10 | 702 | >60 | November | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89656303 | 2023-10-31 | WMS application unavailable at Ollerton DC | Liaise with RedHat to determine the cause of the file system corruption | Root cause | Jafar Sadiq | Redhat confirmed that the initial trigger point is token lost on the cluster due to network communication lost between 2 nodes. The failover can’t happen without the reset of the system, leading to splitbrains. The xfs filesystem can not run into more than 1 node as this is active/passive filesystem, and this led to the filesystem corruption. In short, duplicate IP conflict overhead to File system corruption in above scenario. | Linux Team |  | NA | 2023-06-11 | Closed |  |  |  | Saloni | 2025-02-10 | 702 | >60 | November | 2023 | #VALUE!
Foods | Foods Supply Chain | 89630816 | 2023-10-30 | Issue with the Relex batch processing | On 8-Nov a change will be deployed to amend the logic - The current design is that if an error is detected, all user overrides are dropped from the calculation and batch continues. This has been assessed and amended to drop only the records with error, and provide an exception report containing those records in the morning to the Relex Super Users | Permanent Fix | Anshuman Pani | 24/11 - Matt White advised that this change has been deployed with no re-occurrence | Relex Team |  | NA | 24/11/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 703 | >60 | November | 2023 | #VALUE!
Foods | Foods Supply Chain | 89630816 | 2023-10-30 | Issue with the Relex batch processing | Front end UI validation not possible if the start date is after the end date. Hence action 1 Can Relex please investigate further and provide further suggestions on better error handling. | Problem identification & Alerting | Matt White | 12/12 Joey has advised that the FOA support team hypercare plan is in place for the remainer of peak The permanent approach for this being assessed as part of service design and transition in Q4. BacklogID FOATR - 19510. 24/11 - Working with Relex Technical team to determine next steps on this to add to their roadmap. FOA support team have picked up manual checking | Foods |  | NA | 21/12/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 703 | >60 | December | 2023 | #VALUE!
Foods | Foods Supply Chain | 89630816 | 2023-10-30 | Issue with the Relex batch processing | If the FCS team no longer exists, who do we now inform as a first call to advise of any foods major incidents? | Business & IT Communication | Matt White | 12/12 - Rehan has spoken to Joey who has advised that the FCS on call number and process remains but has been taken up by the Foods Data Quality Team (FDQ) - mebers of FCS have moved into FDQ 24/11 - Matt White has spoken with Spoken Natalie Skinner who will continue to support sending comms to Supply Chain stakeholders during a major incident - long term approach to be determined with Callum Staff | Foods |  | NA | 2023-12-12 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 703 | >60 | December | 2023 | #VALUE!
Customer Channels | Selling Experience | 89585266 | 2023-10-27 | Customer Charge Card & Budget Card orders stuck in WCS | 8K delayed orders 1.Review scheduler capacity for UK & IE and make a change if required 2.Learning - To change status of stuck orders sooner when we have an incident 3.Is it possible to change the re-try concept here i.e. after X attempts will not longer re-try. Or another solution to achieve this. | Problem avoidance | Dhanaseelan Mahalingam | 23/11: 1. The current count of order export is 1200 per minute and it is enough as per the current order placemnt rate for Customer. The issue happened during the issue was becuase of the lck of knowledge on the process of moving the impacted orders to a intermediate status. 2. we have now created SOPs for handling this issue without drop in order flow. 3. Alternative retry mechanisms are not required for now for order exporting as we already having retry for every minute. | WCS |  | NA | 23/11/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 706 | >60 | November | 2023 | #VALUE!
Customer Channels | Service Experience | 89585266 | 2023-10-27 | Customer Charge Card & Budget Card orders stuck in WCS | Kanan & Balaji to raise and progress these with Worldline: 1.Worldline to provide root cause for this incident. 2.Once Worldline understand the rootcause, is it possible to implement a preventative measure? 3.In case of re-occurrence, can Worldline/APO/Axis identify this themselves, trigger restart of service sooner? 4.Worldline service a)Feedback for Worldline – Service experienced throughout Saturday. Worldline’s Service Desk not sufficient out of hours. How can these be improved? b)What are Worldline’s out of hours support for a severity 2 incident? c)Should we be raising our tickets to a severity 1 out of hours to get a better service? d)Review escalation matrix is this still valid/correct? | Root cause | Kanan Oza & Balaji Jaganathan | 1.Worldline to provide root cause for this incident. – Done(Attached) Once Worldline understand the rootcause, is it possible to implement a preventative measure? – Done (Yes, Alert Policy created for proactive monitoring on Customer side - PFOUND-258) 2.In case of re-occurrence, can Worldline/APO/Axis identify this themselves, trigger restart of service sooner? – Done, (Yes, as per Corrective Action Plan mentioned in the RCA and above) 3.Worldline service •Feedback for Worldline – Service experienced throughout Saturday. Worldline’s Service Desk not sufficient out of hours. How can these be improved- Updated matrix has been shared •What are Worldline’s out of hours support for a severity 2 incident? - Updated matrix has been shared •Should we be raising our tickets to a severity 1 out of hours to get a better service? – Yes •Review escalation matrix is this still valid/correct? – Done, the escalation matrix needed an update from Worldline, Updated matrix has been shared | POG |  | NA | 2023-11-12 | Closed | NA | PFOUND-258 |  | Saloni | 2025-02-10 | 706 | >60 | December | 2023 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89647767 | 2023-10-27 | Latency observed in HHTs at Swindon DC | Ensure that the sites are proactively communicated on any issue. | Business & IT Communication | Nandakumar Sivalingam | This has been agreed. | Service Lead |  | NA | 27/11/23 | Closed |  |  |  | Saloni | 2025-02-10 | 706 | >60 | November | 2023 | #VALUE!
GTS | Operations | 89647767 | 2023-10-27 | Latency observed in HHTs at Swindon DC | The alerts were received at 11:53 and 11:50 within the database and WMS layer respectively. The issue was reported by DC colleagues at 12:32, however, the MIM was engaged only at 13:45. It is imperative that the MIM is engaged by the Service lead in a timely manner for faster recovery. | Issue handling/Management | Saloni Chowdhury | We have now agreed with the Service lead, TPMs and TEMs for a timely MIM engagement. | MIM |  | NA | 27/11/23 | Closed |  |  |  | Saloni | 2025-02-10 | 706 | >60 | November | 2023 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89647767 | 2023-10-27 | Latency observed in HHTs at Swindon DC | Create a SOP for effective handling of these scenarios. | Solution & Recovery | Boopathi Palanisamy/ Nandakumar Sivalingam | The SOP Has been created and reviewed for future scenarios. | Database/ WMS devops |  | NA | 2023-09-11 | Closed |  |  |  | Saloni | 2025-02-10 | 706 | >60 | November | 2023 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89647767 | 2023-10-27 | Latency observed in HHTs at Swindon DC | Alerts were received at WMS and database layers indicating long running sessions. What is the plan for improvement? | Problem identification & Alerting | Boopathi Palanisamy/ Nandakumar Sivalingam | 09/11: The SOP has been updated and reviewed. Associates have been educated to proceed with daemon restarts to drive timely resolution Regular approach was taken to kill the long running sessions. A SOP is being updated to address the long running queries | Database/ WMS devops |  | NA | 2023-09-11 | Closed |  |  |  | Saloni | 2025-02-10 | 706 | >60 | November | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89647767 | 2023-10-27 | Latency observed in HHTs at Swindon DC | Perform a database performance review in Swindon | Problem avoidance | Boopathi Palanisamy | 21/11: The database review across other sites are completed and no significant changes are required. 09/11: The database performance review for Swindon is completed. There was a suggestion to uplift the redo size parameter in the database however, this has been eradicated due to PEAK. Also, after disabling the package logging, the database memory ulitization has significantly reduced. Work is in progress to review the DB stats across other sites. ETA: 20/11 This is currently in progress. ETA – 03/11. For Other sites – Work is in progress in parallel. This is to ensure no other sites get affected due to this issue. | Database |  | NA | 21/11/23 | Closed |  |  |  | Saloni | 2025-02-10 | 706 | >60 | November | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89647767 | 2023-10-27 | Latency observed in HHTs at Swindon DC | Improvement on the database logging to effectively handle the data volume. | Solution & Recovery | Boopathi Palanisamy | As part of the incident, the database writer value was increased from 1 to 2. to split the load for faster operations Discussions are ongoing to increase the log file size in the database to ensure efficient load balancing. | Database |  | NA | 2023-04-11 | Closed |  |  |  | Saloni | 2025-02-10 | 706 | >60 | November | 2023 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89647767 | 2023-10-27 | Latency observed in HHTs at Swindon DC | Perform a detailed analysis to identify if any possible network blip has caused the HHT sessions to hit the database at the same time resulting in increase of sessions. | Root cause | Rajesh Kumar Singrarajan | It has been confirmed from the logs that no network blips were observed at the site during the time of the issue | Network |  | NA | 2023-09-11 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 706 | >60 | November | 2023 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89647767 | 2023-10-27 | Latency observed in HHTs at Swindon DC | What caused the increase in the volume of data writing to the database resulting in the issue? | Root cause | Kunal Chichkar | 09/11: As part of combined deliveries project, a new piece of code was implemented 2 months back. The code was running with package logging on and it was writing large number of records in database whenever the receipt message from GIST DC was processed in Swindon DC. This usually comes between 11AM to 12PM on daily basis and during this period we see high number of records being written in database. On 26th there was slight increase in the volume and clubbed with other transaction being processed at same time, the DB reached its threshold on committing the DB transaction and started to slow down in processing these transactions, causing slowness in DC operations. Permanent fix: The package logging has been turned off now. The below exercise is being performed to identify the spike in the data volume. 1. Review the long running sessions, radius server. 2. Review the DHL extract job to identify if it has contributed to the issue. | WMS Devops |  | NA | 2023-09-11 | Closed |  |  |  | Saloni | 2025-02-10 | 706 | >60 | November | 2023 | #VALUE!
Customer Channels | Service Experience | 89624760 | 2023-10-25 | Significant drop in 3rd party brands Dropship products on website | Enable dropship in Availability services | Problem identification & Alerting | Steve Almashoor/ David Gillard | 14/11: Dropship have been enabled 08/11: Dropship will be enabled in the availability services today. 07/11: Followed with both action owners awaiting updates | Dropship |  | NA | 14/11/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 708 | >60 | November | 2023 | #VALUE!
Customer Channels | Service Experience | 89624760 | 2023-10-25 | Significant drop in 3rd party brands Dropship products on website | Supplier level inventory / drop in orders alert? | Problem identification & Alerting | David Gillard/Bola Odumosu | 21/11: David as confirmed that order level or inventory level alerting is not feasible 15/11: David will discuss with Dropship operation teams this week and then will feedback on the latest. 14/11: Followed with David and Bola again, no response yet 09/11: Followed up with David and Bola again, awaiting response 08/11: Followed with action owners again, awaiting updates 07/11: Followed with both action owners awaiting updates | Ops hub / FLC team |  | NA | 21/11/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 708 | >60 | November | 2023 | #VALUE!
Customer Channels | Service Experience | 89624760 | 2023-10-25 | Significant drop in 3rd party brands Dropship products on website | Supplier level dashboard / monitoring | Problem identification & Alerting | David Gillard/Bola Odumosu | 26/02: A dashboard as build, further improvement will be tracked offline. https://www3.an.adobe.com/x/3_130gse 30/01: David has given the dahsboard requirements,however team asked for 3/4 weeks to ananlysis and confirm its fesibility once they confirm this will picked up and tracked under a backlog 25/12: David is laising with Analytics team manager Katie for understanding the feasbility of implementing this new requirement. 07/01: No further updates yet. Still following on the status with action owner 23/12: The action owners are currently on leave and be back on 8th Jan 12/12: The owner ship is still needs to acertained. 12/11: . the requirement for some supplier level commercial reporting to identify issues such as order drop off is not in scope currently. This needs to followed up with commercial teams and data leadship team . I have requuesred for back log that can be created as this is a new feature 21/11: Still awaiting further updates from David and Stef. 15/11: David will discuss with Dropship operation teams this week and then will feedback on the latest. 09/11: Followed up with David and Bola again, awaiting response 08/11: Followed with action owners again, awaiting updates 07/11: Followed with both action owners awaiting updates | Dropship |  | NA | 26/02/24 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 708 | >60 | February | 2024 | #VALUE!
Customer Channels | Service Experience | 89624760 | 2023-10-25 | Significant drop in 3rd party brands Dropship products on website | Workaround to be carried out every Saturday 7am. | Solution & Recovery | Sartori, Stefano | A agreed workaround is in place until the permanent fix is deployed: Email to be sent by Sterling support to ops hub to start the activity. Platform support to validate by running the script. Comms will be updated in real itops channel by Ops hub. | Ops hub/Online |  | NA | 2023-02-11 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 708 | >60 | November | 2023 | #VALUE!
Customer Channels | Service Experience | 89624760 | 2023-10-25 | Significant drop in 3rd party brands Dropship products on website | Permanent fix deployment by OMS in Sterling release. | Permanent Fix | Abishek Kumar | 08/11: The change has been deployed 07/11: Followed on the latest awaiting the planned deployment date planned in next sterling release in Nov | OMS Dev team |  | NA | 2023-08-11 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 708 | >60 | November | 2023 | #VALUE!
Customer Channels | Platform & Store Ops | 89640418 | 2023-10-25 | Multiple store applications inaccessible | Can we use Intune to do a bulk device reboot by doing it in groups. This will save time. Windows platform tablet support are liaising with Microsoft | Solution & Recovery | Mary Priya Lourdu | Microsoft does not support bull restart using groups .Therefore, tech have developed a script solution to perform bulk reboots. | Retail App |  | NA | 25/11/23 | CLosed | https://confluence.marksandspencer.app/display/DS/Options+to+Bulk+Restart+Intune+Managed+Devices |  |  | Saloni | 2025-02-10 | 708 | >60 | November | 2023 | #VALUE!
GTS | ETP- Cloud operations / Frameworks | 89640418 | 2023-10-25 | Multiple store applications inaccessible | Next time agree as best as possible, a common outage window for all impacted applications in AKS. | Problem avoidance | Prathyush Makkaparambil Ramachandran | This will be adhered going forward during any AKS upgrades. Also any AKS related changes have been restricted during PEAK | Cloud |  | NA | 2023-05-11 | Closed |  |  |  | Saloni | 2025-02-10 | 708 | >60 | November | 2023 | #VALUE!
Customer Channels | Platform & Store Ops | 89640418 | 2023-10-25 | Multiple store applications inaccessible | Click and collect product team to review what alerting they have available or need to implement in case of an outage. | Problem identification & Alerting | Rohith Ravindran | Alerts are being tested in non prod. Due to peak activities, the ETA provided is 25/11 28/11: We tried multiple options but couldn't get any reliable alerting using Newrelic. As setting up low traffic alerts will trigger false alerts after store closure And Newrelic don't provide an option to compare traffic against a day and alert, therefore this is not feasible | Retail App |  | NA | 25/12/23 | Closed |  |  |  | Saloni | 2025-02-10 | 708 | >60 | December | 2023 | #VALUE!
GTS | ETP- Cloud operations / Frameworks | 89640418 | 2023-10-25 | Multiple store applications inaccessible | SD were not aware of the upgrade happening and therefore they only had one resource on shift at the time. Ensure advance notification (a month) is given to SD and Service Leads. | Business & IT Communication | Prathyush Makkaparambil Ramachandran | This has been agreed | Cloud |  | NA | 2023-05-11 | Closed |  |  |  | Saloni | 2025-02-10 | 708 | >60 | November | 2023 | #VALUE!
GTS | ETP- Cloud operations / Frameworks | 89640418 | 2023-10-25 | Multiple store applications inaccessible | In future upgrades the cloud team can control and ensure no new nodes are spun up so that the IP address does not get reassigned. Prathyush to ensure the SOP is edited. | Problem avoidance | Prathyush Makkaparambil Ramachandran | The SOP has been updated | Cloud |  | NA | 2023-05-11 | Closed |  |  |  | Saloni | 2025-02-10 | 708 | >60 | November | 2023 | #VALUE!
Customer Channels | Service Experience | 89637079 | 2023-10-25 | Issues with card payments at stores | In P2Pe decryption module, Adjust the retry mechanism for further optimization | Root cause | Laura | 17/11: Worldline confirmed that it is completed | Service leads - Service experience |  | NA | 17/11/23 | Closed |  |  |  | Saloni | 2025-02-10 | 708 | >60 | November | 2023 | #VALUE!
Customer Channels | Service Experience | 89637079 | 2023-10-25 | Issues with card payments at stores | In P2Pe decryption module, autorecovery mechanism enhancement | Permanent Fix | Laura/Raza/Kanan | 27/11: Action is at Worldline and product team has raised the reference PFOUND-380 - WL to track it with them in their regular hypercare call with worldline 21/11: Raza is checking with Worldline on this action 17/11: Worldline updated that they are working on it | Service leads - Service experience |  | NA | 27/11/23 | Closed |  | PFOUND-380 - WL | Open | Saloni | 2025-02-10 | 708 | >60 | November | 2023 | #VALUE!
Customer Channels | Service Experience | 89637079 | 2023-10-25 | Issues with card payments at stores | In P2Pe decryption module, enhance the intrinsic robustness of the decryption module by integrating the learnings of the incident | Permanent Fix | Laura/Raza/Kanan | 27/11: Action is at Worldline and product team has raised the reference PFOUND-381 - WL to track it with them in their regular hypercare callcall with worldline 21/11: Raza is checking with Worldline on this action 17/11: Worldline updated that they are working on it | Service leads - Service experience |  | NA | 27/11/23 | Closed |  | PFOUND-381 - WL | Open | Saloni | 2025-02-10 | 708 | >60 | November | 2023 | #VALUE!
Customer Channels | Service Experience | 89637079 | 2023-10-25 | Issues with card payments at stores | In all modules, study the possibility to add principles of segregation on some of the key components per category | Problem identification & Alerting | Laura/Raza/Kanan | 27/11: Action is at Worldline and product team has raised the reference PFOUND-387 - WL to track it with them in their regular hypercare callcall with worldline | Service leads - Service experience |  | NA | 27/11/23 | Closed |  | PFOUND-387 - WL | Open | Saloni | 2025-02-10 | 708 | >60 | November | 2023 | #VALUE!
Customer Channels | Service Experience | 89637079 | 2023-10-25 | Issues with card payments at stores | In all modules, improve the existing failover mechanisms that protect the platform | Problem identification & Alerting | Laura/Raza/Kanan | 27/11: Action is at Worldline and product team has raised the reference PFOUND-386 - WL to track it with them in their regular hypercare callcall with worldline 21/11: Raza is checking with Worldline on this action 17/11: Worldline updated that they are working on it | Service leads - Service experience |  | NA | 27/11/23 | Closed |  | PFOUND-386 - WL | Open | Saloni | 2025-02-10 | 708 | >60 | November | 2023 | #VALUE!
Customer Channels | Service Experience | 89637079 | 2023-10-25 | Issues with card payments at stores | Ascertain the root cause from Worldline. | Root cause | Raza | 07/11: The issue was caused due to a threshold effect resulting from some latency of in the decryption components response times, and triggering a snowball effect on such components, leading to an unforeseeable availability decrease of the decryption solution. | Payment Foundation Team |  | NA | 2023-07-11 | Closed |  |  |  | Saloni | 2025-02-10 | 708 | >60 | November | 2023 | #VALUE!
Customer Channels | Service Experience | 89637079 | 2023-10-25 | Issues with card payments at stores | Does the underlying issue require a permanent fix? | Permanent Fix | Raza | 07/11: WL updated that they have adjusted the retries mechanism for further optimization | Payment Foundation Team |  | NA | 2023-07-11 | Closed |  |  |  | Saloni | 2025-02-10 | 708 | >60 | November | 2023 | #VALUE!
Customer Channels | Service Experience | 89637079 | 2023-10-25 | Issues with card payments at stores | Arrange a review with worldline | Supplier and support involvement | Rehan/Raza | 24/11: Few actions were agreed with Worldline during the review and are added separately 21/11: Raza to followup with WL on this 16/11: Multiple actions have been agreed like Store communication/incident messaging, Scenario planning, Freeze period clarity and store support and awaiting for further update from WL 15/11: Review with WL Senior leadership is done, awaiting further details from Raza 13/11: Raza is OOO and will be back by 14th 06/11: Next review with WL by 10th with Senior leadership | Payment Foundation Team |  | NA | 24/11/23 | Closed |  |  |  | Saloni | 2025-02-10 | 708 | >60 | November | 2023 | #VALUE!
Customer Channels | Service Experience | 89637079 | 2023-10-25 | Issues with card payments at stores | Review when we are in an offline scenario, what dashboard and monitoring do we have available and see if we can firstly identify the exact impact and look to have an automated process to engage the correct product team to investigate the issue. | Problem identification & Alerting | Bala/Kanan | 12/12: Teams have incorporated the dashboards in along with their main ones and have created alerts for the same 28/11: Teams are currently working on setting up additional alerts 22/11: Alerting policies are addressed this week 17/11: Sessions are going on, Alerting policies will be addressed in this upcoming week. 09/11: All required sessions are discussed and scheduled till 24th Nov and during the sessions teams are working on alert notification mechanisms to understand the impact 07/11: Walkthrough for existing alert and dashboard was given to Payments foundation team. Team requested for additional KT for the application and flow which is in progress currently. | Payment Foundation Team |  | NA | 2023-12-12 | Closed |  |  |  | Saloni | 2025-02-10 | 708 | >60 | December | 2023 | #VALUE!
Customer Channels | Service Experience | 89637079 | 2023-10-25 | Issues with card payments at stores | Do we have any alerts in our network environment that will notify us immediately if we are not getting any response from Worldline | Problem identification & Alerting | Kanan | 27/12: Kanan confirmed that we have alert where we are not depending on worldline one. Alert in network layer is additionally being worked upon with the backlog, hence closing the action 21/12: Have asked Kanan if there are any other alerts other than the worldline 19/12: Kamal updated that "From our previous experience we need to capture the failure events to alert for better monitoring experience. Zero receive packets will automatically switch the payment to offline mode and this alerting is not going to help." Awaiting further response from Kanan 12/12: Kamal (NOC) will work on this in Q4 with backlog and awaiting for a backlog 05/12: NOC team is planning for a workshop on this 27/11: Jira PFOUND-347 created to track the action with NOC 22/11: Kanan to share the Jira ID and copy MIM to the followeup mail to NOC 20/11: Have asked Kanan if a backlog can be raised for it 17/11: WL confirmed that they cannot have any change done before early next year 15/11: Kanan is OOO 13/11: Followed up with Kanan, Kanan raised with WL for alternative PD alerts 09/11: Kanan discussed with WL to get the fix applied sooner rather than post peak 07/11: Kanan is waiting for an update from Worldline after escalation 26/10: Current dashboard in the network layer not able to capture tcp packet data responses from Worldline’s newer platform, need to be fixed at WL | Payment Foundation Team |  | NA | 27/12/23 | Closed |  | PFOUND-347 | Closed | Saloni | 2025-02-10 | 708 | >60 | December | 2023 | #VALUE!
Customer Channels | Service Experience | 89637079 | 2023-10-25 | Issues with card payments at stores | The comms was sent in a delayed manner, review the process for both MIM and business comms relating to card payment issues. | Business & IT Communication | Laura/Rehan/Sathish | MIM and service leads have reviewed the MIM and business comms and created appropriate templates that are stored in a central repository. | Service leads - Service experience |  | NA | 25/10/23 | Closed |  |  |  | Saloni | 2025-02-10 | 708 | >60 | October | 2023 | #VALUE!
Customer Channels | Service Experience | 89637079 | 2023-10-25 | Issues with card payments at stores | Review the relevancy and levels of stakeholders (stores, D&T, Business continuity) that must be communicated to. The complexity here may delay communicating to people who actually need to know about the issue. Review the second layer to stakeholder management comms especially out of hours. | Business & IT Communication | Laura/Darren | 07-11: Laura confirmed that it has been reviewed | Service leads - Service experience |  | NA | 2023-07-11 | Closed |  |  |  | Saloni | 2025-02-10 | 708 | >60 | November | 2023 | #VALUE!
Customer Channels | Service Experience | 89637079 | 2023-10-25 | Issues with card payments at stores | How can Connect Colleague help in the event of a major incident to notify our store colleagues of a retail issue. | Business & IT Communication | Andy/Darren | 22/11: David updated that they don't keep a reference of items on their backlog. They have understood the problem and will be building it as part of Store Help product initiative which will be funded for next financial year. This will be taken care as part of D&T Leadership. 21/11: Andy directed to connect with David Gutteridge (Sr. Pdt Mgr, Store Ops) for the backlog ID and he is OOO today 18/11: Have followed up with Andy for the backlog reference ID 14/11: Andy updated that the action is added to the backlog of Connected Colleague team and awaiting for a reference ID 07/11: Gokul has written to Andy R and Darren G - awaiting reply | CTO and HoP |  | NA | 22/11/23 | Closed |  |  |  | Saloni | 2025-02-10 | 708 | >60 | November | 2023 | #VALUE!
Customer Channels | Service Experience | 89637079 | 2023-10-25 | Issues with card payments at stores | Review whether the SD are asking the correct questions of store colleagues when they call in to report the issue to ensure we record the accurate problem scenario. Review the templates that the service desk use | Problem identification & Alerting | Rehan/Jaya/Raza | 27/11: Raza and Kanan reviewed the existing SD template and confirmed it is fine 24/11: Call is scheduled on 27/11 17/11: Rehan is looking for a slot when all are available 14/11: Jaya is OOO till 15th 07/11: Rehan to setup a meeting with Raza, Kanan , Laura and Jaya where we can review the questions and template | Payment Foundation Team |  | NA | 27/11/23 | Closed |  |  |  | Saloni | 2025-02-10 | 708 | >60 | November | 2023 | #VALUE!
Customer Channels | Service Experience | 89637079 | 2023-10-25 | Issues with card payments at stores | Payments team to review the MI Team text and mail comms DL and add anyone they feel relevant. | Solution & Recovery | Kanan | 27/10: Payment team added to respective DLs and subscribed to WL Instore Alerts | Payment Foundation Team |  | NA | 27/10/23 | Closed |  |  |  | Saloni | 2025-02-10 | 708 | >60 | October | 2023 | #VALUE!
Customer Channels | Service Experience | 89637079 | 2023-10-25 | Issues with card payments at stores | Have a matrix diagram of the details of product teams relating to payments are made available to MIM team. Ensure all relevant teams are part of future PIR’s. | Issue handling/Management | Raza/Amrit | 26/03: Raza shared the document, it is mainly the below and they are updated in contact repo. -Payment Capabilities for settlements, refunds, reconciliation (CATS / PRTS), sparkscash -Payment Foundations for card declines, gift card, colleague discount and sparkspay Global escalations: Dan L., Raza 21/03: Raza is working with his team on the document and expected to share by 25th EOD. 13/03: Dan has completed the contact repo updates, awaiting for Raza's 1 page doc to close the action 08/03: Checked with Raza on 1 page doc and Dan on contact repo 25/02: Followed up with Raza &Team on the document and Contact Repo update. 19/02: Based on the call with Raza, Kanan and Amrit, it was decided that Raza would provide a quick guide for the Payment related issues and for the contact repo update for all the teams, there would be a seperate call internally 12/02: Have followedup with Amrit 02/02: Shared the required details with Amrit and awaiting response 26/01: Raza suggested to connect with Amrit and he is working on it 18/01: Raza to delegate the action to TPM's 09/01: Have scheduled a call by 11/01 with Raza to check on his access 27/12: We have shared the direct link to Raza for checking, he is OOO on store days 22/12: Have shared an alternate link to access the tutorial with Raza and awaiting response 19/12: Have scheduled a call at 11 with Raza 05/12: For Raza's access issue, sharepoint team is working on and he is OOO and will be back by 11/12 27/11: MIM will refer PagerDuty for POG, Raza is having issues in accessing the contact repo Tutorial and to update the details for other payment teams 21/11: Contact Repo is not fetching the details from PAger duty for POG, MIM is checking on it 20/11: Kanan has added Payment Orchestration Gateway (POG) to contact repo 15/11: Have shared the the contact repo tutorial to Raza for other payment teams 13/11: Kanan to tc for Payments foundation team, Raza to update for all other payments teams 08/11: Gokul has shared the contact repo tutorial to Kanan 07/11: MIM to connect with Kanan and help them on updating the contact repository | Payment Foundation(POG)/Experience(FrontEnd)/Capabilities(WCS backend) Team |  | NA | 26/03/24 | Closed |  |  |  | Saloni | 2025-02-10 | 708 | >60 | March | 2024 | #VALUE!
Customer Channels | Service Experience | 89637079 | 2023-10-25 | Issues with card payments at stores | What workarounds do we have in place internally such as circuit breakers and kill switches that will allow offline transactions? Payments team to collaborate with respective teams to analyse the feasibility of the above and when any workaround should be initiated during an issue. | Solution & Recovery | Kanan/Laura | 12/12: Payments team to work with required team with the backlog 05/12: NOC team is planning for a workshop on this 27/11: Jira PFOUND-348 created to track the action with NOC 22/11: Kanan to share the Jira ID and copy MIM to the followeup mail to NOC 17/11: Network team is looking into the feasibility of establishing a common switch in the network layer 14/11: Call is rescheduled with all required stakeholders by 17/11 09/11: NOC team to check if switch can be configured in Network layer 07/11: Laura to initiate a call with Kanan, Richard Wrightwells and NOC to start the discussion about kill switches and resiliency in the event of a World Outage. | Payment Foundation Team |  | NA | 2023-12-12 | Closed |  | PFOUND-348 | Closed | Saloni | 2025-02-10 | 708 | >60 | December | 2023 | #VALUE!
Customer Channels | Service Experience | 89637079 | 2023-10-25 | Issues with card payments at stores | Laura to speak to central store operations about how the comms/advice to stores can be edited to be more specific and prescriptive that will allow stores to know what action to take to manage customer expectations during an outage. | Business & IT Communication | Laura/Payment products team | 07/11: Pre approved comms have been approved by the Business and are stored in the General Chat, files for the on call service lead to use | Payment products team |  | NA | 2023-07-11 | Closed |  |  |  | Saloni | 2025-02-10 | 708 | >60 | November | 2023 | #VALUE!
Customer Channels | Service Experience | 89637079 | 2023-10-25 | Issues with card payments at stores | Get the Worldline Ops manual updated to reflect the relevant contacts within Customer to include the level one support contacts. | Supplier and support involvement | Raza | 29/02: Raza has shared the offline copy to Gary (WL) 25/02: Raza agreed to update the offline copy and send to WL. Followed up with Raza on it 19/02: Based on the call, it was decided to discuss with Laura to update the Ops manual and a mail is sent by Rehan 15/02: Call scheduled with Amrit and Raza on 19th 12/02: Have followedup with Amrit 02/02: Shared the required details with Amrit and awaiting response 26/01: Raza suggested to connect with Amrit and he is working on it 18/01: Raza to delegate the action to TPM's 14/01: Have followed up with him on his availability 09/01: Have scheduled a call by 11/01 with Raza on this 04/01: Followed up with Raza on the status of the Ops manual update 21/12: Raza followed up worldline for the live Ops manual link 19/12: Raza has requested for the live worldline Ops manual link and has followed up now 12/12: Have followed up with Raza and awaiting updates 05/12: Raza is OOO and will be back by 11/12 28/11: Proper channel for Worldline to reach Customer is still being discussed, so that the Ops Manual is updated accordingly 24/11: Discussions are in progress on updating the WL Ops Manual 20/11: Raza is checking on this 18/11: Followed up with Raza on this status 07/11: Raza will liaise with Worldline on updating their ops manual | Payment Foundation Team |  | NA | 29/02/24 | Closed |  |  |  | Saloni | 2025-02-10 | 708 | >60 | February | 2024 | #VALUE!
GTS | Operations | 89610397 | 2023-10-23 | Delay in Q UI availability and Pre-allocations due to hardware failure | During any monitoring overnight, especially in hypercare, if we are still unable to resolve the issue despite multiple actions then engage MIM in a timely manner before the impact becomes significant so that MIM can review the situation. | Impact analysis | MIM | This has been agreed for better understanding on the issue and its impact inorder to derive timely resolution | Operations |  | NA | 23/10/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 710 | >60 | October | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89610397 | 2023-10-23 | Delay in Q UI availability and Pre-allocations due to hardware failure | Review whether there are alerts for FRA filling up and what the thresholds are. Do a review of the file system and FRA alerts to see if they are all fit for purpose. | Problem identification & Alerting | Jishin Jacob | 11/13 - Alert thresholds are reviewed and it is valid. Earlier the threshold was set as : 85% is high and 95% is critical, which is fit for the purpose. After the issue it is now modified to 80% and 85% respectively for the effective alert handling. 11/11 - Jishin to update on the latest on Monday (13/11) | Oracle DBA Support |  | NA | 13/11/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 710 | >60 | November | 2023 | #VALUE!
Foods | Foods Supply Chain | 89610397 | 2023-10-23 | Delay in Q UI availability and Pre-allocations due to hardware failure | Once the foods team was engaged, review how was the wider impacted assessed, appreciated and communicated to a wider audience. | Impact analysis | Andrew Goslin | The key issue was that the impact of the hardware failure and the potential threat to Q was not understood. In particular, the fact that if the storage was full the DB would halt and impact Q services was not clear to the Q devops team. This has been noted for the future. | Foods TEM |  | NA | 2023-10-11 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 710 | >60 | November | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89610397 | 2023-10-23 | Delay in Q UI availability and Pre-allocations due to hardware failure | A lot of actions were done to try and reroute the backups but due to an Oracle bug the filesystem was not recognising the new storage. Test the procedures provided by Oracle in non-prod. | Root cause | Jishin Jacob | 30/11 - To change the FRA destination teams had decided on a workaround - To mount the temporary mount point due to high FRA usage, it needs to be added to the current value of db_recovery_file_dest_size to the free space available at the new temporary mount point and set it at DB level. 21/11 - The steps provided by oracle did not help to recalculate the actual FRA after changing the FRA dest to new mount point, But we have a workaround to handle this situation. This is currenlty being tested 13/11- Team is still working on the relevant testing. Next update on 15th Nov 11/11 - Jishin to update on the latest on Monday (13/11) | Oracle DBA Support |  | NA | 30/11/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 710 | >60 | November | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89610270 | 2023-10-22 | Delay in the Quantum User Interface availability and pre-allocations due to a hardware failure | During any monitoring overnight, especially in hypercare, if we are still unable to resolve the issue despite multiple actions then engage MIM in a timely manner before the impact becomes significant so that MIM can review the situation. | Impact analysis | WMS/Oracle/MIM | This action has been acknowledged by all the teams during the PIR. MIM will be invoked as and then they see the issue getting bigger | All |  | NA | 15/11/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 711 | >60 | November | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89610270 | 2023-10-21 | Delay in the Quantum User Interface availability and pre-allocations due to a hardware failure | Review whether there are alerts for FRA filling up and what the thresholds are. Do a review of the file system and FRA alerts to see if they are all fit for purpose. | Problem identification & Alerting | Jishin | Alert thresholds are reviewed and it is valid. 85% is high and 95% is critical threshold which is fit for the purpose | Oracle DBA Support |  | NA | 2023-10-11 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 712 | >60 | November | 2023 | #VALUE!
Foods | Foods Supply Chain | 89610270 | 2023-10-20 | Delay in the Quantum User Interface availability and pre-allocations due to a hardware failure | Once the foods team was engaged, review how was the wider impacted assessed, appreciated and communicated to a wider audience | Impact analysis | Andrew Goslin | The key issue was that the impact of the hardware failure and the potential threat to Q was not understood. In particular, the fact that if the storage was full the DB would halt and impact Q services was not clear to the Q devops team. This has been noted for the future. | Foods |  | NA | 2023-10-11 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 713 | >60 | November | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89610270 | 2023-10-19 | Delay in the Quantum User Interface availability and pre-allocations due to a hardware failure | A lot of actions were done to try and reroute the backups but due to an Oracle bug the filesystem was not recognising the new storage. Test the procedures provided by Oracle in non-prod. | Root cause | Jishin | The steps provided by oracle did not help to recalculate the actual FRA after changing the FRA dest to new mount point, But we have a workaround to handle this situation. This is tested | Oracle DBA Support |  | NA | 15/11/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 714 | >60 | November | 2023 | #VALUE!
GTS | Digital Workplace Services | 89613207 | 2023-10-11 | Some colleagues were unable to access O365 applications | what type of alert can be implemented in the cloud solution when an abnormal number login failure due to the various reasons – should an alert go to the cyber sec team as “unauthorised” people are logging in. | Problem identification & Alerting | Farid Arab | 08/11 - PIR action taken by Rehan from Saloni. Farid checked this, and service health is already setup under the Cyber Subscription. There is a Service Health dashboard for this. This will only cover true sign in issues on the Microsoft side. Cyber will also be notified of unusual logins. | active Directory |  | NA | 2023-08-11 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 722 | >60 | November | 2023 | #VALUE!
Infosec & Tech Risk | Infosec & Tech Risk | 89613207 | 2023-10-11 | Some colleagues were unable to access O365 applications | The programme create a list of lessons learnt from this incident so that this issue can be prevented going forward | Problem avoidance | Jagan Krishnan | 24/11 - Jegan advised they have created a lessons learnt document and handing it over to IAM BAU team for their future reference. | Info Security |  | NA | 24/11/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 722 | >60 | November | 2023 | #VALUE!
Infosec & Tech Risk | Infosec & Tech Risk | 89613207 | 2023-10-11 | Some colleagues were unable to access O365 applications | Review all M accounts / Recertification of the international team – verify that all users are correct and still valid | Problem avoidance | Peter Boyle/ One Identity | These are long term actions to review and rectify the bad data habits. | Info Security |  | NA |  | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 722 | >60 | January | 1900 | #VALUE!
Infosec & Tech Risk | Infosec & Tech Risk | 89613207 | 2023-10-11 | Some colleagues were unable to access O365 applications | Review the edge case (things that rarely happen) such as country moves/change of employee number | Problem avoidance | Peter Boyle/ One Identity | These are long term actions to review and rectify the bad data habits. | Info Security |  | NA |  | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 722 | >60 | January | 1900 | #VALUE!
Infosec & Tech Risk | Infosec & Tech Risk | 89613207 | 2023-10-11 | Some colleagues were unable to access O365 applications | All P accounts that have been re-enabled for 30 days – if these are genuine, line manager will have to extend beyond 30 days – this is being monitored PB’s team | Problem avoidance | Peter Boyle/ One Identity | Closed as this is ongoing | Info Security |  | NA | 2023-11-10 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 722 | >60 | October | 2023 | #VALUE!
Infosec & Tech Risk | Infosec & Tech Risk | 89613207 | 2023-10-11 | Some colleagues were unable to access O365 applications | Some accounts were obviously out of policy (set to never expire) – we do not want these to never expire – the team has removed the never expire flag and will monitor if the line managers reinstate this | Problem avoidance | Peter Boyle/ One Identity | Closed as this is ongoing | Info Security |  | NA | 2023-11-10 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 722 | >60 | October | 2023 | #VALUE!
Infosec & Tech Risk | Infosec & Tech Risk | 89613207 | 2023-10-11 | Some colleagues were unable to access O365 applications | Ian Banks and team are handling the issues of persistent bad housekeeping through education and training. | Problem avoidance | Ian Banks | Closed as this is ongoing | Info Security |  | NA | 2023-11-10 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 722 | >60 | October | 2023 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89603749 | 2023-10-11 | Ecomm refund issue at Ollerton DC | When WMS were sending the refunds to Sterling it required manually reconciliation and therefore a use case needs to be proposed and drafted for automated this | Solution & Recovery | Nanda/Rajeev | 15/11: Team is still working on automated scripts and it will be tracked as part of the product back log. Awaiting JIRA id. 31/10: Use case/scenarios has been Identified. Team working on creating automated scripts. | WMS Team |  | NA | 21/11/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 722 | >60 | November | 2023 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89603749 | 2023-10-11 | Ecomm refund issue at Ollerton DC | During the major incident call, the WMS team wanted to know which order numbers were contributing to the 20% CFR and this took a significant amount of time to gather. Arthi to see if there is a better way to get the specific order numbers without having to inconvenience .com operations team, it should be possible between Sterling and WMS. Nanda to start the discussion with Andrew Crow to see what raw data they rely on for their CFR dashboard. | Solution & Recovery | Arthi/Nanda and Andrew | 13/11: Nandha confirmed that, the exisiting CFR dashboard is having the data. 07/11: 2nd October 2.9k of orders were shared that had failed already that needed to be investigated. CFR failures can be found here in the tab “Failed orders” 07. Returns - Power BI. Awaiting further updates from Nandha of the dashboard. 31/10: Further follow ups made and awaiting updates | WMS Team |  | NA | 14/11/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 722 | >60 | November | 2023 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89603749 | 2023-10-11 | Ecomm refund issue at Ollerton DC | Normally the return CFR trend is monitored by Andrew Crow’s team (.com operations) however it still took nine days for us to be advised about the issue – why? The CFR was gradually increasing until it hit 20% on 04/10 | Problem identification & Alerting | Andrew Crowe | 07/11: 07/11: It would have taken at least 7 days for the issue to be seen as that is how long we give to customers for their refund so we started missing that promise on day 8. Issue raised on the 2nd of October – post the weekend when the Returns CFR increased. 31/10: Further follow ups made and awaiting updates | .com Operations |  | NA | 2023-07-11 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 722 | >60 | November | 2023 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89603749 | 2023-10-11 | Ecomm refund issue at Ollerton DC | We need to speak to the business about decommissioning the bulk refund job. We can send the numbers of orders where the flag has not been changed as the correct process has not been followed and the business will carry out training for colleagues. | Problem avoidance | Karthick Girichandramohan | 31/10: Bulk refund job cannot decomissioned and the health check emails is now modified to capture the number of order where there flag has not been changed. | WMS Team |  | NA | 31/10/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 722 | >60 | October | 2023 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89603749 | 2023-10-11 | Ecomm refund issue at Ollerton DC | An extra step has been added to the current cutover plan so that it can be placed in any implementation plan to check for historical and purged records that may not have been processed. | Problem avoidance | Karthick Girichandramohan | The action is complete | WMS Team |  | NA |  | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 722 | >60 | January | 1900 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89603749 | 2023-10-11 | Ecomm refund issue at Ollerton DC | Going forward the purging logic has now been changed back to seven days so that only orders more than seven days will be purged. Purging logic has been standardised across all tables. | Problem avoidance | Karthick Girichandramohan | The action is complete | WMS Team |  | NA |  | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 722 | >60 | January | 1900 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89579766 | 2023-10-06 | Latency in orders processing into WMS at Brands | Carry out performance testing on the Order Daemon to ensure we can handle the PEAK volume | Problem avoidance | Nandakumar Sivalingam | 11/13 - After the relevant testing, deployment has been completed on 11/10 to improve daemon performance. 11/11 - Actoins have been assigned to the right engineers to perform the testing. We expect an update on Monday 13/11. 16/10 - This action is still in progress and expected to close by this week 20/10 | Service Lead |  | NA | 13/11/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 727 | >60 | November | 2023 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89579766 | 2023-10-06 | Latency in orders processing into WMS at Brands | Review all the codes associated to Order daemon and ensure there are no further improvements required. | Permanent Fix | Kunal Chichkar | 10/10 - No further merge rules had any issues. As the issue is addressed - Thus closing this off the tracker | WMS Team |  | NA | 2023-10-10 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 727 | >60 | October | 2023 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89579766 | 2023-10-06 | Latency in orders processing into WMS at Brands | Site to provide latest forecasted figures and forecasted hourly peak volume (i. 5k per hour etc) | Solution & Recovery | Nandakumar Sivalingam | 16/10 -Site confirmed that 47K orders were processed in a single day in previous sale (03rd Aug) | Service Lead |  | NA |  | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 727 | >60 | January | 1900 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89579766 | 2023-10-06 | Latency in orders processing into WMS at Brands | Ensure the pending order header and lines record count are visible on the hourly report. | Solution & Recovery | Nandakumar Sivalingam | Changes deployed to the hourly health check for WMS support monitoring on 24/09 | Service Lead |  | NA | 2023-06-10 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 727 | >60 | October | 2023 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89579766 | 2023-10-06 | Latency in orders processing into WMS at Brands | Hypercare plan (monitoring, check point calls etc) for next Promotion and Peak event (November Black Friday weeks) | Problem avoidance | Nandakumar Sivalingam | 11/13 -Hypercare has been agreed with the site from 11/16. 11/11 - Nandha is yet to finalize on the conclusion or decisions made along with the DC colleagues. 16/10 - This action is being reviewed along the DC operationsduring WMS biweekly connect.Discussions are on-going | Service Lead |  | NA | 13/11/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 727 | >60 | November | 2023 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89599990 | 2023-10-04 | Welham Green DC power outage causing wi-fi issues | MIM will be engaged in a more timely manner with wider scale issues and products teams have been made aware to engage MIM where required. | Issue handling/Management | Nandakumar Sivalingam | 09/10: Nanda confirmed "Meeting conducted with in product group and agreed all major issues will be handled via MIM to address any timely communication gapsHave followed up with Nanda on the status of the action" | Service Lead |  | NA | 2023-09-10 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 729 | >60 | October | 2023 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89599990 | 2023-10-04 | Welham Green DC power outage causing wi-fi issues | An excess of traffic for GARP and IPMC was generated through multicast traffic which is normal. However the amount of multicast traffic is abnormal and NOC team to investigate what happened after the power outage that caused the spike. Is there any possibility to stop an excess of this traffic. | Root cause | Rajesh/Kamal | 23/10: Huge multicast traffic generated due to locus robot management server, which was in a hung state after a power outage, locus team recovered the servers. Its recommended to have UPS and generator backup for all the assets in the site. 17/10: An interim solution is to setup UPS for each of the network server comms rack. Next call to discuss further with WG Ops team along with Service Leads is by 23rd. 09/10: Have followed up with Rajesh on the status of the action | Network |  | NA | 23/10/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 729 | >60 | October | 2023 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89599990 | 2023-10-04 | Welham Green DC power outage causing wi-fi issues | Juniper have recommended DDOS protection settings and the NOC team will review with the architects and enable if relevant. | Problem avoidance | Rajesh/Kamal | 23/10: Architect reviewed the recommendation and decided to keep the DDOS threshold as default since it will protect the switching environment from multiple other security threats. 17/10: An interim solution is to setup UPS for each of the network server comms rack. Next call to discuss further with WG Ops team along with Service Leads is by 23rd. 09/10: Have followed up with Rajesh on the status of the action | Network |  | NA | 23/10/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 729 | >60 | October | 2023 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89599990 | 2023-10-04 | Welham Green DC power outage causing wi-fi issues | There is no UPS apart from the one serving the mains cabinet. There is no other UPS for other areas in Welham serving as resilience. Get clarity from site as to where the resilience is. | Problem avoidance | Nandakumar Sivalingam/Site Operations at Welham | 10/10: •Do we have any immediate UPS back up available to run operations in case of a power outage? No •If we have a UPS back up, how long it will last without the main supply? N/A •If we do not have UPS back up, what is the contingency/ risks agreed? The agreement is that a portable generator is brought in within a 4-hour SLA from the point of request With these questions answered, we have clarity on the resilience, hence closing the action 09/10: Have followed up with Nanda on the status of the action | WMS |  | NA | 2023-10-10 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 729 | >60 | October | 2023 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89599990 | 2023-10-04 | Welham Green DC power outage causing wi-fi issues | The North Building UPS is also faulty and is in the process of being replaced on 09/10 | Problem avoidance | Nandakumar Sivalingam/Don | 09/10: Nanda confirmed that "The UPS was replaced successfully on 09/10 (CR#189196) without any operations impact" | WMS |  | NA | 2023-09-10 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 729 | >60 | October | 2023 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89599990 | 2023-10-04 | Welham Green DC power outage causing wi-fi issues | The robotics were still not working after the wireless connectivity was restores as the robotics requires a separate restart – WMS support need to take the lead in engaging Locus support and instructing them to restart their devices once we have confirmed that network connectivity is restored to the relevant AP’s. | Solution & Recovery | Nandakumar Sivalingam | 09/10: Nanda confirmed that "WMS team will work with WG site operations for Locus issues, but need all relevant Tech groups from Customer IT to perform their health check validations and for any issues – need to collaborate for resolution" | Service Lead |  | NA | 2023-09-10 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 729 | >60 | October | 2023 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89599990 | 2023-10-04 | Welham Green DC power outage causing wi-fi issues | An additional step needs to be added in the fault finding to health check the DMZ switch in future. | Solution & Recovery | Rajesh/Kamal | 17/10: Updated the SOP with these steps, hence closing 09/10: Have followed up with Rajesh on the status of the action | Network |  | NA | 17/10/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 729 | >60 | October | 2023 | #VALUE!
Foods | Foods Supply Chain | 89600186 | 2023-10-04 | Drop in Relex supplier order volume | Accenture team to investigate the possibility of a warning and outright rejection for the user to advise that end date is in the past to prevent the issue happening again. | Problem avoidance | Anshuman Pani | 30/10 --Upon investigations from the Relex end, Frontend rejection/validation is not feasible in RELEX Plan/design, however in the Backend validation/rejection of erroneous records is feasible. Relex support to work in the feasibility via the JIRA FOATR-18775 backlog during the sprint planning. | Accenture Relex Team |  | NA | 2023-11-06 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 729 | >60 | June | 2023 | #VALUE!
Foods | Foods Supply Chain | 89600186 | 2023-10-04 | Drop in Relex supplier order volume | SOP to be updated short term, long term have work flows ready for the various failure scenarios/batch check points which will also ensure the data is cleared before the batch is run. | Problem avoidance | Anshuman Pani | 30/10 - Relex support team has confirmed that their SOP has been updated based on this scenario- | Accenture Relex Team |  | NA | 30/10/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 729 | >60 | October | 2023 | #VALUE!
Foods | Foods Supply Chain | 89600186 | 2023-10-04 | Drop in Relex supplier order volume | The team is trying to come up with data level checks that will identify issues such as duplicate allocations. Quality level checks also need to be added to capture invalid or erroneous scenarios in the outbound orders. | Problem avoidance | Anshuman Pani | 30/10 - •Additional data level checks have been added to daily batch output. This includes performing a row count check and comparing to same day of week from last week to confirm that they are within allowable threshold of variation. This information is published to the business user group | Accenture Relex Team |  | NA | 30/10/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 729 | >60 | October | 2023 | #VALUE!
Foods | Foods Supply Chain | 89600186 | 2023-10-04 | Drop in Relex supplier order volume | Need to further look at options that will identify a significant drop or increase in supplier orders downstream before they get to the suppliers. Once the options have been identified we can take these back to Customer Food for them to advise if they want to proceed. | Problem identification & Alerting | Promoth Kumar/Matt White | Update 10/11 - Rehan spoke with Matt White and he advised that our previous checks were only based on file size and now we have amended this to look at the number of records. | Accenture Relex Team |  | NA | 2023-10-11 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 729 | >60 | November | 2023 | #VALUE!
Foods | Foods Supply Chain | 89600186 | 2023-10-04 | Drop in Relex supplier order volume | Review and suggest improvements to the existing major incident communications Tech and business process for incidents with regards to Relex | Business & IT Communication | Promoth Kumar/Matt White | 10/11 We have had a review with Relex and advised them that they need to update MIM directly. They have a new SDM who is clear on the MIM contact details. We shall review the comms from Relex during the next incident to see if it has improved. 07/11 Service Design and Transition are being engaged to improve the service wrap and communication on Relex issues. Joey says that this is being handled under the communication. Rehan to talk to Sathish/Matt | Accenture Relex Team |  | NA | 2023-10-11 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 729 | >60 | November | 2023 | #VALUE!
Group Support | Finance | 89582869 | 2023-09-29 | Issue in POS sales flow in SAP POSDTA | Configure automated alerts in SAP POSDTA for message pile ups | Problem identification & Alerting | Krishnaprasad Rajendran/Balakrishna Chadalawada | 21/11 - This has been addressed during the Nov release. No further issues observed after the latest release. Alerting is working as expected. 30/10 - Due to some underlying issue the alerting set0up was not implemented during the october release. Thus it is postponded to november release ETA 20/11 SAP POSDTA alerting is planned in the Oct release – ETA 20/10. Currently, manual hypercare is in place. Currently, the alerts are being tested in the dev environment. The alerting threshold will be validated before deploying in production. | SAP |  | NA | 21/11/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 734 | >60 | November | 2023 | #VALUE!
Group Support | Finance | 89582869 | 2023-09-29 | Issue in POS sales flow in SAP POSDTA | Reason behind the change failure | Root cause | Remko Smit | As a part of the SAP monthly release on 22/09, a change was introduced to address an existing issue of message failures due to duplicate records insertion (combination of promotion lines with multiple discount types) in the POSDTA tables. On 23/09, there were additional and complex scenarios on the combination of promotion and discount types which resulted in POS sales messages not processing as expected. The root cause attributed to insufficient testing scenarios before the change implementation. | SAP |  | NA | 30/09/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 734 | >60 | September | 2023 | #VALUE!
Group Support | Finance | 89582869 | 2023-09-29 | Issue in POS sales flow in SAP POSDTA | Proactive communication to the downstream systems | Business & IT Communication | Remko Smit /Krishnaprasad Rajendran | The issues started at 22:00 on 22/09, the downstream product teams were notified only at 05:30 on 23/09. With the message pile up threshold determined; proactive communication will be sent to the consumers. Note: There was no impact on business due to delay in comms | SAP |  | NA | 30/09/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 734 | >60 | September | 2023 | #VALUE!
Group Support | Finance | 89582869 | 2023-09-29 | Issue in POS sales flow in SAP POSDTA | Ensure efficient testing in the lower environment by include complex test scenarios | Permanent Fix | Remko Smit/ Balakrishna Chadalawada | Product teams are in the process of identifying a robust test pack by including a more complex combination of promotion and discount types to address the issue. This will also be added in the regression test suite. A backlog SAP-SLS-00174 has been raised for this | SAP |  | NA | 30/09/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 734 | >60 | September | 2023 | #VALUE!
Group Support | Finance | 89582869 | 2023-09-29 | Issue in POS sales flow in SAP POSDTA | Improve the existing manual hypercare to recover the message failures | Solution & Recovery | Remko Smit/Balakrishna Chadalawada | 16/10 - As per the discussions with team, it has been decided that the change is not mandatory as we do have the workarounds in place along with effective hypercare. currently the scope of impact is being assessed again to conclude on the change and this will be further tracked via a backlog - SAP-SLS-00174. Also the SOP is updated on the agreed workaround and Peer Review is initiated formally. The change will be deployed after PEAK after appropriate testing is completed and there is enough confidence to implement in production. Meanwhile the existing manual hypercare will continue until the alerts are configured. As part of manual hypercare, adhoc jobs are executed to process the messages into the downstream systems. A threshold of 300k messages has been set for sending comms to the downstream systems. The SOP has been updated on the same Peer review of the data as per manual hypercare. | SAP |  | NA | 16/10/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 734 | >60 | October | 2023 | #VALUE!
Customer Channels | Selling Experience | 89580029 | 2023-09-28 | Issues placing orders via old safari browser version | Reapply temp fix with a clean tested change using split instead of regex patterns. | Solution & Recovery | Onyx Team | The issu is fixed under the back log - 10995 | Onyx Team |  | NA | 28/09/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 735 | >60 | September | 2023 | #VALUE!
Customer Channels | Selling Experience | 89580029 | 2023-09-28 | Issues placing orders via old safari browser version | Investigate and resolve issue with Akamai cache clear | Solution & Recovery | Onyx Team | The alerting is tracked as part of the Jira back log SHOPBE-1788 | Onyx Team |  | NA | 28/09/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 735 | >60 | September | 2023 | #VALUE!
Customer Channels | Selling Experience | 89580029 | 2023-09-28 | Issues placing orders via old safari browser version | Configure alerting to ensure this issue is detected by the relevant team | Problem identification & Alerting | Onyx Team | The alerting is tracked as part of the Jira back log SHOPBE-1789 | Onyx Team |  | NA | 28/09/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 735 | >60 | September | 2023 | #VALUE!
Customer Channels | Service Experience | 89589952 | 2023-09-27 | Payment issues causing an order outage | Holding page for checkout only so that customers can still browse the site? What messaging should accompany this? In a previous PIR for another incident App team agreed to look at using Optimizely to enhance the holding page and drop locking. Keith Bradshaw is looking into having checkout-only holding page on desktop and mweb. | Issue handling/Management | Apps - Tim Searle/ Matthew Magee Desktop/mWeb - Keith Bradshaw | 06-11: Hisham confirmed that the action was raised for awareness and impossible to track. 31-10: Hisham is checking on this | iOS App Team |  | NA | 2023-06-11 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 736 | >60 | November | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89589952 | 2023-09-27 | Payment issues causing an order outage | Certificate renewal guidelines. Cloud Ops team will share the documentation and will be cascaded to all the teams. | Problem avoidance | Vidhyasagar Balakrishnan | 31-10: Vidhya confirmed that 2 sets of How-To session and recordings are shared with detailed documentation. Along with it template is updated with “not to allow special characters or multiple entries” to avoid any failures. Hence closing | Cloud Ops team |  | NA | 31/10/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 736 | >60 | October | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89589952 | 2023-09-27 | Payment issues causing an order outage | Muziris portal guidelines. Cloud Ops team will record a tutorial which will be shared with all the teams. | Problem avoidance | Vidhyasagar Balakrishnan | 31-10: Vidhya confirmed that 2 sets of How-To session and recordings are shared with detailed documentation. Along with it template is updated with “not to allow special characters or multiple entries” to avoid any failures. Hence closing | Cloud Ops team |  | NA | 31/10/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 736 | >60 | October | 2023 | #VALUE!
Customer Channels | Service Experience | 89589952 | 2023-09-27 | Payment issues causing an order outage | SME or Peer review of the certificate renewal activity to avoid any obvious mistakes or misses. | Problem avoidance | All Product Teams | 06-11: Hisham confirmed that the action was raised for awareness and impossible to track. 31-10: Hisham is checking on this | All product teams |  | NA | 2023-06-11 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 736 | >60 | November | 2023 | #VALUE!
Customer Channels | Service Experience | 89589952 | 2023-09-27 | Payment issues causing an order outage | Review and update the certificate renewal SOP for Payments area so the process is clear to all members of the team. | Problem avoidance | Balaji / Kanan | 06-11: Hisham confirmed that the action was raised for awareness and impossible to track. 31-10: Hisham is checking on this | Payments foundation |  | NA | 2023-06-11 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 736 | >60 | November | 2023 | #VALUE!
Customer Channels | Service Experience | 89589952 | 2023-09-27 | Payment issues causing an order outage | Validations (Hypercare) to encompass the original expiry date (not just the renewal time) so to quickly pick up any misses like this. For example, if the certificate is expiring on 27th and is renewed on 13th, then the validations and hyper care should not be limited to the 13th but should also cover period around 27th. | Problem avoidance | All Product Teams | 06-11: Hisham confirmed that the action was raised for awareness and impossible to track. 31-10: Hisham is checking on this | All product teams |  | NA | 2023-06-11 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 736 | >60 | November | 2023 | #VALUE!
Group Support | Platform & Store Ops | 89580465 | 2023-09-26 | Performance issues in CSSM application | Feasibility of performing a monthly reboot of the CSSM web server | Problem avoidance | Bharath Murugan | The plan is to perform a clean reboot of the CSSM servers once every month – 8th OCT, 5th NOV, the plan for Dec is being discussed. | CSSM DevOps |  | NA | 16/10/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 737 | >60 | October | 2023 | #VALUE!
Customer Channels | Platform & Store Ops | 89580465 | 2023-09-26 | Performance issues in CSSM application | Review the platform architecture of the CSSM application. Is it possible to host the application on a different infrastructure with more I/O capacity to mitigate the issue in future. | Permanent Fix | Bharath Murugan/ Nick Watson | This is a long term action, in parallel, the migration to cloud is also planned It was concluded that CSSM application requires more available memory and the VSAN infrastructure is not an ideal platform. Therefore, Elizabeth and Nick will discuss further the feasibility of moving the application to a different platform. Elizabeth to recommend platform options like Pure Storage etc. In parallel, the plan to move CSSM to CLOUD is also lined up. ETA: by Sept 2024 | CSSM DevOps |  | NA | 16/10/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 737 | >60 | October | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89580465 | 2023-09-26 | Performance issues in CSSM application | What caused the hardware failure? Why the CSSM data rebuild took time as part of the recovery process? | Root cause | Dharmaraj Balasubramanian | A faulty hardware was detected in the ESXI host which serves the CSSM application virtual machines on 21/09 and 15:30 due to a memory module and array controller failure in the infrastructure. The faulty hardware was replaced on 23/09 and has remained stable. As part of the automatic recovery process, the CSSM data was rebuilt into the alternate host. It is believed that due to an increased usage of the CSSM application due to the time of the day, the data rebuild took longer resulting in the overrunning of multiple jobs and performance issues in CSSM. | VM Ware Team |  | NA | 26/09/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 737 | >60 | September | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89580465 | 2023-09-26 | Performance issues in CSSM application | Ascertain the stability of the problematic host after the hardware replacement. What is the plan to introduce the VMs to this host? | Solution & Recovery | Dharmaraj Balasubramanian | 10/10: The host has remained stable with no issues observed with the introduction of the non-critical VMs. The faulty hardware was replaced on 23/09 and the host has been stable for the past 4 days. VMware team are planning to introduce the non-critical VMs to this host and test the stability. | VM Ware Team |  | NA | 16/10/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 737 | >60 | October | 2023 | #VALUE!
Customer Channels | Platform & Store Ops | 89580465 | 2023-09-26 | Performance issues in CSSM application | What caused the system resource contention on the CSSM application servers? | Root cause | Dharmaraj Balasubramanian /Bharath Murugan/Murali Irrinki | 10/10: It is believed that during the data replication in the CSSM database servers on the alternate host, whist the web servers continuously tried to connect to the database servers for processing the messages, it resulted in the spike in memory consumption causing the delay in the message flow. However, there is no significant evidence to prove this. As a precaution, the CSSM web server memory is being uplifted on 08/10 from 6gb to 8gb Initial analysis indicates an increase in the number of MQ explorer user sessions causing memory contention. However, the teams will regroup and perform a detailed analysis of the existing logs to ascertain the cause. | CSSM DevOps |  | NA | 16/10/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 737 | >60 | October | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89580465 | 2023-09-26 | Performance issues in CSSM application | Uplift the memory of the CSSM web server. Configure an alert with a memory threshold. Create a SOP detailing the steps to bring down the memory | Solution & Recovery | Dharmaraj Balasubramanian/Bharath/Ravi S | 16/10: The memory has been uplifted. The alerts are in place. Monitoring is underway to identify the threshold value to avoid false alerts. After the memory uplift on the CSSM server on 22/09, it was identified that the memory utilization is spiking between 75-85%, therefore, a decision has been taken to further uplift the memory from 6gb to 8gb. Application to review the thresholds of the existing alert in CSSM. A SOP to be created detailing the relevant steps to bring down the memory utilization incase the issue recurs. | VM Ware Team |  | NA | 16/10/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 737 | >60 | October | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89580465 | 2023-09-26 | Performance issues in CSSM application | Improvement on the HP engagement process as there was a considerable delay in addressing the faulty hardware issue. | Supplier and support involvement | Elizabeth Golder | Elizabeth has escalated to HP management to address the gap and ensure appropriate support during PEAK | Service Lead - GTS |  | NA | 16/10/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 737 | >60 | October | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89580465 | 2023-09-26 | Performance issues in CSSM application | The automatic recovery process of data rebuilding started on 21/09, however, there was a lack of proactive communication to the impacted product teams | Business & IT Communication | Elizabeth Golder | We have now agreed with the service lead to ensure proactive communication are sent to the relevant teams for timely impact assessment and comms to the stakeholders | Service Lead - GTS |  | NA | 26/09/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 737 | >60 | September | 2023 | #VALUE!
GTS | Enterprise Integration | 89580465 | 2023-09-26 | Performance issues in CSSM application | Feasibility of moving the MQ explorer to a different server | Solution & Recovery | Murali Irrinki | With the memory being uplifted, it has been agreed not to move the MQ explorer sessions to a diff server It has been identified from the logs, that the MQ explorer user sessions are consuming a considerable amount of memory. Product team will look at the feasibility and deploy it before peak (if possible) | Middleware Admin |  | NA | 16/10/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 737 | >60 | October | 2023 | #VALUE!
Customer Channels | Platform & Store Ops | 89580465 | 2023-09-26 | Performance issues in CSSM application | Perform a clean reboot of the CSSM web server before peak. | Problem avoidance | Valliammai Ramasamy/Elizabeth Golder | A clean reboot of the CSSM servers (database, application etc) will be performed as a precautionary measure to terminate any unnecessary sessions likely to be consuming adhoc system resource. This will be performed in the upcoming CSSM outage (already agreed) | Multiple Owners |  | NA | 16/10/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 737 | >60 | October | 2023 | #VALUE!
Customer Channels | Selling Experience | 89574094 | 2023-09-22 | Drop in orders on website | Load Testing There was a discussion around the fact that load testing should be a continuous activity within each team rather than have a once-a-year Peak Readiness load test. | Problem avoidance | Elaine Hawthorn | This is an observation, not an action and impacts wider engineering teams | Service Management |  | NA | 22/09/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 741 | >60 | September | 2023 | #VALUE!
Customer Channels | Customer Engagement | 89574094 | 2023-09-22 | Drop in orders on website | Communication Need to review communication channels during an incident (Teams channels, how we get people on incident bridges) . Elaine to organise a session about this and to include Hisham and Theo | Business & IT Communication | Elaine Hawthorn | 31/10: Elaine has confirmed to close the action, has this has been discussed in other sessions. 04/10 - the Respective channel (Sparks incident) is included into the incident communication channel which will pave way for effective communication between teams while there is a major incident. | Service Management |  | NA | 31/10/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 741 | >60 | October | 2023 | #VALUE!
Customer Channels | Selling Experience | 89574094 | 2023-09-22 | Drop in orders on website | Visibility of push timings and batch sizes Given that the push notification sizes are being ramped up, there needs to be visibility of when the pushes are occurring and what size they are to wider teams. (E.g to Tech and Operational teams) This will help ensure that push notifications are not being carried out at a time when there is reduced capacity such as running on one hall This ties into the performance testing (point 1). Discussed and agreed that the right people are in the relevant Teams channel. Given that it was a unique combination of events which triggered the excessive requests resulting from the push notification, there is no need to take special care regarding when the push notifications occur. | Business & IT Communication | Elaine Hawthorn | Discussed and agreed that the right people are in the relevant Teams channel. Given that it was a unique combination of events which triggered the excessive requests resulting from the push notification, there is no need to take special care regarding when the push notifications occur. | Service Management |  | NA | 22/09/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 741 | >60 | September | 2023 | #VALUE!
Customer Channels | Customer Engagement | 89574094 | 2023-09-22 | Drop in orders on website | Improve error handling in Android App 500 errors were encountered and instead of stopping network calls, the app kept on re-trying the request resulting in a large volume of spurious requests being sent to WCS . Improved error handling is required to prevent the continuous re-tries Two errors are being fixed 1) Handling of re-retrying requests 2) Fix for 500s | Problem avoidance | Matthew Magee | 10/10: The re-trying of requests on Android has been partially addressed, but the full solution will take a lot longer and isn't part of this resolution and it will be tracked under the JIRA back log | Android App |  | NA | 2023-10-10 | Closed | NA | AMNS-11445 |  | Saloni | 2025-02-10 | 741 | >60 | October | 2023 | #VALUE!
Customer Channels | Selling Experience | 89574094 | 2023-09-22 | Drop in orders on website | WCS Fix for requests being sent to Key Store As a result of investigation into the code, it was identified that requests to the WCS key store to obtain the certificate to validate the token are occurring for each request. It is believed that this could be causing a block but this needs to be proved and if correct, a fix is required to obtain the certificate once (rather than for each request). | Permanent Fix | Satish Gopinathan | 31/10: The fix has been deployed successfully 10/10: The testing is still in progress and is planned to deploy into production by 16/01 A fix has been coded and is currently in SIT2 waiting for performance testing w/c 25th September | WCS |  | NA | 31/10/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 741 | >60 | October | 2023 | #VALUE!
Customer Channels | Selling Experience | 89574094 | 2023-09-22 | Drop in orders on website | Rate Limit Cap More investigation is required before the rate limit can be increased further. Have agreed to keep this at 4K for now. (Note: in many of the APIs the limit is 20k) Performance testing required to understand what the cap should be and what WCS can handle | Solution & Recovery | Simon Attard | 31/10: The rate limit can be increased upto 20K, hence there is no fall back required Simon advised that loading testing is being carried out based upon the parameters in place during the incident. The WCS fix will go in (point 3) and then further load testing will take place. Based upon this testing, the rate limit will be agreed so that it should be clear what WCS can cope with. This can then be matched to push notification batch size (point 4) The question was raised that if any limitations are identified which could compromise business proposition, is there a fallback? This is part of a wider discussion | WCS |  | NA | 31/10/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 741 | >60 | October | 2023 | #VALUE!
Customer Channels | Customer Engagement | 89574094 | 2023-09-22 | Drop in orders on website | Financial impact Financial impact to be reviewed in light of potential loss arising from halting of marketing send | Impact analysis | Theo Waardenburg | 08/11: Priya has advised to close this actions as this a good to have option to validate the impact during the issue. Hence closing this action the actions 31/10: The ownership of the impact assessment is being discussed still | WCS |  | NA | 2023-08-11 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 741 | >60 | November | 2023 | #VALUE!
Customer Channels | Customer Engagement | 89574094 | 2023-09-22 | Drop in orders on website | Rate Limit Alert OAuth alert on apps to be amended to be more sensitive . This will enable us to be aware of a rate limit issue sooner. (It was at 1% 401s over 5 minutes, to be reduced to 0.75% over 5 minutes.) | Problem identification & Alerting | Tim Searle | Alerts have also been added in the identity dashboard to capture 429 (too many requests) errors. | WCS |  | NA | 22/09/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 741 | >60 | September | 2023 | #VALUE!
Group Platforms | Finance | 89560574 | 2023-09-21 | Stock discrepancy of £24m affecting supplier payments | It has been agreed that SAP would give more time for peer to peer review of the actual design, test design and test results. | Problem avoidance | Remko/Andrew/Balram | NA/09: Discrepancyprogress | SAP |  | NA | 21/09/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 742 | >60 | September | 2023 | #VALUE!
Group Platforms | Finance | 89560574 | 2023-09-21 | Stock discrepancy of £24m affecting supplier payments | After go live, time needs to be allocated to studying the content of the goods receipts rather than just the fact the GR’s have been posted | Problem avoidance | Remko/Andrew/Balram | NA/09: Discrepancyprogress | SAP |  | NA | 21/09/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 742 | >60 | September | 2023 | #VALUE!
Group Platforms | Finance | 89560574 | 2023-09-21 | Stock discrepancy of £24m affecting supplier payments | Going forward after changes, foods DC stock integrity report can be potentially be used to ensure that the number of GR’s coming in from GIST have been received in SAP. Discussion to be had to agree the way forward as to whether any other tool can be potentially used for the reconciliation. | Solution & Recovery | Remko/Andrew/Balram | 29-09: Remko confirmed that "SAP Foods Mission team (Prabhakar) have confirmed that they will run this business report after future (DC GR related) changes, as additional safety net. If RDC or NDC variance is > 1.5M, then they will investigate whether that relates to the deployed change.". With this agreement, the action is being closed 27-09: Remko is checking with SAP Foods team on using the STock Integrity report for post-golive checks | SAP |  | NA | 29/09/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 742 | >60 | September | 2023 | #VALUE!
Group Platforms | Finance | 89560574 | 2023-09-21 | Stock discrepancy of £24m affecting supplier payments | Review communication process when incidents are managed by Tech teams rather than centrally by MIM. | Business & IT Communication | Remko/Andrew/Balram | 09/10: Remko and Andrew agreed that "going forward Finance Tech and Finance business will agree on who will inform the Finance Leadership" and agreed to close the action 02/10: Andrew is back, have asked the latest updates on this action 27-09: Remko said to reach out to Andrew for this action | SAP |  | NA | 2023-09-10 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 742 | >60 | October | 2023 | #VALUE!
Supply Chain | Foods Supply Chain | 89557480 | 2023-09-19 | Delay in frozen delivery receipt from GXO to CSSM | Root cause – failure of a CISCO component due to a bug which affected their virtual machines at 2am – this impacted multiple clients of GXO EU wide. | Root cause | Adrian Duff (GXO) | Failure of the Cisco UCS component of the VM estate at GXO had caused the central issue. The UCS is the hardware upon which the VMs reside and operate. Cisco has advised of a bug and GXO has received a patch from Cisco which is currently being tested and will be implemented. | Foods |  | NA | 19/09/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 744 | >60 | September | 2023 | #VALUE!
Supply Chain | Foods Supply Chain | 89557480 | 2023-09-19 | Delay in frozen delivery receipt from GXO to CSSM | A patch is being tested and this will be deployed in production when ready to mitigate the known bug identified by Cisco. | Permanent Fix | Adrian Duff (GXO) | 10/10 - The Patch has been provided by Cisco and is tested and is installed into production 03/10 - the follow-up email has been sent to GXO for the latest update | Foods |  | NA | 2023-10-10 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 744 | >60 | October | 2023 | #VALUE!
Supply Chain | Foods Supply Chain | 89557480 | 2023-09-19 | Delay in frozen delivery receipt from GXO to CSSM | Could the restart have been done any sooner to mitigate impact? | Solution & Recovery | Adrian Duff (GXO) | 07/11 Rehan spoke with Joey and GXO have improved their SOP for this issue and will be able to communicate better with Customer and where possible restart their services earlier to save time on recovery 03/10 - the follow-up email has been sent to GXO for the latest update | Foods |  | NA | 2023-07-11 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 744 | >60 | November | 2023 | #VALUE!
Supply Chain | Foods Supply Chain | 89557480 | 2023-09-19 | Delay in frozen delivery receipt from GXO to CSSM | Due to this incident a GXO firewall upgrade was cancelled due on 10/09 (Sat into Sunday) and this needs to be rescheduled | Problem avoidance | Adrian Duff (GXO) | 07/11: Rehan and Joey read the last update and concluded no further action necessary 10/10 -GXO Patching was cancelled on 10/09 but the firewall upgrade went ahead. This caused the issue Sunday morning. It was fixed forward so there is no further work to take place on this. 03/10 - the follow-up email has been sent to GXO for the latest update | Foods |  | NA | 2023-07-11 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 744 | >60 | November | 2023 | #VALUE!
Supply Chain | Foods Supply Chain | 89557480 | 2023-09-19 | Delay in frozen delivery receipt from GXO to CSSM | Review incident communication process at GXO and see if this needs to go through GIST and confirm the process. | Business & IT Communication | Adrian Duff (GXO) and Zachary Moore (GIST) | 07/11 Rehan and Joey spoke and Joey confirmed that the the communication with GXO must go through the RDC network (GIST) who in turn will raise a log with the GXO Operations and GXO IT according. GIST will handle the incident communication process. 10/10 - GXO IT communication can only be to GXO Operations as per their policy and GXO does only desk to desk communication to Ops team while the OPS team is resposible for further communication 03/10 - the follow-up email has been sent to GXO for the latest update | Foods |  | NA | 2023-07-11 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 744 | >60 | November | 2023 | #VALUE!
Supply Chain | Foods Supply Chain | 89557480 | 2023-09-19 | Delay in frozen delivery receipt from GXO to CSSM | The NPC schedule (GIST) needs to kept updated so that real time information is provided – because it wasn’t, the impact of the number of stores was not clear until much later. | Impact analysis | Chris Thompson GIST | 14/02 Action complete 25/01 Chris advises that having spoken to NPC it doesn’t appear that anyone within the IT function currently receives these updates. The updates go to people in retail roles (Abu Thalid and Joe Stoneham) however both of these have transferred from Customer across to Gist now. Please could you advise a suitable mailing list for me to share with NPC to ensure any future changes are communicated to all relevant parties - Joey to proceed 22/01 Chris to send the NPC DL to Joey for review. 02/01- Rehan spoke with Chris Thompson today. The NPC schedule is kept up to date but Chris advised that the DL list the scedule should go to at Customer needs to be refreshed, Rehan advised Joey. 12/12 Joey has asked me to liaise with Chris Thompson at GIST 13/11 Emailed GIST again 08/11 - Emailed Tony and Alice 07/11 - Rehan spoke with Joey and it was agreed that Rehan will email Tony Turner and Alice Sambrook 03/10 - the follow-up email has been sent to GXO for the latest update | Foods |  | NA | 14/02/24 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 744 | >60 | February | 2024 | #VALUE!
Supply Chain | Foods Supply Chain | 89557480 | 2023-09-19 | Delay in frozen delivery receipt from GXO to CSSM | Prepare and provide a distribution list in readiness for incident communications | Business & IT Communication | Vinoth/Jay | 12/12 - Rehan spoke with Joey and they now have the appropriate DL that will be used to reach out to the GIST stakeholders. 27/11 - Rehan chased Joey, Jay and Vinoth again 07/11 Rehan spoke with Joey and we need more context on this action so we can get traction 03/10 - the follow-up email has been sent to GXO for the latest update | Foods |  | NA | 2023-12-12 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 744 | >60 | December | 2023 | #VALUE!
Commercial Trading | Foods Commercial Trading | 89558638 | 2023-09-16 | Delay in Relex overnight batch | Identify an efficient way of sending comms to the relevant stakeholder - Supply chain planners, suppliers, stores colleagues, finance colleagues etc | Business & IT Communication | Joey Ocansey | 08/11: An effective comms process has been agreed. 16/10: This incident involved notification to be sent out to multiple stakeholders, therefore, a call will be scheduled with Joey and the food product teams to streamline an efficient plan on sending comms in future instances. | Foods Service Lead |  | NA | 2023-10-11 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 747 | >60 | November | 2023 | #VALUE!
Commercial Trading | Foods Commercial Trading | 89558638 | 2023-09-16 | Delay in Relex overnight batch | Agree with Relex to ensure proactive communication are sent to Customer FOA team (TCS + Accenture) in case of any central issues. | Problem identification & Alerting | Matt White | 10/11: The list has been shared with Relex including the key Customer contacts, FOA teams (TCS and Accenture) and MIM. 16/09: Agree on the list of recipients to be involved in the comms. (FOA teams) | TPM |  | NA | 2023-09-11 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 747 | >60 | November | 2023 | #VALUE!
Commercial Trading | Foods Commercial Trading | 89558638 | 2023-09-16 | Delay in Relex overnight batch | What is the business resilience plan at Relex? | Problem avoidance | Michael Shotbolt | 09/11: Relex has confirmed that DR is completed successfully. 16/10: There is a significant delay in getting updates from Relex SAAS. Foods business, MATT is chasing with them 16/09: An internal discussion is ongoing at Relex to perform the relevant DR test to ensure business resilience at Customer, especially during PEAK. ETA – Nov 23 | Relex |  | NA | 2023-05-11 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 747 | >60 | November | 2023 | #VALUE!
Commercial Trading | Foods Commercial Trading | 89558638 | 2023-09-16 | Delay in Relex overnight batch | Feasibility of providing a visibility to the Relex service health report to track the progress of the overnight batch | Problem avoidance | Michael Shotbolt | 09/11: Matt White has advised the RELEX SaaS team to reach out to MIM team (with the contacts) in case of any central issue at their end. 16/10: There is a significant delay in getting updates from Relex SAAS. Foods business, MATT is chasing with them 16/09: This is being discussed within the Relex management. | Relex |  | NA | 2023-10-11 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 747 | >60 | November | 2023 | #VALUE!
Commercial Trading | Foods Commercial Trading | 89558638 | 2023-09-16 | Delay in Relex overnight batch | Identify an effective way of engaging Relex during OOO hours | Supplier and support involvement | Michael Shotbolt | 08/11: Matt White has agreed with Relex and a list of key contacts have been agreed to urgently reaching during OOO hours. Also the Service delivery heads rota are captured for effective engagement. 16/10: There is a significant delay in getting updates from Relex SAAS. Foods business, MATT is chasing with them 16/09: The current process to engage Relex is via raising a ticket in JIRA. We have advised Relex to provide a list of key contact details (escalation) for better engagement – especially during PEAK trading months. | Relex |  | NA | 2023-09-11 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 747 | >60 | November | 2023 | #VALUE!
Commercial Trading | Foods Commercial Trading | 89558638 | 2023-09-16 | Delay in Relex overnight batch | Alerting configuration at Relex for proactive issue identification | Problem identification & Alerting | Michael Shotbolt / Relex | 16/09: Relex has confirmed that alerts have now been configured to identify database faults to identify any issues proactively and communicate appropriately | Relex |  | NA | 16/10/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 747 | >60 | October | 2023 | #VALUE!
Commercial Trading | Foods Commercial Trading | 89558638 | 2023-09-16 | Delay in Relex overnight batch | Root cause of the issue – What caused the performance/slowness issue at Relex? Why were empty store order proposal files generated on 10/09 after the Relex nightly run. | Root cause | Michael Shotbolt / Relex | The distributed storage platform (Storage Grid) at Relex consists of 38 database nodes. One of the service responsible for replicating the data across the nodes according was stuck on one of the 38 nodes on 30/08. The stuck service exhausted available nodes by 6:00am BST 9/9, which resulted in the performance/latency in RELEX system 16/09: The performance/slowness issue in the Relex overnight batch was caused due to a faulty database node within the Storage Grid at Relex – managed by NetApp (3rd party supplier to Relex) due to a possible bug in the NetApp environment. This also resulted in the generation of empty store order proposal files on 10/09. However, Relex continue to investigate the detailed root cause analysis with NetApp and a follow – up call will be scheduled based on the feedback received from Relex. | Relex |  | NA | 16/10/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 747 | >60 | October | 2023 | #VALUE!
Commercial Trading | Foods Commercial Trading | 89558638 | 2023-09-16 | Delay in Relex overnight batch | Feasibility of automating the successful delivery of the 28 - day order plan to the suppliers through an email. | Solution & Recovery | Promoth Kumar & Asha Padmanaban | This is not feasible as it is a legacy server. A risk has been accepted in this case. 16/09: The messaging server responsible for delivering the 28-day order plan to the suppliers is a legacy server and no further architectural changes or configuration is possible. However, the feasibility will be verified. | Foods & Messaging |  | NA | 16/10/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 747 | >60 | October | 2023 | #VALUE!
Customer Channels | Platform & Store Ops | 89558638 | 2023-09-16 | Delay in Relex overnight batch | Feasibility of deriving a contingency plan across other impacted products – CSSM SST, Foods analytics reporting (Reporting) to remediate the immediate impact | Solution & Recovery | Valliammai Ramasamy & Timothy Barrett | There is no such contingency plan for Retail and Data 16/09: This needs further discussion and MIM will speak to the service leads to understand the possibility. | Service lead |  | NA | 16/10/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 747 | >60 | October | 2023 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89553489 | 2023-09-14 | Multiple food applications (ASO, SCRD, ORCA and OFP) were unavailable | Alerting found the issue at 7am and we could not have saved any more time in identifying the fact that there was an issue. | Issue handling/Management | Note | It was agreed in the call | Network |  | NA | 14/09/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 749 | >60 | September | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89553489 | 2023-09-14 | Multiple food applications (ASO, SCRD, ORCA and OFP) were unavailable | Whenever a change is deployed relating to intelligent routes a full end to end analysis of the routes will be carried out and added to the implementation plan. Change management and NOC management to cascade this process to their teams. | Problem avoidance | Kamal/Rajesh/Priya | This has been cascaded to all teams and also during CABs change team are raising this as an ask during due dilligence | Service Management |  | NA | 30/09/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 749 | >60 | September | 2023 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89553489 | 2023-09-14 | Multiple food applications (ASO, SCRD, ORCA and OFP) were unavailable | The service flow was not properly appreciated prior to the change and also there is no lower environment. Foods env operates under Active Active – in lower environment there is only one region. | Root cause | Note | Incident caused by change. Objective of change: The current Azure Hub and Spoke design allows traffic to transit through virtual network gateways via Express Route, however this introduces a risk of lateral movement between portfolios. As part of security strategy, this change was deployed to add routes in the production foods route tables thus allowing all the traffic to go via either the azure firewall or PA firewall based in the flow. It will reduce the attacks and vulnerability issues. Change & Recovery update: The change started at 05:35, and it was implemented as per plan and completed at 07:00. After the work, alerting highlighted that a few areas had connectivity issues (MQ and ES API calls failing). It was found that the inter region connectivity failed. As work around a change was made in the firewall policy to allow the traffic through the azure firewall but the issue persisted. It was then decided to revert the change to restore service. | Network |  | NA | 30/09/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 749 | >60 | September | 2023 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89553489 | 2023-09-14 | Multiple food applications (ASO, SCRD, ORCA and OFP) were unavailable | Need to analyse and understand the reported application traffic flow with food application team. | Problem avoidance | Fastin | Team had already done this analysis before the PIR | Network |  | NA | 14/09/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 749 | >60 | September | 2023 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89553489 | 2023-09-14 | Multiple food applications (ASO, SCRD, ORCA and OFP) were unavailable | We need to do the design review including the service flow to ascertain the exact cause of the connectivity issues. | Problem avoidance | Mahendran Mahalingam | Multiple calls were done and it was found that due to cross region connectivity this issue had occurred | Network |  | NA | 30/09/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 749 | >60 | September | 2023 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89553489 | 2023-09-14 | Multiple food applications (ASO, SCRD, ORCA and OFP) were unavailable | We need to review the cross-region firewall policy restriction procedure with cloud architect to ascertain exactly where the cause of the issue is. | Root cause | Fastin & Vidhyasagar | 31/10 - The document is in discussion with the cloud architect and Cybersec, once is approved. The cause is ascertained to be asymmetric routing between 2 cross regions (North Europe and West Europe). 24/10 - Fastin has created design document for this and next week, he will take it cloud architect forum to proceed further. | Network |  | NA | 31/10/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 749 | >60 | October | 2023 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89553489 | 2023-09-14 | Multiple food applications (ASO, SCRD, ORCA and OFP) were unavailable | Revise the reversion plan with exact timelines. | Issue handling/Management | Mahendran Mahalingam | Informed the team to have the reversion plan with exact timelines. | Network |  | NA | 30/09/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 749 | >60 | September | 2023 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89553489 | 2023-09-14 | Multiple food applications (ASO, SCRD, ORCA and OFP) were unavailable | All teams to ensure that they are fully prepared for the next change with full knowledge of the flows and infrastructure and the change should be run under hypercare with experienced SMEs. The change should be deployed at an appropriate time. | Problem avoidance | Note | It was agreed in the call | Network |  | NA | 14/09/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 749 | >60 | September | 2023 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89553489 | 2023-09-14 | Multiple food applications (ASO, SCRD, ORCA and OFP) were unavailable | Speak to Cyber Security and agree whether this really needs to be done before peak | Problem avoidance | Mahendran/Fastin/Cyber Security | 31-10: NOC team confirmed that it will be done post peak | Network |  | NA | 31/10/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 749 | >60 | October | 2023 | #VALUE!
Customer Channels | Customer Engagement | 89551947 | 2023-09-13 | Issue with SparksPay | Process : Update documentation for cert renewal to include the both the domains in SAN value | Problem avoidance | Gautam | Document has been updated | Wallet Experience |  | NA | 2023-09-11 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 750 | >60 | November | 2023 | #VALUE!
Customer Channels | Customer Engagement | 89551947 | 2023-09-13 | Issue with SparksPay | Process – Follow Peer to peer review for certificate renewal requests | Problem avoidance | Gautam | 23/11:There is an automated process which will be used for any certificate request/renewal https://portal.muziris.cloud.mnscorp.net/create/templates/default/certificate-template | Wallet Experience |  | NA | 27/11/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 750 | >60 | November | 2023 | #VALUE!
Customer Channels | Customer Engagement | 89551947 | 2023-09-13 | Issue with SparksPay | Explore options to auto renew the certificates | Problem avoidance | Sandeep | 23/11:There is an automated process which will be used for any certificate request/renewal https://portal.muziris.cloud.mnscorp.net/create/templates/default/certificate-template | Wallet Experience |  | NA | 27/11/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 750 | >60 | November | 2023 | #VALUE!
Customer Channels | Customer Engagement | 89551947 | 2023-09-13 | Issue with SparksPay | Process – Review the sparkspay severity matrix with business | Problem avoidance | Divakar/Ram | 08/11: The Sparks Pay service design and severity matrix is being re-worked as part of launching Sparks Pay In-Store at the end of February 2024. This will be tracked as part of rhe product backlog - Wallet-229 | Wallet Experience |  | NA | 2023-09-11 | Closed | NA | WALLET-229 |  | Saloni | 2025-02-10 | 750 | >60 | November | 2023 | #VALUE!
Customer Channels | Customer Engagement | 89551947 | 2023-09-13 | Issue with SparksPay | Alerting – Setup alerts for drop in traffic (availability) | Problem identification & Alerting | Gautam | 13/09: Alerting has been configured | Wallet Experience |  | NA | 13/09/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 750 | >60 | September | 2023 | #VALUE!
Customer Channels | Customer Engagement | 89551947 | 2023-09-13 | Issue with SparksPay | Process – Make SAN value mandatory while requesting for the digi cert in muziris | Problem avoidance | Venkatesan | Completed - Cert team confirmed that it is already mandatory in Muziris | Wallet Experience |  | NA | 16/09/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 750 | >60 | September | 2023 | #VALUE!
Customer Channels | Service Experience | 89545728 | 2023-09-06 | Timeout issue with Accertify | Review option to ‘override’ TRA exemption to help mitigate the impact on conversion. For incident day, conversion was 83% versus +94%, with commercial impact of £150K | Problem avoidance | Chris Etherington | 26/09: Given that we TRA +99% of transactions through Accertify, taking a blanket approach during this downtime (e.g., apply for all transactions our end) could alleviate this friction which would offset any fraud risk during this period. This is further protected as we are due to move Gift Card transactions to 3D Secure flows in due course. This approach has be agreed and actions has been confirmed to be closed 15/08: Two viable options are explored to mitigate the risk faced when accertify is down. 1.When Accertify is down, we can apply a TRA exemption for all transactions within some local controls 2. Customer stores the last view from Accertify to drive the right behaviour. 14/08: Awaiting update from Chris. | Payment Foundation Team |  | NA | 2023-06-10 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 757 | >60 | October | 2023 | #VALUE!
Customer Channels | Service Experience | 89545728 | 2023-09-06 | Timeout issue with Accertify | Run book to be pulled together with offline & held orders thresholds agreed with business stakeholders for this scenario. This will then allow engineers to be able to disable these checks without having to wait for approvals and help to reduce the order impact and recovery. Needs to cover for both POG & OMS | Solution & Recovery | Payment Foundation Team/ Raza Akram | 26/09: Agreed to invoke 3D Secure for all transactions when a Accertify becomes unavailable, with a swift move to enable the feature switch Dastan to establish a runbook with Service Owners, Operations Manager, from Dotcom & Instore as well as OMS to determine the agreement on SLAs, retries and enable/disable fraud checks SLA’s to be defined with the business stakeholders by when we can switch off the Fraud checks. | Payment Foundation Team |  | NA | 2023-06-10 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 757 | >60 | October | 2023 | #VALUE!
Customer Channels | Service Experience | 89550056 | 2023-09-06 | POS backoffice unavailable | Bala, Wintel and PCM to have a chat with Wintel to see if the alerting s process can be made more efficient | Problem identification & Alerting | Bala/Wintel | 20/09 - A process has been agreed with the teams Wintel, PCM and POS for effective mitigation. 19/09 - POS, Wintel and PCM had a call to discuss on the alerting. Wintel team has agreed to dicuss it further with PCM on the alerting set-up. 15/09 - Bala will schedule a call with PCM and Wintel | POS/Wintel |  | NA | 20/09/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 757 | >60 | September | 2023 | #VALUE!
Customer Channels | Service Experience | 89550056 | 2023-09-06 | POS backoffice unavailable | Exception alerts started at 12:27 and the first call came in at around 12:30. This is a very short period of time and hence nothing could have been done quicker. | Problem identification & Alerting | NA | NA/09: Backofficeprogress | POS |  | NA | 14/09/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 757 | >60 | September | 2023 | #VALUE!
Customer Channels | Service Experience | 89550056 | 2023-09-06 | POS backoffice unavailable | The root cause could be as a result of the SQL2019 upgrade or it could be an issue data/products. The scenarios need to be tested and investigated in non-prod as to why the response time was so long for some queries. | Root cause | POS Devops-Sanjana Prabakar | 16/10 - Testing has been completed and the activity is completed. Trst results are recorded 10/10 - Testing is in-progress. Teams are exploring options on the new release 03/10 - Testing on the scenario was planned for 02/10 and we are yet to get an update on the progress | POS |  | NA | 30/10/2023 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 757 | >60 | 30/10/2023 | #VALUE! | #VALUE!
Customer Channels | Service Experience | 89550056 | 2023-09-06 | POS backoffice unavailable | Review the testing scenarios for POS back office to see what the concurrent number of users the application can handle/maximum load on database at peak time and what is the current actual numbers now – if there is a gap then this needs to be addressed | Problem avoidance | Seeva | 10/10- Script has been modified to accommodate 10 user every 5 secs - basically 10 stores every 5 secs. On a high level 800 stores will be able to ack the red alerts. - enhancement has been made. 03/10 - Seeva is yet to provide an update on this. | POS |  | NA | 2023-10-10 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 757 | >60 | October | 2023 | #VALUE!
Customer Channels | Service Experience | 89550056 | 2023-09-06 | POS backoffice unavailable | Ensure any changes made to hints/queries – the changes are recorded somewhere and version control is implemented. | Problem identification & Alerting | Seeva | 10/10 - GIT Hub is the application that is used for the version controller. 03/10 - Seeva is yet to provide an update on this. | POS |  | NA | 2023-10-10 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 757 | >60 | October | 2023 | #VALUE!
Customer Channels | Service Experience | 89550056 | 2023-09-06 | POS backoffice unavailable | Can we deploy New Relic application monitoring tool for POS Backoffice as we have in tils. | Problem avoidance | Shikhar Khanna | 30/10 - Newrelic is deployed to prod - it was implemented on 24/10 10/10 - Testing is in-progress and it is planned to be implemented in Prod by 24th OCt. 15/09 - currently the deploying of New relic is being done on non prod env and tentatively by 30th Sep it will be deployed in Prod once all the testing scenarios are positive. 06/09 - This is being made ready for the entire POS infrastructure | POS |  | NA | 30/10/2023 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 757 | >60 | 30/10/2023 | #VALUE! | #VALUE!
Customer Channels | Service Experience | 89545728 | 2023-09-06 | Drop in orders on website | Look at introducing the ability to disable fraud checks across both POG & OMS via a single mechanism (via Jenkins pipeline was mentioned for example) | Solution & Recovery | Payment Foundation Team/ Raza Akram | 10/06: recovery for short term and long term unavailabilty of Accertify has been agreed and hence closing this actions as confirmed by Hisham PFOUND team to establish the ‘Plan of Automation’ that can mechanism (via Jenkins pipeline was mentioned for example) disable fraud check within POG & OMS. This has Dependency on OMS tea | Payment Foundation Team/ Raza Akram |  | NA | 2023-06-10 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 757 | >60 | October | 2023 | #VALUE!
Customer Channels | Platform & Store Ops | 89548361 | 2023-09-05 | Issues in the CSSM Foods reporting | We started receiving alerts from 03:00, why was the issue communicated only at 05:18? | Problem identification & Alerting | Bharath Murugan | 05/09: Investigations were carried out by the offshore team and a call was given to the key engineer at 04:45 followed by initiation of a MIM bridge. It has been communicated to the team to ensure more vigilance in alert handling based on the criticality of the impact. | CSSM |  | NA | 2023-05-09 | Closed |  |  |  | Saloni | 2025-02-10 | 758 | >60 | September | 2023 | #VALUE!
GTS | Digital Workplace Services | 89548361 | 2023-09-05 | Issues in the CSSM Foods reporting | The Y account SAM (Security Account Manager) name was changed at 10:38 on 01/09, why did the issue surface itself at 03:00 on 02/09? | Root cause | Farid Arab | 05/09: By default, whenever a new session gets logged into the server, a token gets issued to which is valid for 24 hours. It has been confirmed from the logs that the report replication session got terminated due to token expiry at 03:00 on 02/09 and eventually started failing due to the change in the service account name. | Active Directory |  | NA | 2023-05-09 | Closed |  |  |  | Saloni | 2025-02-10 | 758 | >60 | September | 2023 | #VALUE!
GTS | Digital Workplace Services | 89548361 | 2023-09-05 | Issues in the CSSM Foods reporting | The impacted Y account is responsible for authenticating three different replication servers in CSSM, ascertain the reason behind the impact being limited to one server. | Problem avoidance | Farid Arab | 28/09: Farid updated as "Checked from AD end and the servers are in the same OU and subjected to the same group policies. If the servers were restarted at different times then the authentication sessions will expire at different times, which would be the expected behavior." and agreed to close the action 26/09: Farid is back and expecting update by 27th EOD 20/09: Farid is OOO and expected to be back by 25th 12/09: Muthu updated that "It is practically not possible to check the session timeout settings from the GPO side and the GPO is common to all the machines in OU", will reconfirm with Farid 05/09: CSSM team will provide the other two replication server details to the Active directory team to analyze the session timeout settings for the servers | Active Directory |  | NA | 28/09/23 | Closed |  |  |  | Saloni | 2025-02-10 | 758 | >60 | September | 2023 | #VALUE!
GTS | Digital Workplace Services | 89548361 | 2023-09-05 | Issues in the CSSM Foods reporting | Revisit the production access across the team. How can we avoid logging it to the dev environment from a Prod jump server? | Problem avoidance | Farid Arab | 13/09: Muthu confirmed that RDP has been blocked to both dev and cate AD servers from AD prod jump server and Prod will be connected only through safeguard. Hence closing 12/09:To disable the direct RDP connection will be completed along with patching activity tonight and The Dev and Cate RDP access is restricted from Prod Jump server. 05/09: Actions are being taken to disable the direct RDP (Remote desktop protocol) connection to production via Citrix and the prod environment will be accessed only via Safeguard. With the introduction of Safeguard, the access to dev server from the prod jump server will be revoked through network changes and it (prod jump server) will be purely used for support purposes for production to support the production AD Environment. | Active Directory |  | NA | 13/09/23 | Closed |  |  |  | Saloni | 2025-02-10 | 758 | >60 | September | 2023 | #VALUE!
GTS | Digital Workplace Services | 89548361 | 2023-09-05 | Issues in the CSSM Foods reporting | Create a runbook detailing the checklist whilst testing a script/feature in AD. | Problem avoidance | Farid Arab | 05/09: Any feature/script will be reviewed with the product owner before deploying for testing purposes or into production. | Active Directory |  | NA | 2023-05-09 | Closed |  |  |  | Saloni | 2025-02-10 | 758 | >60 | September | 2023 | #VALUE!
GTS | Digital Workplace Services | 89548361 | 2023-09-05 | Issues in the CSSM Foods reporting | The recovery of the incident was prolonged, how can we ensure that the associates have the right level of knowledge to identify issues in a timely manner? | Solution & Recovery | Farid Arab | 12/09: Muthu updated that Knowledge sharing session is completed. SOP creation is in progress we will get concurrence from Farid and upload to internal SharePoint site. 05/09: Knowledge sharing session and creation of a SOP detailing the failure scenarios and solutions are in progress. | Active Directory |  | NA | 2023-12-09 | Closed |  |  |  | Saloni | 2025-02-10 | 758 | >60 | September | 2023 | #VALUE!
GTS | Digital Workplace Services | 89548361 | 2023-09-05 | Issues in the CSSM Foods reporting | Any modifications made to the Active directory are captured in the Change auditor logs, it took some time to get hold of the colleague having the right level of access to the tool which contributed to delay in the issue resolution. | Solution & Recovery | Farid Arab | 28/09: Farid updated as "Spoke to Ian Banks and he is happy for the AD Team to have this access to Change Auditor. I have raised it with Angela Schoeman from Cyber Security to help with arranging the access. The related requests have been raised for the team to get access" and agreed to close the action 26/09: Farid is back and expecting update by 27th EOD 20/09: Farid is OOO and expected to be back by 25th 12/09:Muthu updated that Farid is still checking with the IAM team on this action. Need to check with him once he is back 05/09: Farid is in discussion with the relevant team to procure Change auditor access for the entire team. | Active Directory |  | NA | 28/09/23 | Closed |  |  |  | Saloni | 2025-02-10 | 758 | >60 | September | 2023 | #VALUE!
GTS | Digital Workplace Services | 89548361 | 2023-09-05 | Issues in the CSSM Foods reporting | Is there an efficient way to distinguish the Prod and Dev environment to prevent any changes being tested in prod. | Problem avoidance | Muthunagappan Subramaniam | 05/09: Currently, the team logs in to a “jump server” to connect to either prod or dev AD environment. The jump server is in Prod, and it is not feasible to change the design from AD Perspective. Team will use production credentials to log on to any jump server and the server clearly reflects “PRODUCTION” in the Background Screen, the same applies for Dev environment. Therefore, this was a manual error. The team has been re-iterated on the rigor and discipline while handling the critical applications. | Active Directory |  | NA | 2023-05-09 | Closed |  |  |  | Saloni | 2025-02-10 | 758 | >60 | September | 2023 | #VALUE!
GTS | Digital Workplace Services | 89548361 | 2023-09-05 | Issues in the CSSM Foods reporting | Root cause of the issue | Root cause | Muthunagappan Subramaniam/ Farid Arab | 05/09: There was a requirement from the Access management team to build a script for performing bulk user account updates during the Peak period. The script was inadvertently tested in the production environment resulting in an abrupt change in the service account name responsible for active directory authentication of the CSSM report replication server. Therefore, the CSSM OLTP (Online Transaction processing) server was unable to connect (authenticate) the reporting server resulting in report replication failures, causing the issue | Active Directory |  | NA | 2023-05-09 | Closed |  |  |  | Saloni | 2025-02-10 | 758 | >60 | September | 2023 | #VALUE!
Customer Channels | Platform & Store Ops | 89548361 | 2023-09-05 | Issues in the CSSM Foods reporting | Efficient impact assessment | Impact analysis | Valliammai Ramasamy | 22/09: Valli has the template for all kind of impacts and is documented 15/09: Valli is working on it 05/09: Due to the nature of the issue, the impact varies based on the duration and time of the issue. Valli will create a template to narrate the impact for the pre & post store opening hours. | Service Lead - Platform and store ops |  | NA | 22/09/23 | Closed |  |  |  | Saloni | 2025-02-10 | 758 | >60 | September | 2023 | #VALUE!
Customer Channels | Selling Experience | TBC | 2023-08-16 | Store Finder not working. | Ensure that alerts are converted/integrated with Remedy | Problem identification & Alerting | Location Servies | 4/9: Alerts are integrated with the remedy | Location Servies |  | NA | 2023-04-09 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 778 | >60 | September | 2023 | #VALUE!
Customer Channels | Selling Experience | TBC | 2023-08-16 | Store Finder not working. | Review Incident Management process for Location Services Team | Problem identification & Alerting | Location Team | 7/11: Rehan spoke with Aadil who advised that an IM process has been craeted and is stored centrally in Confluence for the team to access centrally 4/9: Meeting setup to cover process for engaging Microsoft Bing Team later this week | Location Team |  | NA | 2023-06-11 | Closed |  |  |  | Saloni | 2025-02-10 | 778 | >60 | November | 2023 | #VALUE!
Customer Channels | Selling Experience | TBC | 2023-08-16 | Store Finder not working. | Location team to review resiliency approaches | Problem avoidance | Location Team | 7/11: A risk has been rasied on the risk register id 1998. The product team have advised that as this is not a critical application (day1) Customer do not want to proceed as yet. 4/9: Team have finalised 3 approaches and are awaiting product owner discussion: https://confluence.marksandspencer.app/display/RI/Stores+API+-+Geo+Locator+-+Options | Location Team |  | NA | 2023-06-11 | Closed | 1998 | LDS-414 |  | Saloni | 2025-02-10 | 778 | >60 | November | 2023 | #VALUE!
Customer Channels | Selling Experience | TBC | 2023-08-16 | Store Finder not working. | Alert to be configured for service unavailable error for Geocoder API response | Problem identification & Alerting | WCS LifeCycle | 18/8: Team configured the alerts | WCS LifeCycle |  | NA | 18/08/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 778 | >60 | August | 2023 | #VALUE!
Customer Channels | Selling Experience | TBC | 2023-08-16 | Store Finder not working. | Synthetic Journey to mimic customer experience if this service is unavailable | Problem identification & Alerting | WCS LifeCycle | 13/11 Aadil has advised that the Location team have setup a synthethic monitor which tests every one minute and will alert them if it failsck which checks whether the API is up or down. Aadil says that there could be more done - Aadil will go back to Location team and query further | WCS LifeCycle |  | NA | 13/11/23 | Closed |  |  |  | Saloni | 2025-02-10 | 778 | >60 | November | 2023 | #VALUE!
Customer Channels | Service Experience | 89496762 | 2023-08-15 | Store tills offline while processing refunds. | Update the runbook detailing the required actions to fix the issue in future. | Solution & Recovery | Balaguru Subramanian | The runbooks were updated as part of PEAK readiness | POS devops |  | NA | 16/10/23 | Closed |  |  |  | Saloni | 2025-02-10 | 779 | >60 | October | 2023 | #VALUE!
Customer Channels | Service Experience | 89496762 | 2023-08-15 | Store tills offline while processing refunds. | With the new relic tool implemented in the POS environment, we have now set up pager duty alerts when 100 tills go offline within 5 mins. The call out process is already in place and Remedy integration is in progress. | Problem identification & Alerting | Balaguru Subramanian | Newrelic-Remedy integration is completed | POS devops |  | NA | 22/08/23 | Closed |  |  |  | Saloni | 2025-02-10 | 779 | >60 | August | 2023 | #VALUE!
Customer Channels | Service Experience | 89496762 | 2023-08-15 | Store tills offline while processing refunds. | An alert was triggered at 03:11 which highlighted that the traffic is failing on the problematic server, however, the alerts got auto cleared when the traffic was routed to the other two working servers. Configure an alert to notify the status of the IIS server. | Problem identification & Alerting | Balaguru Subramanian | 29/08: The alerts have been configured. 22/08: Workorder is raised and the SCOM is implementing it. ETA 24/08 To increase the alerting efficiency in POS, teams will now consult with the CSSM team to identify if a similar level of alerting can be configured in POS landscape. In addition, the alerts will be configured to highlight any issue/ status in the IIS servers. | POS Devops |  | NA | 29/08/23 | Closed |  |  |  | Saloni | 2025-02-10 | 779 | >60 | August | 2023 | #VALUE!
Customer Channels | Service Experience | 89496762 | 2023-08-15 | Store tills offline while processing refunds. | There was an alert triggered to backup team when the server facilitating the TSM backup went to a stopped state, as the severity of the alert was medium, no call outs and actions were taken. Increase the severity of the alert for efficient issue identification. | Problem identification & Alerting | Dharmaraj Balasubramanian / Seevaratam Sivasurath/Balaguru Subramanian/ Jafar Sadiq | 22.08:It was decided to retain it as sev3 only, the reason being, that particualr service stopping is one other symptom of the issue and not having much business impact on its own An internal call will be scheduled to address all the alerting scenarios | POS/Wintel |  | NA | 22/08/23 | Closed |  |  |  | Saloni | 2025-02-10 | 779 | >60 | August | 2023 | #VALUE!
Customer Channels | Service Experience | 89496762 | 2023-08-15 | Store tills offline while processing refunds. | Configure an alert to notify the memory constraint observed resulting in the IIS server to go into the error state. | Problem identification & Alerting | Seeva/Bala | The alerts have been configured. | POS |  | NA | 16/10/23 | Closed |  |  |  | Saloni | 2025-02-10 | 779 | >60 | October | 2023 | #VALUE!
Customer Channels | Service Experience | 89496762 | 2023-08-15 | Store tills offline while processing refunds. | Explore the feasibility of amending the design architecture to isolate the traffic (VIP)from the problematic IIS server. | Problem avoidance | Seevaratam Sisurath | Seeva will discuss this with Kamal. This requires extensive analysis and testing with all the scenarios under RPOS-10222 | POS devops |  | NA | 16/10/23 | Closed |  | RPOS-10222 |  | Saloni | 2025-02-10 | 779 | >60 | October | 2023 | #VALUE!
Customer Channels | Service Experience | 89496762 | 2023-08-15 | Store tills offline while processing refunds. | What caused the IIS server to go into error state? | Root cause | Seevaratam Sivasurath | The tills were showing offline as one of the POS IIS servers (Internet Information service – an extensible webserver software for the Windows server) had stopped running due to a memory constraint. This was caused due to the simultaneous execution of the Defender updates at 03:07 on the impacted server and the daily TSM (Tivoli Store Manager) system backup at 03:00. Please note, the defender update is a usual event and is executed at different times in all the 3 POS servers. It has been ascertained that the Defender had huge signature files which ran in parallel with the TSM backup which significantly contributed to the memory issue. Actions have been agreed uplift the memory and the virtual memory configurations | POS Devops |  | NA | 15/08/23 | Closed |  |  |  | Saloni | 2025-02-10 | 779 | >60 | August | 2023 | #VALUE!
Customer Channels | Service Experience | 89496762 | 2023-08-15 | Store tills offline while processing refunds. | Perform the memory uplift and review the virtual memory configurations. | Permanent fix | Seevaratam Sivasurath/ Dharmaraj Balasubramanian | We tried this in PT envt with uplift the memory and drainage the messages but did not make it faster.. please find the Confluence page.. we have a backlog for this one for further turning. POS and Wintel team will arrange a meeting to discuss on the feasibility of uplifting the memory | POS Devops/ Wintel |  | NA | 16/10/23 | Closed |  | https://jira.marksandspencer.app/browse/RPOS-9840) |  | Saloni | 2025-02-10 | 779 | >60 | October | 2023 | #VALUE!
Customer Channels | Service Experience | 89496762 | 2023-08-15 | Store tills offline while processing refunds. | Explore the feasibility of making the “Tills Offline” prompt more user friendly which will provide clear information to avoid any confusion among the colleagues. | Problem avoidance | Sindhuja Palanisamy | A backlog has been created to improve the colleague’s message journey. POSF-184. | POS Devops |  | NA | 22/08/23 | Closed |  | POSF-184. |  | Saloni | 2025-02-10 | 779 | >60 | August | 2023 | #VALUE!
Customer Channels | Service Experience | 89481611 | 2023-08-10 | Multiple drop in orders during August Sale | Review the Firewall alerting | Problem avoidance | Aadil Kasmani/ Mahendran Mahalingam | We had Changed the trigger point of alerting on firewall so that any utilisation issues are reported before saturation point (e.g. Dataplane alerts before it gets to 100% CPU) This has been changed so that the trigger alert is 75% | Service owner |  | NA | 2023-10-08 | closed | NA | NA | N/A | Saloni | 2025-02-10 | 784 | >60 | August | 2023 | #VALUE!
Customer Channels | Service Experience | 89481611 | 2023-08-10 | Multiple drop in orders during August Sale | Microsoft were able to see error at their end and they have suggested to contact Palo Alto Vendor to understand the network bandwidth calculation at their end. | Problem identification & Alerting | Aadil Kasmani/ Mahendran Mahalingam | 19/09 - Several recommentations has been shared by Palo Alto for the preventive measures. Those recommendations have been implemented and the environment is stable since then. 14/08 - Team has raised a case with Palo Alto to understand minute by minute logs and errors from their end | Service owner |  | NA | 19/09/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 784 | >60 | September | 2023 | #VALUE!
Customer Channels | Selling Experience | 89481611 | 2023-08-10 | Multiple drop in orders during August Sale | Teams to devolop a holding page for checkout only, so that customers can continue to browse the site. | Problem avoidance | Apps - Tim Searle/ Matthew Magee Desktop/mweb - Keith Bradshaw | 11/10- The change has been implemented for Maintenance Mode in the iOS app for using the holdin page and drop locking feature Optimizely. 16/10 - The holding page is managed in Akamai thus Keith is unsure if this requries a development.. He will check with his team and will get back on the same There is an existing action from PIR 6503 where the App team agreed to look at where using Optimizely to enhance the holding page and drop locking. Keith Bradshaw is looking into having checkout-only holding page on desktop and mweb | .com |  | NA | 2023-11-10 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 784 | >60 | October | 2023 | #VALUE!
Customer Channels | Selling Experience | 89481611 | 2023-08-10 | Multiple drop in orders during August Sale | Review criteria for putting up the holding page. Like drop in traffic % compared to previous hour, how long issue has been ongoing , determination of the ETA on the fix. | Problem avoidance | Himanshu Khanna/ Jack Tye | 18/08 - Team has agreed to deploy the holding page on a case by case scenario but as for a "guideline" it will be if we see a drop of 75% or more on orders in minute by minute dashboard. Team will produce some guidelines regarding percentage drop Note: it is not feasible to map out all scenarios | .com |  | NA | 18/08/23 | closed | NA | NA | N/A | Saloni | 2025-02-10 | 784 | >60 | August | 2023 | #VALUE!
Customer Channels | Selling Experience | 89481611 | 2023-08-10 | Multiple drop in orders during August Sale | Review of timeouts | Problem avoidance | Pulkit Goyal | Teams will review the timeouts as the current ones are not fit for purpose. Pulkit has carried out analysis to work out the optimal setting (i.e. protect WCS but does not cause excessive errors) and these changes was implemented on 14th Aug. | .com |  | NA | 14/08/23 | closed | NA | NA | N/A | Saloni | 2025-02-10 | 784 | >60 | August | 2023 | #VALUE!
Customer Channels | Selling Experience | 89481611 | 2023-08-10 | Multiple drop in orders during August Sale | Perform End-to-end performance testing for peak taking into account all new functionality e.g. GraphQL, Stock Availability Service, Onyx and related API | Problem avoidance | Ramsankar Ramaswamy/ Ramachandrarao RVS | 05/09 - E2E performance testing cannot be achieved as this will need a lot of technical changes and wouldn't help peak. But each team has agreed to perform the performance testing as part of the peak readiness. 14/08- Ram and Rams will discuss with individual teams to get their buy-in to carry out this testing.. | .com |  | NA | 2023-05-09 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 784 | >60 | September | 2023 | #VALUE!
Customer Channels | Selling Experience | 89481611 | 2023-08-10 | Multiple drop in orders during August Sale | Investigate the feasibility and development of a circuit break within WCS to stop sending traffic to the endpoint whilst it is unresponsive. | Solution & Recovery | Rudolf Horvath/ Ramachandrarao RVS | 30/10 - The Scheduler has been enabled in prod, few trial runs have been done which was successfull. We have few more Schedulers to be implemented which will be done via : https://jira.marksandspencer.app/browse/CM-10809. 19/10 - The change has gone live in the recent release and teams are awaiting the prerequisites checklist to be done at WCS side and once they are done, teams will enable the scheduler. ETA: 23/10 03/10 - The WCS release is planned for tomorrow (4th Oct) and circuit breaker is part of it. Its currently based on a switch and initially going into dormant mode. Once tested successfully in prod, the feature switch will be enabled. Approx - ETA: 17/10 11/09 - Development is in progress in WCS and we will plan to deploy it in R163 by end of September (25th Sep) | STPM |  | NA | 2023-01-11 | Closed |  | https://jira.marksandspencer.app/browse/CM-10809 |  | Saloni | 2025-02-10 | 784 | >60 | November | 2023 | #VALUE!
Customer Channels | Service Experience | 89481611 | 2023-08-10 | Multiple drop in orders during August Sale | Mongo D/B was almost hitting 100% memory which caused the performance issues. The Uplift of memory needs to be worked upon | Problem avoidance | Steve Almashoor | 03/10 - Memory uplift was done before September Sale and there were no issues 10/08 - Team will be performing a memory lift and will be carrying out performance testing and stress testing before September Sale (on 21st Sept) | Product Manager |  | NA | 2023-03-10 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 784 | >60 | October | 2023 | #VALUE!
Group Support | HR | 89462143 | 2023-08-02 | Performance issues in the Time & Attendance application | The uplift of the CPU and the memory needs to be reviewed to see if it can be scaled back | Permanent fix | Alex Fergus | 04/09: Alex confirmed that there is no scaling back till after peak, so can be closed 29/08: Have followed up with Alex on the open actions 19/08: Alex is OOO returning on 22nd, Hence requested Hannah if she has an update 12/08: Followed up with Alex on the status 02/08: Hold on downgrading CPU & memory as we are about to recruit 8k to 9k colleagues for peak – agree key timings with BY | HR |  | NA | 2023-04-09 | Closed |  |  |  | Saloni | 2025-02-10 | 792 | >60 | September | 2023 | #VALUE!
Group Support | HR | 89462143 | 2023-08-02 | Performance issues in the Time & Attendance application | There has been some miscommunication and misunderstanding with regards to key Customer. | Problem avoidance | Alex Fergus | 04/09: Alex confirmed that a fortnightly call of key events now scheduled. this can be closed 29/08: Have followed up with Alex on the open actions 19/08: Alex is OOO returning on 22nd, Hence requested Hannah if she has an update 12/08: Followed up with Alex on the status 02/08: Customer to share key quarterly events with BY and if any events identify that testing is required or have unknown scenarios then work together. | HR |  | NA | 2023-04-09 | Closed |  |  |  | Saloni | 2025-02-10 | 792 | >60 | September | 2023 | #VALUE!
Group Support | HR | 89462143 | 2023-08-02 | Performance issues in the Time & Attendance application | When Customer communicated to store colleagues that they could apply for leave for the 2024 period, this was communicated in one go. If it had been staggered then the pressure on the system would not have been as much as the problem may have been avoided | Problem avoidance | Alex Fergus | 13/09: The business have agreed to stagger next year 04/09: Alex updated that teams are still working on this action 29/08: Have followed up with Alex on the open actions 19/08: Alex is OOO returning on 22nd, Hence requested Hannah if she has an update 12/08: Followed up with Alex on the status 02/08: Stagger comms by region or plan in a way that doesn’t put pressure on the system. Alex to propose this to the business | HR |  | NA | 13/09/23 | Closed |  |  |  | Saloni | 2025-02-10 | 792 | >60 | September | 2023 | #VALUE!
Group Support | HR | 89462143 | 2023-08-02 | Performance issues in the Time & Attendance application | As per design the running of any jobs in parallel with users logged into the application was not considered and therefore now needs an in depth review. | Problem avoidance | Alex Fergus / Bhavana Rao | 27/09: Alex confirmed that the testing has completed 15/09: Testing is still in progress 04/09: Alex updated that review is still in progress. A draft timings has been suggested and being tested. 29/08: Have followed up with Alex on the open actions 19/08: Alex is OOO returning on 22nd, Hence requested Hannah if she has an update 12/08: Followed up with Alex on the status 02/08: Review the T&A jobs in terms of durations and start times along with peak usage of the application and change the job timings if required – Alex/Bhavna | HR |  | NA | 27/09/23 | Closed |  |  |  | Saloni | 2025-02-10 | 792 | >60 | September | 2023 | #VALUE!
Group Support | HR | 89462143 | 2023-08-02 | Performance issues in the Time & Attendance application | Proactive reviews of the system could identify issues before colleagues report them | Problem avoidance | Bhavana Rao | 12/09:Customer have agreed to include this in the quarterly reviews now, When Customer communicated to store colleagues that they could apply for leave for the 2024 period, this was communicated in one go. If it had been staggered then the pressure on the system would not have been as much as the problem may have been avoided and business have agree to stagger next year. Hence closing the action 04/09: Alex updated that teams are still working on this action 29/08: Have followed up with Alex on the open actions 19/08: Alex is OOO returning on 22nd, Hence requested Hannah if she has an update 12/08: Followed up with Alex on the status 02/08: BY to conduct quarterly proactive environmental review and see if it is still fit for purpose. | BY |  | NA | 2023-12-09 | Closed |  |  |  | Saloni | 2025-02-10 | 792 | >60 | September | 2023 | #VALUE!
Group Support | HR | 89462143 | 2023-08-02 | Performance issues in the Time & Attendance application | What was the detailed root cause of the CPU 100% utilisation? | Root cause | BY | 03/08: BY team has sent their RCA document 02/08: Root cause report to be sent to Customer | BY |  | NA | 2023-03-08 | Closed |  |  |  | Saloni | 2025-02-10 | 792 | >60 | August | 2023 | #VALUE!
Customer Channels | Customer Engagement | 89453324 | 2023-07-31 | Customers unable to place order on iOS App | Concerns about the query parameter approach. Consider using a strictly necessary cookie instead to improve handover of consent from Native to webview | Problem avoidance | Andreas Christophides | 08/09: In the Max's confluence page, latest update is that this action is "complete: both iOS and Android have engineered a more robust solution in collaboration with the "OneTrust Web" team and this is in final testing. Please note the existing methods of passing consent will continue to be supported and used by customers who choose not to update their app to the latest versions" 02/09: Followed up with Elaine on the latest updates 07/08: Service Lead Elaine confirmed that teams are working on it and further updates will be available by end of August | iOS App Team |  | NA | 2023-05-09 | Closed |  |  |  | Saloni | 2025-02-10 | 794 | >60 | September | 2023 | #VALUE!
Customer Channels | Customer Engagement | 89453324 | 2023-07-31 | Customers unable to place order on iOS App | Review use of feature flags for anything that touches parts of core App | Problem avoidance | Ben Corston/Matthew Magee | 17/10 - With the confluence page https://confluence.marksandspencer.app/pages/viewpage.action?spaceKey=DS&title=Blameless+review%3A+iOS+mweb+sev2 the action is being closed 11/10 - Matthew updated that "The initiative is with our Heads of and Senior Heads of Engineering to discuss how we approach SIT-2 improvements in general. As I say it's a multi-year, multi-squad effort. There isn't "a backlog" for such a programme of work. It's not possible. It's not appropriate". Discussing with Service Lead Divakar on next steps to close these actions. 04/10 - The underlying cause sits with the relevant API teams and processes on the Apps teams were changed and EMs are working with developers to ensure even more testing happens when changing business critical areas of the code. The longer term initiatives (a replacement for SIT-2 that's fit for purpose) are strategic goals that will take many years to realise. As this is a long term process these will be followed-up via the backlog. Note: They are not relevant to Peak activities. 02/10: Have followed up with Matthew for the backlog 20/09: Matthew updated that "they are all very very long term initiatives (new SIT environment, new end-to-end testing suite, new forced upgrade mechanism). They are on our mind as we plan, but as yet not in a backlog and It requires the cooperation of several squads across the portfolio, so not easily no. I am having a 1:1 with the CTO today so I'll see how he views it and get back. 15/09: Have followed up with Max on the latest status 08/09: In the Max's confluence page, this action is assigned to Matthew Magee 02/09: Followed up with Elaine on the latest updates 07/08: Service Lead Elaine confirmed that teams are working on it and further updates will be available by end of August | iOS App Team |  | NA | 17/10/23 | Closed |  |  |  | Saloni | 2025-02-10 | 794 | >60 | October | 2023 | #VALUE!
Customer Channels | Customer Engagement | 89453324 | 2023-07-31 | Customers unable to place order on iOS App | Clarify financial impact of incident | Impact analysis | Himanshu Khanna | 22/09: Himanshu confirmed that they mapped mapped an overall impact of £490k gross 12/09: Followed up with Himanshu on the latest 02/09: Followed up with Elaine on the latest updates 07/08: Service Lead Elaine confirmed that teams are working on it and further updates will be available by end of August 31/07: initial view from analytics suggests £455k but this needs clarification | Business Operations |  | NA | 22/09/23 | Closed |  |  |  | Saloni | 2025-02-10 | 794 | >60 | September | 2023 | #VALUE!
Customer Channels | Customer Engagement | 89453324 | 2023-07-31 | Customers unable to place order on iOS App | Will investigate whether Contact Centre agents can carry out initial triage in terms of advising which channel the customer had the problem on e.g. There were reports of customers getting a ‘sorry’ page and not being able to place orders, but it was not clear that this was just on iOS App | Problem identification & Alerting | Himanshu Khanna | 22/09: Himanshu confirmed that, we had fed back to Contact Centre Operations to capture the channel upfront when customers are reporting issues 12/09:Followed up with Himanshu on the status 02/09: Followed up with Elaine on the latest updates 07/08: Service Lead Elaine confirmed that teams are working on it and further updates will be available by end of August | Business Operations |  | NA | 22/09/23 | Closed |  |  |  | Saloni | 2025-02-10 | 794 | >60 | September | 2023 | #VALUE!
Customer Channels | Customer Engagement | 89453324 | 2023-07-31 | Customers unable to place order on iOS App | Will investigate whether Discover could have provided additional /better information to help/speed up the initial triage | Problem identification & Alerting | Himanshu Khanna | 26/09: Himanshu confirmed that as Discover doesn't run on application, it couldn't have provided additional /better information to help/speed up the initial triage 22/09: Himanshu is checking on it 12/09:Followed up with Himanshu on the status 02/09: Followed up with Elaine on the latest updates 07/08: Service Lead Elaine confirmed that teams are working on it and further updates will be available by end of August | Business Operations |  | NA | 26/09/23 | Closed |  |  |  | Saloni | 2025-02-10 | 794 | >60 | September | 2023 | #VALUE!
Customer Channels | Customer Engagement | 89453324 | 2023-07-31 | Customers unable to place order on iOS App | Review forced upgrade approach (impact, decision makers , technical approach etc) | Impact analysis | Matthew Magee | 17/10 - With the confluence page https://confluence.marksandspencer.app/pages/viewpage.action?spaceKey=DS&title=Blameless+review%3A+iOS+mweb+sev2 the action is being closed 11/10 - Matthew updated that "The initiative is with our Heads of and Senior Heads of Engineering to discuss how we approach SIT-2 improvements in general. As I say it's a multi-year, multi-squad effort. There isn't "a backlog" for such a programme of work. It's not possible. It's not appropriate". Discussing with Service Lead Divakar on next steps to close these actions. 02/10: Have followed up with Matthew for the backlog 20/09: Matthew updated that "they are all very very long term initiatives (new SIT environment, new end-to-end testing suite, new forced upgrade mechanism). They are on our mind as we plan, but as yet not in a backlog and It requires the cooperation of several squads across the portfolio, so not easily no. I am having a 1:1 with the CTO today so I'll see how he views it and get back. 15/09: Have followed up with Max on the latest status 08/09: In the Max's confluence page, there are no updates for this action 02/09: Followed up with Elaine on the latest updates 07/08: Service Lead Elaine confirmed that teams are working on it and further updates on the actions will be available by end of August 31/07: Currently can only do a forced upgrade for all users or no users. Will review whether or not it is possible to do it for a specific release. In the backlog | iOS App Team |  | NA | 17/10/23 | Closed |  |  |  | Saloni | 2025-02-10 | 794 | >60 | October | 2023 | #VALUE!
Customer Channels | Customer Engagement | 89453324 | 2023-07-31 | Customers unable to place order on iOS App | App teams to continue work on runbook | Problem avoidance | Matthew Magee and Aadil | 17/10 - With the confluence page https://confluence.marksandspencer.app/pages/viewpage.action?spaceKey=DS&title=Blameless+review%3A+iOS+mweb+sev2 the action is being closed 11/10 - Matthew updated that "The initiative is with our Heads of and Senior Heads of Engineering to discuss how we approach SIT-2 improvements in general. As I say it's a multi-year, multi-squad effort. There isn't "a backlog" for such a programme of work. It's not possible. It's not appropriate". Discussing with Service Lead Divakar on next steps to close these actions. 04/10 - The underlying cause sits with the relevant API teams and processes on the Apps teams were changed and EMs are working with developers to ensure even more testing happens when changing business critical areas of the code. The longer term initiatives (a replacement for SIT-2 that's fit for purpose) are strategic goals that will take many years to realise. As this is a long term process these will be followed-up via the backlog. Note: They are not relevant to Peak activities 02/10: Have followed up with Matthew for the backlog 15/09: Have followed up with Max on the latest status 08/09: In the Max's confluence page, latest update is that this action is in progress 02/09: Followed up with Elaine on the latest updates 07/08: Service Lead Elaine confirmed that teams are working on it and further updates will be available by end of August | iOS App Team |  | NA | 17/10/23 | Closed |  |  |  | Saloni | 2025-02-10 | 794 | >60 | October | 2023 | #VALUE!
Customer Channels | Customer Engagement | 89453324 | 2023-07-31 | Customers unable to place order on iOS App | Recreate the issue in 8.3 version. This will enable a test case to be identified to help with future testing | Problem avoidance | Matthew Magee and Aadil | 17/10 - With the confluence page https://confluence.marksandspencer.app/pages/viewpage.action?spaceKey=DS&title=Blameless+review%3A+iOS+mweb+sev2 the action is being closed 11/10 - Matthew updated that "The initiative is with our Heads of and Senior Heads of Engineering to discuss how we approach SIT-2 improvements in general. As I say it's a multi-year, multi-squad effort. There isn't "a backlog" for such a programme of work. It's not possible. It's not appropriate". Discussing with Service Lead Divakar on next steps to close these actions. 04/10 - The underlying cause sits with the relevant API teams and processes on the Apps teams were changed and EMs are working with developers to ensure even more testing happens when changing business critical areas of the code. The longer term initiatives (a replacement for SIT-2 that's fit for purpose) are strategic goals that will take many years to realise. As this is a long term process these will be followed-up via the backlog. Note: They are not relevant to Peak activities 02/10: Have followed up with Matthew for the backlog 20/09: Matthew updated that "they are all very very long term initiatives (new SIT environment, new end-to-end testing suite, new forced upgrade mechanism). They are on our mind as we plan, but as yet not in a backlog and It requires the cooperation of several squads across the portfolio, so not easily no. I am having a 1:1 with the CTO today so I'll see how he views it and get back. 15/09: Have followed up with Max on the latest status 12/09: In the Max's confluence page, there is no further update. Followed up with Elaine 02/09: Followed up with Elaine on the latest updates 07/08: Service Lead Elaine confirmed that teams are working on it and further updates will be available by end of August | iOS App Team |  | NA | 17/10/23 | Closed |  |  |  | Saloni | 2025-02-10 | 794 | >60 | October | 2023 | #VALUE!
Customer Channels | Customer Engagement | 89453324 | 2023-07-31 | Customers unable to place order on iOS App | Improvement on end-to-end testing to ensure nothing is broken after a release | Problem identification & Alerting | Matthew Magee and Aadil | 17/10 - With the confluence page https://confluence.marksandspencer.app/pages/viewpage.action?spaceKey=DS&title=Blameless+review%3A+iOS+mweb+sev2 the action is being closed 11/10 - Matthew updated that "The initiative is with our Heads of and Senior Heads of Engineering to discuss how we approach SIT-2 improvements in general. As I say it's a multi-year, multi-squad effort. There isn't "a backlog" for such a programme of work. It's not possible. It's not appropriate". Discussing with Service Lead Divakar on next steps to close these actions. 04/10 - The underlying cause is with the relevant API teams, and processes on the Apps teams were changed and Engineering Managers are working with developers to ensure even more testing happens when changing business critical areas of the code. 02/10: Have followed up with Matthew for the backlog 20/09: Matthew updated that "they are all very very long term initiatives (new SIT environment, new end-to-end testing suite, new forced upgrade mechanism). They are on our mind as we plan, but as yet not in a backlog and It requires the cooperation of several squads across the portfolio, so not easily no. I am having a 1:1 with the CTO today so I'll see how he views it and get back. 15/09: Have followed up with Max on the latest status 12/09: In the Max's confluence page, there is no further update. Followed up with Elaine 02/09: Followed up with Elaine on the latest updates 07/08: Service Lead Elaine confirmed that teams are working on it and further updates will be available by end of August 31/07:There was a discussion regarding the wider issue of testing. Need an environment that mimics production but there are cost implications. This does not form an action for this PIR specifically, it is a wider issue | iOS App Team |  | NA | 17/10/23 | Closed |  |  |  | Saloni | 2025-02-10 | 794 | >60 | October | 2023 | #VALUE!
Customer Channels | Customer Engagement | 89453324 | 2023-07-31 | Customers unable to place order on iOS App | Will investigate if the iOS App team could have made better use of business metrics to identify drop in order conversion. E.g. have an automated alert from Adobe which identifies drop in iOS App order conversion. | Problem identification & Alerting | Max Pilgrim | 17/10 - With the confluence page https://confluence.marksandspencer.app/pages/viewpage.action?spaceKey=DS&title=Blameless+review%3A+iOS+mweb+sev2 the action is being closed 11/10 - MAx updated the below and he is OOO currently"the ones that are not yet closed are all fairly mid- to long-term actions. Broader improvements not only related to the incident that took place. most of them all fall into this category. Few are either done or making good progress. "Recreate the issue in 8.3 version. This will enable a test case to be identified to help with future testing" would be the only one that I suggest is closest to the actual incident that took place, and I will speak to Matt about this." 04/10 - The underlying cause sits with the relevant API teams and processes on the Apps teams were changed and EMs are working with developers to ensure even more testing happens when changing business critical areas of the code. The longer term initiatives (a replacement for SIT-2 that's fit for purpose) are strategic goals that will take many years to realise. As this is a long term process these will be followed-up via the backlog. Note: They are not relevant to Peak activities 02/10: Max was OOO and have followed up on the status of this action 15/09: Have followed up with Max on the latest status 08/09: In the Max's confluence page, the latest update states that "in advance of UK compliance launch in mid Sept, UK - Byrne, Samuel has offered to help set up some dedicated Adobe dashboarding looking at such key business metrics - session to agree these and get in place diarised for 11th Sep. 02/09: Followed up with Elaine on the latest updates 07/08: Service Lead Elaine confirmed that teams are working on it and further updates will be available by end of August | iOS App Team |  | NA | 17/10/23 | Closed |  |  |  | Saloni | 2025-02-10 | 794 | >60 | October | 2023 | #VALUE!
Customer Channels | Customer Engagement | 89453324 | 2023-07-31 | Customers unable to place order on iOS App | Carry out “5 Why” root cause analysis (i.e. actions for future complex tickets) | Root cause | Michael Sororokin | Complete | iOS App Team |  | NA | 31/07/23 | Closed |  |  |  | Saloni | 2025-02-10 | 794 | >60 | July | 2023 | #VALUE!
Customer Channels | Customer Engagement | 89453324 | 2023-07-31 | Customers unable to place order on iOS App | On WCS there 5xx-4xx alerting is set up for overall traffic. This means that even if some critical pages have issues e.g. order placement pages, the thresholds may not be breached. | Problem avoidance | Pulkit Goyal | 05/09: Pulkit confirmed that around 9 separate alerts for individual wcs commands in new relic are created 02/09: Followed up with Elaine on the latest updates 07/08: Service Lead Elaine confirmed that teams are working on it and further updates will be available by end of August 31/07:Will add alerting for individual critical pages such as SPC, Order placement, basket, checkout etc. | WCS Lifecycle |  | NA | 2023-05-09 | closed |  |  |  | Saloni | 2025-02-10 | 794 | >60 | September | 2023 | #VALUE!
Customer Channels | Customer Engagement | 89453324 | 2023-07-31 | Customers unable to place order on iOS App | Configure Optimizely to enable application of messaging/drop lock targeted at specific versions of the App | Problem avoidance | Tim Searle/Matthew Magee/Alex Omand/Mariora | 17/10 - With the confluence page https://confluence.marksandspencer.app/pages/viewpage.action?spaceKey=DS&title=Blameless+review%3A+iOS+mweb+sev2 the action is being closed 11/10 - Matthew updated that "The initiative is with our Heads of and Senior Heads of Engineering to discuss how we approach SIT-2 improvements in general. As I say it's a multi-year, multi-squad effort. There isn't "a backlog" for such a programme of work. It's not possible. It's not appropriate". Discussing with Service Lead Divakar on next steps to close these actions. 04/10 - The underlying cause sits with the relevant API teams and processes on the Apps teams were changed and EMs are working with developers to ensure even more testing happens when changing business critical areas of the code. The longer term initiatives (a replacement for SIT-2 that's fit for purpose) are strategic goals that will take many years to realise. As this is a long term process these will be followed-up via the backlog. Note: They are not relevant to Peak activities 02/10: Have followed up with Matthew for the backlog 20/09: Matthew updated that "they are all very very long term initiatives (new SIT environment, new end-to-end testing suite, new forced upgrade mechanism). They are on our mind as we plan, but as yet not in a backlog and It requires the cooperation of several squads across the portfolio, so not easily no. I am having a 1:1 with the CTO today so I'll see how he views it and get back. 15/09: Have followed up with Max on the latest status 08/09: In the Max's confluence page, this action is assigned to Alex Omand & Mariora 02/09: Followed up with Elaine on the latest updates 07/08: Service Lead Elaine confirmed that teams are working on it and further updates will be available by end of August | iOS App Team |  | NA | 17/10/23 | Closed |  |  |  | Saloni | 2025-02-10 | 794 | >60 | October | 2023 | #VALUE!
Supply Chain | Foods Supply Chain | 89459808 | 2023-07-27 | Customer outbound messages were piled up in Cloud B2B shared gateway | Replicate the queue manager alerts in New relic for all dot com queue. | Problem identification & Alerting | Azhagesan | 21/08: The is priortised in the current sprint and is currently in progress. Its is being tracked under - EMULTI-15137 14/08: This is still progress 27/07: Most of the alerts are replicated in Splunk and New relic. The remaining one’s are being configured | Dot com Integration |  | NA | 21/08/23 | closed | NA | EMULTI-15137 |  | Saloni | 2025-02-10 | 798 | >60 | August | 2023 | #VALUE!
Supply Chain | Foods Supply Chain | 89459808 | 2023-07-27 | Customer outbound messages were piled up in Cloud B2B shared gateway | Review the escalation policy for GIST to reach Customer in case of any issues | Supplier and support involvement | Joey | 21/08: There is no changes in escalation process between Customer and GIST, However it will re iterated in the service review meetings 14/08: Awaiting updates from Joey | Foods supply chain |  | NA | 21/08/23 | closed | NA |  |  | Saloni | 2025-02-10 | 798 | >60 | August | 2023 | #VALUE!
GTS | Enterprise Integration | 89459808 | 2023-07-27 | Customer outbound messages were piled up in Cloud B2B shared gateway | Create inactive alerts for all dot com queues | Problem identification & Alerting | Raj/ Azhagesan / Swathika | 14/08: This will priortised will Sprint 3 or 4. | Dot com Integration |  | NA | 14/08/23 | closed | NA | EMULTI-15380 |  | Saloni | 2025-02-10 | 798 | >60 | August | 2023 | #VALUE!
GTS | Enterprise Integration | 89459808 | 2023-07-27 | Customer outbound messages were piled up in Cloud B2B shared gateway | Address the knowledge gap while validating any message flows | Solution & Recovery | Sreeraj Cheriyil | 09/08: This has communicated with the teams | Integration Services |  | NA | 2023-09-08 | closed | NA | NA | N/A | Saloni | 2025-02-10 | 798 | >60 | August | 2023 | #VALUE!
GTS | Enterprise Integration | 89459808 | 2023-07-27 | Customer outbound messages were piled up in Cloud B2B shared gateway | Feasibility of automating the channel recovery? | Solution & Recovery | Swathika | 27/07: If the channel is recoverable the channel will automatically restart, however in certain scenario’s manual validation is required for recovering the channel | Cloud Frameworks team |  | NA | 27/07/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 798 | >60 | July | 2023 | #VALUE!
GTS | Enterprise Integration | 89459808 | 2023-07-27 | Customer outbound messages were piled up in Cloud B2B shared gateway | Ensure that alerting is configured for all the channels/queue manager | Problem identification & Alerting | Swathika | 04/09: All the necessary alertings have been reviewed and configured 14/08: The alerting review will be done as part of peak excerise 27/07: The alerting has been configured for all the channels/Queue manager; this is currently revalidated. | Cloud Frameworks team |  | NA | 2023-04-09 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 798 | >60 | September | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89459808 | 2023-07-27 | Customer outbound messages were piled up in Cloud B2B shared gateway | Configure Sev1 alerts to notify if there are any message pile ups in the cloud B2B shared gateway | Problem identification & Alerting | Swathika | 27/07: Alerts have been configured to notify if the channels are not in running status for more than 5 mins | Cloud Frameworks team |  | NA | 27/07/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 798 | >60 | July | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89459808 | 2023-07-27 | Customer outbound messages were piled up in Cloud B2B shared gateway | Configure sev1 alerts to notify any issues with channel. | Problem identification & Alerting | Swathika | 27/07: Alerts have been configured to notify if there are any message pile ups | Cloud Frameworks team |  | NA | 27/07/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 798 | >60 | July | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89459808 | 2023-07-27 | Customer outbound messages were piled up in Cloud B2B shared gateway | What caused the network connectivity issue between two queue managers ? | Root cause | Swathika | 12/09: Root cause is inconclusive 14/08- 04/09 - Multiple follows have been made investigations are still progress. 14/08: Team is laising with Network on the further investigations. | Cloud Frameworks team |  | NA | 2023-12-09 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 798 | >60 | September | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89459808 | 2023-07-27 | Customer outbound messages were piled up in Cloud B2B shared gateway | Why did the channel go to retry state? | Root cause | Swathika | A potential network connectivity issue between the cloud B2B queue managers impacted the flow of messages resulting in the shared gateway channel to go into retry state. . Ideally during such scenario, a channel restart is required to resume the message flow. | Cloud Frameworks team |  | NA | 27/07/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 798 | >60 | July | 2023 | #VALUE!
GTS | Enterprise Integration | 89459808 | 2023-07-27 | Customer outbound messages were piled up in Cloud B2B shared gateway | Proactive communication to wider stake holder and impacted systems. | Business & IT Communication | Swathika/Raj | 27/07: A process is in place to communicate to all the source and destination systems (third party). | Integration Services |  | NA | 27/07/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 798 | >60 | July | 2023 | #VALUE!
GTS | Enterprise Integration | 89459808 | 2023-07-27 | Customer outbound messages were piled up in Cloud B2B shared gateway | Extract and share the alerting threshold with GIST for all the flows that involves GIST. | Problem identification & Alerting | Swathika/Raj | 07/07: The interface details have been shared with Foods supply chain team. 14/08: Swathika advised this feasible, however they will check whether these information can be shared with vendor. | Integration Services |  | NA | 2023-07-07 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 798 | >60 | July | 2023 | #VALUE!
Supply Chain | Foods Supply Chain | 89459808 | 2023-07-27 | Customer outbound messages were piled up in Cloud B2B shared gateway | How can we proactively identify the issues with Costa orders interfacing into OpenText before the issue is reported by supply chain colleagues/suppliers. | Problem identification & Alerting | Vinoth purushothaman | It is part of backlogs, not getting prioritized now because planned COSTA decommission during Sept’23. No action will be taken on this and hence we are closing the action | ORCA |  | NA | 31/07/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 798 | >60 | July | 2023 | #VALUE!
Supply Chain | Foods Supply Chain | 89459808 | 2023-07-27 | Customer outbound messages were piled up in Cloud B2B shared gateway | Explore the feasibility of automating the recon between ORCA and OT for costa orders? | Problem avoidance | Vinoth purushothaman | It is part of backlogs, not getting prioritized now because planned COSTA decommission during Sept’23. No action will be taken on this and hence we are closing the action | ORCA |  | NA | 31/07/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 798 | >60 | July | 2023 | #VALUE!
Supply Chain | Foods Supply Chain | 89459808 | 2023-07-27 | Customer outbound messages were piled up in Cloud B2B shared gateway | Review the E2E alerting and threshold for all the GIST flows. | Problem identification & Alerting | Vinoth purushothaman | 12/09: Alerting review is complete 14/08: Awaiting further updates from Middleware team 31/07: Alerts are in place for respective applications for all flows, ASN, GR, Pre-allocation extracts. Will wait Integration team extracts and Threshold limit to check and re-validate it. ETA depends on update from Swathika/Raj | Foods supply chain |  | NA | 2023-12-09 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 798 | >60 | September | 2023 | #VALUE!
Supply Chain | Foods Supply Chain | 89459808 | 2023-07-27 | Customer outbound messages were piled up in Cloud B2B shared gateway | Perform E2E validation of messages being sent to GIST to avoid any miscommunication | Solution & Recovery | Vinoth purushothaman | 31/07: This was communicated to team to give additional call out and confirmation from Middleware team before responding to GIST or any 3rd consumers flowing via B2B layer | FITs |  | NA | 31/07/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 798 | >60 | July | 2023 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89458208 | 2023-07-26 | Castle Donington WCS services were unavailable | Reason behind the unavailability the application services after the failover | Root cause | Jishin/ Thomas | As per the current design, we do not have sufficient capacity to run the services in one server. This has been addressed with another action. | SSI Vendor |  | NA | 26/07/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 799 | >60 | July | 2023 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89458208 | 2023-07-26 | Castle Donington WCS services were unavailable | Currently the networks switches are connected to single power supply. Review the resiliency plan | Problem avoidance | Kamal | The LAN refresh project will fix the problem by having dual power source on the switches | Network |  | NA | 26/07/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 799 | >60 | July | 2023 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89458208 | 2023-07-26 | Castle Donington WCS services were unavailable | What caused the reboot of multiple network switches? | Root cause | Kamal | 26/07:The switch and servers (one DB and one app server) were rebooted due to a possible power issue. This needs further investigation by City FM | Network |  | NA | 26/07/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 799 | >60 | July | 2023 | #VALUE!
GTS | Enterprise Integration | 89458208 | 2023-07-26 | Castle Donington WCS services were unavailable | Whilst the application server was rebooted the MQ channel went to stopped state and it was manually restored. Explore the feasibility of automating the recovery of MQ channel after a server reboot | Solution & Recovery | Murali Irrinki | 03/8: Followed up with the team and awaiting for an update. 15/08: These servers are legacy and is under migration scope. Also the MQ services are restarted using a script and the SOP needs to be updated to restart MQ service we are restarting the WCS DB servers. | Middleware Admin |  | NA | 15/08/23 | closed | NA | NA | N/A | Saloni | 2025-02-10 | 799 | >60 | August | 2023 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89458208 | 2023-07-26 | Castle Donington WCS services were unavailable | Validate whether all the servers across the site are connected to dual power supply. | Problem avoidance | Murali Nasapu | 30/08: Only one server is not have the dual powersupply and remaining have dual power supply and can be monitored via ILO 14/08: Followed up, but still awaiting an update Multiple ILOs are not working and hence it cannot be validated remotely. CD IT must validate physically | Service lead - CD |  | NA | 30/08/23 | closed | NA | NA | N/A | Saloni | 2025-02-10 | 799 | >60 | August | 2023 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89458208 | 2023-07-26 | Castle Donington WCS services were unavailable | Why did the services not fail over to UPS? | Problem avoidance | Murali Srinivasan | UPS is available as back up; however, we believe the power back up was not kicked in because the power blip was very short. | Service lead - CD |  | NA | 26/07/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 799 | >60 | July | 2023 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89458208 | 2023-07-26 | Castle Donington WCS services were unavailable | Review the resiliency plan to run the WCS without any issues. | Problem avoidance | Sabrina/Murali | 26/09: Murali Nasapu has confirmed that this being tracked as part of their back log. hence closing this from the tracker. Back log detail awaited. 22/08:Ideally WCS should be running on two app servers, however if there is any issue with one server, we should have ability to run the application on one server. This is to ensure high availability. SSI is to assess whether servers have enough capacity and capability to run services on one WCS server to minimise the downtime and recommend next steps. Suggestion has been made to SSI, to perform high availability testing to determine the capacity uplifts required etc 21/08: No further updates from vendor, escalated to Service owners 03/8: Followed up with the team and awaiting for an update. | SSI Vendor |  | NA | 26/09/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 799 | >60 | September | 2023 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89458208 | 2023-07-26 | Castle Donington WCS services were unavailable | Increase the port ranges to mitigate the capacity issue caused by debugging logs (Port: 10100 to 10200) | Problem avoidance | Thomas/ Sabrina | 26/09: Murali Nasapu has confirmed that this being tracked as part of their back log. hence closing this from the tracker. Back log detail awaited. 21/08: No further updates from vendor, escalated to Service owners 03/8: Followed up with the team and awaiting for an update. | SSI Vendor |  | NA | 26/09/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 799 | >60 | September | 2023 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89458208 | 2023-07-26 | Castle Donington WCS services were unavailable | Explore the feasibility of automating the recovery/ reboot of the application services. | Solution & Recovery | Thomas/Sabrina | 26/09: Murali Nasapu has confirmed that this being tracked as part of their back log. hence closing this from the tracker. Back log detail awaited. 22:08: SSI has to confirm the requirements to increase the port range. Once that is complete a call will be arranged with Customer Network team and SSI to collectively agree next steps to close this action 21/08: No further updates from vendor, escalated to Service owners 14/08: Followed up, however no further updates from the vendor to be escalated with the service lead 03/8: Followed up with the team and awaiting for an update. | SSI Vendor |  | NA | 26/09/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 799 | >60 | September | 2023 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89458208 | 2023-07-26 | Castle Donington WCS services were unavailable | Investigate further to understand any issues between UPS and the power cabinets. | Problem avoidance | Victor Smith | 03/08: Victor has confirmed that there were no UPS issues as well | City FM |  | NA | 2023-03-08 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 799 | >60 | August | 2023 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89458208 | 2023-07-26 | Castle Donington WCS services were unavailable | What caused the power interruption across all the 3 chambers at the site? | Root cause | Victor Smith | 03/08 Victor has confirmed that there no power issue , hence closing this action as root causes inconclusive | City FM |  | NA | 2023-03-08 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 799 | >60 | August | 2023 | #VALUE!
Customer Channels | Service Experience | 89449493 | 2023-07-24 | Tills offline estate wide | Effective resource management should be applied to avoid long stretched hours during a major incident | Issue handling/management | Darren Gibson | Darren to discuss with Satya how the managers can better be held accountable for resource welfare (In TCS and Customer) | CTO - Customer channels |  | NA | 2023-02-08 | Closed | NA |  |  | Saloni | 2025-02-10 | 801 | >60 | August | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89449493 | 2023-07-24 | Tills offline estate wide | Are we aware of all the services that should be enabled and running on our servers across the estate? | Problem identification & Alerting | Elizabeth Golder | 10/09: The deployment of a tool is not feasible. 29/08: Jafar had joined the call today however, we did not get any significant updates on the tool hunt. Elizabeth is OOO. Will need to get further updates from her. ETA 31/08. 14/08: After a detailed discussion between the tools team and TCS COE team, there is no straightforward solution in identifying a tool to identify the enabled services in the servers. However, they have suggested tools like – Solar Winds, which is already in for network monitoring, this needs further investigation to explore the feasibility of enabling it for server monitoring. If the above is feasible, can we configure an alert if there is an abnormal memory consumption by a service? Explore ways to use our standard tools to create a run state monitor across the estate so that we know what services should be enabled as default. 01/08: There are no existing tools to check the run stats. Team are exploring the feasibility and will update on 14/08. | Service Lead - GTS |  | NA | 2023-10-09 | Closed | NA |  |  | Saloni | 2025-02-10 | 801 | >60 | September | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89449493 | 2023-07-24 | Tills offline estate wide | We need to be able to see the current configuration and be able to COMPARE it to what was set at deployment to identify any changes | Problem identification & Alerting | Elizabeth Golder | 10/09: The deployment of a tool is not feasible. 29/08: Jafar had joined the call today however, we did not get any significant updates on the tool hunt. Elizabeth is OOO. Will need to get further updates from her. ETA 31/08. 14/08: After a detailed discussion between the tools team and TCS COE team, there is no straightforward solution in identifying a tool to identify the enabled services in the servers. However, they have suggested tools like – Solar Winds, which is already in for network monitoring, this needs further investigation to explore the feasibility of enabling it for server monitoring. If the above is feasible, can we configure an alert if there is an abnormal memory consumption by a service? 01/08: There are no existing tools to check the run stats. Team are exploring the feasibility and will update on 14/08. Review the current build process for configuration maintenance and recording the systemic changes that progressively occur. | Service Lead - GTS |  | NA | 2023-10-09 | Closed | NA |  |  | Saloni | 2025-02-10 | 801 | >60 | September | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89449493 | 2023-07-24 | Tills offline estate wide | It took a significant amount of time to identify the cause of the issue | Problem identification & Alerting | Elizabeth Golder | 01/08: Once the tool is devised to identify the services running in a server, the issue identification and recovery will be seameless Find a way we can identify an issue on a hung server in a timelier manner. | Service Lead - GTS |  | NA | 2023-02-08 | Closed | NA |  |  | Saloni | 2025-02-10 | 801 | >60 | August | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89449493 | 2023-07-24 | Tills offline estate wide | It seems to be taking a significant amount of time to rebuild our infrastructure during major incidents. | Solution & Recovery | Elizabeth Golder | 01/08: This has been discussed with Jane and Idriss and there is no other efficient way to rebuild a server. As this incurs a high cost, this action has been suspended Propose a more efficient way of rebuilding servers in our infrastructure. | Service Lead - GTS |  | NA | 2023-02-08 | Closed | NA |  |  | Saloni | 2025-02-10 | 801 | >60 | August | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89449493 | 2023-07-24 | Tills offline estate wide | Once the rebuild proposal is ready, based on a ROI study we can start deploying the rebuild solution. | Solution & Recovery | Elizabeth Golder | 01/08: This has been discussed with Jane and Idriss and there is no other efficient way to rebuild a server. As this incurs a high cost, this action has been suspended Ascertain what systems remain on-prem and then see if the rebuild proposal action is feasible. | Service Lead - GTS |  | NA | 2023-02-08 | Closed | NA |  |  | Saloni | 2025-02-10 | 801 | >60 | August | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89449493 | 2023-07-24 | Tills offline estate wide | The POS SQL servers did not have the up-to-date patches | Problem avoidance | Elizabeth Golder | Include Darren Gibson in the monthly patch cycle review.Review the state of SSAS across the estate | Service Lead - GTS |  | NA | 2023-02-08 | Closed | NA |  |  | Saloni | 2025-02-10 | 801 | >60 | August | 2023 | #VALUE!
Supply Chain | Foods Supply Chain | 89449493 | 2023-07-24 | Tills offline estate wide | Foods – The day 1 impact was mitigated after applying the contingency plan. | Solution & Recovery | Joey Ocansey | Foods team have tested their contingency plan to handle the Day 2 impact, further analysis will be performed to verify if the day 3 impact can be handled effectively. No pending actions | Service Lead - Foods |  | NA | 2023-02-08 | Closed | NA |  |  | Saloni | 2025-02-10 | 801 | >60 | August | 2023 | #VALUE!
Customer Channels | Enterprise Technology Platform | 89449493 | 2023-07-24 | Tills offline estate wide | It took time to find the relevant comms template and it needed amending. | Business & IT Communication | Laura Whittle/ Sindhuja | 29/08: Store comms doc has been reviewed. 14/08: An internal discussion in progress to assess the impact and walkthrough with the business team and streamline the comm documents for a seamless communication. Review store comms templates | Service leads - Service experience |  | NA | 29/08/23 | Closed | NA |  |  | Saloni | 2025-02-10 | 801 | >60 | August | 2023 | #VALUE!
Customer Channels | Platform & Store Ops | 89449493 | 2023-07-24 | Tills offline estate wide | When the service desk get a lot of calls, as the system is overloaded it’s hard to set an IVR. We need a better way of communicating to people on the ground in stores of issues. | Business & IT Communication | Laura Whittle/Valliammai Ramasamy | 21/09: There is no issues with IVR, SD SDM (Jaya) and service lead (Luara) has monitored for a while and confirmed that the IVR is working fine with out an issues. 29/08: This is in progress with Mitel. Valli to confirm 14/08: The call is due to to get scheduled in the WC 21/08. 02/08: A call scheduled with Mitel on the IVR with Valli and Jaya. ETA: next week There is a product backlog to announce incidents on Tills /Honeywells and would this work if tills are offline? What can be done to try and resolve/workaround the IVR issue with Mitel | Service Leads - Service exp & Platform and store ops |  | NA | 20/09/23 | Closed | NA |  |  | Saloni | 2025-02-10 | 801 | >60 | September | 2023 | #VALUE!
Customer Channels | Service Experience | 89449493 | 2023-07-24 | Tills offline estate wide | Scope of improvement in impact assessment across the business portfolios | Impact analysis | Laura/Joey/Valli/Hisham/George/Deepali | 02/08: Reporting needs improvement. This will be picked up by the Data SL. Valli will address the documentation in CSSM Each service owner to confirm the various impacts from each of their business areas. | Multiple Owners |  | NA | 2023-02-08 | Closed | NA |  |  | Saloni | 2025-02-10 | 801 | >60 | August | 2023 | #VALUE!
GTS | Operations | 89449493 | 2023-07-24 | Tills offline estate wide | During a mim call there are conversations which include questions about overall design and how things should work, which then lead to recovery actions. However discussions such as these lead to much longer calls and sometimes irrelevant discussion | Issue handling/management | MIM | MIM to review housekeeping on the calls. This has been agreed with the MIM team to perform MIM bridge housekeeping every morning | SIAM |  | NA | 2023-02-08 | Closed | NA |  |  | Saloni | 2025-02-10 | 801 | >60 | August | 2023 | #VALUE!
GTS | Operations | 89449493 | 2023-07-24 | Tills offline estate wide | It was suggested that most of the impact could have been prevented if the applications high availability (HA) have been enabled. | Solution & Recovery | Priyadharshini Somasundaram | Evaluate all day one (high priority) applications and ensure they have high availability enabled and if not what needs to be done. This is a long term action and will be tracked under the Service continuity process workflow | Service Continuity |  | NA | 16/10/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 801 | >60 | October | 2023 | #VALUE!
Customer Channels | Service Experience | 89449493 | 2023-07-24 | Tills offline estate wide | We need to establish processes which will allow us to fault find issues in a timely manner in our POS environment | Problem identification & Alerting | Richard WrightWells | 01/08: There is a confluence page detailing the failure scenarios like a runbook- https://confluence.marksandspencer.app/display/PP/Till+Feature+Failure+Scenarios Create a matrix for all the different failure scenarios for POS tills from network to application/ | POS |  | NA | 2023-02-08 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 801 | >60 | August | 2023 | #VALUE!
Customer Channels | Service Experience | 89449493 | 2023-07-24 | Tills offline estate wide | We did not have an alternative server or environment to fail back to. | Solution & Recovery | Richard/Seeva | 29/08: A decision has been taken to build a new server to keep it ready to fail over in case of any issues and restore data with TSM backup. RPOS-9844 14/08: The design changes to ensure HA needs further discussion with Head of Product as it requires funding – In progress 07/08: Seeva confirmed that they are in process of creating a design for the DR serve testing. This requires approval from Darren 01/08: DR discussion in progress. Also looking at the POS design to ensure HA. Review the desired service level during an issue. Tthis warrants a risk. Revisit DR/high availability solution and ensure the solution is tested regularly | POS |  | NA | 29/08/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 801 | >60 | August | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89449493 | 2023-07-24 | Tills offline estate wide | The call out process to key SME’s needs to be automated as far as possible to mitigate the need for the manual effort of calling out support teams | Issue handling/Management | Sam Clemet /Darren Gibson/Sathishkumar Sheshiah | Revisit the number of applications that need to be moved over to the cloud and use pager duty to automate the incident callout. This is a long term action and will be treated as a tech debt | Multiple Owners |  | NA | 2023-02-08 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 801 | >60 | August | 2023 | #VALUE!
GTS | Operations | 89449493 | 2023-07-24 | Tills offline estate wide | It took 1hr 15 mins to get an engineer on the call from MS and then the engineer kept changing. We did not get a windows engineer on the call for 8 hours. | Supplier and support involvement | Sathish | Escalate the challenges with Microsoft with vendor management. Sathish has spoken to Vinish from Microsoft | SIAM |  | NA | 2023-02-08 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 801 | >60 | August | 2023 | #VALUE!
Customer Channels | Service Experience | 89449493 | 2023-07-24 | Tills offline estate wide | During the investigation, we could see a very high number of audit logs being continually generated. This could be normal or could be a symptom of the incident. | Problem identification & Alerting | Seeva | 16/10: The prod deployment will be tracked under RPOS-10015 05/10: This change will be implemented in non prod by end of Oct. The plan is to deploy in prod during mid nov. 14/08: Microsoft confirmed that the existing parameter was auditing all the “INSERT” and “SELECT” commands, causing the spike in audit logs. Product team will change the parameter to exclude the inserts and selects that is being tested in dev region. ETA 29/08. ETA of prod implementation: 29/09.. 01/08: Team are following up with Microsoft and we await an update on 14/08 Follow up with MS on where the transactional level auditing was appearing from. | POS Devops |  | NA | 16/10/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 801 | >60 | October | 2023 | #VALUE!
Customer Channels | Service Experience | 89449493 | 2023-07-24 | Tills offline estate wide | Review the patching levels in the POS environment | Solution & Recovery | Seeva | Ensure that all patching within the POS environment after the incident are consistent. This has been completed | POS |  | NA | 2023-07-08 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 801 | >60 | August | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89449493 | 2023-07-24 | Tills offline estate wide | Controlled patching process | Problem avoidance | Seeva | 11/08: A meeting was held between Infra and POS teams to agree the phased patching process , include SQL team, Configuration and stop and start service will be covered in the IODM and Service transition agreed to share the test results and walkthrough with them and get the approval from Eliz/Dhrama/Jafar, patching SQL/wintel teams will inform us when the patches are available so that they can create the Implan, POS team will create the IODM, run it in NON-prod and in prod we will do it Three phases Review and confirm the phased patching process including step by step verification. Ensure that we revisit snapshots as part of the process.Review the service transition process as windows/SQL may not have signed off on the patching. | POS/Wintel |  | NA | 2023-07-08 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 801 | >60 | August | 2023 | #VALUE!
Customer Channels | Service Experience | 89449493 | 2023-07-24 | Tills offline estate wide | During a patching process, the relevant product team SMEs should be involved. | Problem avoidance | Seeva/Dharma | Ensure SQL team are included in SQL patching as part of the IODM | POS/Wintel |  | NA | 2023-07-08 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 801 | >60 | August | 2023 | #VALUE!
Customer Channels | Service Experience | 89449493 | 2023-07-24 | Tills offline estate wide | During the call, there were SMEs with restricted permissions and access to allow them to carry out critical actions | Solution & Recovery | Seeva/Elizabeth/Simon Harris/Darren Gibson /Jane Gilmour | 14/08: We have identified that few links were inaccessible and certain files could not be downloaded. For Customer laptops, EUC team will help in enabling the software required to open such links. For TCS laptops, the colleague must use AVD (Azure Virtual Desktop), WVD (Windows Virtual Desktop) to access certain links. This will be communicated across the Infra team to avoid access issues in future. 02/08: Seeva has sent the list of required access that were restricted during the issue window. Infra team to check further Review the ability for people to download necessary tools and have the necessary access and permissions.Is Citrix good enough for the job? | Multiple Owners |  | NA | 14/08/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 801 | >60 | August | 2023 | #VALUE!
Customer Channels | Service Experience | 89449493 | 2023-07-24 | Tills offline estate wide | Improve the handling of the various elements of the system managed by different teams | Problem avoidance | Seeva/Jafar Sadiq/Richard | 14/08: A meeting was scheduled to agree on the RACI matrix. Refer to Action 18 – The IODM template has been updated as well. With regards to the different aspects in the POS environment, produce a RACI matrix to show the segregation of tasks/responsibilities. | Multiple Owners |  | NA | 14/08/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 801 | >60 | August | 2023 | #VALUE!
Customer Channels | Service Experience | 89449493 | 2023-07-24 | Tills offline estate wide | The POS run books need reviewing as it has been a long time since the last major POS incident. | Solution & Recovery | Seeva/Richard | 01/08: Teams are in process of reviewing the POS run books to identify the gap and resolve them. A confluence page has been created Review the current POS run books | POS |  | NA | 2023-07-08 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 801 | >60 | August | 2023 | #VALUE!
Customer Channels | Service Experience | 89449493 | 2023-07-24 | Tills offline estate wide | Review the alerting tools required for the POS environment | Problem identification & Alerting | Seevaratam Sivasurath | Ensure that new relic is installed on all POS servers – A backlog has been created in JIRA to install the new relic alerts | POS |  | NA | 2023-07-08 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 801 | >60 | August | 2023 | #VALUE!
Customer Channels | Service Experience | 89449493 | 2023-07-24 | Tills offline estate wide | It took a significant period to systemically catchup with backlogged POS transactions. | Solution & Recovery | Seevaratam Sivasurath | 29/08: Prduct team have analysed but this requires more fine tuning and will be tracked under a backlog RPOS-9840 14/08: Product team tried fine tuning the query, uplifted the system resources (infra), however, this needs more analysis and testing. A confluence page has been created. We can now identify the duration to process the messages. 01/08: Team are running the peak data load in non prod and identify any issues causing the prolonged backlog recovery. Review our SLO’s and establish tests to ensure we meet these. | POS |  | NA | 29/08/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 801 | >60 | August | 2023 | #VALUE!
Customer Channels | Service Experience | 89449493 | 2023-07-24 | Tills offline estate wide | Our test environment did not match our live environment. | Problem avoidance | Seevaratam Sivasurath | 29/08: Product team have replicated all the components to ensure Non prod and prod are in synch. 14/08: We have analysed every component in the prod POS environment. Non prod is in progress. Carry out an overall review and ascertain each of the differences and see if and how we can address | POS |  | NA | 31/08/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 801 | >60 | August | 2023 | #VALUE!
Customer Channels | Service Experience | 89449493 | 2023-07-24 | Tills offline estate wide | Feasibility of procuring an effective way of communication | Business & IT Communication | Service Owners/MIM | Service owners to review the DL’s for business comms and MIM’s are looking at the possibility of the central MIM channel | Service leads/SIAM |  | NA | 2023-02-08 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 801 | >60 | August | 2023 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89449493 | 2023-07-24 | Tills offline estate wide | C&H – Orders were under-allocated because no sold quantity had been deducted from store stock numbers. | Solution & Recovery | Shanmuganathan Murugan | The work around is to manually push the orders once the thresholds are agreed with planning team. This needs proper planning and documented. | CnH Team |  | NA | 2023-02-08 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 801 | >60 | August | 2023 | #VALUE!
Customer Channels | Service Experience | 89449493 | 2023-07-24 | Tills offline estate wide | Retail – Significant impact | Solution & Recovery | Sindhu/Laura | 07/08: POSD-9629: Performance issue with Cafe personality till when centre is offline. For other impacts like gift card etc, design changes are being explored and this will be picked within the portfolio - lead by Richard. Establish how we can better mitigate the offline journey for the following unexpected impacts: · Gift card and refunds journey to be reviewed. · Hospitality till performance · In store order payments · Digital receipts and sparks rewards | POS/ Service lead - Service experience |  | NA | 2023-07-08 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 801 | >60 | August | 2023 | #VALUE!
Customer Channels | Selling Experience | 89440261 | 2023-07-24 | Errors on Product Listing Pages (PLP) and Search Results Pages (SRP) in Customer .com | Confirm whether Mobile Apps were impacted/received alerts for the incident | Impact analysis | Aadil/Mobile App team | 03/08: Aadil has confirmed that Mobile Apps were impacted with increased errors during the issue, but not as many as Web, however the alert did not trigger on their end | Mobile App team |  | NA | 2023-03-08 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 801 | >60 | August | 2023 | #VALUE!
Customer Channels | Customer Engagement | 89440261 | 2023-07-24 | Errors on Product Listing Pages (PLP) and Search Results Pages (SRP) in Customer .com | Review GQL-Mesh Security/WAF/Rate Limiting capability for potential DDoS scenarios and explore APIkey usage to identify consumers of mesh | Problem avoidance | GQL-Mesh | 12/09: The problem action is tracked as part of their back log - 3857 12/09: Aadil is chasing the product for expedite and close the action 03/08: Security & gql-mesh team had a meeting on 02/08 regarding WAF and architecture, however the review is not complete yet. | GQL-Mesh |  | NA | 2023-12-09 | closed | NA | 3857 |  | Saloni | 2025-02-10 | 801 | >60 | September | 2023 | #VALUE!
Customer Channels | Customer Engagement | 89440261 | 2023-07-24 | Errors on Product Listing Pages (PLP) and Search Results Pages (SRP) in Customer .com | Onyx Browse Team to get a list of approved bots from SEO team. Identify the source of the traffic & discuss how we can block any other bot activity | Problem avoidance | Onyx Browse | Team confirmed that the Bot on Saturday was legitimate requests from FoundIt (Third Party). Identity of source of Friday requests is still unknown. Action for blocking offending taken up separately as action item number 3 | Onyx Browse |  | NA | 24/07/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 801 | >60 | July | 2023 | #VALUE!
Customer Channels | Customer Engagement | 89440261 | 2023-07-24 | Errors on Product Listing Pages (PLP) and Search Results Pages (SRP) in Customer .com | Review process of communication when Multiple Product teams are investigating incidents independently and how this can be improved | Business & IT Communication | Onyx-Browse/Gql-mesh/Search & Sort Teams | 12/09: Product teams have agreed to collobrate internally over a teams channel during a incident 12/09: Aadil is chasing the product for expedite and close the action 03/08: This action remains open has further discussions are yet to be made | Onyx-Browse/Gql-mesh/Search & Sort Teams |  | NA | 2023-12-09 | closed | NA | NA | N/A | Saloni | 2025-02-10 | 801 | >60 | September | 2023 | #VALUE!
Customer Channels | Customer Engagement | 89440261 | 2023-07-24 | Errors on Product Listing Pages (PLP) and Search Results Pages (SRP) in Customer .com | To clarify with Bloomreach the Multi-Term query reference they made in RCA and whether this exacerbated the issue. Also to review with them their current rate limiting procedure with Customer. | Root cause | Search & Sort Team | 03/08: Mutli term query is a definition to us and the current rate limiting procedure continues to be in place unless Customer subcribe for dedicated clusters with additional payment. Hence closing this action as we explored about this. | Search & Sort Team |  | NA | 2023-08-08 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 801 | >60 | August | 2023 | #VALUE!
Customer Channels | Customer Engagement | 89440261 | 2023-07-24 | Errors on Product Listing Pages (PLP) and Search Results Pages (SRP) in Customer .com | Search Team to implement a Circuit Breaker on Search Abstraction Layer to prevent over | Problem avoidance | Search & Sort Team | 03/08: Circuit breaker on search abstruction layer has been deployed | Search & Sort Team |  | NA | 2023-03-08 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 801 | >60 | August | 2023 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89439216 | 2023-07-21 | Stores unable to connect the honeywells and printers to the wireless network | There is a SNAT setting in the interface – was disabled by default and therefore didn’t clear the stale sessions left over after the BGP flap. It has been noted that this setting will be enable on the next upgrade | Problem avoidance | Kamal | 31/7: The mentioned setting is enabled in the newer version 7.0.9 | Network |  | NA | 31/07/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 804 | >60 | July | 2023 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89439216 | 2023-07-21 | Stores unable to connect the honeywells and printers to the wireless network | BGP flaps occurred due to the upgrade to 7.0.12 – root cause pending | Root cause | Kamal | 8/8: This was occurred due to stale connections which is arrested by applying a workaroun in 7.0.9 version 31/7: Followed up with the team and awaiting for an update. | Network |  | NA | 2023-08-08 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 804 | >60 | August | 2023 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89439216 | 2023-07-21 | Stores unable to connect the honeywells and printers to the wireless network | NOC team to be advised to update Teams proactively for any issues that may cause impact to customers or are of concern. | Business & IT Communication | Rajesh/ Shankar K | 31/7: This has been communicated to the entire team to higlight any issues in the support channel for everyone's awareness. | Network |  | NA | 31/07/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 804 | >60 | July | 2023 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89439216 | 2023-07-21 | Stores unable to connect the honeywells and printers to the wireless network | Amend NOC sop to actually test AP functionality if it has errors rather than assume all is ok – | Solution & Recovery | Rajesh/ Shankar K | 22/8: The SOP document has been updated 03/8: Followed up with the team and awaiting for an update. | Network |  | NA | 22/8/2023 | closed | NA | NA | N/A | Saloni | 2025-02-10 | 804 | >60 | 22/8/2023 | #VALUE! | #VALUE!
GTS | ETP- Connectivity,service & solution | 89439216 | 2023-07-21 | Stores unable to connect the honeywells and printers to the wireless network | Update design doc for the SDWAN stores | Problem avoidance | Shanthanu | 10/9: The design document is updated 14/8: Shntanu is working with the vendor to update the design document 03/8: Followed up with the team and awaiting for an update. | Network |  | NA | 2023-09-10 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 804 | >60 | October | 2023 | #VALUE!
Customer Channels | Customer Engagement | 89441018 | 2023-07-20 | Customers unable to apply for Sparks Pay | Sparkspay browse team to be notified of future planned outages by HSBC | Business & IT Communication | Dan Beggs (HSBC) | Planned IT Change Notifications – Applicable for all future changes, closing as agreed that sparkspay browse team will be notified | HSBC Team |  | NA | 20/07/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 805 | >60 | July | 2023 | #VALUE!
Customer Channels | Customer Engagement | 89441018 | 2023-07-20 | Customers unable to apply for Sparks Pay | Communication - Service design document to be updated with right escalation contacts from worldline and Customer side | Business & IT Communication | Dan Beggs (HSBC) | Escalation contacts details maintained by MSB is updated and hence closing the action | HSBC Team |  | NA | 20/07/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 805 | >60 | July | 2023 | #VALUE!
Customer Channels | Customer Engagement | 89441018 | 2023-07-20 | Customers unable to apply for Sparks Pay | HSBC technical team to be notified of any major marketing campaigns to boost the sparkspay customer base. | Problem avoidance | Dan Beggs(HSBC) | For all HSBC Marketing Campaigns - their technical teams also will be notified for all future campaigns was agreed and the action closed | HSBC Team |  | NA | 20/07/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 805 | >60 | July | 2023 | #VALUE!
Customer Channels | Customer Engagement | 89441018 | 2023-07-20 | Customers unable to apply for Sparks Pay | Incident reporting – Check feasibility to get remedy access for MSB to raise incidents | Supplier and support involvement | Divakar | 08/08: access request can be raised for Customer bank (MSB) to raise sev1 with all the required restriction in place | HSBC Team |  | NA | 2023-04-08 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 805 | >60 | August | 2023 | #VALUE!
Customer Channels | Customer Engagement | 89441018 | 2023-07-20 | Customers unable to apply for Sparks Pay | Communication - Key stake holders in customer engagement did not receive communication about this incident. Review the incident comms DL. | Business & IT Communication | Divakar Hariraju | Key stakeholders who were missed in the incident DL have now been added. In addition to that they have been included in the Sev 1 and Sev 2 email notification teams channel as well. | HSBC Team |  | NA | 25/07/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 805 | >60 | July | 2023 | #VALUE!
Customer Channels | Customer Engagement | 89441018 | 2023-07-20 | Customers unable to apply for Sparks Pay | Better alert classification needs to be created so that support teams can react faster to customer impacting errors. Review all the alerts and its thresholds | Problem identification & Alerting | Paul Adams (HSBC) | Problem record created by HSBC - PRB0056179. Divakar updated that HSBC have already implemented the alerts on 28th July and it is in monitoring status at the moment | HSBC Team |  | NA | 2023-01-08 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 805 | >60 | August | 2023 | #VALUE!
Customer Channels | Customer Engagement | 89441018 | 2023-07-20 | Customers unable to apply for Sparks Pay | End to end testing to be done by HSBC in the lower environment before making prod changes. A lower level environment needs to be reviewed and created. | Problem avoidance | Thomas Miller (HSBC) | HSBC organisational level approval required to build a compatible lower env. So there is no definite target date at the moment. Hence, closed | HSBC Team |  | NA | 20/07/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 805 | >60 | July | 2023 | #VALUE!
Customer Channels | Customer Engagement | 89441018 | 2023-07-20 | Customers unable to apply for Sparks Pay | Hypercare – HSBC need to introduce hypercare for any prod changes. Awareness reports should be produced for future changes/releases | Problem avoidance | Thomas Miller (HSBC) | Hypercare – HSBC need to introduce hypercare for any prod changes. Awareness reports should be produced for future changes/releases. Agreed in the call, hence closed | HSBC Team |  | NA | 20/07/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 805 | >60 | July | 2023 | #VALUE!
Customer Channels | Customer Engagement | 89441018 | 2023-07-20 | Customers unable to apply for Sparks Pay | Incident management – Revisit sparkspay severity matrix and escalation process | Supplier and support involvement | Tom Smith and Ramavtar | 09/11: The Sparks Pay service design and severity matrix is being re-worked as part of launching Sparks Pay In-Store at the end of February 2024. This will be tracked as part of rhe product backlog - Wallet-229 07/11: Spoke to Vadi in absence of Priya, Awaiting latest on the pending actions. 31/10: Remedy group details are being gathered for more clarity before providing a sessions. 04/10 - All the Scenario's have been captured and a session will be planned with SD to educate them on the process for effective support enagegment 29/08: Two actions have been agreed after the meeting with Customer bank,- Review and Share all the possible failure scenarios and remedy groups with our service desk. Based on the scenarios Service desk will assign the issues to respective remedy group which will help in speeding up the escalation process. Once the scenarios are indentified the a call will be set up with SD 08/08: Awaiting for the availability of HSBC and Customer bank busniess availability which will be planned after 24th Aug Meeting to be scheduled with MSB, worldline and Customer to discuss and improve the escalation process | Wallet Experience |  | NA | 2023-09-11 | Closed | NA | WALLET-229 |  | Saloni | 2025-02-10 | 805 | >60 | November | 2023 | #VALUE!
Customer Channels | Service Experience | 89441651 | 2023-07-18 | Delay in .com customer orders and order flow to the fulfilment partners | Review option to ‘override’ TRA exemption to help mitigate the impact on conversion. For incident day, conversion was 83% versus +94%, with commercial impact of £150K | Problem avoidance | Chris Etherington | 12/09: Action willbe tracked as part of 89545728 15/08: Two viable options are explored to mitigate the risk faced when accertify is down. 1.When Accertify is down, we can apply a TRA exemption for all transactions within some local controls 2. Customer stores the last view from Accertify to drive the right behaviour. 14/08: Awaiting update from Chris. | Payment Foundation Team |  | NA | 2023-12-09 | closed | NA | NA | N/A | Saloni | 2025-02-10 | 807 | >60 | September | 2023 | #VALUE!
Customer Channels | Service Experience | 89441651 | 2023-07-18 | Delay in .com customer orders and order flow to the fulfilment partners | Document a Service Wrap for Accertify. 1. Need to include SLA’s both response and resolution 2. Escalation process and contact details covering out of business hours as well | Supplier and support involvement | Chris Etherington Raza Akram | 04/09: 04/09: Support document with SLA response for the incident and escalation contacts has been shared. Sessions with Accertify planned for w/c 31/7 | Payment Foundation Team |  | NA | 2023-04-09 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 807 | >60 | September | 2023 | #VALUE!
Customer Channels | Service Experience | 89441651 | 2023-07-18 | Delay in .com customer orders and order flow to the fulfilment partners | Actions to work with Accertify on Root cause, need answers to the following: 1. RCA does not cover how they missed the wrong configuration of the Chicago environment? 2. Other than correcting the configuration, is there anything they’re going to do from a WoW perspective to prevent this from happening again? Service 1. Comms from Accertify were not good throughout the incident, need to raise this with them with the aim to help improve this. Maintenance 1. Is Sat a good day for maintenance? It’s a busy trading day and as its over a weekend less people are around working. 2. In our contract with Accertify do we have the ability to defer when maintenance occurs? Don’t want these to occur when we have business events planned Knowledge 1. Grow understanding of the Accertify Status Page so this can be referred to during future incidents 2. Accertify naming conventions for their difference service, what do these mean to Customer which ones do we use | Root cause | Chris Etherington Suzanne Millar Raza Akram | Accertify during the scheduled maintenance to upgrade its storage environment, there was a challenge in bringing the storage components back. This forced the Interceptas, ADI, and the Accertify Device platform to shut down due to the dependence on storage infrastructure to house virtual backend stores for the virtual machines that power the Accertify platform. Eventually requiring a redeployment of infrastructure components to their previous version and restarting all of the virtual machines restored the services. 12/09: Awaiting further feedback Sessions with Accertify planned for w/c 31/7 | Payment Foundation Team |  | NA | 2023-06-10 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 807 | >60 | October | 2023 | #VALUE!
Customer Channels | Service Experience | 89441651 | 2023-07-18 | Delay in .com customer orders and order flow to the fulfilment partners | 293 customers had an experienced whereby they received a payment decline email from us for their order, however order was created and sent down for fulfilment successfully. Need to understand cause & provide a fix for this. | Solution & Recovery | Payment Foundation Team/ Raza Akram | If this needs to be automated, it has to be handled by OMS team to make sure the necessary & appropriate notifications are sent to customers on such impacts. Already completed – Completed on 17/07 Misconfiguration in the scheduler – two were running at the same time and we removed the extra scheduler | Payment Foundation Team/ Raza Akram |  | NA | 18/07/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 807 | >60 | July | 2023 | #VALUE!
Customer Channels | Service Experience | 89441651 | 2023-07-18 | Delay in .com customer orders and order flow to the fulfilment partners | The processing of the offline orders took a long time in WCS. Need to performance test so we understand Payment Capabilities/ Raza Akram the limit we can push the configurations set on the WCS schedulers in case needed again in future. | Solution & Recovery | Payment Foundation Team/ Raza Akram | 04/09: The offline scheduler change has been deployed in production to process 200 orders within 1 min (4x scedueler). We have the ability, to increase this amount a further 5x, to process 1000 orders per 1 min (if necessary). PCAP team to handle this change in WCS to increase intake of offline orders via more schedulers. Go live by August 15 Planning to execute 4 schedulers. Each picks up orders based on the order group. Allows us to process offline orders by 4x the capacity. | Payment Foundation Team/ Raza Akram |  | NA | 2023-04-09 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 807 | >60 | September | 2023 | #VALUE!
Customer Channels | Service Experience | 89441651 | 2023-07-18 | Delay in .com customer orders and order flow to the fulfilment partners | Look at introducing the ability to disable fraud checks across both POG & OMS via a single mechanism (via Jenkins pipeline was mentioned for example) | Solution & Recovery | Payment Foundation Team/ Raza Akram | 12/09: Action willbe tracked as part of 89545728 PFOUND team to establish the ‘Plan of Automation’ that can mechanism (via Jenkins pipeline was mentioned for example) disable fraud check within POG & OMS. This has Dependency on OMS tea | Payment Foundation Team/ Raza Akram |  | NA | 2023-12-09 | closed | NA | NA | N/A | Saloni | 2025-02-10 | 807 | >60 | September | 2023 | #VALUE!
Customer Channels | Service Experience | 89441651 | 2023-07-18 | Delay in .com customer orders and order flow to the fulfilment partners | Run book to be pulled together with offline & held orders thresholds agreed with business stakeholders for this scenario. This will then allow engineers to be able to disable these checks without having to wait for approvals and help to reduce the order impact and recovery. Needs to cover for both POG & OMS | Solution & Recovery | Payment Foundation Team/ Raza Akram | 12/09: Action willbe tracked as part of 89545728 Dastan to establish a runbook with Service Owners, Operations Manager, from Dotcom & Instore as well as OMS to determine the agreement on SLAs, retries and enable/disable fraud checks SLA’s to be defined with the business stakeholders by when we can switch off the Fraud checks. | Payment Foundation Team |  | NA | 2023-12-09 | closed | NA | NA | N/A | Saloni | 2025-02-10 | 807 | >60 | September | 2023 | #VALUE!
Customer Channels | Service Experience | 89441651 | 2023-07-18 | Delay in .com customer orders and order flow to the fulfilment partners | To remove the hold from an order in OMS this has to be done manually, can only be applied to 100 orders at a time and is open to human errors. Need a recovery mechanism to be delivered so this can be performed in bulk and remove/reduce the human error risk. | Solution & Recovery | Rajeev Ekambaram | 21/08: A config change has been made in OMS to clear 'N' number of orders from hold. Automation Scope has been reviewed and agreed. Implementation (Configuration) in progress | OMS team |  | NA | 21/08/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 807 | >60 | August | 2023 | #VALUE!
Customer Channels | Service Experience | 89441651 | 2023-07-18 | Delay in .com customer orders and order flow to the fulfilment partners | 2.1K order create failures occurred in OMS whilst post auth checks were switched off. Need to understand cause & provide fix for this. RCA understood, code change required to fix this, story to be raised and taken to Product Team for prioritisation. | Solution & Recovery | Rajeev Ekambaram | 21/08: The backlog DNCTA-8249 has been picked up and is aimed to closed by end of this sprint and it will be tracked under the back log Target to be completed before 15-Aug. | OMS team |  | NA | 21/08/23 | Closed | NA | DNCTA-8249 |  | Saloni | 2025-02-10 | 807 | >60 | August | 2023 | #VALUE!
Customer Channels | Platform & Store Ops | 89415385 | 2023-07-10 | Foods waste value understated across various reports | The issue did not affect just waste and other transactions were affected. CSSM team to ensure they highlight the different categories and departments within Foods waste the messages are in and provide written evidence for the MIM call so that all are aware. This is to be added in all relevant SOPs. | Solution & Recovery | Ravikumar S | 14/07: All SOP's have been updated and the teams are made aware of it | CSSM Devops |  | NA | 14/07/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 815 | >60 | July | 2023 | #VALUE!
Customer Channels | Platform & Store Ops | 89415385 | 2023-07-10 | Foods waste value understated across various reports | In the event that the alert for failed or retry is triggered in future, the team that spots it must update the Teams support channel immediately | Business & IT Communication | Ravikumar S | This has been communicated to the team to ensure once the alert is triggered a proactive communication is posted in the teams channel | CSSM Devops |  | NA | 2023-11-07 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 815 | >60 | July | 2023 | #VALUE!
Customer Channels | Platform & Store Ops | 89415385 | 2023-07-10 | Foods waste value understated across various reports | A de-duplicate logic needs to be added and a backlog has been created. CSSM-9752 | Problem avoidance | Ravikumar S | A backlog CSSM-9752 has been created | CSSM Devops |  | NA | 2023-11-07 | Closed | NA | CSSM-9752 | Closed | Saloni | 2025-02-10 | 815 | >60 | July | 2023 | #VALUE!
Customer Channels | Platform & Store Ops | 89415385 | 2023-07-10 | Foods waste value understated across various reports | Messages once triggered should be cleared from retry queue – messages should systemically be cleared once retriggered. CSSM team has reviewed and validated the current SOP’s and have been reiterated to the team. In future the team will reach out to senior SME’s if the issue deals with multiple stuck messages | Solution & Recovery | Ravikumar S | Once the 81K messages were triggered, the alert retrospectively triggered in human error as the date of the messages was not checked. | CSSM Devops |  | NA | 2023-11-07 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 815 | >60 | July | 2023 | #VALUE!
Customer Channels | Platform & Store Ops | 89415385 | 2023-07-10 | Foods waste value understated across various reports | Actual root cause statement of why the 81K messages went into retry status is pending | Root cause | Ravikumar S | 14/07: As the RCA for the messages in the retry queue remains inconclusive - CSSM product teamhave configured a job dependecy to ensure the relevant job processing the foods waste adjustment can get processed successfully without any capacity constraints. | CSSM Devops |  | NA | 14/07/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 815 | >60 | July | 2023 | #VALUE!
Customer Channels | Platform & Store Ops | 89415385 | 2023-07-10 | Foods waste value understated across various reports | When working with retriggering messages and financial variance, all SOP’s are to be amended to ensure all tasks are double checked by an independent support person. | Solution & Recovery | Ravikumar S/ Rajasekar Subramaniam/ Remko Smit | 24/07: Bharat confirmed from CSSM that SOPs are updated and teams are made aware, As all teams have agreed on this action and conveyed to the team closing this action 17/07: Remko confimred that SAP systems have agreed to have peer review of tasks where viable, also sivasubrmani pappusamy from integration confirmed that from middleware end all in place 14/07: From CSSM, Ravi will update around 20th July | CSSM Devops/ Integration/ SAP |  | NA | 24/07/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 815 | >60 | July | 2023 | #VALUE!
Customer Channels | Platform & Store Ops | 89415385 | 2023-07-10 | Foods waste value understated across various reports | In the PIR the possibility of reducing the risk of missing things was discussed and we all need to keep mindful of the problem scenarios and the update given on the call must be verified and understood prior to be called out. | Problem avoidance | Various | This has been communicated across in the PIR to ensure appropriate scenarios are taken into consideration and explore improvised triaging options | All |  | NA | 2023-11-07 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 815 | >60 | July | 2023 | #VALUE!
Customer Channels | Service Experience | 89413024 | 2023-07-06 | Customers getting errors while tracking orders | Do we need to review the time zone in Salesforce and set to BST? | Solution & Recovery | Ajay Sharma | Raise case with Sales force to set time zone to BST and follow up. 7-Jul - Raised the Salesforce ticket: Case #44913543 for time zone difference in Salesforce Data extension. Update from Salesforce that time different of around 7 hours when storing data into data extension (which are used in a journey). Please note that the time difference of 7 hours accounts for the CST Time Zone. If you subtract 7 hours from the timestamp value, it would then equate CST time. Unfortunately, this is by design and there are no standard feature of changing this behaviour. Having said that, you can can look to convert the value into a desired time zone. | Sterling |  | NA | 2023-10-07 | Closed | NA |  |  | Saloni | 2025-02-10 | 819 | >60 | July | 2023 | #VALUE!
Customer Channels | Service Experience | 89413024 | 2023-07-06 | Customers getting errors while tracking orders | Knowledge gap to be addressed for Kafka - Sessions for Kafka to be conducted for product teams – Run book for frequent Kafka issues to be created and shared. | Problem avoidance | Aravind Rajaveeraswamy | This action has been completed as part of PEAK readiness | Integration Services |  | NA | 16/10/23 | Closed | NA |  |  | Saloni | 2025-02-10 | 819 | >60 | October | 2023 | #VALUE!
Customer Channels | Service Experience | 89413024 | 2023-07-06 | Customers getting errors while tracking orders | Returns confirmation RET-1 email template - Alert to be added at EM to identify duplicates. RET-1 > 5 emails based on return number | Problem identification & Alerting | Mukundan Rajagopalan | 17/07: The alert setup for duplicate RET-1 mails was completed EM. | Enterprise Middleware Team |  | NA | 17/07/23 | Closed | NA |  |  | Saloni | 2025-02-10 | 819 | >60 | July | 2023 | #VALUE!
Customer Channels | Service Experience | 89413024 | 2023-07-06 | Customers getting errors while tracking orders | Why didn’t we identify the SMS message that was sent to EM for returns confirmation since it went live? – SMS failed with generic error. Team to verify and get back if this can be identified for future | Solution & Recovery | Mukundan Rajagopalan | Analysis output from EM team - The SMS requests from returns were missing <tns:SMS> segment in the source xml. Due to this, incomplete json was getting framed in EM and getting rejected by Twilio with generic error at B2B layer. Due to this reason, exception/events didn't capture in EM. Only after returns team notified us about this issue, we looked at the I &O audit difference and investigated further. | Enterprise Middleware Team |  | NA | 2023-06-07 | Closed | NA |  |  | Saloni | 2025-02-10 | 819 | >60 | July | 2023 | #VALUE!
Customer Channels | Service Experience | 89413024 | 2023-07-06 | Customers getting errors while tracking orders | Identify Customer Owner for Confluent Kafka and create awareness on the support model of event platform team and Confluent. | Supplier and support involvement | Parit Shah | Parit Shah and Monish Nair are the Customer POC in terms of Confluent issues | Event Platform Team |  | NA | 2023-10-07 | Closed | NA |  |  | Saloni | 2025-02-10 | 819 | >60 | July | 2023 | #VALUE!
Customer Channels | Service Experience | 89413024 | 2023-07-06 | Customers getting errors while tracking orders | Improve logging so that product team is completely capable to analyze impact / issue – This should be done at BEAM end. | Impact analysis | Peter Rostron | 16/10: This action will be taken care by dot com business teams along with BEAM 10/10: Peter in in offshore visit and will provide an update by 19/10. 15/09: Peter and Clare have engaged with Louisa McCarron and Tomas Balon (from BEAM team) to discuss the specific requests that were blocked and are awaiting feedback on how to proceed. ETA: 09/10 10/07: The quality of data in BEAM is not good and BEAM team has rejected Q2 requests raised by returns team. | Product Manager |  | NA | 16/10/23 | Closed | NA |  |  | Saloni | 2025-02-10 | 819 | >60 | October | 2023 | #VALUE!
Customer Channels | Service Experience | 89413024 | 2023-07-06 | Customers getting errors while tracking orders | Review admin Access for product team. Only one member in team has confluent cloud admin access. | Solution & Recovery | Prem Gopalan | No user will have Confluent UI access. Instead, they can use cap drop. There is a self-service portal which can be used for day-to-day requests. | Returns Team |  | NA | 2023-10-07 | Closed | NA |  |  | Saloni | 2025-02-10 | 819 | >60 | July | 2023 | #VALUE!
Customer Channels | Service Experience | 89413024 | 2023-07-06 | Customers getting errors while tracking orders | Provide an option to resend the returns confirmation email from track returns page | Solution & Recovery | Prem Gopalan | A backlog has been created to resent the email confirmation from the returns page | Returns team |  | NA | 2023-10-07 | Closed | NA | https://jira.marksandspencer.app/browse/FULRE-1766 |  | Saloni | 2025-02-10 | 819 | >60 | July | 2023 | #VALUE!
Customer Channels | Service Experience | 89413024 | 2023-07-06 | Customers getting errors while tracking orders | The instructions to get barcode/QR code – Add in FAQ page | Solution & Recovery | Prem Gopalan | 17/07: This required co ordination with the Prod control Team and is anticipated to be completed by 27/07/2023. 05/08: This requires investigation and analysis and hence will be picked up in Sprint 2 | Returns team |  | NA | 2023-05-08 | Closed | NA |  |  | Saloni | 2025-02-10 | 819 | >60 | August | 2023 | #VALUE!
Customer Channels | Service Experience | 89413024 | 2023-07-06 | Customers getting errors while tracking orders | Is there any way to avoid duplicate emails being sent? | Problem avoidance | Prem Gopalan | 17/07: Prem Goapalan has confirmed that they will work on a mechanism to avoid duplicate emails being sent to the customer in the SPRINT 2. | Returns team |  | NA | 17/07/23 | Closed | NA |  |  | Saloni | 2025-02-10 | 819 | >60 | July | 2023 | #VALUE!
Customer Channels | Service Experience | 89413024 | 2023-07-06 | Customers getting errors while tracking orders | Alert for backlog – in Kafka topic / partition | Problem identification & Alerting | Prem Gopalan | A backlog has been created to configure the alerts in the Kafka partition | Returns Team |  | NA | 2023-10-07 | Closed | NA | https://jira.marksandspencer.app/browse/FULRE-1746 |  | Saloni | 2025-02-10 | 819 | >60 | July | 2023 | #VALUE!
Customer Channels | Service Experience | 89413024 | 2023-07-06 | Customers getting errors while tracking orders | Build a safe way to retrigger emails in case of exceptions / error | Solution & Recovery | Prem Gopalan | A backlog has been created to build a way to retrigger customer emails during exception scenarios | Returns Team |  | NA | 2023-10-07 | Closed | NA | https://jira.marksandspencer.app/browse/FULRE-1748 |  | Saloni | 2025-02-10 | 819 | >60 | July | 2023 | #VALUE!
Customer Channels | Service Experience | 89413024 | 2023-07-06 | Customers getting errors while tracking orders | Add a few seconds delay to trigger returns confirmation email and Email validation to not send any empty or blank for mandatory values. | Problem avoidance | Prem Gopalan | A backlog has been created to add a few seconds delay to trigger returns confirmation email and Email validation to not send any empty or blank for mandatory values. | Returns Team |  | NA | 2023-10-07 | Closed | NA | https://jira.marksandspencer.app/browse/FULRE-1764 https://jira.marksandspencer.app/browse/FULRE-1746 |  | Saloni | 2025-02-10 | 819 | >60 | July | 2023 | #VALUE!
Customer Channels | Service Experience | 89413024 | 2023-07-06 | Customers getting errors while tracking orders | New relic synthetic test to be implemented. Add into backlog. | Problem identification & Alerting | Prem Gopalan | A backlog has been created to implement the new relic synthetic test cases to identify these issues in an appropriate manner | Returns Team |  | NA | 2023-10-07 | Closed | NA | https://jira.marksandspencer.app/browse/FULRE-1765 |  | Saloni | 2025-02-10 | 819 | >60 | July | 2023 | #VALUE!
Customer Channels | Service Experience | 89413024 | 2023-07-06 | Customers getting errors while tracking orders | Validation / exception handling to be done to track and view returns page. Additional alerts if required to be added. | Problem identification & Alerting | Prem Gopalan | A backlog has been created to handle the exception scenarios inorder to recover the issues in a timely manner | Returns Team |  | NA | 2023-10-07 | Closed | NA | https://jira.marksandspencer.app/browse/FULRE-1767 |  | Saloni | 2025-02-10 | 819 | >60 | July | 2023 | #VALUE!
Customer Channels | Service Experience | 89413024 | 2023-07-06 | Customers getting errors while tracking orders | Identify root cause - Customers getting error in Returns tracking page and blank barcode in returns email conformation due to slowness. | Root cause | Prem Gopalan | 16/10: After a detailed analysis with the vendors Microsoft and Kafka, the root cause has remained inconclusive. Appropriate logs will be captured if the issue recurs. 15/09: Prem have confirmed they are having biweekly calls with the vendors to understand the RC. ETA: 18/10/ 07/08: There are no issues observed at Customer. A case has been raised with Microsoft and Kafka Confluent to analyse further. There is no promised ETA from the vendor. | ReturnsTeam |  | NA | 16/10/23 | Closed | NA |  |  | Saloni | 2025-02-10 | 819 | >60 | October | 2023 | #VALUE!
Infosec & Tech Risk | Infosec & Tech Risk | 89410912 | 2023-07-03 | Customers cannot place orders via desktop, mobile , apps | Given the high level of complexity, limited change control and the sensitivity of scripts to change, a more rigorous regime of testing is recommended. Although it is recognised that the preproduction environment does not accurately reflect the production environment so there will be limitations to the effectiveness of such testing. | Problem avoidance | Alison Sullivan | 24/08: Any changes for PIM, we have agreed that it will be tested in Staging environment before pushing into production which will ensure the issues seen will not be recur. 11/07: There is not a like-for-like environment for testing. Alison and her team do carry out extensive testing of tags. The root cause of the problem was PIM , not Tealium/the tags themselves. While this was a PIM change, there are other things that can impact this script. Lack of alerting and testing on this is still not acceptable, There should be an action on engineering to help add in some guard rails and make sure they are triggered off the back of an Tealium/PIM/Akamai change | Info Security |  | NA | 24/08/23 | Closed | NA |  |  | Saloni | 2025-02-10 | 822 | >60 | August | 2023 | #VALUE!
Customer Channels | Customer Engagement | 89410912 | 2023-07-03 | Customers cannot place orders via desktop, mobile , apps | If there is a sev 1 or sev 2, the relevant person in Business Ops should be called via ‘phone Possibly look at re-instating WhatsApp group | Solution & Recovery | Elaine Hawthorn | During any Sev1 Sev2 incidents, it has been agreed to dial the relevant business ops SPOC. No feasibility of reinstating whatsapp group 11/07: Tech Ops to set up a meeting with relevant people/teams e.g. Business Ops, Product teams to agree capability , WCS life cycle team | Tech Ops and Business Ops |  | NA | 21/09/23 | Closed | NA |  |  | Saloni | 2025-02-10 | 822 | >60 | September | 2023 | #VALUE!
Customer Channels | Customer Engagement | 89410912 | 2023-07-03 | Customers cannot place orders via desktop, mobile , apps | For such impact of this incident .Com Ops to be engaged by direct communication as updates in shared channels may not be picked up promptly | Business & IT Communication | Elaine Hawthorn | During any Sev1 Sev2 incidents, it has been agreed to dial the relevant business and tech ops SPOC. No feasibility of reinstating whatsapp group 11/07:If there is a sev 1 or sev 2, the relevant person in Business Ops should be called via phone. Possibly look at re-instating WhatsApp group | Tech Ops and Business Ops |  | NA | 21/09/23 | Closed | NA |  |  | Saloni | 2025-02-10 | 822 | >60 | September | 2023 | #VALUE!
Customer Channels | Selling Experience | 89410912 | 2023-07-03 | Customers cannot place orders via desktop, mobile , apps | Due to the current Customer architecture and our level of technical debt we continue to allow third-party scripts to run on our website and we allow third parties to make changes. This inevitably adds to complexity, which is already high and increases availability risk. We should continue to review the Customer architecture in this context and seek opportunities to simplify and strengthen | Permanent fix | Ian Banks | 16/10: A new third party vendor has been appointed to audit the tags across the pages on the website. 24/08: Info sec has reviewed the tags with Steve and agreed to include Steve and Himanshu in future conversations around the tags. There is a wider piece of work happening from the selling experience which will be part of the activity Steve and the team is doing. Liaise with Steve to get the id for the activity. Steve advised that some tags are a ‘necessary evil’ but there is a review of this area planned with an external agency. Both Steve and Himanshu should be included in any conversations that InfoSec have relating to tags. There is a known problem with ownership of tags/scripts. Part of the work that Steve will be doing in Selling experience is to identify owners. | Info Security |  | NA | 16/10/23 | Closed | NA |  |  | Saloni | 2025-02-10 | 822 | >60 | October | 2023 | #VALUE!
Infosec & Tech Risk | Infosec & Tech Risk | 89410912 | 2023-07-03 | Customers cannot place orders via desktop, mobile , apps | Akamai has acknowledged this bug and is urgently working on a solution. They will provide a patch update as soon as it's ready. | Permanent fix | Jijin Vellilapully | 15/08: Patch has been applied by Akamai and tested to be fixed. | Infosec |  | NA | 15/08/23 | Closed | NA |  |  | Saloni | 2025-02-10 | 822 | >60 | August | 2023 | #VALUE!
Infosec & Tech Risk | Infosec & Tech Risk | 89410912 | 2023-07-03 | Customers cannot place orders via desktop, mobile , apps | Customer may also need to revisit the use of PIM as it may be too intrusive for our current architecture | Permanent fix | Jijin Vellilapully | 15/08: PIM product had a bug which have been reviewed. It is producing value to the wider Customer identifying 3rd party scripts running on the website which we were able to remediate. Any changes performed will be tested in Staging before pushing into production 11/07: Jijin advised that this is being reviewed. Currently no changes are being made in PIM. Need to re-visit use of PIM with Akamai PIM changes will have a CM (Jira) created to allow visibility of changes. Jijin will own this. Until there is confidence in PIM, it was agreed that any changes to it should be done out of business hours. The path to Production should be fully tested | Info Security |  | NA | 15/08/23 | Closed | NA |  |  | Saloni | 2025-02-10 | 822 | >60 | August | 2023 | #VALUE!
Infosec & Tech Risk | Infosec & Tech Risk | 89410912 | 2023-07-03 | Customers cannot place orders via desktop, mobile , apps | Carry out testing in lower environment to confirm our understanding of root cause. | Root cause | Jijin Vellilapully and Sumitro Chakravarty | 15/08: Testing in staging completed and it was identified the root cause version was fixed as part of the bug applied 07/08: Akamai has fixed the bug in their enviornment. There is a deployment next week related to PIM validation which will bring closure to this action. Jijin will make the PIM change and Sumitro will help with the WCS related changes. This can also be used to work out the recovery plan if the problem were to occur again. | InfoSec , WCS, Lifecycle mgt team and Engineering |  | NA | 15/08/23 | Closed | NA |  |  | Saloni | 2025-02-10 | 822 | >60 | August | 2023 | #VALUE!
Infosec & Tech Risk | Infosec & Tech Risk | 89410912 | 2023-07-03 | Customers cannot place orders via desktop, mobile , apps | Customer should revisit the lessons learned from next, ASOS and Tesco to see what further exemplars they and similar organisations present. Such lessons can be fed into our ongoing strategy to influence the longer-term evolution of our architecture” | Problem avoidance | Jijin/ Rachel | 24/08: Reviewing how to progress on this as we need to engage with the Retail group to understand the use of third party scripts. This action is more of a strategic one. 11/07: Jijin to check with Rachel and see how this one is being progressed | Info Security |  | NA | 24/08/23 | Closed | NA |  |  | Saloni | 2025-02-10 | 822 | >60 | August | 2023 | #VALUE!
Infosec & Tech Risk | Infosec & Tech Risk | 89410912 | 2023-07-03 | Customers cannot place orders via desktop, mobile , apps | A previous exercise, looking at comparable organisations, including ASOS, TESCO and Next demonstrated that these companies strictly limit third-party scripts that run on their pages and minimise a third-party’s freedom to modify such scripts. It should be noted that Java scripts have upstream and downstream dependencies and consequences which must be considered when approving changes. Steve to be included in this work to avoid duplication with the work that he is carrying out | Problem avoidance | Rachel Laursen | 24/08: Any Production PIM changes will be carried out via Change Request and approved by the relevant stakeholders. Steve has been engaged on the review activity for the tags and confirmed there is wider piece of work happening to correct the tags and identify ownership from the selling experience team | Info Security |  | NA | 24/08/23 | Closed | NA |  |  | Saloni | 2025-02-10 | 822 | >60 | August | 2023 | #VALUE!
Customer Channels | Selling Experience | 89410912 | 2023-07-03 | Customers cannot place orders via desktop, mobile , apps | Integrate NewRelic browser SDK in FEAR/FESK apps to detect and debug earlier | Problem identification & Alerting | Steve Warren | New Relic alerts have been configured across all the pages | Engineering |  | NA | 16/10/23 | Closed | NA |  |  | Saloni | 2025-02-10 | 822 | >60 | October | 2023 | #VALUE!
Customer Channels | Selling Experience | 89410912 | 2023-07-03 | Customers cannot place orders via desktop, mobile , apps | We need to accelerate onyx rollout so Adobe Target can be replaced by Optimizely, and as the site moves across to Onyx we will be able to get rid of "utag.sync.js" (the 'blocking' script) entirely | Problem avoidance | Steve Warren | The migration activity from Adobe Target to Optimizely across Channels has been completed | Engineering |  | NA | 16/10/23 | Closed | NA |  |  | Saloni | 2025-02-10 | 822 | >60 | October | 2023 | #VALUE!
Customer Channels | Selling Experience | 89410912 | 2023-07-03 | Customers cannot place orders via desktop, mobile , apps | 1. Java Script We should be able to track browser errors in New Relic. However, there are so many javascript errors on all pages that it is impossible to identify ‘new’ js errors. Should we get Product teams to sort out all js errors so that ‘new’ errors can be easily identified. Need alerting on JS errors and reduce the number of them. Steve to review 2. General Is alerting adequate? Do we need to introduce any new alerts?, if so where. Need alerting on front end of checkout. In order to do this we need an audit of which pages that do not have NR alerting . Aadil to provide (can Observepoint be used for this?). Once Aadil has provided the list, Steve will own the action | Problem identification & Alerting | Steve Warren and Elaine Hawthorn | We have reviewed the alerting mechanism for all the Java script errors. | Engineering and tech Ops |  | NA | 16/10/23 | Closed | NA |  |  | Saloni | 2025-02-10 | 822 | >60 | October | 2023 | #VALUE!
Infosec & Tech Risk | Infosec & Tech Risk | 89410912 | 2023-07-03 | Customers cannot place orders via desktop, mobile , apps | Every team that contributes to the .Com website should be made aware of a significant incident. We need a clear "engineering" list of who to include for the different parts of the site as we have a lot of new people in MnS | Solution & Recovery | Steve Warren Jijin Velilapully Elaine Hawthorn | 15/08: InfoSec group needs to be involved in any .Com related issues. 11.07: The timeline for Infosec being involved in the incident was too long. InfoSec should be made aware of incidents as soon as they are communicated to others. Furthermore, all teams should proactively check for issues related to their systems, and report back | Engineering, Infosec and Tech Ops |  | NA | 15/08/23 | Closed | NA |  |  | Saloni | 2025-02-10 | 822 | >60 | August | 2023 | #VALUE!
Infosec & Tech Risk | Infosec & Tech Risk | 89410912 | 2023-07-03 | Customers cannot place orders via desktop, mobile , apps | Customer need to hold Akamai to account to enable a better understanding of why there is such sensitivity to change. This activity should have been non-impactful, and we cannot say with any certainty that similar activities would not have unforeseen consequences” | Solution & Recovery | Steve Warren/ Jijin Vellilapully | 14/08: Reviewed with Akamai around the option to test any production changes in Staging environment before activation for end customers. This process will be followed for any future changes 07/08: Akamai has fixed the bug in their enviornment. There is a deployment next week related to PIM validation which will bring closure to this action. Akamai advised that it is a bug their side. Akamai Account Manager is involved. Sensitivity to change here explicitly means making akamai rule changes and setting to ignore, and not changes in general. All Changes should be tested regardless of how harmless they appear. Engineering should provide an automated suite of tests that MUST be triggered after all changes to reduce risk | Infosec and Engineering |  | NA | 15/08/23 | Closed | NA |  |  | Saloni | 2025-02-10 | 822 | >60 | August | 2023 | #VALUE!
Customer Channels | Customer Engagement | 89410912 | 2023-07-03 | Customers cannot place orders via desktop, mobile , apps | Software systems are inherently complex, and any change has the potential for unexpected harm to be done. Any change to production should be sanity tested, preferably via automation. In this incident, if the PIM change had been sanity tested, the link between the change and the incident could have been made sooner | Solution & Recovery | Steve Warren/ Jijin Vellilapully | 15/08: Reviewed with Akamai around the option to test any production changes in Staging environment before activation for end customers. This process will be followed for any future changes. Agreed all production changes in Akamai will be carried out as part of the CR process. | Engineering, InfoSec |  | NA | 15/08/23 | Closed | NA |  |  | Saloni | 2025-02-10 | 822 | >60 | August | 2023 | #VALUE!
Infosec & Tech Risk | Infosec & Tech Risk | 89410912 | 2023-07-03 | Customers cannot place orders via desktop, mobile , apps | End to end diagnostic capabilities not sufficient. The teams were not able to narrow down the root cause & where in the application flow the failure was occurring. Review effectiveness of participation when running an incident in headless set up | Solution & Recovery | Steve Warren/ Jijin Vellilapully | 15/08: InfoSec group needs to be involved in any .Com related issues 11/07: one of the problems was getting the right people on the bridge. Need to understand who to involve need consolidated list of all changes. | Infosec and Engineering |  | NA | 15/08/23 | Closed | NA |  |  | Saloni | 2025-02-10 | 822 | >60 | August | 2023 | #VALUE!
Infosec & Tech Risk | Infosec & Tech Risk | 89409612 | 2023-06-29 | Multiple users reported that they are not able to login to Outlook and applications via SSO (Single Sign-On) | Ensure limited and restricted testing is done on production AD to ensure that no adverse issues occur. This testing can also be done in read only mode. Change the process to account for prod AD testing | Problem avoidance | Duane Bergh/ Farid Arab | 15/08: All testing will be done in Non-Prod where possible, limited and controlled testing will only be allowed in PROD where full funtionality testing in non-prod is not possible due to environmental differences. This will be done at change assessment time by DWS AD Team before the email approval is provided. (the email approval that is usually attached to the CR in Remedy) 07/08: Farid and Duanne are OOO, need to get some updates once they are back. 25/07: Saloni had a call with Duane to provide an urgent update, Peter has advised that he will send an update on 07/08/2023 | WPT Identity team |  | NA | 15/08/23 | Closed | NA |  |  | Saloni | 2025-02-10 | 826 | >60 | August | 2023 | #VALUE!
Infosec & Tech Risk | Infosec & Tech Risk | 89409612 | 2023-06-29 | Multiple users reported that they are not able to login to Outlook and applications via SSO (Single Sign-On) | Change the current change process for any work relating to AD to ensure all key SME’s including all vendors are on the call and the work is done under strict hypercare to ensure every step is verified. | Solution & Recovery | Duane Bergh/ Farid Arab | 15/08: Going forward an AD SME will be involved in such changes during implementation to oversee. This will be done as part of the change approval assessment. An AD engineer will be assigned when the Email approval is provided by DWS AD Team. An Engineer will only be assigned if deemed necessary for large changes to applications that could potentially make changes to AD objects and impact users. 07/08: Farid and Duanne are OOO, need to get some updates once they are back. 25/07: Saloni had a call with Duane to provide an urgent update, Peter has advised that he will send an update on 07/08/2023 | WPT Identity team |  | NA | 15/08/23 | Closed | NA |  |  | Saloni | 2025-02-10 | 826 | >60 | August | 2023 | #VALUE!
Infosec & Tech Risk | Infosec & Tech Risk | 89409612 | 2023-06-29 | Multiple users reported that they are not able to login to Outlook and applications via SSO (Single Sign-On) | Speak to Microsoft about what options they have to help us restore AD in the event of a similar recurrence. Also validate this with Andy Neilson and Farid Arab | Solution & Recovery | Duane Bergh/ Farid Arab | 15/08: Discussion with Microsoft took place, the recommendation was to utilise exisiting AD Recovery tools like Semperis and Quest Recovery Manager for AD 07/08: Farid and Duanne are OOO, need to get some updates once they are back. 25/07: Saloni had a call with Duane to provide an urgent update, Peter has advised that he will send an update on 07/08/2023 | WPT Identity team |  | NA | 15/08/23 | Closed | NA |  |  | Saloni | 2025-02-10 | 826 | >60 | August | 2023 | #VALUE!
Infosec & Tech Risk | Infosec & Tech Risk | 89409612 | 2023-06-29 | Multiple users reported that they are not able to login to Outlook and applications via SSO (Single Sign-On) | Ascertain what tools we need to be able to restore AD back as quickly as possible | Solution & Recovery | Duane Bergh/ Farid Arab | 14/08: One Identity has provided Quest Recovery Manager for AD to help with AD restoration, the tool is also recommended by Microsoft and is currently being setup and tested in CATE and will be in PROD for the next Go Live of One Identity. (Please note that OneIdentity and Quest are the same company) 07/08: Farid and Duanne are OOO, need to get some updates once they are back. 25/07: Saloni had a call with Duane to provide an urgent update, Peter has advised that he will send an update on 07/08/2023 | WPT Identity team |  | NA | 15/08/23 | Closed | NA |  |  | Saloni | 2025-02-10 | 826 | >60 | August | 2023 | #VALUE!
Infosec & Tech Risk | Infosec & Tech Risk | 89409612 | 2023-06-29 | Multiple users reported that they are not able to login to Outlook and applications via SSO (Single Sign-On) | At 7.45am the team attempted to recover the position by manually clearing records in Identity Manager, but this action initiated further updates to AD, including Account disablement and Group Removal. | Problem avoidance | Peter Boyle/ One Identity | 04/08: A change to a custom script but that wasn't the main issue as the chain of events would have inevitably happened at some other point. The core issue was that a custom template had not been updated to reflect Production AD values. All templates and scripts have now been reviewed by the vendor and we are underway with testing again now. Test results will be reviewed by the vendor and we will only proceed once they confirm that we have evidenced all test case as per their suggestion. 14/07: Saloni had a call with Peter to provide an urgent update, Peter has advised that he will send an update on 18/07/2023 Removes the account from ID manager and ID manager thinks they should be disabled. Treated them as leavers. Should have blocked the connecter first – lesson learnt. Done in good faith.Create a new process for the next go live of ID manager – the end to end process and usage of tools. | Info Security |  | NA | 2023-07-08 | Closed | NA |  |  | Saloni | 2025-02-10 | 826 | >60 | August | 2023 | #VALUE!
Infosec & Tech Risk | Infosec & Tech Risk | 89409612 | 2023-06-29 | Multiple users reported that they are not able to login to Outlook and applications via SSO (Single Sign-On) | Ascertain how a CATE template came to be promoted in PROD | Root cause | Peter Boyle/ One Identity | 04/08: A change to a custom script but that wasn't the main issue as the chain of events would have inevitably happened at some other point. The core issue was that a custom template had not been updated to reflect Production AD values. All templates and scripts have now been reviewed by the vendor and the team are underway with testing. Test results will be reviewed by the vendor and we will only proceed once they confirm that we have evidenced all test case as per their suggestion. 14/07: Saloni had a call with Peter to provide an urgent update, Peter has advised that he will send an update on 18/07/2023. | Info Security |  | NA | 2023-07-08 | Closed | NA |  |  | Saloni | 2025-02-10 | 826 | >60 | August | 2023 | #VALUE!
Infosec & Tech Risk | Infosec & Tech Risk | 89409612 | 2023-06-29 | Multiple users reported that they are not able to login to Outlook and applications via SSO (Single Sign-On) | Ascertain the trigger that caused the chain of events that led to all AD accounts being changed from 01:41 | Root cause | Peter Boyle/ One Identity | 07/08 A change to a custom script but that wasn't the main issue as the chain of events would have inevitably happened at some other point. The core issue was that a custom template had not been updated to reflect Production AD values. All templates and scripts have now been reviewed by the vendor and the team are underway with testing. Test results will be reviewed by the vendor and we will only proceed once they confirm that we have evidenced all test case as per their suggestion. 14/07: Saloni had a call with Peter to provide an urgent update, Peter has advised that he will send an update on 18/07/2023 | Info Security |  | NA | 2023-07-08 | Closed | NA |  |  | Saloni | 2025-02-10 | 826 | >60 | August | 2023 | #VALUE!
GTS | Operations | 89409612 | 2023-06-29 | Multiple users reported that they are not able to login to Outlook and applications via SSO (Single Sign-On) | Work with John Frost in BC to ascertain the best way to broadcast a cross portfolio incident in case we lose the ability to log in. | Business & IT Communication | Sathish/ John Frost | This is a long term action and a detailed discussion is to be arranged to determine a mode of comms to the user community. | SIAM/ Business Continuity |  | NA | 16/10/23 | Closed | NA |  |  | Saloni | 2025-02-10 | 826 | >60 | October | 2023 | #VALUE!
GTS | Operations | 89409612 | 2023-06-29 | Multiple users reported that they are not able to login to Outlook and applications via SSO (Single Sign-On) | Review the sev 0 process and ensure that tasks can be done in parallel and how communication can be improved | Business & IT Communication | Sathish/ Rehan | A discussion will take place between MIM and Infosec to arrange a mock sev 0 inorder to refresh the process and comms. A data is yet to be finalized. Infosec has been given a walkthrough of the sev0 process. | MIM |  | NA | 2023-03-08 | Closed | NA |  |  | Saloni | 2025-02-10 | 826 | >60 | August | 2023 | #VALUE!
GTS | Operations | 89409612 | 2023-06-29 | Multiple users reported that they are not able to login to Outlook and applications via SSO (Single Sign-On) | It took time to ascertain which users needed to be restored as matter of priority. Do we need to create and maintain a list of priority people/areas with their P numbers and contact details | Impact analysis | Sathish/John Frost | This is a long term action and a detailed discussion is to be arranged to determine a mode of identifying the impacted users. | SIAM/ Business Continuity |  | NA | 16/10/23 | Closed | NA |  |  | Saloni | 2025-02-10 | 826 | >60 | October | 2023 | #VALUE!
Group Support | HR | 89402066 | 2023-06-28 | MyHR T&A application incorrectly excluding breaks for colleague timesheet punches | Root cause of the issue | Root cause | BY team/Alex | A configuration change within the T&A application to prevent colleagues from manual break punches was overridden by an unknown job at Blue Yonder which hindered the auto generation of breaks resulting in incorrect colleague payments calculation | HR |  | NA | 28/06/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 827 | >60 | June | 2023 | #VALUE!
Group Support | HR | 89402066 | 2023-06-28 | MyHR T&A application incorrectly excluding breaks for colleague timesheet punches | Is there a process to engage the BY team on a MIM bridge to assess the impact? | Impact analysis | BY team/Alex | A process has been agreed to keep MIM informed on such scenario’s and MIM will be involved based on the impact of the issue. | HR |  | NA | 28/06/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 827 | >60 | June | 2023 | #VALUE!
Group Support | HR | 89402066 | 2023-06-28 | MyHR T&A application incorrectly excluding breaks for colleague timesheet punches | A staff member in store takes their break and punches for this break - if this break time is different to the system generated break time it causes issues in the calculation. BY have been asked to create an alert to notify us of this clash in timiings so that it can be proactively dealt with before the pay run. | Problem identification & Alerting | BY team/Alex | 14/07 - BY team has created the appropriate alerts and it will be into production by end of week. Alex (prodcut Owner) has agreed to close the action 04/07: We had a call with Alex and he will work with BY to explore the feasibility of configuring alerts for identifying any incorrect break punches resulting in incorrect break calculation in the T&A application. Alex will follow up with BY and update by 11/07. To enhance the process, daily health checks will be planned. In parallel, the feasibility of configuring an alert for incorrect break calculation in the application. | HR |  | NA | 14/07/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 827 | >60 | July | 2023 | #VALUE!
Group Support | HR | 89402066 | 2023-06-28 | MyHR T&A application incorrectly excluding breaks for colleague timesheet punches | Scope of implementing a workaround to mitigate impact during future occurrences. | Solution & Recovery | BY team/Alex | There is an existing script, documented in the SOP and the same is updated with this scenario as well. | HR |  | NA | 28/06/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 827 | >60 | June | 2023 | #VALUE!
Group Support | HR | 89402066 | 2023-06-28 | MyHR T&A application incorrectly excluding breaks for colleague timesheet punches | Feasibility to improve the post implementation checks and introduce additional test cases before deploying any fix into production. | Problem avoidance | BY team/Alex | The new functionality was developed to prevent manual break punches and was thoroughly tested. However, the weekly Jobs were not included in the testing which had overridden the change, causing the issue. It has been agreed to improve the testing by introducing new test cases. | HR |  | NA | 28/06/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 827 | >60 | June | 2023 | #VALUE!
Group Support | HR | 89402066 | 2023-06-28 | MyHR T&A application incorrectly excluding breaks for colleague timesheet punches | Feasibility of improving the SOP’s/Reference documents to improve the scripting/testing process? | Problem avoidance | BY team/Alex | 14/07 - the SOP has been updated with the required steps and these steps are included in the stores training documentation 04/07: Alex (product Owner) to check with T&A (accenture) team and will feedback with an update UAT team has been informed to update the SOP. The same will be updated with all the required details. | HR |  | NA | 14/07/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 827 | >60 | July | 2023 | #VALUE!
Group Support | HR | 89402066 | 2023-06-28 | MyHR T&A application incorrectly excluding breaks for colleague timesheet punches | What is the permanent fix? | Permanent fix | BY team/Alex | 14/07 - The permanent fix is a roadmap item for the blueyonder product, which has been submitted and it will further be tracked by the Product Owner (Alex) via the Project ID -BY 04793799. Alex (prodcut Owner) has agreed to close the action 04/07: Alex (product Owner) to check with T&A (accenture) team and will feedback with an update Currently, colleagues are allowed to punch for their breaks manually as the auto- break calculation is being overridden by the weekly jobs. BY team will work on the permanent fix providing us with a better solution to systemically calculate breaks also Store comms are sent advising them to strictly follow the break rules/timings. In parallel, efforts will be made to improve the workaround to mitigate the impact. | HR |  | NA | 14/07/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 827 | >60 | July | 2023 | #VALUE!
Group Support | Finance | 89395055 | 2023-06-23 | Ecom sales understated by £835K in GMOR BO and BEAM reports | Manual checks to ensure processing is running as normal prior to the incident were done at 4-5pm and 10-11am UK time – this frequency was not sufficient– checks timings have now been changed 21:00, 22:30, 02:00 10:00, 16:00 – this will give us confidence that there are no locks and system is clean | Problem identification & Alerting | Krishna Prasad | The agreed timings has now been configured to perform manual checks | SAP |  | NA | 26/06/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 832 | >60 | June | 2023 | #VALUE!
Group Support | Finance | 89395055 | 2023-06-23 | Ecom sales understated by £835K in GMOR BO and BEAM reports | Krishnaprasad Rajendran to lead the investigation into the creation of bespoke alerts for this scenario. No out of the box alerting solution available for POSTDTA – the product owner has been asked (Balram Pulgam) to create a backlog to prioritise and initiate this in quarterly planning (Q3) | Problem identification & Alerting | Krishna Prasad | 10/07: Consideting limitations as POSDTA is a SaaS product hosted by the SAP vendor. This was discussed in the Quarterly Planning with the Product Manager and added this to the backlog.. 04/07: Awaiting backlog details from Krishna | SAP |  | NA | 2023-10-07 | Closed | NA | SAP-SLS-00144 |  | Saloni | 2025-02-10 | 832 | >60 | July | 2023 | #VALUE!
Group Support | Finance | 89395055 | 2023-06-23 | Ecom sales understated by £835K in GMOR BO and BEAM reports | Assess the feasibility of a source to target reconciliation. | Problem avoidance | Narayana Moorthy Kanagaraj | 14/07: POSDTA alerts are planned (SAP four wall change) in sprint B of Q2 (Backlog ID ‘SAP-SLS-00144’) in addition to the discovery work of Sterling and POSDTA recon. 13/07: A Q2 discovery item for POS to POSDTA to SAP message monitoring 10/07: Followed up with Moorthy awaiting an update 30/06: Recon report between Sterling and POSDTA was deployed last year. However, it was stopped as the output was not proper. We will further check with SAP Product manager for prioritization. | SAP |  | NA | 14/07/23 | Closed | NA | SAP-SLS-00144 |  | Saloni | 2025-02-10 | 832 | >60 | July | 2023 | #VALUE!
Group Support | Finance | 89395055 | 2023-06-23 | Ecom sales understated by £835K in GMOR BO and BEAM reports | Ask SAP vendor if anything else is available that can be easily implemented – find the root cause and then approach SAP vendor to see if anything else is available | Root cause | Narayana Moorthy Kanagaraj | 14/07: Replicate the locking scenario in non-prod is not possible. However, the over running alert has been reduced from 120 minutes to 116 minutes in ConrolM.A SEV2 incident will be triggered when the job is over running and necessary action (monitor and remove locks) will be taken based on alerts. 13/07: This is the update on the "445K late returns" from this morning; i.e. we are working with OSS on RCA but they insist on replication in Test environment (not possible) 10/07: Followed up with Moorthy awaiting an update 30/06: SAP vendor requested to provide reproducible examples in lower environment. However, we could not replicate it without manual intervention. As per current anlaysis, issue occurred in SAP standard NAVIX table. We are further exploring options to replicate the scenario. As part of workaround, manual hypercare is planned at 22:00 and 02:00 BST to ensure that Ecom sales are not piled up in POSDTA. | SAP |  | NA | 14/07/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 832 | >60 | July | 2023 | #VALUE!
Customer Channels | Platform & Store Ops | 89382363 | 2023-06-21 | 56 selling price changes reached FMD and POS (tills) but not ECS (tickets) | What is the best practice when working on both prod and non-prod is WINSCP the best way? Ravi to talk to engineering COE and brainstorm. | Problem avoidance | Ravikumar. S | 11/07 - FileZilla has been implemented in Non-prod and different colors codings has bene set-up to differentiate with Prod. 07/07 - FileZilla opensource has been installed and this tool is being explored for configuring mutiple colors (kind of differentiating ) Our ECS team has explored options in WNSCP and has identified that we can configure multiple colors in WINSCP. This will easily help user in differentiating the Non-prod and Prod. This can be suggested to the other account using WINSCP. Alternatively teams are looking for an option to use FileZilla opensource and the workorder has been placed for the same to get this tool for exploration | TPM- ECS |  | NA | 2023-11-07 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 834 | >60 | July | 2023 | #VALUE!
Customer Channels | Platform & Store Ops | 89382363 | 2023-06-21 | 56 selling price changes reached FMD and POS (tills) but not ECS (tickets) | How can we differentiate between prod and non-prod screens that are already open – Ravi to brainstorm a solution which we can potentially deploy to other areas. | Problem avoidance | Ravikumar. S | Our ECS team has explored options in WNSCP and has identified that we can configure multiple colors in WINSCP. This will easily help user in differentiating the Non-prod and Prod. This has been suggested to the other account using WINSCP. | TPM- ECS |  | NA | 26/06/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 834 | >60 | June | 2023 | #VALUE!
Customer Channels | Platform & Store Ops | 89382363 | 2023-06-21 | 56 selling price changes reached FMD and POS (tills) but not ECS (tickets) | ECS and RET team needs to be added to the report in number 2 – ECS vendor to do this | Supplier and support involvement | Ravikumar.S | Discussions were made with ECS and they have suggested that when there is incorporation of Event manager thus this action is not required. Also ECS is using traditional approach currently and will be moving to modern solution very soon. This this action is not required to be implemented as per ECS. | TPM- ECS |  | NA | 26/06/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 834 | >60 | June | 2023 | #VALUE!
Customer Channels | Platform & Store Ops | 89382363 | 2023-06-21 | 56 selling price changes reached FMD and POS (tills) but not ECS (tickets) | RET team have removed prod passwords from being auto saved in WINSCP which means they will now manually have to enter the password. | Root cause | Vikram | The prod URL has been deleted from WINSCP and if it is needed it can be manually entered again. | ECS Team |  | NA | 21/06/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 834 | >60 | June | 2023 | #VALUE!
Customer Channels | Platform & Store Ops | 89382363 | 2023-06-21 | 56 selling price changes reached FMD and POS (tills) but not ECS (tickets) | Event based alerting to be created for unprocessed processed changes after the planogram deployment 26/6 | Problem identification & Alerting | Vikram | 11/07 - Teams are unable to get the event based alerting as they are facing a challenge there, a case has been opened with Vendor ECS on the same. however to address the alerting part, scheduled based alerting has been set-up. TEams will work internally in the event based alerting 07/07 - Alerting that was set-up and tested in non-prod did not work as expected. The team is checking on other feasibility, parallelly a case will be opened with Vendor ECS for futher analysis 04/07 - Aleting has been setup in CATE and the same will be put in production 07/07 Deployments has been done and teams are on hypercare. Once the hypercare and few pre-checks are positive. The alerting will be set-up | ECS Team |  | NA | 2023-11-07 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 834 | >60 | July | 2023 | #VALUE!
Customer Channels | Platform & Store Ops | 89382363 | 2023-06-21 | 56 selling price changes reached FMD and POS (tills) but not ECS (tickets) | File processing had stopped, and we were not notified. | Problem avoidance | Vikram/ECS team | The ECS team has therefore set up a 7am report to be shared to RET team to identify pending files that have not yet been processed. | ECS Team |  | NA | 21/06/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 834 | >60 | June | 2023 | #VALUE!
Customer Channels | Platform & Store Ops | 89382363 | 2023-06-21 | 56 selling price changes reached FMD and POS (tills) but not ECS (tickets) | Vikram to ask if the report can be created twice a day nearer to the times the files are processed; 22:00 and 11:00 | Problem avoidance | Vikram/ECS vendor | Vendor ECS has responded stating that " The reports can't be changed as its generic job for other clients" | ECS Team |  | NA | 26/06/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 834 | >60 | June | 2023 | #VALUE!
Customer Channels | Service Experience | 89385821 | 2023-06-20 | B2B customers unable to use their e-codes/e-gift cards | Progress root cause investigation with Scene 7. Need to have a technical with Scene 7. | Root cause | Lorna Woodman | The B2B e-gift cards involves Akamai Dynamic Media delivery at Customer pointing to the Adobe managed CDN (Content Delivery Network). When the CDN has the content in cache, it is served from the CDN cache, otherwise, the CDN will fetch the content from one of its origin servers. Th origin servers are located in different datacentres - Amsterdam, London and Ireland. The Ireland datacentre was built recently and some validation steps were missed at Adobe causing http traffic not being enabled resulting in thtermittent 500 internal server errors. Root cause : Vendor Scene 7 confirmed that the B2B e-gift card URL using HTTP was not enabled in the recently built Adobe datacentre due to insufficient testing resulting in the 500 internal server errors. | Customer Promise Web Engineering |  | NA | 2023-10-07 | Closed | NA |  |  | Saloni | 2025-02-10 | 835 | >60 | July | 2023 | #VALUE!
Customer Channels | Service Experience | 89385821 | 2023-06-20 | B2B customers unable to use their e-codes/e-gift cards | Scene 7’s level of support Incident response and updates from 3rd party Scene 7, not sufficient. 1. Currently we don’t know who our Account Manager is, this needs to be confirmed. 2. Need to understand what level of support Scene 7 should be providing us during major incident scenarios. 3. Confirm escalation process. | Supplier and support involvement | Lorna Woodman | It has been advised to loop in Harrison Green and Michelle Gurjao harrisong@adobe.com mgurjao@adobe.com during future Adobe incidents inorder to ensure better support from the vendor | Customer Promise Web Engineering |  | NA | 2023-10-07 | Closed | NA |  |  | Saloni | 2025-02-10 | 835 | >60 | July | 2023 | #VALUE!
Customer Channels | Service Experience | 89385821 | 2023-06-20 | B2B customers unable to use their e-codes/e-gift cards | Workaround code change Review to confirm is this change to remain in place or is a further change required in EM on PRD002 flow. Currently within the EM code there is logic to apply the start of the image URL (http://asset2.marksandspencer.com/is/image/mands/) and add to the end of it the attribute ID coming from PIM, EM then sends this full URL within the image location field to OMS Example complete URL - http://asset2.marksandspencer.com/is/image/mands/MS_08_T46_0717 | Permanent Fix | Nicole Otigbah | 21/06: Closing this is action backlog as the team tracking permanent fix under product backlog bucket. | Customer Promise Web Engineering |  | NA | 29/06/23 | Closed | NA | EG-5979 |  | Saloni | 2025-02-10 | 835 | >60 | June | 2023 | #VALUE!
Customer Channels | Service Experience | 89385821 | 2023-06-20 | B2B customers unable to use their e-codes/e-gift cards | Alerts configured: 1. 50 failures in last 2 mins 2. 10 failures in last 2 mins Confirm what is the average traffic in 2 mins? Then review and change thresholds if needed | Problem identification & Alerting | Vijesh Mehta | 03/07: Alerts configured | Customer Promise Web Engineering |  | NA | 2023-04-07 | Closed | NA | EG-5977 |  | Saloni | 2025-02-10 | 835 | >60 | July | 2023 | #VALUE!
Customer Channels | Service Experience | 89385821 | 2023-06-20 | B2B customers unable to use their e-codes/e-gift cards | Need to ensure PO & Service Lead is engaged when service is impacted. Service Lead made aware of this issue via stakeholders. | Problem avoidance | Vijesh Mehta | 03/07: Conveyed the stakeholders to involve Service Leads during any issue | Customer Promise Web Engineering |  | NA | 2023-04-07 | Closed | NA | EG-5978 |  | Saloni | 2025-02-10 | 835 | >60 | July | 2023 | #VALUE!
Commercial Trading | Foods Commercial Trading | 89350725 | 2023-06-09 | Incorrect Foods SRD ranging file sent to Quantum and Relex | Colleagues were waiting for a long time for correct/useful/meaningful data to become available. This then has a knock-on impact for decision making and, in some cases, impact mitigation actions. | Impact analysis | Andrew Goslin/ Promoth Kumar | Delay in receiving data from Tech and once data arrived, it was not complete/useful (Quality). Tech teams to investigate how useful data requirements can be shared quicker Note: Standard/Minimum data requirements that must be maintained: <Product Data>UPC Code / UPC Description/ Product Group / Super Group / Category <Store Data>Store code / Store Description / STG (Store Group) / Depot Code / Depot Description. 23/06 - The team has been educated on this and the wider business view has been explained to the team. Promoth has guarenteed that team will take the right steps at the right time, the process has been improved. Also it has been agreed that the right SME will join the call to instruct the team. Appropriate trainings are passed on to the team | TEM |  | NA | 23/06/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 846 | >60 | June | 2023 | #VALUE!
Commercial Trading | Foods Commercial Trading | 89350725 | 2023-06-09 | Incorrect Foods SRD ranging file sent to Quantum and Relex | Process improvement by introducing a new alert and Check Points (Tech and stakeholder enhancement) | Problem identification & Alerting | Ian Griffiths/ Karthika Sethuraman | SRD team (PO and engineering) to investigate the feasibility of introducing an improvement to the service by creating an alert based on a tolerance overnight calculation process which would trigger a report (or update a dashboard) for colleague validation. Based on this, two options could potentially be triggered <1. Continue SRD batch process> / <2. stop processing and begin in-depth investigation> Note: Downstream considerations will also be needed (delay/impact to batch and consuming systems etc) + what contingency process will need to be triggered based off of specific cutoffs. 26/06 - Few initiatives are taken up by the team for Q2 (JUl-SEP). Karthika to provide an update by End of Q2. 31/07 - Since this is a long term action, it will further be tracked via the backlog mentioned in the backlog col - O | Product Owner/ SRD |  | NA | 31/07/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 846 | >60 | July | 2023 | #VALUE!
Commercial Trading | Foods Commercial Trading | 89350725 | 2023-06-09 | Incorrect Foods SRD ranging file sent to Quantum and Relex | The correction of SRD file in the first instance failed during data validation due to missing data and we had re do the same and it wasn’t highlighted on the call for more than 1.5 hours how can this be prevented while recovering the data going forward? | Solution & Recovery | Karthika Sethuraman | 18/07 - Colleagues have been advised accordingly on the steps they need to follow to prevent the human errors also the relevant SOP's has been updated. It has been agreed that there was a human error while performing the adhoc run with the corrected range file at 13:55. It was then addressed in the next run at 16:25. 26/06 - Few initiatives are taken up by the team for Q2 (JUl-SEP). Karthika to provide an update by End of Q2. | SRD |  | NA | 17/07/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 846 | >60 | July | 2023 | #VALUE!
Commercial Trading | Foods Commercial Trading | 89350725 | 2023-06-09 | Incorrect Foods SRD ranging file sent to Quantum and Relex | Identify the intensity of the issue and communicate to the wider forum for proactive notification to the relevant stakeholders. | Problem identification & Alerting | Karthika Sethuraman | In this case, the SRD team identified the issue with one product at 09:00 and the service lead was made aware at 10:00 by the business. To remediate the gap, it has been agreed to communicate to the wider audience (Service lead, TEM and MIM) immediately after the issue has been reported to the team. | SRD |  | NA | 2023-09-06 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 846 | >60 | June | 2023 | #VALUE!
Commercial Trading | Foods Commercial Trading | 89350725 | 2023-06-09 | Incorrect Foods SRD ranging file sent to Quantum and Relex | Why the issue was not identified during the testing and what was the post implementation checks performed and was there any Hypercare in place to validate the data after the change Improvement on post implementation checks (e.g data 'quality' validation pre vs post change) + early warning/comms opportunities before impacts start or stakeholder alert | Problem avoidance | Karthika Sethuraman | There was a difference in datasets while the change was tested in non-prod. In addition, there was a gap in identifying the range drops during the post implementation checks. This has been addressed in action 1. Improvement on post implementation checks (e.g data 'quality' validation pre vs post change) + early warning/comms opportunities before impacts start or stakeholder alert 26/06 - Few initiatives are taken up by the team for Q2 (JUl-SEP). Karthika to provide an update by End of Q2. 31/07 - Since this is a long term action, it will further be tracked via the backlog mentioned in the backlog col - O | SRD |  | NA | 31/07/23 | Closed | NA | FSRD-3342 | N/A | Saloni | 2025-02-10 | 846 | >60 | July | 2023 | #VALUE!
Commercial Trading | Foods Commercial Trading | 89350725 | 2023-06-09 | Incorrect Foods SRD ranging file sent to Quantum and Relex | Introduce threshold alerts in SRD DS to identify if there are any deviations in ranging and refrain the sending of the file to the downstream systems. Also explore the feasibility to introduce alerts in Relex as we have in Quantum | Problem identification & Alerting | Karthika Sethuraman | This is current being explored. 26/06 - Few initiatives are taken up by the team for Q2 (JUl-SEP). Karthika to provide an update by End of Q2. 31/07 - Since this is a long term action, it will further be tracked via the backlog mentioned in the backlog col - O | SRD |  | NA | 31/07/23 | Closed | NA | FSRD-3342 | N/A | Saloni | 2025-02-10 | 846 | >60 | July | 2023 | #VALUE!
Commercial Trading | Foods Commercial Trading | 89350725 | 2023-06-09 | Incorrect Foods SRD ranging file sent to Quantum and Relex | Incorrect Logging process was followed, causing a slight delay into the initial log management and major incident process | Problem identification & Alerting | Matt White, Andrew Goslin, Joey Ocansey, Promoth Kumar, Ian Griffiths | 24/07 - Andrew,Joey and team had workshop on Friday (21/07) with his team and had dicussed on the log raising process - The gap was within the handover between teams - Teams have been reminded to use the support channels and correct comms paths to inform people of issues when they are in flight. | Customer, TEM, Service Lead, PO |  | NA | 24/07/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 846 | >60 | July | 2023 | #VALUE!
Supply Chain | Foods Supply Chain | 89350725 | 2023-06-09 | Incorrect Foods SRD ranging file sent to Quantum and Relex | New ASO backup process | Solution & Recovery | Promoth Kumar | This process was useful during the SRD incident. A clear process on this has been shared for the team with the details on communication to GIST, What scenarios this can be used for? and are there any restrictions etc. The team is aware of the same. Promoth had comformed the same | TEM |  | NA | 23/06/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 846 | >60 | June | 2023 | #VALUE!
Commercial Trading | Foods Commercial Trading | 89350725 | 2023-06-09 | Incorrect Foods SRD ranging file sent to Quantum and Relex | The use of PO Amends as a recovery option during Foods Order impact incidents. | Solution & Recovery | Promoth Kumar | As a result of supplier order impacting incidents, colleagues may need to work with suppliers to perform amendments against any or all impacted PO's. In the recent past, it has taken many hours to get impact data made available from Tech. But the reason for the delay is due to lot of manual efforts that is needed to get the right data. It takes a manual effort to amend the PO's , SAP utliaztion. No automation feasible as these are real money and has a high value this is done carefully and manually also this porcess is the agreed legal contract between suppliers and MnS | TEM |  | NA | 23/06/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 846 | >60 | June | 2023 | #VALUE!
Commercial Trading | Foods Commercial Trading | 89350725 | 2023-06-09 | Incorrect Foods SRD ranging file sent to Quantum and Relex | Review the DLs and the membership included in the MIM comms | Business & IT Communication | Promoth Kumar | In progress | TEM |  | NA | 2023-09-06 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 846 | >60 | June | 2023 | #VALUE!
Commercial Trading | Foods Commercial Trading | 89350725 | 2023-06-09 | Incorrect Foods SRD ranging file sent to Quantum and Relex | Team should ensure all the action are tracked in the MIM instead of having a side conversation outside the call. | Solution & Recovery | Promoth Kumar | This has been addressed and it has been agreed to provide a detailed and timely update of any other actions being performed outside the MIM bridge. | TEM |  | NA | 2023-09-06 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 846 | >60 | June | 2023 | #VALUE!
Commercial Trading | Foods Commercial Trading | 89350725 | 2023-06-09 | Incorrect Foods SRD ranging file sent to Quantum and Relex | Feasibility of automating the PO amendment going forward to minimise the recovery time. | Solution & Recovery | Promoth Kumar | It takes a manual effort to amend the PO's , SAP utliaztion. No automation feasible as these are real money and has a high value this is done carefully and manually also this porcess is the agreed legal contract between suppliers and MnS | TEM |  | NA | 23/06/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 846 | >60 | June | 2023 | #VALUE!
Commercial Trading | Foods Commercial Trading | 89350725 | 2023-06-09 | Incorrect Foods SRD ranging file sent to Quantum and Relex | The recovery took more than 4 hours, how can the recovery of the issue be improved for such issues going forward? | Solution & Recovery | Promoth Kumar | The recovery required the successful completion of the overnight batch with the correct data. Also, there were complexities in data extraction for the impacted products or orders and thereby send it to business for impact mitigation. Actions have been agreed to address this | TEM |  | NA | 2023-09-06 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 846 | >60 | June | 2023 | #VALUE!
Commercial Trading | Foods Commercial Trading | 89350725 | 2023-06-09 | Incorrect Foods SRD ranging file sent to Quantum and Relex | There was an alert triggered at Q to highlight the variance in the allocation. What actions were taken? | Problem identification & Alerting | Promoth Kumar | An alert was triggered at 00:30 on 26/05 which highlighted the variance between the order file from 25/05 and 26/05, however, upon receiving the confirmation from SRD, the variance was ignored. | TEM |  | NA | 2023-09-06 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 846 | >60 | June | 2023 | #VALUE!
GTS | Digital Workplace Services | 89350725 | 2023-06-09 | Incorrect Foods SRD ranging file sent to Quantum and Relex | Accessibility of data on the MIM bridge. | Solution & Recovery | Saran Rajkumar | 10/07: There is no option to allow the attach option in MIM bridges with external participants. However, MIM will perform housekeeping and remove the external participants to allow the option during MI calls. MIM have thoroughly checked the behaviour of all the MIM bridges and have ascertained that the MIM2 bridge is behaving different than the others as it is not facilitating the data sharing as seamless as it is in the other bridges due to the lack of the “attach” option. Ideally, all the bridges should have the same features. Work is in progress with the relevant team to find out the cause and re-introduce the attach file option. | Messaging Team |  | NA | 2023-10-07 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 846 | >60 | July | 2023 | #VALUE!
Customer Channels | Service Experience | 89367334 | 2023-06-09 | Global Apigee issue impacting multiple applications using API services | Apigee to confirm DR process and time to failover and also confirm formal root cause. | Problem avoidance | Aadil Kasmani | 10/07: Sravan has spoken to Sathish and Dinesh and have been advised to raise a risk and close the action with the RISK id - 1856 5/7: Once we identify Apgiee Product Owner then we need to discuss with him on DR exercise 19/06: Root cause - Apigee confirmed that an increase in the heap memory had impacted one of their Cassandra database nodes servicing a subset of Apigee customers in the eu-west-1 region. This resulted in latency across multiple API services, causing the issue. | Service lead |  | NA |  | CLosed | NA | NA | N/A | Saloni | 2025-02-10 | 846 | >60 | January | 1900 | #VALUE!
Customer Channels | Service Experience | 89367334 | 2023-06-09 | Global Apigee issue impacting multiple applications using API services | Improvements in datastore node autohealing | Problem avoidance | Aadil Kasmani | 10/7: Aadil inormed that this action needs to be assigned to Apigee product owner to track the progress with Apigee. Sravan has spoken to Sathish and Dinesh and have been advised to raise a risk and close the action with the RISK id - 1856 19/6: Awaiting updates from Apigee | Service lead |  | NA |  | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 846 | >60 | January | 1900 | #VALUE!
Customer Channels | Service Experience | 89367334 | 2023-06-09 | Global Apigee issue impacting multiple applications using API services | Alerting to be configured for memory heap usage | Problem avoidance | Aadil Kasmani | 10/7: Aadil inormed that this action needs to be assigned to Apigee product owner to track the progress with Apigee. Sravan has spoken to Sathish and Dinesh and have been advised to raise a risk and close the action with the RISK id - 1856 19/6: Awaiting updates from Apigee | Service lead |  | NA |  | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 846 | >60 | January | 1900 | #VALUE!
GTS | Operations | 89367334 | 2023-06-09 | Global Apigee issue impacting multiple applications using API services | Document the potential impact of an Apigee outage in the AIM tool | Impact analysis | MIM | 10/07: This action needs to be driven by product owner. Sravan has spoken to Sathish and Dinesh and have been advised to raise a risk and close the action with the RISK id - 1856 19/6: An email has been sent to TEMs to gather and update the impact analysis in AIM tool | MIM |  | NA |  | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 846 | >60 | January | 1900 | #VALUE!
GTS | Operations | 89367334 | 2023-06-09 | Global Apigee issue impacting multiple applications using API services | Identify the owner of Apigee and review its suitability for the future given the dependency on applications across the board | Problem avoidance | Sathish Sheshiah | 10/07: Sravan has spoken to Sathish and Dinesh and have been advised to raise a risk and close the action with the RISK id - 1856 5/7: We have had some feedback from Idriss but ownership not concluded yet. Anna will follow-up with Idriss again and update us. 19/6: This is pending with Jane and Idriss who is currently heping to idntify the product owner | MIM |  | NA |  | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 846 | >60 | January | 1900 | #VALUE!
GTS | Operations | 89367334 | 2023-06-09 | Global Apigee issue impacting multiple applications using API services | Around 5 different teams received alerts in a timely manner however we need to review how we can translate those alerts into actual understanding of the impact so that we can communicate to the business. | Impact analysis | Sathish Sheshiah | 10/07: Sravan has spoken to Sathish and Dinesh and have been advised to raise a risk and close the action with the RISK id 5/7: We have had some feedback from Idriss but ownership not concluded yet. Anna will follow-up with Idriss again and update us. 19/6: This is pending with Jane and Idriss who is currently heping to idntify the product owner. Once the owner is identified develop a centrally stores impact statement indicating what applications are impacted across the Customer business of Apigee as a whole goes down. | MIM |  | NA | 25/07/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 846 | >60 | July | 2023 | #VALUE!
GTS | Operations | 89367334 | 2023-06-09 | Global Apigee issue impacting multiple applications using API services | Ascertain what the contract with Apigee states with regards to Apigee engineers joining our MIM calls during central outages. | Supplier and support involvement | VMO/MIM | 3/8: This action needs to be driven by product owner. Sravan has spoken to Sathish and Dinesh and have been advised to raise a risk and close the action with the RISK id - 1856 10/7: Followed up with Arun who informed he did not hear anything back from Apgiee team, he will follow-up and update me back 29/6: Followed up with Arun from VMO team who informed that he has not got any update back and will follow-up again 19/6: Arun N from VMO team will check and update the status back by end of Friday | VMO/MIM |  | NA |  | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 846 | >60 | January | 1900 | #VALUE!
Commercial Trading | Foods Commercial Trading | 89362084 | 2023-06-07 | P&P (Pricing & Promotion) changes reflecting incorrect prices for certain products on the tills | Review 'all' pricing procedure documents and ensure the latest and correct user/system interactions are captured and are clear/simple to follow.Explore options to simplify the TPR screens/Procedure so these can be done in one step? | Solution & Recovery | Chris Davey /David Davis | There is an existing process document in place which will be followed until a simplified version has been built 26/06 - follow-up email has been sent, yet to receive an update | Foods pricing Operations |  | NA | 14/07/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 848 | >60 | July | 2023 | #VALUE!
Customer Channels | Service Experience | 89362084 | 2023-06-07 | P&P (Pricing & Promotion) changes reflecting incorrect prices for certain products on the tills | Is there an SAP contingency process/SOP that can be used if an upcoming pricing issue is spotted post in-day cut off? | Solution & Recovery | Chris Davey/ Balaguru Subramanian Vikram Natarajan Ravichandran | The below steps are followed when the price changes reflect incorrectly in the tills and tickets: 1. Inform the trading team. 2. Correct prices are manually updated in POS and ECS to reflect correctly in the tills and tickets. | POS/ECS |  | NA | 2023-07-06 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 848 | >60 | June | 2023 | #VALUE!
Commercial Trading | Foods Commercial Trading | 89362084 | 2023-06-07 | P&P (Pricing & Promotion) changes reflecting incorrect prices for certain products on the tills | Feasibility of automating any user activities in SAP? (Upload templated file and generate batch... simplified UI (User Interface) etc.) | Problem avoidance | Chris to flag business case/Demand to David Davis | Customer is currently exploring to find a simpler process to execute the TPR process but this action item is a long term process as confirmed by David Davis (product owner -Foods). To fulfil this action they need to plan,design and develop. David had ensured that this is in progress but it is an iterative process. Initial plan would be to begin this journey from Aug, and to test what they can achieve by the end of this financial year and go again in 2024-25. Thus we are closing this action from the tracker and this will be further work upon by the team internally via backlog during the Q3- 2023. | Foods pricing Operations/ P&P business |  | NA | 18/07/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 848 | >60 | July | 2023 | #VALUE!
Commercial Trading | Foods Commercial Trading | 89362084 | 2023-06-07 | P&P (Pricing & Promotion) changes reflecting incorrect prices for certain products on the tills | Possibility to notify/warn the users when incorrect process is followed in SAP? or other systems? | Problem avoidance | David Davis | Customer is currently exploring to find a simpler process to execute the TPR process but this action item is a long term process as confirmed by David Davis (product owner -Foods). To fulfil this action they need to plan,design and develop. David had ensured that this is in progress but it is an iterative process. Initial plan would be to begin this journey from Aug, and to test what they can achieve by the end of this financial year and go again in 2024-25. Thus we are closing this action from the tracker and this will be further work upon by the team internally via backlog during the Q3- 2023. | Foods pricing Operations |  | NA | 18/07/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 848 | >60 | July | 2023 | #VALUE!
Commercial Trading | Foods Commercial Trading | 89362084 | 2023-06-07 | P&P (Pricing & Promotion) changes reflecting incorrect prices for certain products on the tills | Devise a plan to perform E2E reconciliation during any price changes made in SAP across each downstream systems before processing. | Problem avoidance | David Davis/ Joey | 24/07 - Joey is chasing the product owner to get the appropriate backlog ID 04/07 - There is already a Backlog item for E2E reconciliation (including each system) with David Davis (Foods Product Owner) to review and prioritise. Also Joey is aware of the same 30/06 [SAP update] - E2E recon needs to be progressed via new requirement/Demand as every system has its own way of processing TPRs. [POS update]: If expected price/store combination is provided to POS from upstream systems, it would take 2 hours for manual reconciliation in POS after food feed processing on the night(around 11PM). If any discrepancy is found, further concurrence would be needed from SAP/DS and business to make any updates needed. 15/05 - A call is being scheduled on 16/06 to devise a plan to reconcile the price changes across each system before processing. 16/06: Any type of recon between SAP, ES, FMD, DS, RET and POS will involve a significant volume of data comparison and efforts, which is time consuming and not sustainable as a manual activity; therefore the Engineering teams, across each of the apps and services within the P&P flow, will explore viable/feasible options (if any) that could be utilised in order to perform reconciliation across the E2E pricing flow. 15/08 - Joey is still chasing up with the Product owner on the Backlog ID for the E2E reconcilaiton. 30/08 - The action is included as part of the Q3 which is long pending actoin. Since it has been added as an initiaive on Q3. This is surely beong worked upon. Thus closing this off the tracker. | POS/ECS/SAP/DS |  | NA | 30/08/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 848 | >60 | August | 2023 | #VALUE!
Commercial Trading | Foods Commercial Trading | 89362084 | 2023-06-07 | P&P (Pricing & Promotion) changes reflecting incorrect prices for certain products on the tills | Feasibility to configure an E2E system reconciliation process for proactive identification of such issues before store opening hours. | Problem identification & Alerting | David Davis/ Mark Charlwood | 07/07 - Business (P&P) team has stated that having a E2E recon is very complex and he had confirmed that this is not feasible practically 04/07: Rehan along with the team had a call with Mark Charlwood and have requested for an update on the actions. Mark has agreed to respond via email by midday 05/07. This is currently being discussed across all the systems involved – SAP, FMD, POS and ECS 26/06 - follow-up email has been sent, yet to receive an update | Foods pricing Operations |  | NA | 2023-07-07 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 848 | >60 | July | 2023 | #VALUE!
Commercial Trading | Foods Commercial Trading | 89362084 | 2023-06-07 | P&P (Pricing & Promotion) changes reflecting incorrect prices for certain products on the tills | P&P colleagues to proactively communicate to SAP the UPC details in the upcoming price changes. We have agreed to introduce hypercare in the upcoming price changes activity across the relevant teams to prevent any issues. | Problem avoidance | Jon & Remko | 24/07 - Jonathan to confirm and acknowledge once his session with his team is done 18/07 - Jonathan claimed that most of this team was on off last week thus he was not able to conduct sessions with the team. He is planning to schedule a session this week. 11/07 -Had a word with Jonathan early this week and he has provided an ETA of 17/07 to group-up with the team and to understand the Gaps/requirements. He has agreed to come back with an update by end of week (14/07) 31/07 - Jon has agreed follow-up on these actions via the problem record -#64860 as these actions will consume more time. | Foods Business & SAP |  | NA | 31/07/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 848 | >60 | July | 2023 | #VALUE!
Commercial Trading | Foods Commercial Trading | 89362084 | 2023-06-07 | P&P (Pricing & Promotion) changes reflecting incorrect prices for certain products on the tills | Create testing scenarios to ensure the process with 80 UPCs to confirm | Root cause | Jonathan Philby | 24/07 - several logs has been raised with few others team to test the scenario with small chunks of UPC's, logs are still under "work in progress" 18/07 - Jonathan to confirm on the testing scenario by end of week 11/07 - Jonathan has confirmed that this will be sorted by Next Monday (17/07) It is presumed that there can be an underlying issue with the process where bulk UPCs are amended. Hence, we will test the process with small chunks of UPCs to confirm. 31/07 - Jon has agreed follow-up on these actions via the problem record -#64860 as these actions will consume more time. | Foods pricing Operations |  | NA | 31/07/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 848 | >60 | July | 2023 | #VALUE!
Group Support | Finance | 89362084 | 2023-06-07 | P&P (Pricing & Promotion) changes reflecting incorrect prices for certain products on the tills | Conduct a process refreshing session between SAP and P&P colleagues. | Solution & Recovery | Jonathan Philby /Remko Smit | 24/07 - Jonathan to confirm and acknowledge once his session with his team is done 18/07 - Jonathan claimed that most of this team was on off last week thus he was not able to conduct sessions with the team. He is planning to schedule a session this week. 11/07 -Had a word with Jonathan early this week and he has provided an ETA of 17/07 to group-up with the team and to understand the Gaps/requirements. He has agreed to come back with an update by end of week (14/07) 31/07 - Jon and team has agreed follow-up on these actions via the problem record -#64860 as these actions will consume more time. | SAP Retail |  | NA | 31/07/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 848 | >60 | July | 2023 | #VALUE!
Group Support | Finance | 89362084 | 2023-06-07 | P&P (Pricing & Promotion) changes reflecting incorrect prices for certain products on the tills | Why did some of the 887 Irish promo ends become effective early, on Saturday 03/06 instead of Sunday 04/06 as per design? | Solution & Recovery | Narayana Moorthy Kanagaraj | Tech to explore options to introduce a “prompt” during deactivation/reactivation of a promotion highlighting any UPCs where actions have already been taken. 30/06 : [Update from SAP devops] - As per SAP standard, deactivation/reactivation process is happening. It will allow the second step of activation as user needs to enter the activation date once again. However, system will not allow to deactivate once again as the line items were already deactivated. Thus this option is not feasible for the deletion and we do have a prompt for activation. | SAP Retail |  | NA | 30/06/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 848 | >60 | June | 2023 | #VALUE!
Group Support | Finance | 89362084 | 2023-06-07 | P&P (Pricing & Promotion) changes reflecting incorrect prices for certain products on the tills | It was highlighted that during the process of making prices, there are multiple unnecessary prompts pop up on the screen. Is there a way we can optimize it? | Solution & Recovery | Narayana Moorthy Kanagaraj | 30/06- Multiple prompts were introduced based on Business requirement around 4 or 5 years before. If any specific prompt is not needed now, it can be discussed with Product manager (David Davis) and it can be taken as a new requirement/demand. Teams to co-ordinate internall have have them removed | SAP Retail |  | NA | 30/06/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 848 | >60 | June | 2023 | #VALUE!
Group Support | Finance | 89362084 | 2023-06-07 | P&P (Pricing & Promotion) changes reflecting incorrect prices for certain products on the tills | Are there any known scenarios in SAP standard product that mask/hide user interactions or do not audit/register updates. | Root cause | Narayana Moorthy Kanagaraj | SAP do have scenario's like whenever user action has been taken in a promotion, changes will be stored in change pointer table based on the field that is enabled to capture changes. The same will be discussed with the right team to make sure they are aligned | SAP Retail |  | NA | 30/06/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 848 | >60 | June | 2023 | #VALUE!
Customer Channels | Service Experience | 89359796 | 2023-06-06 | Incorrect returns policy lead-time for full price products returns | Ops hub is not confident using the existing returns dashboard to identify impact. Data issues and concerns have been listed to power BI team. This will have to be followed up to closure. | Impact analysis | Aarthi | 09/06: Working with BEAM team to enhance the WISMR dashboard. Fist set of fixes have been deployed on 8th June. Working on other data issues | Order Management and Returns / Power BI team |  | NA | 2023-09-06 | Closed | NA | FULRE-1579 |  | Saloni | 2025-02-10 | 849 | >60 | June | 2023 | #VALUE!
Customer Channels | Service Experience | 89359796 | 2023-06-06 | Incorrect returns policy lead-time for full price products returns | How did this issue pass PCT though we identified issue in regression? Returns team to include Mixed basket scenario in PCT | Problem avoidance | Aarthi | 09/06:Test case updated and included in ROI ILR PCT | Order Management and Returns |  | NA | 2023-09-06 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 849 | >60 | June | 2023 | #VALUE!
Customer Channels | Service Experience | 89359796 | 2023-06-06 | Incorrect returns policy lead-time for full price products returns | Permanent solution from WCS team to send sale flag as expected. A review for this fix is required after an extension testing with OMS, WCS and Returns. | Permanent Fix | Aarthi | 21/06: - Planned for Q2-23 and will be tracked under product backlog 09/06:B&C product teams picked up the Dev. Will be planned in the next WCS release | WCS Basket & Checkout team |  | NA | 21/06/23 | Closed | NA | FULRE-1669 |  | Saloni | 2025-02-10 | 849 | >60 | June | 2023 | #VALUE!
Customer Channels | Service Experience | 89359796 | 2023-06-06 | Incorrect returns policy lead-time for full price products returns | The Issue has been identified in lower environment. The testing was done only from OMS flow. E2E testing should be done in lower environment without manual interpretation at least for sanity. | Problem avoidance | Aarthi | 09/06: Teams have been advised to call out upstream /down stream impact mandatorily . | Order Management and Returns / E2E testing team |  | NA | 2023-09-06 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 849 | >60 | June | 2023 | #VALUE!
Customer Channels | Service Experience | 89359796 | 2023-06-06 | Incorrect returns policy lead-time for full price products returns | Create a Sale dashboard having the sale, non-sale, mixed (sale + Non sale) order numbers at WCS end. | Impact analysis | Arthi Suriyanarayanan | 21/06: - Planned for Q2-23 and will be tracked under product backlog 09/06: Yet to be picked by the product team | WCS Basket & Checkout team |  | NA | 21/06/23 | Closed | NA | FULRE-1669 |  | Saloni | 2025-02-10 | 849 | >60 | June | 2023 | #VALUE!
Customer Channels | Service Experience | 89359796 | 2023-06-06 | Incorrect returns policy lead-time for full price products returns | Test data quality in SIT2 environment should be reviewed. | Problem avoidance | Arthi Suriyanarayanan | 21/06: - Planned for Q2-23 and will be tracked under product backlog 09/06: Yet to be picked by the product team | Aravind / Rams/Mohan |  | NA | 21/06/23 | Closed | NA | FULRE-1669 |  | Saloni | 2025-02-10 | 849 | >60 | June | 2023 | #VALUE!
Group Platforms | HR | 89364597 | 2023-06-05 | Time and Attendance application was inaccessible via desktop | Root cause of the issue | Root cause | Ganesh Regoubady (BY TAM) | The database query responsible for user authentication had picked up an inefficient execution plan due to a huge volume of data in the database, causing the issue. The Blue Yonder purge job responsible for the database housekeeping did not run from 31/03 due to a conflict with the schedule restart of the APE engine resulting in the huge data volume. | T&A Accenture |  | NA | 2023-05-06 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 850 | >60 | June | 2023 | #VALUE!
Group Platforms | HR | 89364597 | 2023-06-05 | Time and Attendance application was inaccessible via desktop | Possibility to increase the frequency of the flush job execution at BY. | Solution & Recovery | Sanoop Madathil | The flush job is scheduled to run every 4 hours and there is no scope of manual amendments | T&A Accenture |  | NA | 2023-05-06 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 850 | >60 | June | 2023 | #VALUE!
Group Platforms | HR | 89364597 | 2023-06-05 | Time and Attendance application was inaccessible via desktop | Feasibility to improve the post check implementation and introduce additional test cases before deploying any change into production. | Problem avoidance | Sanoop Madathil | They will record the specifics of the purge during the smoke test and will use then, in case there are any changes to the system.The purge details has been incorporated to their smoketest automation. | T&A Accenture |  | NA | 2023-05-06 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 850 | >60 | June | 2023 | #VALUE!
Group Platforms | HR | 89364597 | 2023-06-05 | Time and Attendance application was inaccessible via desktop | The purge job had not executed from 31st March 2023, why was this not identified at BY? | Problem identification & Alerting | Sanoop Madathil | The APE schedule restart runs at 05:00 initially, it was preponed to 00:00 by a change on 31/03 which caused a conflict with the purge job (running default at 00:00). This was not identified due to inefficient testing and post implementation checks. In addition, there was no alerting for the purge job in the BY environment. | T&A Accenture |  | NA | 2023-05-06 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 850 | >60 | June | 2023 | #VALUE!
Group Platforms | HR | 89364597 | 2023-06-05 | Time and Attendance application was inaccessible via desktop | Implement workaround to mitigate impact during future occurrences. | Solution & Recovery | Sanoop Madathil | A manual script is in place to purge the sessions in the database. | T&A Accenture |  | NA | 2023-05-06 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 850 | >60 | June | 2023 | #VALUE!
Group Platforms | HR | 89364597 | 2023-06-05 | Time and Attendance application was inaccessible via desktop | Configure alerting to proactively identify any authentication issues and provide proactive notification | Problem identification & Alerting | Sanoop Madathil | Selenium script has been deployed to the production controller. | T&A Accenture |  | NA | 23/06/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 850 | >60 | June | 2023 | #VALUE!
Group Platforms | HR | 89364597 | 2023-06-05 | Time and Attendance application was inaccessible via desktop | Explore ways to schedule the purge job after the systemic restart of the APE engine | Problem avoidance | Sanoop Madathil | The Job scheduel has been moved to 12:15, adjustments had already been made to the system, and the job flow is now as expected | T&A Accenture |  | NA | 2023-05-06 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 850 | >60 | June | 2023 | #VALUE!
Group Support | HR | 89364597 | 2023-06-05 | Time and Attendance application was inaccessible via desktop | Feasibility of configuring an alert to proactively notify when the purge job had not started on time and proactively notify Customer during such scenarios. | Problem identification & Alerting | Sanoop Madathil | 18/07 - This is still under development with the BY team and the team had confirmed this to be a long term process. Thus closing this action with a BY backlog. PRB0045580 The support team is looking into several possibilities to include as part of the job alerting system because this is not a straight forward task. 26/06 - follow-up email has been sent to T&A team for update | T&A Accenture |  | NA | 18/07/23 | Closed | NA | PRB0045580 | N/A | Saloni | 2025-02-10 | 850 | >60 | July | 2023 | #VALUE!
Customer Channels | Selling Experience | 89342875 | 2023-06-02 | MTO sofa PDPs leading to error message. | Alerting to be reviewed by FESK PDP. In particular, to see whether an alert can be triggered if there is inactivity on the service | Problem identification & Alerting | Suriyadevi Varatharaju | 28/06: The alerting has configured. 09/06: Planned to be taken in the next sprint starting 14-Jun | Ecommerce Team |  | NA | 28/06/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 853 | >60 | June | 2023 | #VALUE!
Customer Channels | Service Experience | 89360258 | 2023-06-02 | Issues with gift card transactions in the tills | Fetch the void gift card transactions at stores. | Impact analysis | Balaguru Subramanian | 02/06: This is required to ascertain the impact during the issue. | POS |  | NA | 2023-02-06 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 853 | >60 | June | 2023 | #VALUE!
Customer Channels | Service Experience | 89360258 | 2023-06-02 | Issues with gift card transactions in the tills | Introduce alerts at tills highlight the gift card transaction failures via the existing new relic mechanism. | Problem identification & Alerting | Balaguru Subramanian | 07/06:New relic alert in place for card related issue in tills. 02/06: It is currently being built. | POS |  | NA | 2023-07-06 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 853 | >60 | June | 2023 | #VALUE!
Customer Channels | Service Experience | 89360258 | 2023-06-02 | Issues with gift card transactions in the tills | Feasibility of failing over the DR traffic to PROD when there is an issue in DR to remediate the impact | Solution & Recovery | Kamal/Sreejith | 09/06: The CICD pipeline was moved to Concourse to Azure in 2022 the 'Enable F5' a load balancer paremeter was set incorrectly during the migrations. Since we used the Azure pipeline only in 2023 for implementing the change in SVS after long time. Hence the DR should work fine as the config is corrected. 02/06: The feasibility is being explored | SVS |  | NA | 27/06/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 853 | >60 | June | 2023 | #VALUE!
Customer Channels | Service Experience | 89360258 | 2023-06-02 | Issues with gift card transactions in the tills | Explore ways to help eradicate the manual element during any change implementation. Can we introduce an automated way to perform configuration checks across PROD and DR. | Problem avoidance | Sreejith Purushothaman | 03/07: All the config file are in made in synch as an one time activity in 2023, only gap is that the synch should have been done in 2022 after migration. There is no automatic solution validate the config between PROD and DR. 02/06: This needs rigorous discussions and will be tracked under a backlog | SVS |  | NA | 27/06/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 853 | >60 | June | 2023 | #VALUE!
Customer Channels | Service Experience | 89360258 | 2023-06-02 | Issues with gift card transactions in the tills | Version control of any new tool that is being introduced to deploy any changes into production | Problem avoidance | Sreejith Purushothaman | 23/06: The version control is in place, now we will ensure that the correct version file will be used has it has been corrected now. 09/06: targetted for next Sprint | SVS |  | NA | 27/06/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 853 | >60 | June | 2023 | #VALUE!
Customer Channels | Service Experience | 89360258 | 2023-06-02 | Issues with gift card transactions in the tills | Feasibility to improve the testing environment for effective identification of the issue during the testing phase of the change. | Problem avoidance | Sreejith Purushothaman | 02/06: It has been confirmed that the existing incorrect configuration was not identified during the testing due to a human error. It has been agreed to involve a check to compare the configurations across prod and DR before deploying in the production environment | SVS |  | NA | 2023-02-06 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 853 | >60 | June | 2023 | #VALUE!
Customer Channels | Service Experience | 89360258 | 2023-06-02 | Issues with gift card transactions in the tills | Improve the scope of post implementation checks | Problem avoidance | Sreejith Purushothaman | 02/06: Refer the below actions (Introduce alerts at tills highlight the gift card transaction failures via the existing new relic mechanism). It has been also agreed to involve network and POS team to validate the functionalities after the deployment. | SVS |  | NA | 2023-02-06 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 853 | >60 | June | 2023 | #VALUE!
Customer Channels | Service Experience | 89360258 | 2023-06-02 | Issues with gift card transactions in the tills | Introduce alerting in the SVS layer when there is no POS or dot com traffic. | Problem identification & Alerting | Sreejith Purushothaman | 27/06: Alerting has been configured. 20/06: The consumer specific metrix has been added to exisiting dashboard in both PROD and DR 09/06: targetted for next Sprint 02/06:A dashboard has been created across the prod and DR region to specify the POS and dot com transactions separately. This will help identify any issues in the traffic flow after future deployments. The feasibility of configuring an alert is in progress. | SVS |  | NA | 27/06/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 853 | >60 | June | 2023 | #VALUE!
Customer Channels | Service Experience | 89360258 | 2023-06-02 | Issues with gift card transactions in the tills | Root cause of the issue | Root cause | Sreejith Purushothaman | 02/06: It has been confirmed that the “Enable F5” configuration was inadvertently set up as “false” in the DR environment during the built of SVS (gift card) change deployment tool last year. On 01/06, when the network timeout change was deployed in the SVS DR layer, this erroneous configuration was not identified due to a human error which impacted the inflow of traffic between the POS and the gift card services. | SVS |  | NA | 2023-02-06 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 853 | >60 | June | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89358542 | 2023-06-02 | Colleagues unable to access the shared files after the power maintenance activity at Waterside. | Work with MnS on the migration plan to get off the old devices | Permanent Fix | Elizabeth Golder | 02/06: A decision on the reboot of the device/controller went for a toss as the devices were out of support/End of life. Thus, these devices should be replaced with new ones.. 09/06: This is being looked at under the ETP SP Exit programme | Storage |  | NA | 2023-09-06 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 853 | >60 | June | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89358542 | 2023-06-02 | Colleagues unable to access the shared files after the power maintenance activity at Waterside. | Check with the MHM if they are informed while organizing and managing such power activities | Problem avoidance | Elizabeth/Kamal | 02/06:NOC and MHM are made aware of the process by the Service lead. Going forward it has been agreed that MHM tech should be available at the site during such activities. | MHM |  | NA | 2023-02-06 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 853 | >60 | June | 2023 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89358542 | 2023-06-02 | Colleagues unable to access the shared files after the power maintenance activity at Waterside. | Root cause of the issue | Root cause | Kamal | 02/06: The planned power maintenance at Waterside, has caused the communication issue between the storage device and file servers. There was a DR in place within the controllers of the storage device. Unfortunately, the available DR controller was unhealthy, which led to a total outage. Actions have been agreed to inform the concerned teams whilst performing such activity. | Network |  | NA | 2023-02-06 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 853 | >60 | June | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89358542 | 2023-06-02 | Colleagues unable to access the shared files after the power maintenance activity at Waterside. | Reviewing the power design for all the devices at the comms rooms at Waterside | Problem avoidance | Kamal/Jafar/ Sailesh | 24/07 - No reponse from Sailesh, and the same has been escalated further 02/06: Review on the power design for the network devices at the site is being performed currently. Teams to check on the feasibility to accommodate for these storage devices aswell in the same slot 20/06 - Kamal was informed on the same. Sailesh and Kamal to co-ordinate and to get the review doe along with the network activity which is planned for july 1st. 30/09 - UPS Testing was completed in all the floors of WS everything seems to be configured as expected. we couldt check on every devices in-depth as it is a tedious one. But as per the overview, all the devices at the comms room is configured as expected. New SOP's are being designd by the teams to effeciently locate and to mitigate the issues. SOP updatoin is beong tracked via another actoin. | Storage Support |  | NA | 30/08/23 | closed | NA | NA | N/A | Saloni | 2025-02-10 | 853 | >60 | August | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89358542 | 2023-06-02 | Colleagues unable to access the shared files after the power maintenance activity at Waterside. | Improve the process of securing an on-site engineer to check the device physically | Solution & Recovery | Promode | 02/06: WPT engineers (9*5) should have access to the room to attend and assist during any issues supported by the remote team (limited to basic checks) until the appropriate resource can travel the site – MHM based in SP 24*7. 10/06 - WPT engineers are provided access to the site. | MHM |  | NA | 2023-09-06 | closed | NA | NA | N/A | Saloni | 2025-02-10 | 853 | >60 | June | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89358542 | 2023-06-02 | Colleagues unable to access the shared files after the power maintenance activity at Waterside. | Perform the DR test frequently as part of service continuity. | Problem avoidance | Sailesh Kaluva | 24/07 - No reponse from Sailesh, and the same has been escalated further 02/06: It was confirmed that the DR activity was lastly performed 3 years ago, and teams did face few challenges during data validation in DR. It has been agreed to perform the DR test activity frequently and to have the process document updated to immediately mitigate the issue 20/06 - Sailesh will work with SM team to have the schedule for the DR test. but note, these servers are EOL/EOS need to be replaced or decommissed. 31/07 - Reviewed the Storage Utilization of various filesystems at SW HNAS and once we have space reclaimed will implement the migration from File to Object Replication. 07/08 The Migration plan from file to Object replications is in progress and it is planned to be implmented by Aug'23 . 11/09 - I have escalated these actions to Jeeva/Jafar for an update on this action as I did not receive any update from Sailesh 19/09 - The prerequisite tasks to enable Object replication for WSHNAS  SWHNAS is completed and tested. A date is yet to be finalized for the prod change. 03/10 : DR Test has been done with the TEST Filesystem and teams have documented the Steps. Now the WatersideSwindon replication runs on Object Replication similar to SPSW. | Storage Support |  | NA | 2023-03-10 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 853 | >60 | October | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89358542 | 2023-06-02 | Colleagues unable to access the shared files after the power maintenance activity at Waterside. | Review the alerting for the controllers and HNAS devices | Problem identification & Alerting | Sailesh Kaluva | 02/06: Alerting was in place however, was not actioned in a timely manner. We have agreed actions to address this. | Storage Support |  | NA | 2023-02-06 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 853 | >60 | June | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89358542 | 2023-06-02 | Colleagues unable to access the shared files after the power maintenance activity at Waterside. | Did the existing Disc error contribute to the incident? | Problem identification & Alerting | Sailesh Kaluva | 02/06:The disc failures are usual and frequent, this is addressed during the health checks. Team has confirmed that the existing disc error did not contribute to the issue | Storage Support |  | NA | 2023-02-06 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 853 | >60 | June | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89358542 | 2023-06-02 | Colleagues unable to access the shared files after the power maintenance activity at Waterside. | Review and improvise the documentation on the hardware reboot/data replication and validation process | Solution & Recovery | Sailesh Kaluva | 24/07 - No reponse from Sailesh, and the same has been escalated further 02/06: There were some initial challenges to proceed with the hardware reboot as it was uncertain if the controller would come up post the reboot. Also, they were concerned on the data loss. Actions have been agreed to have the document updated with the right process so that the reboot can be performed without any delay. 20/06 - The replication process document is compeletly being reviewed and re-worked. This would take a month to complete. 31/07 - Once the migration is complete will update the SOP Accordingly for replication. Storage reboot is not a activity to be documented as its will be done only when decommissioned / Scraped. 07/08 - The Migration plan from file to Object replications is in progress and it is planned to be implmented by Aug'23 11/09 - I have escalated these actions to Jeeva/Jafar for an update on this action as I did not receive any update from Sailesh 19/09 - The document has been updated on the data replication. | Storage Support |  | NA | 19/09/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 853 | >60 | September | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89358542 | 2023-06-02 | Colleagues unable to access the shared files after the power maintenance activity at Waterside. | Review the failover process (DR) and update the SOP accordingly | Problem avoidance | Sailesh Kaluva/Priya | 24/07 - No reponse from Sailesh, and the same has been escalated further 20/06: Few challenges were observed during the pre-checks for the DR process which required additional guidance. The SOP will be updated accordingly 31/07 - Reviewed the DR strategy for HNAS WS --> SW and devised to move the replication from File Replication to Object Replication. Once the migration is complete will update the SOP Accordingly. 07/08 - The Migration plan from file to Object replications is in progress and it is planned to be implmented by Aug'23 11/09 - I have escalated these actions to Jeeva/Jafar for an update on this action as I did not receive any update from Sailesh 19/09 - High availability has been tested and Storage Reboot is a Vendor supported activity which is usually done during a decommission and it will not be part of the SOP | Storage Support |  | NA | 19/09/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 853 | >60 | September | 2023 | #VALUE!
Customer Channels | Service Experience | 89351882 | 2023-06-02 | Android App Not Loading Account Details | To ensure a validation checklist is in place to ensure once Akamai changes are deployed there is no impact | Problem avoidance | Aadil Kasmani | 04/07: The Akamai team will not able to have a checklist, Aadil has advised that most the team which takes the change to Akamai will have visibilty on the use of compenent that is being changed, Since Akamai team is not able to have a checklist this will now be part of the .COM cab to validate the impact of the component as a validation check list . Hence closing this as there will be process in place 09/06:Picked up by the Mobile App Team in the current sprint | Akamai |  | NA | 2023-04-07 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 853 | >60 | July | 2023 | #VALUE!
Customer Channels | Service Experience | 89351882 | 2023-06-02 | Android App Not Loading Account Details | Android App to take a long term action to follow the approach used by iOS for redirects. | Permanent Fix | Florian Lamotte | 09/06:Picked up by the Mobile App Team in the current sprint. It a Long term action and will be tracked through a back log - AMNS-10544 | Andriod App |  | NA | 2023-09-06 | Closed | NA | AMNS-10544 |  | Saloni | 2025-02-10 | 853 | >60 | June | 2023 | #VALUE!
Customer Channels | Service Experience | 89351882 | 2023-06-02 | Android App Not Loading Account Details | To Check if any alerting is present on technical systems | Problem identification & Alerting | Florian Lamotte | 04/07:Initial alerting is in place, however addiaional alerting in terms of web view is being explored. Florian has confirmed that this will be taking and will be picked soon. Hence it will be tracked under a back log id and we initial alerting in place 09/06:Picked up by the Mobile App Team in the current sprint 02/06:Account Product team to check from their perspective | Andriod App |  | NA | 2023-04-07 | Closed | NA | AMNS-10341 |  | Saloni | 2025-02-10 | 853 | >60 | July | 2023 | #VALUE!
Customer Channels | Service Experience | 89351281 | 2023-06-01 | Orders Cancelled After Stuck in Awaiting Reservation Status | Why was the AS showing these items in stock and why was the volume high? (These are in order of frequency and most impacting during our offline period ) 1.During offline scenario WCS should be triggering reservations back to the AS. This was not happening due to a missing API permission; this has been added on 31/05 and these are now being triggered 2.AS is still receiving IAA’s whilst these are on hold during OMS releases (during this period we had 15K) Can we use WXS during outages? 3.Open issues in the AS causing stock differences between AS & OMS, this is minimal numbers and will go away once we switch on ATP/NDD to the AS | Root cause | 1.Dhanaseelan Mahalingam 2.Dhanaseelan Mahalingam 3.N/A | 1.Completed on 31/05/23 2.Need a follow up call 3.Nothing further required, waiting for AS service to take over ATP & NDD calls | .com |  | NA | 31/05/23 | Closed | NA |  |  | Saloni | 2025-02-10 | 854 | >60 | May | 2023 | #VALUE!
Customer Channels | Service Experience | 89351281 | 2023-06-01 | Orders Cancelled After Stuck in Awaiting Reservation Status | Alerting – Inactivity alert added on WCS for reservation during offline | Problem identification & Alerting | Dhanaseelan Mahalingam | Completed | .com |  | NA | 31/05/23 | Closed | NA |  |  | Saloni | 2025-02-10 | 854 | >60 | May | 2023 | #VALUE!
Customer Channels | Service Experience | 89351281 | 2023-06-01 | Orders Cancelled After Stuck in Awaiting Reservation Status | Further time to be spent on impact assessment and agreeing the severity for major incidents with stakeholders | Business & IT Communication | Emma Rotheram | 20/05: Action have completed. 09/08:Existing Service Matrix to be revisited and agreed with all stake holders | .com |  | NA | 20/06/23 | closed | NA |  |  | Saloni | 2025-02-10 | 854 | >60 | June | 2023 | #VALUE!
Customer Channels | Service Experience | 89351281 | 2023-06-01 | Orders Cancelled After Stuck in Awaiting Reservation Status | Testing - Include offline & different stock picture scenarios in regression testing pack for the release | Problem avoidance | Mohanakrishnan Ganesan | 09/06: Added in regression suite. Will be included in the regression suite for next Sterling Release planned on 29-Jun | TPM |  | NA | 2023-09-06 | Closed | NA | E2ET-27086 |  | Saloni | 2025-02-10 | 854 | >60 | June | 2023 | #VALUE!
Customer Channels | Service Experience | 89351281 | 2023-06-01 | Orders Cancelled After Stuck in Awaiting Reservation Status | CMWA bug which has been introduced and causing orders to get stuck in awaiting reservation, targeting to apply a fix 5th June | Solution & Recovery | Rajeev Ekambaram | 09/06: Permanent fix planned on 08-Jun | Sterling |  | NA | 20/06/23 | Closed | NA | DNCTA-7889 |  | Saloni | 2025-02-10 | 854 | >60 | June | 2023 | #VALUE!
Customer Channels | Service Experience | 89351281 | 2023-06-01 | Orders Cancelled After Stuck in Awaiting Reservation Status | Alerting – Alert added to catch orders in awaiting reservation status, not at shipnode level | Problem identification & Alerting | Vipin Kumar | Completed | sterling |  | NA | 27/05/23 | Closed | NA |  |  | Saloni | 2025-02-10 | 854 | >60 | May | 2023 | #VALUE!
Customer Channels | Service Experience | 89359175 | 2023-05-31 | Returns Label Generation API service is down | The Escalation policy awareness session should be conducted at product team level. Mock drill to be conducted to create awareness. | Supplier and support involvement | Aravind | 14/07: The mock drill will be planned with in the team. Awaiting the back log details to track the same from product end. 10/07: Escalation matrix has been brefied to the team. Awaiting updates on the plan for Mock drill. 09/06: Mock drill yet to scheduled | Service experience |  | NA | 14/07/23 | Closed | NA | FULRE-1669 |  | Saloni | 2025-02-10 | 855 | >60 | July | 2023 | #VALUE!
Customer Channels | Service Experience | 89359175 | 2023-05-31 | Returns Label Generation API service is down | Get confirmation from dependent API services who all consuming the secret key | Problem avoidance | Aravind/Rajeev | 09/06. CMWA, WISMR, Dropship, Mediation Layer, OMS API - confirmed that they updated the pipeline. | Order Management Returns |  | NA | 2023-09-06 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 855 | >60 | June | 2023 | #VALUE!
Customer Channels | Service Experience | 89359175 | 2023-05-31 | Returns Label Generation API service is down | Alert / notification of Secret key expiry | Problem identification & Alerting | Cloud Technology Compliance Team | 04/08: CTL team have checked with Microsoft and there is no expiry reminder automatically triggered. Nothing more can done on this ticket, Hence we are closing it. 21/07: Configuration of the alert is yet to be planned, awaiting an ETA 14/07: This actions is still in progress, awiaitng additional details on the progress made. 09/06:Followed up with Cloud technlogy compliance team who is working with microsoft to resolve this This is a known issue that the alert/notification for secret key is not working. Already reported and working with Microsoft team. | Cloud Technology Compliance Team |  | NA | 2023-04-08 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 855 | >60 | August | 2023 | #VALUE!
Customer Channels | Service Experience | 89359175 | 2023-05-31 | Returns Label Generation API service is down | Implement DR Capability for Returns Label generation API service | Problem avoidance | Prem Gopal | 21/06: Planned for Q2-23 and will be tracked under the product back log 09/06: Discussion in progress | Order Management Returns |  | NA | 21/06/23 | Closed | NA | FULRE-1608/FULRE-1669 |  | Saloni | 2025-02-10 | 855 | >60 | June | 2023 | #VALUE!
Customer Channels | Service Experience | 89359175 | 2023-05-31 | Returns Label Generation API service is down | Improve application availability during deployment: Rolling restart deployment to be implemented as temporary solution. Implement Blue green deployment as permanent solution. | Problem avoidance | Prem Gopal | 09/06: Rolling restart capability already available . Developers are now educated on usage of rolling restart | Order Management Returns |  | NA | 2023-09-06 | Closed | NA | FULRE-1609 |  | Saloni | 2025-02-10 | 855 | >60 | June | 2023 | #VALUE!
Customer Channels | Service Experience | 89359175 | 2023-05-31 | Returns Label Generation API service is down | No activity alert should be configured for returns application | Problem identification & Alerting | Prem Gopal | 03/07- Alerts have been configured 09/06:Alerts review and updation in progress | Order Management Returns |  | NA | 2023-03-07 | Closed | NA | FULRE-1468 |  | Saloni | 2025-02-10 | 855 | >60 | July | 2023 | #VALUE!
Customer Channels | Service Experience | 89359175 | 2023-05-31 | Returns Label Generation API service is down | Review process for use of Azure service principle. Steps to be followed during Secret key expiry Discuss to identify owner for Shared Infrastructure maintenance | Problem avoidance | Sam / Ramsankar | 09/06:Internal session held and options documented. Session with Sam next week | Order Management Returns |  | NA | 2023-09-06 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 855 | >60 | June | 2023 | #VALUE!
Customer Channels | Service Experience | 89359175 | 2023-05-31 | Returns Label Generation API service is down | Single cluster is shared by multiple applications. There is no defined way to identify this and dependency between applications are high. Review of the architectural design. Process to identify consuming applications should be identified. | Problem identification & Alerting | Suresh, Loganathan | 21/06: Planned for Q2-23 and will be tracked under the product back log 09/06: Technical discussions are underway. Options are being documented and will be presented to Sam C and take it forward | Order Management Returns |  | NA | 21/06/23 | Closed | NA | FULRE-1669 |  | Saloni | 2025-02-10 | 855 | >60 | June | 2023 | #VALUE!
Customer Channels | Service Experience | 89350726 | 2023-05-30 | Messages sent from sterling to Collection DB failed in Sterling | Post deployment validations will be done by respective Engineers who developed the change. This should include even dormant changes. | Problem avoidance | OMS Dev | 09/06: OMS TPMs confirmed this will be implemented from the next sterling release | OMS Dev |  | NA | 2023-09-06 | Closed | NA | DNCTA-7881 |  | Saloni | 2025-02-10 | 856 | >60 | June | 2023 | #VALUE!
Customer Channels | Service Experience | 89350726 | 2023-05-30 | Messages sent from sterling to Collection DB failed in Sterling | Review approach to update the config fixes during regression after Gold+ automatically | Problem avoidance | OMS Dev | 09/06: Reviewing the feasible appraoch. To be implemented for next Sterling Release | OMS Dev |  | NA | 2023-09-06 | Closed | NA | DNCTA-7882 |  | Saloni | 2025-02-10 | 856 | >60 | June | 2023 | #VALUE!
Customer Channels | Service Experience | 89350726 | 2023-05-30 | Messages sent from sterling to Collection DB failed in Sterling | Individual bugs to be raised for each issue/fix during regression | Solution & Recovery | OMS Dev / E2E Testing | 09/06: OMS TPMs confirmed this will be implemented from the next sterling release | OMS Dev / E2E Testing |  | NA | 2023-09-06 | Closed | NA | DNCTA-7883 |  | Saloni | 2025-02-10 | 856 | >60 | June | 2023 | #VALUE!
Customer Channels | Service Experience | 89350726 | 2023-05-30 | Messages sent from sterling to Collection DB failed in Sterling | Review all flows for the need for Queue inactivity alert and add inactivity alerts for those queues | Problem avoidance | Sterling support | 30/08 : The inactivitys have been queued 29/08: The review is still in progress, considering the the number of queues, the review is taking time. 03/08: Critical queues have been indentified and team is progress of configuring the alerts. ETA- 15/08 24/07: Rajeev advised that he will provide an update by the end of this week 17/07 - Followed up with Rajeev awaiitng further updates 03/07: Team extracted the list queue and is in process of reviewing it. This needs manual effort to validate each line items and hence its taking time. Once the queues are reviewed the respecitive alerts will be configured 09/06: Analysis in progress to identify all the critical MQs | Sterling support |  | NA | 30/08/23 | Closed | NA | DNCTA-7885 |  | Saloni | 2025-02-10 | 856 | >60 | August | 2023 | #VALUE!
Customer Channels | Service Experience | 89350726 | 2023-05-30 | Messages sent from sterling to Collection DB failed in Sterling | Review Health Check in Release KT and add if any flows need to be validated | Problem avoidance | Sterling Support and OMS Dev | 09/06: Health check scope will be revisited for each release days and add any Release specific flows as when needed | Sterling Support and OMS Dev |  | NA | 2023-09-06 | Closed | NA | DNCTA-7886 |  | Saloni | 2025-02-10 | 856 | >60 | June | 2023 | #VALUE!
Customer Channels | Service Experience | 89350726 | 2023-05-30 | Messages sent from sterling to Collection DB failed in Sterling | Add Inactivity alert in Collection App | Problem identification & Alerting | Web Engineering | 21/06- Inactivity alerts added 09/06:Priortised by product teams in the current sprint and next sprints | Web Engineering |  | NA | 21/06/23 | Closed | NA | EG-5912 |  | Saloni | 2025-02-10 | 856 | >60 | June | 2023 | #VALUE!
Customer Channels | Service Experience | 89350726 | 2023-05-30 | Messages sent from sterling to Collection DB failed in Sterling | Review collection App for opportunities to set up inactivity alert | Problem avoidance | Web Engineering | 21/06- Inactivity alerts added 09/06:Priortised by product teams in the current sprint and next sprints | Web Engineering |  | NA | 21/06/23 | Closed | NA | EG-5912 |  | Saloni | 2025-02-10 | 856 | >60 | June | 2023 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89344497 | 2023-05-26 | Performance issues with multiple applications hosted on Microsoft 0365 and Azure services | Feasibility to configure an alert to proactively identify issues with Microsoft application via Solar Winds | Problem identification & Alerting | Kamalakannan Kanniappan | This is being tracked under a backlog. NKB-1445 | Network |  | NA | 2023-05-06 | Closed | NA | NKB-1445 |  | Saloni | 2025-02-10 | 860 | >60 | June | 2023 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89344497 | 2023-05-26 | Performance issues with multiple applications hosted on Microsoft 0365 and Azure services | Feasibility to configure an alert to proactively identify any connectivity issues between zscaler and Microsoft applications | Problem identification & Alerting | Kamalakannan Kanniappan | This is completed.. | Network |  | NA | 2023-05-06 | Closed | NA |  |  | Saloni | 2025-02-10 | 860 | >60 | June | 2023 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89344497 | 2023-05-26 | Performance issues with multiple applications hosted on Microsoft 0365 and Azure services | Root cause of the issue | Root Cause | Promode Gnanaguru/Kamalakannan Kanniappan | A central connectivity issue between Microsoft and their Internet Service Providers (ISP) impacting multiple customers including Customer which also interrupted the connectivity between Microsoft and Zscaler via their London V and Frankfurt datacentres. Escalations have been made to Microsoft and Zscaler account manager for a detailed root cause analysis | Network |  | NA | 31/05/23 | Closed | NA |  |  | Saloni | 2025-02-10 | 860 | >60 | May | 2023 | #VALUE!
GTS | Digital Workplace Services | 89344497 | 2023-05-26 | Performance issues with multiple applications hosted on Microsoft 0365 and Azure services | Agree with Microsoft to introduce proactive alerting during any service disruption | Problem identification & Alerting | Saran Rajkumar | This is yet to be agreed. 26/06: Promode is OOO, will need to discuss with him if its actually possible to have a MS alerting in place 04/07: Alerting is possible at Microsoft however, those alerts are internal to server specific and Microsoft wont disclose those information to their customers. Hence, this is not feasible | Messaging Team |  | NA | 2023-04-07 | Closed | NA |  |  | Saloni | 2025-02-10 | 860 | >60 | July | 2023 | #VALUE!
GTS | Operations | 89344497 | 2023-05-26 | Performance issues with multiple applications hosted on Microsoft 0365 and Azure services | Advise Microsoft on any key events at Customer to ensure proactive monitoring and timely notification of any issue. | Problem avoidance | Sathishkumar Sheshiah | Microsoft will provide updates in their GETHELP portal and this needs a longer time hence, closing it off the tracker. Also, it has been agreed to inform Microsoft of any Customer key events | Service Management |  | NA | 2023-07-08 | Closed | NA |  |  | Saloni | 2025-02-10 | 860 | >60 | August | 2023 | #VALUE!
GTS | Operations | 89344497 | 2023-05-26 | Performance issues with multiple applications hosted on Microsoft 0365 and Azure services | Improve the Microsoft engagement during any MI calls. | Supplier and support involvement | Sathishkumar Sheshiah | Microsoft have been reiterated the urgency and has agreed to improve their scope of engagement and escalation policy | Service Management |  | NA | 2023-07-08 | Closed | NA |  |  | Saloni | 2025-02-10 | 860 | >60 | August | 2023 | #VALUE!
Digital & Data | Digital & Data | 89346002 | 2023-05-25 | Understated POS sales data in FAQT, SWAT, Retail Dashboard and other reporting system | Not started alert has been configured for the SAGG Vs EDW recon job. | Problem identification & Alerting | Gaurav | Complete | EDW Support |  | NA | 25/05/23 | Closed | NA |  |  | Saloni | 2025-02-10 | 861 | >60 | May | 2023 | #VALUE!
Digital & Data | Digital & Data | 89346002 | 2023-05-25 | Understated POS sales data in FAQT, SWAT, Retail Dashboard and other reporting system | Set job overrunning alert for 35 min rather than one hour | Problem avoidance | Gaurav | Complete | EDW Support |  | NA | 25/05/23 | Closed | NA |  |  | Saloni | 2025-02-10 | 861 | >60 | May | 2023 | #VALUE!
Digital & Data | Digital & Data | 89346002 | 2023-05-25 | Understated POS sales data in FAQT, SWAT, Retail Dashboard and other reporting system | Create handover template – EDW team they have a h/o process but nothing to detail alerts that occurred and to handover what should be done for the alerts by the next on coming shift. | Problem avoidance | Gaurav | Complete | EDW Support |  | NA | 25/05/23 | Closed | NA |  |  | Saloni | 2025-02-10 | 861 | >60 | May | 2023 | #VALUE!
Digital & Data | Digital & Data | 89346002 | 2023-05-25 | Understated POS sales data in FAQT, SWAT, Retail Dashboard and other reporting system | Add EDW team members to support channel | Business & IT Communication | Gaurav | Complete | EDW Support |  | NA | 25/05/23 | Closed | NA |  |  | Saloni | 2025-02-10 | 861 | >60 | May | 2023 | #VALUE!
Digital & Data | Digital & Data | 89346002 | 2023-05-25 | Understated POS sales data in FAQT, SWAT, Retail Dashboard and other reporting system | Advise all teams of the Teams support channel and its purpose – review internal EDW escalation process | Business & IT Communication | Gaurav | 26/5: sent the request to add team members in the Support channel and conveyed the importance of that channel 25/5: Gaurav to confirm that escalation process has been reviewed and communicated internally to the EDW team | EDW Support |  | NA | 26/05/23 | Closed | NA |  |  | Saloni | 2025-02-10 | 861 | >60 | May | 2023 | #VALUE!
Digital & Data | Digital & Data | 89346002 | 2023-05-25 | Understated POS sales data in FAQT, SWAT, Retail Dashboard and other reporting system | Review on call backup process and ensure there are enough resources out of hours in case its busy and one resource cannot focus on critical and other issues. | Supplier and support involvement | Gaurav | 26/5:we have decided to keep a backup resource (in shift plan) as well in case of multiple job failures 25/5: In progress | EDW Support |  | NA | 26/05/23 | Closed | NA |  |  | Saloni | 2025-02-10 | 861 | >60 | May | 2023 | #VALUE!
Digital & Data | Digital & Data | 89346002 | 2023-05-25 | Understated POS sales data in FAQT, SWAT, Retail Dashboard and other reporting system | DS admin/EDW team to investigate why the 12pm 010 job was stuck | Root cause | Mani/Gaurav | There are few other jobs that has failed or LSF (load sharing facility) unable to submit jobs in DS whilst connecting to the DS node. There were similar issues in the past and IBM has advised to increase a grid parameter value. | EDW Support |  | NA | 25/05/23 | Closed | NA |  |  | Saloni | 2025-02-10 | 861 | >60 | May | 2023 | #VALUE!
Commercial Trading | Foods Commercial Trading | 89342062 | 2023-05-23 | Prices in two stores are trading at 5% higher than the tickets are reflecting. | Need to ascertain if the team doing the changes on 21/05 were aware of the process to advise the POS team prior to changing store level prices to country level. If they were not aware, then they need to be made aware that this needs to be the process until it can be reviewed and changed | Root cause | Joey Ocansey | 20/06 - The document has been drafted to be provided to the business. Joey and team to have a connect with the business this week and will update accordingly. 11/07 - Joey has confirmed that the document has been finalized and it has bee shared with business to follow and the same has been agreed by the business | Foods Service lead |  | NA | 2023-11-07 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 863 | >60 | July | 2023 | #VALUE!
Group Support | Finance | 89342062 | 2023-05-23 | Prices in two stores are trading at 5% higher than the tickets are reflecting. | In the interim, until the longer term solution is in place, identify if it is possible to add a pop up message in the SAPGUI where the changes are made to remind the colleagues that POS team need to be aware of the change. If it is possible then design and implement and add this into the procedure. | Problem avoidance | Remko | Balram (SAP Product Manager) and remko had decided that there would not be significant benefit to add technical debt (in the form of custom code) to SAP, especially considering the low frequency of this particular business scenario and the fact that we have a preventative business process step as well (which has been reiterated to the two business teams involved). Likewise pricing is planned to be moved out of SAP into a more strategic Foods solution. | SAP |  | NA | 2023-09-06 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 863 | >60 | June | 2023 | #VALUE!
Customer Channels | Service Experience | 89342062 | 2023-05-23 | Prices in two stores are trading at 5% higher than the tickets are reflecting. | Review the whole price changing process down to POS and propose any easier automated solutions in the interim | Problem avoidance | Seeva/Bala | 09/06: Not in current scope, requesting to add in scope the document for the process that needs to be followed by business when it is decided to move store back to region/country has been shared with SAP and Joey to integarte it with the busniess as agreed. | POS team |  | NA | 2023-09-06 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 863 | >60 | June | 2023 | #VALUE!
Customer Channels | Service Experience | 89342062 | 2023-05-23 | Prices in two stores are trading at 5% higher than the tickets are reflecting. | Provide the process document in the interim and add that, WO needs to be raised so that down streams are aware. Add this to the business colleague’s document. | Problem avoidance | Seeva/Bala | 09/06: Targetted for June end Process has been reviewed and the as-is need to be followed. Communication to POS Support is shared hereby, which needs to be incorporated into overall business document | POS team |  | NA | 2023-09-06 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 863 | >60 | June | 2023 | #VALUE!
Customer Channels | Service Experience | 89334769 | 2023-05-22 | Dropship order confirmation messages failing in Sterling | Set up a QBR between CommerceHub and Customer | Problem avoidance | David | 21/07: The first QBR review session was held on 17th July 10/07: The QBR is scheduled with Commercehub next week to discuss further In Progress. 1st QBR will happen in mid-June. One point to check – How do we get communicated reg the CommerceHub releases. DL that should be used. | Commerce Hub |  | NA | 21/07/23 | Closed | NA | DSAT-611 |  | Saloni | 2025-02-10 | 864 | >60 | July | 2023 | #VALUE!
Customer Channels | Service Experience | 89334769 | 2023-05-22 | Dropship order confirmation messages failing in Sterling | Support email received from Customer should be sent to right team in CommerceHub | Business & IT Communication | David | Completed. Necessary amendments were made regarding this at CommerceHub end. | Commerce Hub |  | NA | 23/05/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 864 | >60 | May | 2023 | #VALUE!
Customer Channels | Service Experience | 89334769 | 2023-05-22 | Dropship order confirmation messages failing in Sterling | Error messaging was misleading which led to increased investigation time. CommerceHub should work on updating correct Error messaging. | Problem identification & Alerting | David | 07/21 - Due to competing priorities we are unable to start development till Sprint 3.This action will be tracked under the back log as its priorised only for Sprint 3 10/07: Followed with David Gillard and awaiting an update 14/06- 04/07: Arthi (SO) is laising with to David to follow up with Commerce hub, we are still waiting an update | Commerce Hub |  | NA | 21/07/23 | Closed | NA | DSAT-612 |  | Saloni | 2025-02-10 | 864 | >60 | July | 2023 | #VALUE!
Customer Channels | Service Experience | 89334769 | 2023-05-22 | Dropship order confirmation messages failing in Sterling | CommerceHub to improve alerting at their end. | Problem identification & Alerting | David | 03/07: David has confirmed that team will continue to review with Commerce hub and further follow up needs to be continued hence closing this actions 21/07: Bola to advise after QBR session with CommerceHub on 17th July.Alert configuration to be prioritized, ETA to follow 10/07: The QBR is scheduled with Commercehub next week to discuss further 14/06- 04/07: Arthi (SO) is laising with to David to follow up with Commerce hub, we are still waiting an update | Commerce Hub |  | NA | 2023-03-03 | Closed | NA | DSAT-613 |  | Saloni | 2025-02-10 | 864 | >60 | March | 2023 | #VALUE!
Customer Channels | Service Experience | 89334769 | 2023-05-22 | Dropship order confirmation messages failing in Sterling | Alerting at CommerceHub end. There is an alert set up at their end at retailer level to be received when no activity. But this was not enabled due to low volumes. | Problem identification & Alerting | David | 03/03 Commerce hub in process setting up an alert, however we are yet to the go live date, this will be tracked under the JIRA backlog . Hence closing this action from tracker 21/07: Alerting configuration is yet to be planned , awaiting an ETA 10/07:10/07: The QBR is scheduled with Commercehub next week to discuss further CommerceHub is awaiting details from Customer on the volume based on which alerts will be set up. | Commerce Hub |  | NA | 2023-03-03 | Closed | NA | DSAT-614 |  | Saloni | 2025-02-10 | 864 | >60 | March | 2023 | #VALUE!
Customer Channels | Service Experience | 89334769 | 2023-05-22 | Dropship order confirmation messages failing in Sterling | Update Service design document on process of engaging CommerceHub support team | Supplier and support involvement | David | 03/07: Document updated | Commerce Hub |  | NA | 2023-03-07 | closed | NA | DSAT-617 |  | Saloni | 2025-02-10 | 864 | >60 | July | 2023 | #VALUE!
Customer Channels | Service Experience | 89334769 | 2023-05-22 | Dropship order confirmation messages failing in Sterling | Create a template to dropship team on when and how to engage Stakeholders and CommerceHub | Supplier and support involvement | David | 03/07: Template created | Commerce Hub |  | NA | 2023-03-07 | closed | NA | DSAT-618 |  | Saloni | 2025-02-10 | 864 | >60 | July | 2023 | #VALUE!
Customer Channels | Service Experience | 89334769 | 2023-05-22 | Dropship order confirmation messages failing in Sterling | Root cause from Commerce Hub. | Root cause | David | Completed. Root cause provided by CommerceHub is as below: What happened? The internal project structure for the validation engine was overhauled and included in another project and has been for many months. An unrelated change was implemented in a different branch of the new project structure that had an unexpected impact on the validation engine. Why was Customer impacted? The change specifically impacted validation on the field items.retailerItemIds for which Marks and Spencer have a custom validation rule set up. How was it fixed? The conflicting branches have now been combined into a single branch with all previous fixes from both branches restored. | Commerce Hub |  | NA | 23/05/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 864 | >60 | May | 2023 | #VALUE!
Customer Channels | Service Experience | 89334769 | 2023-05-22 | Dropship order confirmation messages failing in Sterling | SEV matrix must be defined at CommerceHub level and Customer Internal level with threshold. This will help the team to call out / communicate to stakeholders based on severity and criticality. To be agreed with Hayley, Mark Laming | Business & IT Communication | David/ Arthi | 27/06: Severity matrix has been updated | Commerce Hub |  | NA | 27/06/23 | Closed | NA | DSAT-616 |  | Saloni | 2025-02-10 | 864 | >60 | June | 2023 | #VALUE!
Customer Channels | Service Experience | 89334769 | 2023-05-22 | Dropship order confirmation messages failing in Sterling | Feasiblity of Dropship dashboard at supplier level | Problem identification & Alerting | Arthi Suriyanarayanan | 21/07: Laming mark has a CFR dashboard at supplier level. Any other data at supplier level they have access to Commercehub platform to view the same. No more Action DSAT-615 is closed. 10/07: There is CFR dashboard at supplier level, however further discussions are inprogress to look for feasilibity of enhancement Arthi to check with Mark if they have any such dashboard. | Service lead |  | NA | 21/07/23 | Closed | NA | DSAT-615 |  | Saloni | 2025-02-10 | 864 | >60 | July | 2023 | #VALUE!
Customer Channels | Service Experience | 89334769 | 2023-05-22 | Dropship order confirmation messages failing in Sterling | Exceptions are captured in general queue where Brands and other fulfillment partners exceptions are received. Replaying from this queue is difficult. Dropship nodes should send exception in separate queue which will help quick replay / analysis. | Solution & Recovery | Bola | 21/06: Planned for Q2-23 and will be tracked under the product back log | Commerce Hub |  | NA | 21/06/23 | closed | NA | DSAT-551 |  | Saloni | 2025-02-10 | 864 | >60 | June | 2023 | #VALUE!
Customer Channels | Service Experience | 89334769 | 2023-05-22 | Dropship order confirmation messages failing in Sterling | Automate replay of orders to CommerceHub for a selected time period at supplier level. | Solution & Recovery | Bola | 21/06 - Added to the dropship current sprint Q1 Sprint 6 | Commerce Hub |  | NA | 30/06/23 | Closed | NA | DSAT-552 |  | Saloni | 2025-02-10 | 864 | >60 | June | 2023 | #VALUE!
Customer Channels | Customer Engagement | 89325577 | 2023-05-19 | Customers were unable to collect coffee stamps with new purchases. | Remove the existing application credential from mongo and create a new one with customised role and deploy application with the new credential for connecting. | Problem avoidance | Antony Narcissot | 10/07: Antony has confirmed that the action has been addressed, Awaiting more details on the action taken, however marking this as closed 20/06 to 10/07: Followed update with Antony awaiting an update on the progress 13/06:This is progressed as part of the current sprint awaiting updates. 19/05: This requires code change and deployment. Revised target date will be shared for this action post discussion with PO. | Sparks & loyality |  | NA | 2023-10-07 | Closed | NA | CMPN-137 |  | Saloni | 2025-02-10 | 867 | >60 | July | 2023 | #VALUE!
Customer Channels | Customer Engagement | 89325577 | 2023-05-19 | Customers were unable to collect coffee stamps with new purchases. | Look at creating specific customised roles for mongoDB access, which will prevent running any drop or delete commands, even if the user has written access. | Problem avoidance | Antony Narcissot | 10/07: Antony has confirmed that the action has been addressed, Awaiting more details on the action taken, however marking this as closed 20/06 to 10/07: Followed update with Antony awaiting an update on the progress 13/06:This is progressed as part of the current sprint awaiting updates. 19/05: Revised target date for this action will be shared post discussion with Mongo DB support | Sparks & loyality |  | NA | 2023-10-07 | Closed | NA | CMPN-138 |  | Saloni | 2025-02-10 | 867 | >60 | July | 2023 | #VALUE!
Customer Channels | Customer Engagement | 89325577 | 2023-05-19 | Customers were unable to collect coffee stamps with new purchases. | Enhance the script for editing any stamp offer config collection details | Problem avoidance | Antony Narcissot | 10/07: Antony has confirmed that the action has been addressed, Awaiting more details on the action taken, however marking this as closed 13/06:This is progressed as part of the current sprint awaiting updates. 19/05: This requires code change and deployment. Revised target date will be shared for this action post discussion with PO. | Sparks & loyality |  | NA | 2023-10-07 | Closed | NA | CMPN-139 |  | Saloni | 2025-02-10 | 867 | >60 | July | 2023 | #VALUE!
Customer Channels | Customer Engagement | 89325577 | 2023-05-19 | Customers were unable to collect coffee stamps with new purchases. | Inform the team, to use read only users on mongoDB compass/Atlas, to login to mongoDB | Problem avoidance | Antony Narcissot | 19/05: Action completed | Sparks & loyality |  | NA | 19/05/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 867 | >60 | May | 2023 | #VALUE!
Customer Channels | Customer Engagement | 89325577 | 2023-05-19 | Customers were unable to collect coffee stamps with new purchases. | Remove write access for all except one user and application for the prod DB. a. Short Term - We have limited the users with write access to 1 user and the application. b. Long Term - We need to revisit the policy of credentials on key vaults and restricting the application cred access. | Problem avoidance | Antony Narcissot | 19/05: Action completed | Sparks & loyality |  | NA | 19/05/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 867 | >60 | May | 2023 | #VALUE!
Customer Channels | Customer Engagement | 89325577 | 2023-05-19 | Customers were unable to collect coffee stamps with new purchases. | Continue the existing way of using python script to add any new stamp offers to the config collection. a. The script is run on non-prod and tested, before inserting data into production. b. The script is maintained on the git repo. | Problem avoidance | Antony Narcissot | 19/05: Action completed | Sparks & loyality |  | NA | 19/05/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 867 | >60 | May | 2023 | #VALUE!
Customer Channels | Customer Engagement | 89325577 | 2023-05-19 | Customers were unable to collect coffee stamps with new purchases. | Create a new Remedy group specifically for Campaign Management Product and integrate with Pager Duty & New Relic, to enable better visibility and tracking of issues Product Team to raise an incident in future instances through Remedy Tool | Problem identification & Alerting | Antony Narcissot | 10/07: Antony has confirmed that the action has been addressed, Awaiting more details on the action taken, however marking this as closed 20/06 to 10/07: Followed update with Antony awaiting an update on the progress 20/06: The action is still inprogress of finalising this as the currently focusing pagerduty setup 13/06: This is progressed as part of the current sprint awaiting updates. | Sparks & loyality |  | NA | 2023-10-07 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 867 | >60 | July | 2023 | #VALUE!
Customer Channels | Customer Engagement | 89325577 | 2023-05-19 | Customers were unable to collect coffee stamps with new purchases. | Add alert in DB, when the logical data in the disk goes below a certain threshold | Problem identification & Alerting | Antony Narcissot | 19/05: Action completed | Sparks & loyality |  | NA | 19/05/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 867 | >60 | May | 2023 | #VALUE!
Customer Channels | Customer Engagement | 89325577 | 2023-05-19 | Customers were unable to collect coffee stamps with new purchases. | Create an alert around expected balance update traffic every hour, from 6AM to 8 PM. If traffic dips below, trigger an alert. (This will indicate problems that can arise due to other issues as well) | Problem identification & Alerting | Antony Narcissot | 19/05: Action completed | Sparks & loyality |  | NA | 19/05/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 867 | >60 | May | 2023 | #VALUE!
Commercial Trading | Foods Commercial Trading | 89316223 | 2023-05-17 | One Customer Foods Platform application inaccessible | Explore the feasibility of configuring an alert | Problem identification & Alerting | Hariharan Sudhan | 06/06: Alerts have been configured 17/05: The token expiry is tracked manually, options are explored to configure an alert. | OFP |  | NA | 2023-06-06 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 869 | >60 | June | 2023 | #VALUE!
Commercial Trading | Foods Commercial Trading | 89316223 | 2023-05-17 | One Customer Foods Platform application inaccessible | Can we renew the token automatically if not what measure can be put in place to avoid the token expiry? | Problem avoidance | Hariharan Sudhan | 17/05: The token cannot be automatically renewed, and it needs to be updated before the expiry. The setup to remind the token expiry a month before the expiry date has been hardcoded in new relic to avoid any miss in renewal of the tokens. | OFP |  | NA | 17/05/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 869 | >60 | May | 2023 | #VALUE!
Customer Channels | Platform & Store Ops | 89320290 | 2023-05-16 | Performance degradation while accessing the Customer application at BP stores | Feasibility to increase the network bandwidth at BP. | Permanent fix | Laura | Bandwidth has been expanded by BP from 20 MB to 30 MB | Service Lead |  | NA | 20/06/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 870 | >60 | June | 2023 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89320290 | 2023-05-16 | Performance degradation while accessing the Customer application at BP stores | What was the cause for the memory leak on the SRX device on 12/05? | Root cause | NOC | It has been identified that there were no memory issue on the concentrators. The reason behind the memory error is the high network throttling at BP end due to limited bandwidth between Customer and BP, causing constant movement of stores from one concentrator to another. | Network |  | NA | 16/05/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 870 | >60 | May | 2023 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89320290 | 2023-05-16 | Performance degradation while accessing the Customer application at BP stores | If the issue re-occurs, what is the plan to mitigate the impact to the stores? | Solution & Recovery | NOC | Scripts have been created/updated in Solar winds to move multiple stores to the other LON for immediate mitigation Note: This activity will incur an outage of 1 hour The existing SOP is being updated accordingly. | Network |  | NA | 16/05/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 870 | >60 | May | 2023 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89320290 | 2023-05-16 | Performance degradation while accessing the Customer application at BP stores | Create a SOP detailing the mitigation steps for timely recovery. | Solution & Recovery | NOC | Sop has been updated accordingly | Network |  | NA | 15/06/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 870 | >60 | June | 2023 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89320290 | 2023-05-16 | Performance degradation while accessing the Customer application at BP stores | Feasibility to improve the alerting for proactive identification of the issue. | Problem identification & Alerting | NOC | With the provisional increase in the network bandwidth the threshold for the existing alert has been amended and it has been agreed with network team to proactively highlight the issue in teams channel. | Network |  | NA | 16/05/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 870 | >60 | May | 2023 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89320290 | 2023-05-16 | Performance degradation while accessing the Customer application at BP stores | Is there a plan to replace the SRX devices associated with the concentrators as they are EOL/EOS? | Problem avoidance | NOC | Currently SDWAN migration is in progress, after which the BP and BT devices will be replaced. There is an existing risk to track this. | Network |  | NA | 16/05/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 870 | >60 | May | 2023 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89320290 | 2023-05-16 | Performance degradation while accessing the Customer application at BP stores | Devise a plan to reboot the LON1 and LON2 concentrators at regular intervals. | Problem avoidance | NOC | 11/07 -The next reboot is planned before the peak also the reboot schedule has been updated on the centrel Repository NOC has agreed to perform the LON reboots once a year. The schedule will be updated in the SOP and the centralized tracker. 27/06 - NOC to discuss with BP and to agree on the Schedule for reboots | Network |  | NA | 2023-11-07 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 870 | >60 | July | 2023 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89320290 | 2023-05-16 | Performance degradation while accessing the Customer application at BP stores | Conduct a knowledge sharing session to review BP infrastructure for better understanding the issue and for timely resolution | Solution & Recovery | NOC | This has been completed | Network |  | NA | 16/05/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 870 | >60 | May | 2023 | #VALUE!
Customer Channels | Platform & Store Ops | 89320290 | 2023-05-16 | Performance degradation while accessing the Customer application at BP stores | Devise a proper plan to schedule the SCEP updates for the BP stores until the permanent fix is in place. | Problem avoidance | Store infra/Valli | The SCEP updates to the BP stores are scheduled in smaller chunks through multiple batches to handle the scenario. | Service Owner |  | NA | 16/05/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 870 | >60 | May | 2023 | #VALUE!
Customer Channels | Service Experience | 89331108 | 2023-05-16 | Network connectivity issues impacting gift card transactions and carrier label printing at Donington and C&H Bradford | Transactions did not flow to SVS for a considerable amount of time, and they should have some form of alerting to indicate the lack of transactions. | Problem identification & Alerting | Priyanka Kumar | Examine the alerting SVS have and see if they have an alert to indicate lack of traffic for prolonged period. Awaiting updates from the service lead 25/06: There is no updates from the service lead. Requested SL to check on the feasibility of an alert configuration at SVS . 27/06: PO has confirmed that there was an exisiting alert at SVS end to identify the lack of transaction however the configuration was incorrect set up for the North American schedule, this has now been rectified to European schedule. Here are the current times of day the alerts are set up for, SVS don’t operate them over night to prevent false alarms as most clients have very little activity late at night or in the small hours of the morning. Mon – Sat: 9am – 10pm( now changed to 7am- 11pm) Sun: 10am – 7pm Exception: 25th December | Product Owner |  | NA | 27/06/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 870 | >60 | June | 2023 | #VALUE!
Customer Channels | Service Experience | 89331108 | 2023-05-16 | Network connectivity issues impacting gift card transactions and carrier label printing at Donington and C&H Bradford | It took time to reach SVS vendor | Supplier and support involvement | Priyanka Kumar | Ask SVS for an escalation process and ascertain the best way to raise an incident SVS 12/06: there is an service design document which needs updating. we weren't sure who the owner is from Customer as this need to be keep updated in case there are any incidents or issues. PO have shared a copy with Raza Akram who is currently reviewing and will make all the necessary amendments. 26/06: The document is being finalized and will be completed by 27/06 27/06: The documen is published | Product Owner |  | NA | 30/06/23 | CLosed | NA | NA | N/A | Saloni | 2025-02-10 | 870 | >60 | June | 2023 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89331108 | 2023-05-16 | Network connectivity issues impacting gift card transactions and carrier label printing at Donington and C&H Bradford | How can we improve the impact assessment process to make it timelier and clearer in the event of a similar incident where a network component such as VIP or a node is disabled? | Impact analysis | Rajesh/Kamal | Review and suggest the best proposal such as populating the description field next to the node name. We have enabled alert to trigger NOC DL incase of any working VIP goes to disabled state and take actions. | Network |  | NA | 27/06/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 870 | >60 | June | 2023 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89331108 | 2023-05-16 | Network connectivity issues impacting gift card transactions and carrier label printing at Donington and C&H Bradford | When nodes need to be disabled for any activity, until we can automate this process, how can the manual process be improved to prevent human errors? | Root cause | Rajesh/Kamal | Review and change the SOP, mandate the checking of each node, and select node by node rather than “select all”. There is no feasibility to systemically block “selecting all” – however instructions will be clear in the SOP. Team has amended the procedure document to search with complete VIP/Pool member name and perform the enable/disable activity in F5 | Network |  | NA | 27/06/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 870 | >60 | June | 2023 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89331108 | 2023-05-16 | Network connectivity issues impacting gift card transactions and carrier label printing at Donington and C&H Bradford | The naming conventions of DR and PROD and very similar and can cause confusion. | Problem avoidance | Rajesh/Kamal | NOC team to review the naming convention and if possible, suggest something that clearly differentiates between different domains backlog ID- NKB-1440 for both actions and planning in progress | Network |  | NA | 27/06/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 870 | >60 | June | 2023 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89331108 | 2023-05-16 | Network connectivity issues impacting gift card transactions and carrier label printing at Donington and C&H Bradford | When will tasks such as disabling and enabling nodes be automated? | Permanent Fix | Rajesh/Kamal | Planning discussions have started to use tools such as Terraform to automate the simpler tasks such as disabling and enabling nodes which are already documented in SOP’s. backlog ID- NKB-1440 for both actions and planning in progress | Network |  | NA | 27/06/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 870 | >60 | June | 2023 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89331108 | 2023-05-16 | Network connectivity issues impacting gift card transactions and carrier label printing at Donington and C&H Bradford | It took some time to ascertain when the gift card API was at fault, how can we engage the relevant teams in a timelier manner | Supplier and support involvement | Rehan/Sreejith | Provide the link to the contact repository so that that the payments team can update their contact details. This has been completed. | Network |  | NA | 28/05/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 870 | >60 | May | 2023 | #VALUE!
Customer Channels | Service Experience | 89331108 | 2023-05-16 | Network connectivity issues impacting gift card transactions and carrier label printing at Donington and C&H Bradford | The new relic query has changed and therefore not showing the error count hence the payments team could not see the issue clearly through an alert. | Problem identification & Alerting | Sreejith | Correct the new relic alerting to ensure the errors are clear and reflecting on the dashboard. | SVS |  | NA | 28/05/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 870 | >60 | May | 2023 | #VALUE!
Customer Channels | Service Experience | 89331108 | 2023-05-16 | Network connectivity issues impacting gift card transactions and carrier label printing at Donington and C&H Bradford | In the event of a recurrence, we should have a run book that can be quickly referred to | Solution & Recovery | Sreejith | Create an incident run book which will include a flow of all the systems included in the gift card process – to differentiate also between stores and website. This has been created now | SVS |  | NA | 28/05/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 870 | >60 | May | 2023 | #VALUE!
C&H and Intl | C&H Commercial Trading | 89324621 | 2023-05-16 | Issues in processing PLM messages | Review the challenges that were experienced in the investigation of the issue and the interaction between Customer and PTC. | Supplier and support involvement | Ashok/Raj/ Jerome | We reviwed the process and Integration team will loop in service leads if the issue is not resolved in 1 day | Product support/PTC team |  | NA | 2023-08-06 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 870 | >60 | June | 2023 | #VALUE!
C&H and Intl | C&H Commercial Trading | 89324621 | 2023-05-16 | Issues in processing PLM messages | Long term fix for the password policy | Permanent Fix | Jerome Poilvet | PTC has changed the expiration date to 2027 as a first initiative also the password has been reset and is shared to the team. | PTC team |  | NA | 18/05/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 870 | >60 | May | 2023 | #VALUE!
C&H and Intl | C&H Commercial Trading | 89324621 | 2023-05-16 | Issues in processing PLM messages | Alerting should be in place for the application as the root cause may not always be password expiration – API health check could be configured. | Problem identification & Alerting | Jerome Poilvet | 24/07 - Product Manager of PTC has claimed that for system defined users / integration users password expiration policy alerting will not be applicable. However it has been agreed with our intergration team to improvise the alerting at their end to prevent the message pile-up issue '11/07 - Vendor PTC is working on the alerting along with their Product manager. We are still awating response from them. Escalation Emails has been sent for the same | PTC team |  | NA | 24/07/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 870 | >60 | July | 2023 | #VALUE!
C&H and Intl | C&H Commercial Trading | 89324621 | 2023-05-16 | Issues in processing PLM messages | Integration alerts did trigger and notify us of 401 errors which are authentications issues. However the error had special characters in it which caused confusion - PTC and integration team to deal with this. | Problem identification & Alerting | Raj Subramanian/PTC | 26/06 - SOP has been updated accordingly by the Integration team. The SOP contains the steps on effective handling of such Scenario's in future | Product support/PTC team |  | NA | 27/06/23 | closed | NA | NA | N/A | Saloni | 2025-02-10 | 870 | >60 | June | 2023 | #VALUE!
C&H and Intl | C&H Commercial Trading | 89324621 | 2023-05-16 | Issues in processing PLM messages | We are currently using Jerome’s credentials and need a permanent solution – EXPIRES IN TWO DAYS | Solution & Recovery | Sumeet and Vinay | Old prod account details have been deployed into production with the expiration date to 2027 | PTC team |  | NA | 18/05/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 870 | >60 | May | 2023 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89331108 | 2023-05-16 | Can alerting be improved to identify issues with VIP’s being disabled. | This has been completed. | Problem identification & Alerting | Rajesh/Kamal | This has been completed | Network |  | NA | 16/05/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 870 | >60 | May | 2023 | #VALUE!
Customer Channels | Platform & Store Ops | 89318800 | 2023-05-15 | Stores were not able to access My Compliance app. | Why did not we have the issue reported in lower environments when the changes were tested and why we did not identify the issue during our post checks after the changes in production? | Problem avoidance | Umadevi/Manali | 15/5: Issue only in Prod for redirect UI. A case was raised 2305090030000879 with Azure to understand the root cause | My Compliance Team |  | NA | 24/05/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 871 | >60 | May | 2023 | #VALUE!
Customer Channels | Platform & Store Ops | 89318800 | 2023-05-15 | Stores were not able to access My Compliance app. | Why was the CR process not followed - ideally even for 4 wall CR's we need CR's to be created with testing results and implementation plan (along with reversion plan) to be in place. | Problem identification & Alerting | Umadevi/Manali | Accenture team agreed to follow the CR process henceforth. | My Compliance Team |  | NA | 15/05/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 871 | >60 | May | 2023 | #VALUE!
Customer Channels | Platform & Store Ops | 89318800 | 2023-05-15 | Stores were not able to access My Compliance app. | Was there any alerting that would have alerted us? | Problem identification & Alerting | Umadevi/Manali | 24/5: Alerts were configured | My Compliance Team |  | NA | 24/05/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 871 | >60 | May | 2023 | #VALUE!
Customer Channels | Service Experience | 89327395 | 2023-05-15 | C&H products showing OOS on PDP's | Monitoring - Build an AS availability view and build in OOS thresholds | Problem identification & Alerting | Amutha Subramanian | 21/06 - AS availability view has been completed 20/06: Planned in Sprint-6 (Q1) 26/05 - Followed up with Emma on status of the actions | Stock service team |  | NA | 21/06/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 871 | >60 | June | 2023 | #VALUE!
Customer Channels | Service Experience | 89327395 | 2023-05-15 | C&H products showing OOS on PDP's | Alerting - Once the monitoring of AS availability view is in place then build in the alerting | Problem identification & Alerting | Amutha Subramanian | 21/08 - TPM AC confirmed that the action is completed 04/08 - Moved to end of Sprint 2 with ETA as 15th August 28/07 - TPM updated that the alerting is expected to be completed by 1st August 21/07 - TPM updated that it is yet to be planned 17/07 - TPM Abhishek kumar(TPM) confirmed that it is yet to be planned. 07/07 - ETA for setting up the alert will be provided by next week 04/07 - PM has sent an email to the TPM - Ambalavan Chokkalingam (AC) to understand the latest ETA on the monitoring setup. Also highligted that alerting actions cannot be closed with backlog IDs. Updates are being sent across weekly and PM has been asked to speak to the TPM to gather more details and update here. 20/06: Planned in Sprint-1 (Q2) 26/05 - Followed up with Emma on status of the actions | Stock service team |  | NA | 21/08/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 871 | >60 | August | 2023 | #VALUE!
Customer Channels | Service Experience | 89327395 | 2023-05-15 | C&H products showing OOS on PDP's | Alerting – Review the current alerting available in OMS and set these up on the AS where required | Problem identification & Alerting | Amutha Subramanian | 21/07 - Abhishek confirmed that Alerts are configured 17/07 - TPM Abhishek kumar(TPM) confirmed that it is expected to be completed by 18th. 07/07 - ETA for setting up the alert will be provided by next week 04/07 - PM has sent an email to the TPM - Ambalavan Chokkalingam to understand the latest ETA on creating the alerting post the monitoring setup. Also highligted that alerting actions cannot be closed with backlog IDs. Updates are being sent across weekly and PM has been asked to speak to the TPM to gather more details and update here. 20/06: Planned in Sprint-6 (Q1) 26/05 - Followed up with Emma on status of the actions | Stock service team |  | NA | 21/07/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 871 | >60 | July | 2023 | #VALUE!
Customer Channels | Service Experience | 89327395 | 2023-05-15 | C&H products showing OOS on PDP's | Prevention - Rules to be followed going forwards for the daily manual activity whilst we are in the transition state. 1. Don’t action if above 3K items, hold and investigate further 2. Don’t action until received confirmation SOD has completed in OMS 3. Keep files of the manual updates applied | Problem avoidance | Amutha Subramanian | 20/06- All the AS engineers are made aware and will adhere to the process 26/05 - Followed up with Emma on status of the actions | Stock service team |  | NA | 20/05/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 871 | >60 | May | 2023 | #VALUE!
Customer Channels | Service Experience | 89327395 | 2023-05-15 | C&H products showing OOS on PDP's | Prevention – Automate the below daily manual activity 1. Don’t action if above 3K items, hold and investigate further 2. Don’t action until received confirmation SOD has completed in OMS 3. Keep files of the manual updates applied | Problem avoidance | Amutha Subramanian | 21/06 - Planned for Q2-23 and will be tracked under the back log 20/06: Planned in Sprint-6 (Q1) 26/05 - Followed up with Emma on status of the actions | Stock service team |  | NA | 21/06/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 871 | >60 | June | 2023 | #VALUE!
Customer Channels | Service Experience | 89327395 | 2023-05-15 | C&H products showing OOS on PDP's | Review other manual activities/workarounds on the AS, do we have a plan to automate these or provide a change/fix to stop the need of them | Permanent Fix | Amutha Subramanian | 21/06 - Planned for Q2-23 and will be tracked under the back log 20/06: Planned in Sprint-6 (Q1) 26/05 - Followed up with Emma on status of the actions | Stock service team |  | NA | 21/06/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 871 | >60 | June | 2023 | #VALUE!
Customer Channels | Service Experience | 89327395 | 2023-05-15 | C&H products showing OOS on PDP's | Message to team - Being aware of operations impact when running manual activities on this service | Impact analysis | Amutha Subramanian | 20/06- All the AS engineers are made aware and will adhere to the process 26/05 - Followed up with Emma on status of the actions | Stock service team |  | NA | 20/05/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 871 | >60 | May | 2023 | #VALUE!
Customer Channels | Service Experience | 89327395 | 2023-05-15 | C&H products showing OOS on PDP's | Alerting - Manual activity alert to be changed to trigger on back of SOD EOF has processed in OMS | Problem identification & Alerting | Jackson Solomon | 20/06: Alerts created and Closed on Sprint-4(Q1 26/05 - Followed up with Emma on status of the actions | sterling |  | NA | 20/05/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 871 | >60 | May | 2023 | #VALUE!
Customer Channels | Service Experience | 89327395 | 2023-05-15 | C&H products showing OOS on PDP's | Alerting - Add AS Team to the OMS inbound SOD alerts | Problem identification & Alerting | Rajeev Ekambaram | 20/06: Alerting has been configured. 26/05 - Followed up with Emma on status of the actions | Sterling |  | NA | 20/05/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 871 | >60 | May | 2023 | #VALUE!
Customer Channels | Service Experience | 89327395 | 2023-05-15 | C&H products showing OOS on PDP's | Include AS Team into the comms Sterling Support sends during Sterling outages | Business & IT Communication | Rajeev Ekambaram | 20/06: Includee AS Team into the comms Sterling Support sends during Sterling outages and hence action has been closed 26/05 - Followed up with Emma on status of the actions | Sterling |  | NA | 20/05/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 871 | >60 | May | 2023 | #VALUE!
Customer Channels | Service Experience | 89327395 | 2023-05-15 | C&H products showing OOS on PDP's | Monitoring – Is it possible for the PO & AS Team to have access to the Adobe availability Dashboards Brands & Customer Ops Hub use | Problem identification & Alerting | Steve Almashoor | 21/08 - TPM AC confirmed that the action is completed 07/08 - TPM confirmed ETA as 15th August 04/08 - TPM updated that we don't have an ETA from Amutha Subramanian 28/07 - TPM updated that it is in progress 21/07 - TPM updated that it is yet to be planned 17/07 - TPM Abhishek kumar(TPM) confirmed that it is yet to be planned. 04/07 - PM has sent an email to the TPM - Ambalavan Chokkalingam(AC) to understand the progress on creating the monitoring setup. Updates are being sent across weekly and PM has been asked to speak to the TPM to gather more details and update here. 21/06 - To be planned 20/06: Product manager (Steve A) owning this 26/05 - Followed up with Emma on status of the actions | Product Owner |  | NA | 21/08/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 871 | >60 | August | 2023 | #VALUE!
Customer Channels | Service Experience | 89327395 | 2023-05-15 | C&H products showing OOS on PDP's | Ready for AS end state – Introduce SOD recons between DC’s/shipnodes & AS and highlight when threshold is breached of missing items so this can be followed up with the relevant team/DC | Problem identification & Alerting | Steve Almashoor | 21/06 - Planned for Q2-23 and will be tracked under the back log 20/06: Product Manager (Steve) to review the approach and priortise this 26/05 - Followed up with Emma on status of the actions | Product Owner |  | NA | 21/06/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 871 | >60 | June | 2023 | #VALUE!
Customer Channels | Service Experience | 89327393 | 2023-05-15 | Brands depts showing OOS on Website | Change Ticket – Within the ticket not only advise of the depts going live add the ship node mapping as well. | Impact analysis | Amutha Subramanian | 21/06- Planned for Q2 '23 and will be tracked under back log 20/06: Priortised by product teams in the current sprint and next sprints 26/05 - Followed up with Emma on status of the actions | Stock service team |  | NA |  | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 871 | >60 | January | 1900 | #VALUE!
Customer Channels | Service Experience | 89327393 | 2023-05-15 | Brands depts showing OOS on Website | Monitoring - Build an AS availability view and build in OOS thresholds | Problem avoidance | Amutha Subramanian | 04/08 - TPM confirmed that the monitoring is in place, hence closing 28/07 - TPM updated that the monitoring is expected to be completed by 1st August 21/07 - Abhishek updated that it is in progress and expected to complete by end of Sprint 2. 17/07 - TPM Abhishek kumar(TPM) confirmed that it is partially done, Extention of work is planned in Q2 sprint-2 07/07 - Dependant on alerting action on AS 04/07 - Mail sent PM to Ambalavan Chokkalingam to understand the latest ETA on creating the views. Updates are being sent across weekly and PM has been asked to speak to the TPM to gather more details and update PM. 20/06: Planned for Sprint-6 (Q1) 26/05 - Followed up with Emma on status of the actions | Stock service team |  | NA | 2023-04-08 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 871 | >60 | August | 2023 | #VALUE!
Customer Channels | Service Experience | 89327393 | 2023-05-15 | Brands depts showing OOS on Website | Alerting - Once monitoring is in place then build in the alerting | Problem identification & Alerting | Amutha Subramanian | 21/08 - TPM AC confirmed that the action is completed 19/08 - 19/08 - Followedup with TPM AC on the status 04/08 - Moved to end of Sprint 2 with ETA as 15th August 28/07 - TPM updated that the monitoring is expected to be completed by 1st August 21/07 - TPM updated that it is yet to be planned 17/07 - TPM Abhishek kumar(TPM) confirmed that it is yet to be planned. 07/07 - ETA for setting up the alert will be provided by next week 04/07 - Mail sent by PM to Ambalavan Chokkalingam to understand the latest ETA on creating the AS availability views. Updates are being sent across weekly and PM has been asked to speak to the TPM to gather more details and update PM. 21/06: Team had planned to configure the alerts in Q2-2 20/06: alerting is planned for Sprint-1 (Q2) 26/05 - Followed up with Emma on status of the actions | Stock service team |  | NA | 21/08/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 871 | >60 | August | 2023 | #VALUE!
Customer Channels | Service Experience | 89327393 | 2023-05-15 | Brands depts showing OOS on Website | When introducing a new ship node on the AS: 1. What are the prerequisites? (Include adding ship node to the country node master collection configuration) 2. How to validate they have all been completed? Is this possible via a tool? 3. Need an audit trail to show this. | Problem identification & Alerting | Amutha Subramanian | 21/06 - All activities part of this action are completed 20/06: Priortised by product teams in the current sprint and next sprints 26/05 - Followed up with Emma on status of the actions | Stock service team |  | NA | 21/06/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 871 | >60 | June | 2023 | #VALUE!
Customer Channels | Service Experience | 89327393 | 2023-05-15 | Brands depts showing OOS on Website | Add Brands stakeholders to the required incident comms DL’s | Business & IT Communication | Emma Rotheram | Added stakeholders to DL | Service Lead |  | NA | 15/05/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 871 | >60 | May | 2023 | #VALUE!
Customer Channels | Service Experience | 89327393 | 2023-05-15 | Brands depts showing OOS on Website | Are PDP able to measure OOS? Work is going on at the moment using Content Square by the Analytics Team | Problem identification & Alerting | Steve Almashoor | 03/07 - Closing with the Backlog ID 21/06 - Yet to be planned 20/06: Product manager (Steve Almashoor) owning this to implement with Analytics team. 26/05 - Followed up with Emma on status of the actions | Product Owner |  | NA | 2023-04-07 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 871 | >60 | July | 2023 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89295245 | 2023-05-03 | Performance issue with Customer application in BP stores | At 03:54, alerts were triggered indicating high utilization on the network. What actions were taken and how can we improve to proactively identify such issues in future? | Problem identification & Alerting | Balasubramanyam Pagadala | Team assumed that the stores were closed therefore, this was not communicated to the relevant support teams. It has been agreed during the PIR, that network team will update the relevant support teams in the Support team channel in case of such alerts in future. | Network |  | NA | 2023-05-06 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 883 | >60 | June | 2023 | #VALUE!
Customer Channels | Platform & Store Ops | 89295245 | 2023-05-03 | Performance issue with Customer application in BP stores | Explore the feasibility to introduce a NOMAD component to ensure a systemic and automatic package distribution. | Problem avoidance | Deepakkumar Ramanujam | As this is a legacy application there is no chance to enable the NOMAD for the automate distribution of packages. | Service Lead |  | NA | 2023-05-06 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 883 | >60 | June | 2023 | #VALUE!
Customer Channels | Platform & Store Ops | 89295245 | 2023-05-03 | Performance issue with Customer application in BP stores | There were no records of the estimated time of package distribution, number of stores planned for each scheduled batch, batch schedule times etc from the previous deployments. Create a tracker detailing the various attributes of any deployment for future use. | Solution & Recovery | Deepakkumar Ramanujam | The Manual tracker is in place with the number of to be deployed on batches with the deployment date and time. | Infrastructure Device Platform |  | NA | 2023-05-06 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 883 | >60 | June | 2023 | #VALUE!
Customer Channels | Platform & Store Ops | 89295245 | 2023-05-03 | Performance issue with Customer application in BP stores | Feasibility of configuring completion alerts for each scheduled batch during a patch deployment | Problem identification & Alerting | Deepakkumar Ramanujam | There is no feasibility of alerting to be set-up post the batch completion as those are tracked by manual monitoring and maually trigerred. | Infrastructure Device Platform |  | NA | 2023-05-06 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 883 | >60 | June | 2023 | #VALUE!
Customer Channels | Platform & Store Ops | 89295245 | 2023-05-03 | Performance issue with Customer application in BP stores | Why there was a delay in identifying the cause of issue (SCEP Updates)? | Solution & Recovery | Deepakkumar Ramanujam | As there was a lower volume of stores planned for the deployment, product team had randomly scheduled the package distribution at 02:30. Therefore, it has been decided to agree on a particular time window for the patches to be deployed in future. See action#3. | Infrastructure Device Platform |  | NA | 2023-05-06 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 883 | >60 | June | 2023 | #VALUE!
Customer Channels | Platform & Store Ops | 89295245 | 2023-05-03 | Performance issue with Customer application in BP stores | Once the deployment time window has been agreed, team to update the deployment process document | Solution & Recovery | Deepakkumar Ramanujam | This will be done once action#3 is completed. | Infrastructure Device Platform |  | NA | 2023-05-06 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 883 | >60 | June | 2023 | #VALUE!
Customer Channels | Platform & Store Ops | 89295245 | 2023-05-03 | Performance issue with Customer application in BP stores | Root cause behind the deployment of the Scep updates sent across the BP stores during the business hours. | Root Cause | Deepakkumar Ramanujam | The SCEP updates are scheduled in batches anytime between 22:30 and 04:00 based on the number of stores planned. On 25/04, the first batch of the package distribution was randomly scheduled to run at 02:30 due to low volume of planned stores, hence the deployment was extended for BP stores due to insufficient network bandwidth between Hughes and BP | Infrastructure Device Platform |  | NA | 2023-05-06 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 883 | >60 | June | 2023 | #VALUE!
Customer Channels | Platform & Store Ops | 89295245 | 2023-05-03 | Performance issue with Customer application in BP stores | What is the usual schedule for these Scep updates? | Problem identification & Alerting | Dhilip Kumar | These SCEP updates are usually deployed in batches every week across the 1000 stores in the estate. However, the last patch update was deployed in March which did not cause any issues. In March, due to the higher number of stores, the first batch ran at 12:00, however, in April, it was scheduled at 02:30 due to lower volume of stores, therefore, action has been agreed to ascertain a particular time window suitable for these deployment across the BP stores without impacting their operations | Infrastructure Device Platform |  | NA | 2023-05-06 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 883 | >60 | June | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89295245 | 2023-05-03 | Performance issue with Customer application in BP stores | Update the centralised server repository with appropriate description, functionalities, and support teams. | Solution & Recovery | Jeevanandhan Selvaraj | 20/06 - CMDB is updated with the latest, especailly for the question server (MSHSRMNSUKP1156) | CMDB |  | NA | 20/03/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 883 | >60 | March | 2023 | #VALUE!
Customer Channels | Platform & Store Ops | 89295245 | 2023-05-03 | Performance issue with Customer application in BP stores | Feasibility of increasing the network bandwidth for the BP link as a permanent solution? | Solution & Recovery | Laura Whittle | Bandwidth has been expanded by BP from 20 MB to 30 MB | Infrastructure Device Platform |  | NA | 20/06/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 883 | >60 | June | 2023 | #VALUE!
Customer Channels | Platform & Store Ops | 89295245 | 2023-05-03 | Performance issue with Customer application in BP stores | Agree a time window to deploy the anti-virus updates into the BP stores. | Problem avoidance | Laura Whittle | The service lead has confirmed the deployment time window tot he respective support team. | Service Lead |  | NA | 2023-05-06 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 883 | >60 | June | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89300491 | 2023-04-28 | WMS application unavailable at Castle Donington and Ollerton DCs | Did we receive an alert indicating the unreachable status of the primary server? What actions were taken to resolve the issue? Is there any feasibility of improvement in the alerting mechanism? | Problem identification & Alerting | Boopathi Palanisamy | An alert was received at 13:40 indicating that the primary server was in unreachable state. Thereafter, CD colleagues reported the issue. There is no feasibility of implementing any additional alerting to highlight the gradual degradation of the database services. | Database |  | NA | 28/04/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 888 | >60 | April | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89300491 | 2023-04-28 | WMS application unavailable at Castle Donington and Ollerton DCs | Did we receive an alert indicating the unreachable status of the primary server? What actions were taken to resolve the issue? Is there any feasibility of improvement in the alerting mechanism? | Problem identification & Alerting | Boopathi Palanisamy | An alert was received at 13:40 indicating that the primary server was in unreachable state. Thereafter, CD colleagues reported the issue. There is no feasibility of implementing any additional alerting to highlight the gradual degradation of the database services. | Oracle DBA Support |  | NA | 29/04/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 888 | >60 | April | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89300491 | 2023-04-28 | WMS application unavailable at Castle Donington and Ollerton DCs | Enable the automatic failover of the database services for other sites. | Problem avoidance | Elizabeth Golder | They have a different set up to CD WMS using Redhat clusters so this change isn't needed. | Service Lead |  | NA | 2023-09-06 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 888 | >60 | June | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89300491 | 2023-04-28 | WMS application unavailable at Castle Donington and Ollerton DCs | Improve the level of support from HP during major incidents over the weekend. | Supplier and support involvement | Elizabeth Golder | This has been addressed now. | Service Lead |  | NA | 2023-02-05 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 888 | >60 | May | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89300491 | 2023-04-28 | WMS application unavailable at Castle Donington and Ollerton DCs | Root cause behind the primary database server in the SP cluster going to an unreachable state? | Root Cause | Jafar Sadiq | Severity 1 cases have been raised with vendors HP and Redhat for further triage. Vendor HP advised that 3 out of 4 storage switches were offline, which were then replaced. Also, HP identified issues with the SFP in one of the ports on the storage switches, which was then replaced to bring up the storage switches. As the primary server continue to be unstable, the SFP in one of the ports on the server was replaced, after which the server came online. | Oracle DBA Support |  | NA | 2023-02-05 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 888 | >60 | May | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89300491 | 2023-04-28 | WMS application unavailable at Castle Donington and Ollerton DCs | When the primary server went unreachable, the services did not fail over automatically to the secondary server. Why was the automatic failover not enabled? | Solution & Recovery | Jafar Sadiq | After the tech stack upgrade, to test the high availability on the secondary server, the automatic failover was not enabled to prevent service disruption. This has now been enabled. | Database |  | NA | 28/04/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 888 | >60 | April | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89300491 | 2023-04-28 | WMS application unavailable at Castle Donington and Ollerton DCs | Perform regular patching and firmware upgrade on the database server to avoid any issues. | Problem avoidance | Jafar Sadiq | This has been addressed and the patching and firmare upgrade will be patched as per usual. | Database |  | NA | 28/04/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 888 | >60 | April | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89300491 | 2023-04-28 | WMS application unavailable at Castle Donington and Ollerton DCs | When the primary server went unreachable, the services did not fail over automatically to the secondary server. Why was the automatic failover not enabled? | Solution & Recovery | Jafar Sadiq | After the tech stack upgrade, to test the high availability on the secondary server, the automatic failover was not enabled to prevent service disruption. This has now been enabled. | Linux Spport |  | NA | 29/04/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 888 | >60 | April | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89300491 | 2023-04-28 | WMS application unavailable at Castle Donington and Ollerton DCs | Perform regular patching and firmware upgrade on the database server to avoid any issues. | Problem avoidance | Jafar Sadiq | This has been addressed and the patching and firmware upgrade will be patched as per usual. | Linux Support |  | NA | 29/04/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 888 | >60 | April | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89300491 | 2023-04-28 | WMS application unavailable at Castle Donington and Ollerton DCs | Update the DR document to perform the Donington DR testing from both app and infra end. | Solution & Recovery | Jafar Sadiq/Murali Nasapu | The document is currently being updates and will be validated at all levels before planning the DR testing. DR/Application recovery document updated for WMS applications. | WMS devops / Infra teams |  | NA | 28/06/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 888 | >60 | June | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89300491 | 2023-04-28 | WMS application unavailable at Castle Donington and Ollerton DCs | As the application is currently running without resilience, hypercare monitoring continues to be in place until the primary server issue is resolved and added back to the cluster. | Solution & Recovery | MIM, WMS, CDIT, NOC, Database and Linux | As agreed with the delivery heads, MIM, WMS, CDIT and the Infra teams will have regular catch up calls at 08:00 and 19:00 BST over the weekend for proactive updates on the service stability and progress on the issue triage with the vendors. | Multiple Owners |  | NA | 2023-02-05 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 888 | >60 | May | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89300491 | 2023-04-28 | WMS application unavailable at Castle Donington and Ollerton DCs | It was highlighted that the DR testing was not performed for Donington, this requires an outage to be agreed with the site. How can we expedite the testing to ensure resilience in case of any further issues. | Solution & Recovery | Murali Nasapu | It has been agreed to plan the DR testing properly in the upcoming outage at the site. ETA to be confirmed WMS DR testing completed as part of Tech stack upgrade in Aug 2022. Also Ollerton will be migrated to new WMS instance from Sep 2023 | WMS Devops |  | NA | 2023-04-07 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 888 | >60 | July | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89300491 | 2023-04-28 | WMS application unavailable at Castle Donington and Ollerton DCs | Once the primary server issue is resolved, test the automatic failover mechanism to ensure there is no service disruption in future occurrences. | Solution & Recovery | Murali Nasapu/ Jafar Sadiq | The primary server has now been added back to the cluster, the automatic failover will be planned in the next planned outage at the site as there will be a blip during the failover. | Castle Donington IT support/Linux Support |  | NA | 23/05/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 888 | >60 | May | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89300491 | 2023-04-28 | WMS application unavailable at Castle Donington and Ollerton DCs | Configure alerts to identify issues with the ports associated with the storage switches. | Problem identification & Alerting | Sailesh Kaluva | 10/07: A change has been raised to configure alerts to identify the issued ports associated with the storage switches under CRQ#184704 on 19/07 between 20:00 and 22:00. The feasibility of configuring an alert is being explored. This required network approval which has been received now. Storage team are looking at the feasibility and will implement it via a change. 26/06: Tech have received all the required approval and are awaiting a slot to configre the alerts via a change, possibly by 30/06. | Storage Support |  | NA | 24/07/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 888 | >60 | July | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89300491 | 2023-04-28 | WMS application unavailable at Castle Donington and Ollerton DCs | Review the HP contract to understand the level of support with the CISCO switches. | Supplier and support involvement | Sathish Selvapillai | This is completed | Linux Support |  | NA | 25/05/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 888 | >60 | May | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89300491 | 2023-04-28 | WMS application unavailable at Castle Donington and Ollerton DCs | Configure alerts to identify issues with the ports associated with a server. | Problem identification & Alerting | Sudalai Suresh | As the primary server went into an unreachable state, no alerts were triggered to highlight issues at server end. | Linux Support |  | NA | 2023-02-05 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 888 | >60 | May | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89300491 | 2023-04-28 | WMS application unavailable at Castle Donington and Ollerton DCs | By design, with one faulty SFP, the server should not have gone into “hung” state. Detailed root cause analysis on the faulty SFP bringing down the server. | Root Cause | Suresh Sudalai | Tech confirmed that in this setup OS disk also comes from storage end, normally that should be within server as local disk. As there are insufficient logs for that in OS level hence Redhat can't confirm anything why its went hung. As per Redhat, the issue occurred due to storage failure. | Linux team |  | NA | 20/06/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 888 | >60 | June | 2023 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89277635 | 2023-04-28 | Fatal erros on WMS hanging adapter service at Donington | Provide alternative access for SSI users to support both remotely and onsite | Solution & Recovery | Murali Srinivasan | Completed | Service lead - CD |  | NA | 28/04/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 888 | >60 | April | 2023 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89277635 | 2023-04-28 | Fatal erros on WMS hanging adapter service at Donington | To review existing SOP with regards to pre-conditions and add a task to clear all Inbound rails prior to the Outage and SSI to perform the clean-up service activity | Problem avoidance | Murali Srinivasan | Completed | Service lead - CD |  | NA | 2023-08-05 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 888 | >60 | May | 2023 | #VALUE!
Group Support | Finance | 89293860 | 2023-04-27 | COSTA purchase order interface was unavailable | The SAP release was extended by 60 mins due to some BW exception clearance activity? Why was this not done during the pre-requisite activity? What caused the exceptions? Is there a proper SOP for the housekeeping activity before a release? How can we prevent any further extended outage? | Root cause | Murali/Rhammya | After the completion of the regular pre-requisite activities, it was identified that some unknown/ghost transactions were still getting posted in the system every 15 mins, although there were no activities performed. The clearance of these transactions took longer which contributed to an hour extension of the SAP release. There are no logs/evidence identified to understand the source of these transactions, however, tech teams are in process of replicating the issue in the non-prod environment | SAP BW |  | NA | 27/04/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 889 | >60 | April | 2023 | #VALUE!
Group Support | Finance | 89293860 | 2023-04-27 | COSTA purchase order interface was unavailable | Communication from vendor SAP in case of any interim changes at their end, after the testing is completed in the Customer environment. | Business & IT Communication | Prabavathi Palani | There is an existing process where vendor SAP sends comms during any change at their end. However, it must be agreed with vendor SAP to communicate during any such interim changes, after testing is completed in the Customer environment. If required, testing needs to be performed again before implementing it in the Customer landscape. | SAP |  | NA | 22/05/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 889 | >60 | May | 2023 | #VALUE!
Group Support | Finance | 89293860 | 2023-04-27 | COSTA purchase order interface was unavailable | The last run of the PO processing job was at 08:30 and it was only at 14:00 when it was identified that the job was not running as expected. Can we configure an alert for a cyclic job not running properly? How can we improve the job release activity after a change? | Root cause | Prabavathi Palani | It has been confirmed that there was a miscommunication between the SAP release team and other relevant teams while releasing the jobs after the release. Actions have been agreed to address this. | SAP |  | NA | 27/04/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 889 | >60 | April | 2023 | #VALUE!
Group Support | Finance | 89293860 | 2023-04-27 | COSTA purchase order interface was unavailable | Is there an alert configured for PO interface being unavailable? If yes, was it triggered on 21/04 and what actions were taken? | Problem identification & Alerting | Prabavathi Palani | While deploying the package, we received an error message which highlighted the issue. In an ideal scenario, if there is no inflow of messages in the interface, an alert will be triggered. | SAP |  | NA | 27/04/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 889 | >60 | April | 2023 | #VALUE!
Group Support | Finance | 89293860 | 2023-04-27 | COSTA purchase order interface was unavailable | What is the cause behind the invalid characters in the SAP deployment package? Was it identified during testing? | Root cause | Prabavathi Palani | There were no issues observed in the testing phase. Due to an interim change made in the SAP cloud solution (by SAP Vendor) to exclude non-ASCII characters in the deployment package description, after the testing completed in the Customer environment. As the release package deployed in the Customer environment had a non-ASCII character, it caused the issue. | SAP |  | NA | 27/04/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 889 | >60 | April | 2023 | #VALUE!
Group Support | Finance | 89293860 | 2023-04-27 | COSTA purchase order interface was unavailable | Communication to be sent across the relevant stakeholders if an outage is extended than its normal completion time. | Business & IT Communication | Remko | This has been addressed. | SAP |  | NA | 27/04/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 889 | >60 | April | 2023 | #VALUE!
Group Support | Finance | 89293860 | 2023-04-27 | COSTA purchase order interface was unavailable | Ensure that enhanced hypercare is in place to monitor the critical jobs (cyclic/non-cyclic) after a release. | Business & IT Communication | Remko | To ensure that the jobs are released in a systemic and controlled way, actions have been agreed in action #9. In addition, the post deployment hypercare will be extended for an hour to monitor the critical jobs. | SAP |  | NA | 27/04/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 889 | >60 | April | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89293860 | 2023-04-27 | COSTA purchase order interface was unavailable | Extract a report highlighting all the jobs in a folder level with a “waiting for a resource” condition and any jobs with order date functionality. | Problem avoidance | Sathya Malyandi | To avoid any further miscommunication in the job release process after any release, an automated report will be generated from Control M to highlight any critical/non-critical jobs which has been missed in the process. This is currently in progress. This was performed via an outage on 20/06 | Control M team |  | NA | 23/06/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 889 | >60 | June | 2023 | #VALUE!
GTS | Operations | 89293860 | 2023-04-27 | COSTA purchase order interface was unavailable | A template has been designed to circulate across the support teams during a deployment activity or major incident to capture proper instructions for successful job executions | Problem avoidance | Suganya Chinnadurai | To ensure a systemic and seamless job release process, PCM will circulate a template across the relevant teams to capture additional information required to trigger a job at a folder, condition level etc. | BACC lead |  | NA | 23/05/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 889 | >60 | May | 2023 | #VALUE!
Supply Chain | Foods Supply Chain | 89287810 | 2023-04-25 | Foods final orders were duplicated for 60 suppliers | Review the incident handling and MIM engagement process for any issues related to Relex | Business & IT Communication | Joey/TEMs | 25/04: Agreed to invoke MIM process depending on the impact. | Relex |  | NA | 25/04/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 891 | >60 | April | 2023 | #VALUE!
Supply Chain | Foods Supply Chain | 89287810 | 2023-04-25 | Foods final orders were duplicated for 60 suppliers | Review the change deployment process in foods portfolio to ensure it covers testing scenario, impact/risk assessment and post change validation and hypercare | Problem avoidance | Joey/TEMs | 03/05: This has been discussed on the Foods weekly Release with all TPM’s… only on reviewing all the artifacts , change is approved to take it forward. | Relex |  | NA | 2023-03-05 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 891 | >60 | May | 2023 | #VALUE!
Commercial Trading | Foods Commercial Trading | 89287810 | 2023-04-25 | Foods final orders were duplicated for 60 suppliers | Configuring validation to ensure that number of products in FOA and Relex are in line | Problem avoidance | Pradeep Ratinam | 13/06: The control file changes has been deployed successfully 17/05: The development of the CTRL file(no of products in the cutover file) generation and the integration work to push the file from FOAL to CXM is ready. The CXM changes are in development. The changes will test and deployed by 30th May 09/05: Awaiting updates from the team | CXM |  | NA | 13/06/23 | Closed | NA | FSORP-20292 |  | Saloni | 2025-02-10 | 891 | >60 | June | 2023 | #VALUE!
Commercial Trading | Foods Commercial Trading | 89287810 | 2023-04-25 | Foods final orders were duplicated for 60 suppliers | Configure alerting to notify if there is any failure/discrepancy while processing the orders from Relex into CXM | Problem identification & Alerting | Pradeep Ratinam | 25/04:Alerting is being configured to notify if the Relex data is not loaded into CXM and additional dependency is being added on the CXM job so that the job will not process the data to downstream if the Relex orders are not loaded in to CXM. 03/05: The change has deployed | CXM |  | NA | 2023-03-05 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 891 | >60 | May | 2023 | #VALUE!
Commercial Trading | Foods Commercial Trading | 89287810 | 2023-04-25 | Foods final orders were duplicated for 60 suppliers | Overnight checks for FFO to check for more granular data | Problem avoidance | Promoth Kumar | 25/04: Agreed to ensure that enhanced hypercare will be put in place from day 1 after a change (end to end) | Relex |  | NA | 25/04/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 891 | >60 | April | 2023 | #VALUE!
Commercial Trading | Foods Commercial Trading | 89287810 | 2023-04-25 | Foods final orders were duplicated for 60 suppliers | Agree with all portfolios if the testing can be extended to existing consumers for their critical interfaces after a change | Problem avoidance | Promoth Kumar | 03/05: This action depends on the complexity of the change , and business critically of the application / downstream system impacted…. Impact assessment to be done , testing scope can be defined based on the above.. This has been communicated within Foods portfolio to follow the above process for any changes. | Relex |  | NA | 2023-03-05 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 891 | >60 | May | 2023 | #VALUE!
Commercial Trading | Foods Commercial Trading | 89287810 | 2023-04-25 | Foods final orders were duplicated for 60 suppliers | Why was the issue not identified while testing this change? | Problem avoidance | Promoth Kumar | 25/04: The change was tested end to end specific to the FOA to DS. Hence action 4 has been agreed to extend the testing for existing consumers | Relex |  | NA | 25/04/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 891 | >60 | April | 2023 | #VALUE!
GTS | Enterprise Integration | 89287810 | 2023-04-25 | Foods final orders were duplicated for 60 suppliers | Review the change deployment process in middleware system to ensure that peer review process is adhered. | Problem avoidance | Rajasekar Subramanian | 25/04: Agreed on the call that the peer review process will be adhered to, and this will be re-educated to the team. | MQFTE |  | NA | 25/04/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 891 | >60 | April | 2023 | #VALUE!
GTS | Enterprise Integration | 89287810 | 2023-04-25 | Foods final orders were duplicated for 60 suppliers | Review the rationale of the CICD deployment process to see if this remain the most suitable method | Problem avoidance | Rajasekar Subramanian | 16/05:For MQFTE monitor based deployments(affected pattern in this case), CICD currently has the feature to do only the incremental deployments(by comparing the production code base with the new changes and deploy the delta changes alone for all the applicable consumers) instead of deploying the whole interface. In the failure scenario, since the incorrect code base was taken for CXM, CICD treated this a change(expected) and hence CXM consumer was also considered for deployment along with DS consumer. In order to avoid these deployment issues caused to inadvertent changes as part of the change requirement , we are planning to create a ansible report feature which will give a snapshot of all the impacted components that will be deployed during the execution. The same report will be reviewed for any inadvertent changes before we sign off the change.(Same process already in place for ACE/IIB Integration) Analysis/design in progress to add this feature and will aim to deploy this change in CI/CD by end of this quarter and it being tracked under the back log id 05/05: Team is assessing the feasibility for alternative options of deployment in the CI CD framework | MQFTE |  | NA | 31/05/23 | Closed | NA | INTSVCS-50019 |  | Saloni | 2025-02-10 | 891 | >60 | May | 2023 | #VALUE!
Customer Channels | Platform & Store Ops | 89291867 | 2023-04-24 | CSSM did not receive the store information for 378 stores | Communication to be sent across the relevant teams - MQFTE, DS, CSSM and POS if there is a data issue in CLCAS. | Business & IT Communication | Anuhya Paruchuri | Detailed comms will be sent across the appropriate stakeholders to provide prior notification of any issues | Property team (ClCAS) |  | NA | 24/04/23 | Closed | NA |  |  | Saloni | 2025-02-10 | 892 | >60 | April | 2023 | #VALUE!
Customer Channels | Platform & Store Ops | 89291867 | 2023-04-24 | CSSM did not receive the store information for 378 stores | Feasibility of generating the store location file with .part extension instead of .xml. This will ensure complete generation of file before getting transferred into DS via MQFTE | Problem avoidance | Anuhya Paruchuri | As CLCAS is a legacy application and in the verge of getting migrated to a different solution, it is not possible to perform any amendment to the existing job configuration. A risk 1834 has been raised to address this | Property team (ClCAS) |  | NA | 2023-12-05 | Closed | NA |  |  | Saloni | 2025-02-10 | 892 | >60 | May | 2023 | #VALUE!
Customer Channels | Platform & Store Ops | 89291867 | 2023-04-24 | CSSM did not receive the store information for 378 stores | Root cause behind the partial file generation in CLCAS. | Root cause | Anuhya Paruchuri | The CLCAS job responsible for generating the store location file failed on 21/04 due to a file contention, as the file was picked up by the MQFTE file transfer job which runs every 1 min as per design. This resulted in the generation of the partial file which was then picked up by the Datastage job on 22/04 and thereby sent it to CSSM, causing the issue. | Property team (ClCAS) |  | NA | 24/04/23 | Closed | NA |  |  | Saloni | 2025-02-10 | 892 | >60 | April | 2023 | #VALUE!
Customer Channels | Platform & Store Ops | 89291867 | 2023-04-24 | CSSM did not receive the store information for 378 stores | Feasibiliy to develop a feature displaying a message honeywells to advise of a CSSM issue. | Business & IT Communication | Mahender Govardan | 12/07: A backlog CPEG-8292 has been raised to develop the feature displaying a message on the honeywells to advise of any central store issue 05/07: Nancy Ledsome the product owner will liaise with the team to raise a backlog. Have spoken to Valli the SL, however, no response Speak to the product owner, this will be tracked under a backlog. | Product Owner |  | NA | 2023-11-07 | Closed | NA | CPEG-8292 |  | Saloni | 2025-02-10 | 892 | >60 | July | 2023 | #VALUE!
GTS | Enterprise Integration | 89291867 | 2023-04-24 | CSSM did not receive the store information for 378 stores | Feasibility to fine tune the MQFTE transfer job configuration. | Solution & Recovery | Rajasekar Subramanian | It has been agreed to amend the MQFTE transfer job run from 1 min to 2 mins. In addition, the job will only transfer the file to DS when there is no change in the file size for two consecutive runs. Implemented under CRQ#175445 | Integration Services |  | NA | 2023-12-05 | Closed | NA |  |  | Saloni | 2025-02-10 | 892 | >60 | May | 2023 | #VALUE!
GTS | Enterprise Integration | 89291867 | 2023-04-24 | CSSM did not receive the store information for 378 stores | Validations to be performed in the datastage layer before processing the store location files from CLCAS via MQFTE. | Problem identification & Alerting | Sreeraj Cheriyil | Additional validations and alerting have been configured to validate store allocation file based of the file structure before processing them in datastage. | Integration Services |  | NA | 2023-12-05 | Closed | NA |  |  | Saloni | 2025-02-10 | 892 | >60 | May | 2023 | #VALUE!
GTS | Enterprise Integration | 89291867 | 2023-04-24 | CSSM did not receive the store information for 378 stores | CLCAS had sent the complete store file after the partial file was sent to DS, why was the complete file not picked up by Datastage? A SOP will be created detailing the steps to recover such issues in future | Solution & Recovery | Sreeraj Cheriyil | It has been confirmed that CLCAS had sent the complete store location file at 21:30, 21/04, however, it was a miss from Datastage to process the correct file into CSSM. This has been addressed and an additional validation will be performed for both 17:30 and 22:00 DS job runs to avoid this issue in future. See action #3. SOP created and validated | Integration Services |  | NA | 2023-12-05 | Closed | NA |  |  | Saloni | 2025-02-10 | 892 | >60 | May | 2023 | #VALUE!
Customer Channels | Platform & Store Ops | 89291867 | 2023-04-24 | CSSM did not receive the store information for 378 stores | Is it required to perform a daily full refresh in CSSM? Can delta refreshes be the alternative solution? | Problem avoidance | Velrajan Chelliah | Currently, delta refreshes are not possible due to technical complexities. However, options will be explored under a backlog 23/06: CSSM we only process full refresh.. As pert current CSSM architecture , we cant change to delta.. its required huge architectural change in CSSM | CSSM Devops |  | NA | 23/06/23 | Closed | NA |  |  | Saloni | 2025-02-10 | 892 | >60 | June | 2023 | #VALUE!
Customer Channels | Platform & Store Ops | 89291867 | 2023-04-24 | CSSM did not receive the store information for 378 stores | Additional checks to be performed in CSSM to validate the data volume before loading the data into the main database table. | Problem identification & Alerting | Velrajan Chelliah | Tech will perform data comparison based on the volume with the previous days to avoid any issues. Discussions are in progress to automate the process. This has been completed. | CSSM Devops |  | NA | 26/05/23 | Closed | NA |  |  | Saloni | 2025-02-10 | 892 | >60 | May | 2023 | #VALUE!
Customer Channels | Selling Experience | 89262468 | 2023-04-13 | Dine In, Bank and Help pages broken on website | There is a concern that with the new model of requesting cache clears (having to ask each owner of the page to clear cache), this could delay incident resolution time. Andy agreed to speak to Darren about this | Solution & Recovery | Andrew Redman | 14/08: Chris Peace updated that "Onyx Interim cache clear process established with trading, operations and front-end teams. Strategic approach to managing future caching requirements is in progress. (Cache clear management for Fesk / WCS unchanged – platform ops.)" and confirmed to close the action 09/08: Chris Peace to provide the backlog ids 02/08: Ramsankar discussed with Steve (Head off Engg for Selling) and is working based on his suggestion to identify owners for these pages with Chris P(STPM for one of the product groups) to get the backlogs created. 01/08: Ram is having a connect with Customer to discuss further on this today, will have updates in the afternoon 24/07: Call with Customer is scheduled today, based on the outcome - he will gather the specific product for the actions and share the concerned Jira IDs 18/07: ramsankar ramaswamy(TEM) will connect with the Customer and provide the specific Jira ID for action 10/07: Ramakrishnan chidambaram (TEM) confirmed that there is a call with Customer on these actions by 11th and will update post that and he will also check on the backlog/reference for this project 04/07: Followed up with Hisham on Project ID 21/06: TEM's have not shared details on this incident 08/06: Hisham told that TEM's will update latest on it soon 26/05: Waiting for project ID from Hisham 16/05: Elaine confirmed it is associated with "the move from FESK to Onyx". Waiting for reference to close the action 05/05: Elaine confirmed that most of the actions are all part of the on-going development with no end date and have asked if they are part of any project 29/04: Elaine to update early next week on the updates Following on from the PIR meeting there was a separate meeting about cache clears. The recommended solution to is to automate the process (content publish should auto invalidate the cache). This is an engineering task that needs to be built. Andy has spoken to Darren about this and further conversations required. In an emergency situation (e.g. Sev 1) , anyone who has Akamai access can be requested to clear cache across different page types | TLT |  | NA | 14/08/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 903 | >60 | August | 2023 | #VALUE!
Customer Channels | Selling Experience | 89262468 | 2023-04-13 | Dine In, Bank and Help pages broken on website | Ensure business teams know the correct processes and procedures for content creation: •Give a demo to the Site Merch team showing them how to use the components | Solution & Recovery | Durgesh Palaniswami | A demo has already been carried out for both Site Merch and Production teams. | Content Creation team |  | NA | 18/04/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 903 | >60 | April | 2023 | #VALUE!
Customer Channels | Selling Experience | 89262468 | 2023-04-13 | Dine In, Bank and Help pages broken on website | Regarding alerting, the method that is currently used is to track broken pages via New Relic. However, there was a concern that New Relic may not show the full scale of the problem because the pages were broken (but not showing an error). Need to look at all page types (WCS, FESK, Onyx) Requires further discussion | Problem identification & Alerting | Elaine Hawthorn | 14/08: Chris Peace updated that "Onyx and Contentful ‘content alerting provisions’ and fallbacks established. Contentful ‘cheat sheet’ created to help Front-End teams manage and respond to potential content issues/errors. Education and upskilling to front-end teams also provided." and confirmed to close the action 09/08: Chris Peace to provide the backlog ids 02/08: Ramsankar discussed with Steve (Head off Engg for Selling) and is working based on his suggestion to identify owners for these pages with Chris P(STPM for one of the product groups) to get the backlogs created. 01/08: Ram is having a connect with Customer to discuss further on this today, will have updates in the afternoon 24/07: Call with Customer is scheduled today, based on the outcome - he will gather the specific product for the actions and share the concerned Jira IDs 18/07: ramsankar ramaswamy(TEM) will connect with the Customer and provide the specific Jira ID for action 10/07: Ramakrishnan chidambaram (TEM) confirmed that there is a call with Customer on these actions by 11th and will update post that and he will also check on the backlog/reference for this project 04/07: Followed up with Hisham on Project ID 21/06: TEM's have not shared details on this incident 08/06: Hisham told that TEM's will update latest on it soon 26/05: Waiting for project ID from Hisham16/05: Elaine confirmed it is associated with "the move from FESK to Onyx". Waiting for reference to close the action 05/05: Elaine confirmed that most of the actions are all part of the on-going development with no end date and have asked if they are part of any project 29/04: Elaine to update early next week on the updates | Service lead |  | NA | 14/08/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 903 | >60 | August | 2023 | #VALUE!
Customer Channels | Selling Experience | 89262468 | 2023-04-13 | Dine In, Bank and Help pages broken on website | Given that 2 (code) changes were investigated before it was identified that the problem was caused by a content change, it was questioned how quickly can changes be traced. At the moment, with CAB, it is relatively easy to trace code changes but it is unclear what will happen with Onyx and continuous deployment. Need to understand how Onyx changes can be identified, is there anywhere that key changes can be viewed? | Solution & Recovery | Elaine Hawthorn | 14/08: Chris Peace updated that "Onyx and Contentful ‘content alerting provisions’ and fallbacks established. Contentful ‘cheat sheet’ created to help Front-End teams manage and respond to potential content issues/errors. Education and upskilling to front-end teams also provided." and confirmed to close the action 09/08: Chris Peace to provide the backlog ids 02/08: Ramsankar discussed with Steve (Head off Engg for Selling) and is working based on his suggestion to identify owners for these pages with Chris P(STPM for one of the product groups) to get the backlogs created. 01/08: Ram is having a connect with Customer to discuss further on this today, will have updates in the afternoon 24/07: Call with Customer is scheduled today, based on the outcome - he will gather the specific product for the actions and share the concerned Jira IDs 18/07: ramsankar ramaswamy(TEM) will connect with the Customer and provide the specific Jira ID for action 10/07: Ramakrishnan chidambaram (TEM) confirmed that there is a call with Customer on these actions by 11th and will update post that and he will also check on the backlog/reference for this project 04/07: Followed up with Hisham on Project ID 21/06: TEM's have not shared details on this incident 08/06: Hisham told that TEM's will update latest on it soon 26/05: Waiting for project ID from Hisham16/05: Elaine confirmed it is associated with "the move from FESK to Onyx". Waiting for reference to close the action 05/05: Elaine confirmed that most of the actions are all part of the on-going development with no end date and have asked if they are part of any project 29/04: Elaine to update early next week on the updates | Service lead |  | NA | 14/08/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 903 | >60 | August | 2023 | #VALUE!
Customer Channels | Selling Experience | 89262468 | 2023-04-13 | Dine In, Bank and Help pages broken on website | Given that it appears relatively easy to break content via user error, we need to ensure that there are robust measures in place within Contentful, it should not be possible to put in content that breaks things. | Problem avoidance | Elaine Hawthorn | 13/06: This has already been addressed in PIR64150- INC89207562 – Sev 2 Customer.com Onyx is down impacting Home Page, some PLPs and PDPs . Fall back was implemented. The action was : “Error handling within Onyx needs to be improved. Users should be able to make content changes without breaking the application e.g. introducing fall back content if any content is missing etc, graceful handing of errors” 26/05: Waiting for project ID from Hisham 16/05: Elaine confirmed it is associated with "the move from FESK to Onyx". Waiting for reference to close the action 05/05: Elaine confirmed that most of the actions are all part of the on-going development with no end date and have asked if they are part of any project 29/04: Elaine to update early next week on the updates This has already been addressed in PIR64150- INC89207562 – Sev 2 Customer.com Onyx is down impacting Home Page, some PLPs and PDPs The action was : “Error handling within Onyx needs to be improved. Users should be able to make content changes without breaking the application e.g. introducing fall back content if any content is missing etc, graceful handing of errors” | Service lead |  | NA | 13/06/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 903 | >60 | June | 2023 | #VALUE!
Customer Channels | Selling Experience | 89262468 | 2023-04-13 | Dine In, Bank and Help pages broken on website | Template comms for stores to be defined | Business & IT Communication | Hisham Khalid & Laura Whittle | 4/5: Template preparation completed 29/04: Elaine to update early next week on the updates In progress | Service Lead |  | NA | 2023-04-05 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 903 | >60 | May | 2023 | #VALUE!
Customer Channels | Selling Experience | 89262468 | 2023-04-13 | Dine In, Bank and Help pages broken on website | We need to identify whether or not any additional pages should have a New Relic journey. Omniture will be used to identify key pages that may need NR journeys | Problem avoidance | Phoebe Wilson | 13/09: Aiden Watson confirmed that there are no more pages needed to added, hence closing 04/09: Teams are still working on identifying additional pages 29/08: Teams are working on identifying the pages 20/08: Followed up with Ramsankar on the status 14/08: Chris Peace working with Alice Hobbs and Selling front-end teams. 09/08: Chris Peace to provide the backlog ids 02/08: Ramsankar discussed with Steve (Head off Engg for Selling) and is working based on his suggestion to identify owners for these pages with Chris P(STPM for one of the product groups) to get the backlogs created. 01/08: Ram is having a connect with Customer to discuss further on this today, will have updates in the afternoon 24/07: Call with Customer is scheduled today, based on the outcome - he will gather the specific product for the actions and share the concerned Jira IDs 18/07: ramsankar ramaswamy(TEM) will connect with the Customer and provide the specific Jira ID for action 10/07: Ramakrishnan chidambaram (TEM) confirmed that there is a call with Customer on these actions by 11th and will update post that and he will also check on the backlog/reference for this project 04/07: Followed up with Hisham on Project ID 21/06: TEM's have not shared details on this incident 08/06: Hisham told that TEM's will update latest on it soon 26/05: Waiting for project ID from Hisham 16/05: Elaine confirmed it is associated with "the move from FESK to Onyx". Waiting for reference to close the action 05/05: Elaine confirmed that most of the actions are all part of the on-going development with no end date and have asked if they are part of any project 29/04: Elaine to update early next week on the updates This is in progress. Information is being collected from various teams | Content Creation team |  | NA | 13/09/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 903 | >60 | September | 2023 | #VALUE!
Customer Channels | Selling Experience | 89262468 | 2023-04-13 | Dine In, Bank and Help pages broken on website | Discussed having visibility of content changes. Process of tracking content changes within Contentful will be documented | Problem avoidance | Phoebe Wilson | 13/6:There is a Teams channel where release details are shared. A guide will be written detailing how to find all of the content for a release in the Contentful tool itself 26/05: Waiting for project ID from Hisham 16/05: Elaine confirmed it is associated with "the move from FESK to Onyx". Waiting for reference to close the action 05/05: Elaine confirmed that most of the actions are all part of the on-going development with no end date and have asked if they are part of any project 29/04: Elaine to update early next week on the updates There is a Teams channel where release details are shared. A guide will be written detailing how to find all of the content for a release in the Contentful tool itself | Content Creation team |  | NA | 13/06/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 903 | >60 | June | 2023 | #VALUE!
Customer Channels | Selling Experience | 89262468 | 2023-04-13 | Dine In, Bank and Help pages broken on website | Ensure business teams know the correct processes and procedures for content creation: •Within the Preview environment there will be a checklist to ensure that all page types have the relevant QA carried out e.g. WCS, FESK and Onyx pages. | Solution & Recovery | Phoebe Wilson | This will be added to the QA checklist (plus Contentful checklist) | Content Creation team |  | NA | 18/04/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 903 | >60 | April | 2023 | #VALUE!
Customer Channels | Selling Experience | 89262468 | 2023-04-13 | Dine In, Bank and Help pages broken on website | Ensure business teams know the correct processes and procedures for content creation: •Write a Standard Operating Procedure (SOP) for the Site Merchandising team detailing how to use the new form correctly. | Solution & Recovery | Phoebe Wilson | SOP is now documented and verified | Content Creation team |  | NA | 18/04/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 903 | >60 | April | 2023 | #VALUE!
Digital & Data | Digital & Data | 89270388 | 2023-04-13 | Delay to the EDW SWAT flow due to multiple Job failures | Check for any similar incident (if any) observed in the past to understand the root cause | Root cause | MS team/Unix team/EDW team | The root cause has identified and this action has been closed. | All |  | NA | 17/04/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 903 | >60 | April | 2023 | #VALUE!
GTS | Enterprise Integration | 89270388 | 2023-04-13 | Delay to the EDW SWAT flow due to multiple Job failures | Root cause behind the missing system folders and permission issues. | Root cause | Manivannan | The replay logs for 9th to 10th April was validated and confirmed that no deletion was performed in the master application server. After the missing files were restored, issue was identified due to lack of permission (Read/write/delete). The permission was enabled to fix the issue. | Middleware Admin |  | NA | 17/04/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 903 | >60 | April | 2023 | #VALUE!
GTS | Enterprise Integration | 89270388 | 2023-04-13 | Delay to the EDW SWAT flow due to multiple Job failures | There were no issues identified while validating the master nodes logs, checks to performed remaining node sessions to identify the root cause. | Root cause | Manivannan | This is action is no longer needed as we identified that RCA | Middleware Admin |  | NA | 17/04/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 903 | >60 | April | 2023 | #VALUE!
GTS | Enterprise Integration | 89270388 | 2023-04-13 | Delay to the EDW SWAT flow due to multiple Job failures | What caused the permission issue after the restoring the folder was recovery? | Solution & Recovery | Manivannan | 17/04: The folders with full permissions (777) were replaced by incorrect folders files and permission was correct for the folders to recover the issue. | Middleware team |  | NA | 17/04/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 903 | >60 | April | 2023 | #VALUE!
Digital & Data | Digital & Data | 89270388 | 2023-04-13 | Delay to the EDW SWAT flow due to multiple Job failures | How can we reduce the recovery time of the job failure going forward during such issues. | Solution & Recovery | Manivannan/Samik | It has been agreed to recover the jobs in parallel instead of recovering the jobs one by one depending on the issue scenario. | EDW Support/Middleware |  | NA | 13/04/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 903 | >60 | April | 2023 | #VALUE!
Digital & Data | Digital & Data | 89270388 | 2023-04-13 | Delay to the EDW SWAT flow due to multiple Job failures | Review whether any EDW housekeeping/ archival jobs have triggered the folder deletion on 9th and 10th April | Root cause | Samik | 17/04: While recovering a weekly job ‘EDWDFSP012’ failure on 10th April 2023 the parameter was set to archive the files at a directory level instead of archiving the specific folder to recover the job failure due to a human error had caused the issue. | EDW Support |  | NA | 17/04/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 903 | >60 | April | 2023 | #VALUE!
Digital & Data | Digital & Data | 89270388 | 2023-04-13 | Delay to the EDW SWAT flow due to multiple Job failures | Why was MIM engaged with a delay at 03:50, while the issue started on the previous day at 20:00? | Supplier and support involvement | Samik | Initially there were few job failures. MIM was engaged when the issue started impacting multiple jobs. | EDW Support |  | NA | 13/04/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 903 | >60 | April | 2023 | #VALUE!
Digital & Data | Digital & Data | 89270388 | 2023-04-13 | Delay to the EDW SWAT flow due to multiple Job failures | Explore the feasibility of configuring an alert whenever a folder gets deleted from the folder structure. | Problem identification & Alerting | Samik | the solution is not very feasible. Reason: There are multiple areas where job is designed to delete files/folder post retention period or post processing the current days data. Even the job caused the issue is designed to the same thing. The miss was that incorrect path was provided for deletion. | EDW Support |  | NA | 2023-02-04 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 903 | >60 | April | 2023 | #VALUE!
Digital & Data | Digital & Data | 89270388 | 2023-04-13 | Delay to the EDW SWAT flow due to multiple Job failures | The GML flow was projected to complete by 09:00, however it got completed by 10:34 with a delay. Why there was a discrepancy in the projection? | Solution & Recovery | Samik | The source directory was created as a file while recovering the issue. It took time to rectify this issue and thereby reprocessing the file. It has been agreed to be vigilant while recovering job failures hereafter. | EDW Support |  | NA | 17/04/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 903 | >60 | April | 2023 | #VALUE!
Digital & Data | Digital & Data | 89270388 | 2023-04-13 | Delay to the EDW SWAT flow due to multiple Job failures | How do we improve the communication sent to the impacted downstream and business stakeholders? | Business & IT Communication | Samik | Team has been edcuated on the communication process and it is agreed on the process as well | EDW Support |  | NA | 24/04/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 903 | >60 | April | 2023 | #VALUE!
Digital & Data | Digital & Data | 89270388 | 2023-04-13 | Delay to the EDW SWAT flow due to multiple Job failures | Create a SOP to recover the job failure ‘EDWDFSP012’ | Solution & Recovery | Samik | 17/04: The existing SOP has been updated with the latest Scenario. | EDW Support |  | NA | 17/04/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 903 | >60 | April | 2023 | #VALUE!
Digital & Data | Digital & Data | 89270388 | 2023-04-13 | Delay to the EDW SWAT flow due to multiple Job failures | The failed jobs need to be re-run via Control-M instead of rerunning them manually to avoid manual errors. | Solution & Recovery | Samik | 17/04: Agreed on the call that the job failures will be recovered via Control-M and no manual re-run of the jobs will be performed going forward. The entire has been instructed to strictly adhere the job failure recovery process via Control-M | EDW Support |  | NA | 17/04/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 903 | >60 | April | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89270388 | 2023-04-13 | Delay to the EDW SWAT flow due to multiple Job failures | Checks to be performed on the application server to identify any delete/remove command execution. | Root cause | Suresh Sudalai | Sample path details has been shared by Samik/EDW team to Linux. | Linux/Unix |  | NA | 17/04/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 903 | >60 | April | 2023 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89268516 | 2023-04-12 | Castle Donington DC users unable to print carrier labels intermittently | Review the software version of the A4 and Label printers across Castle Donington vs the impacted ones. | Solution & Recovery | Murali Srinivasan | The software Versoin of both the impacted and the non-impacted Printer remains the same. Thus conclused that software version is not the root cause for the issue | Service lead- CD |  | NA | 24/04/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 904 | >60 | April | 2023 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89268516 | 2023-04-12 | Castle Donington DC users unable to print carrier labels intermittently | What caused the few printers to stop working? Why was the issue specific to ground floor, while the first-floor printers were working fine? | Root cause | Mustafa Muzamil | The root cause for the printers to be affected in the Groundfloor only is ascertained due to printers in ground floor is connected to a old Non-support Switch. The switch has been rebooted on 18th april and it is added as a part of the Switch upgrade project. | Network |  | NA | 24/04/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 904 | >60 | April | 2023 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89268516 | 2023-04-12 | Castle Donington DC users unable to print carrier labels intermittently | Resilience - The majority of the devices (A4 printers, label printers and workstations) on the ground floor are connected to a single stack, is there a feasibility to distribute the connection by introducing multiple stacks? | Problem avoidance | Mustafa Muzamil | Having the Printers conencted to multiple Stack idea has been shared with the project team. AS this is a long term project, Project team has taken this action under considerations to be added to the LAN upgrade project. | Network |  | NA | 24/04/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 904 | >60 | April | 2023 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89268516 | 2023-04-12 | Castle Donington DC users unable to print carrier labels intermittently | Can alerting/health checks be introduced to proactively identify the accessibility of the printers? | Problem identification & Alerting | Rajesh Kumar Singrarajan | As part of hypercare monitoring, there is a polling feature enabled for the IP address of the impacted printers to trigger an alert in case the issue occurs again. This will now be extended to the workstations as a temporary solution until the switches are replaced. | Network |  | NA | 24/04/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 904 | >60 | April | 2023 | #VALUE!
Customer Channels | Selling Experience | 89249625 | 2023-04-11 | Payment settlement for Customer Your School Uniform website orders not processed | Do we have any reconciliation process to identify payment mismatch. If not should be implemented | Problem identification & Alerting | Jahian Kabir. | 14/06: there is already a process in place and any issue identified in reconciliation will be reported to stakeholders. 25/04: Awaiting further updates from Finance team. | Finance Team |  | NA | 14/06/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 905 | >60 | June | 2023 | #VALUE!
Customer Channels | Selling Experience | 89249625 | 2023-04-11 | Payment settlement for Customer Your School Uniform website orders not processed | Microsoft Dynamics 365 upgrades to be done is 3times in 18months. as per contract. | Problem avoidance | Arthi Suriyanarayanan | 03/05:Agreed with Visionet as per contract. Upgraded to latest version 10.32 on 16/4/2023. 02/05: Follow up made and awaiting update. The service owner and the team continues to follow up with the vendor vision net 25/04: We continue to follow up vision net on the RCA and other actions | Vision Net |  | NA | 2023-03-05 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 905 | >60 | May | 2023 | #VALUE!
Customer Channels | Selling Experience | 89249625 | 2023-04-11 | Payment settlement for Customer Your School Uniform website orders not processed | The settlement was not captured since 7th Feb but was identified only on 29th Feb. Why couldn’t we identify the settlement failures early? Or Why couldn’t we identify that there was no orders marked to settled status since 7th Feb? | Problem identification & Alerting | Arthi Suriyanarayanan | 03/05: : Ideally, the issue where cash-flow is not detected regularly should come under the purview of the finance team. As part of our daily checks, we checked whether our batch jobs are working fine, we have now enhanced the process to ensure that we check the orders status as well. 02/05: Follow up made and awaiting update. The service owner and the team continues to follow up with the vendor vision net 25/04: We continue to follow up vision net on the RCA and other actions | Vision Net |  | NA | 14/06/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 905 | >60 | June | 2023 | #VALUE!
Customer Channels | Selling Experience | 89249625 | 2023-04-11 | Payment settlement for Customer Your School Uniform website orders not processed | What are the criteria and outcome of daily health check? Can that be shared with – Colin, Greig, Hisham, Arthi, Andrew | Problem avoidance | Arthi Suriyanarayanan | 03/05: Weekly health check report will be shared by Visionet to Customer. 02/05: Follow up made and awaiting update. The service owner and the team continues to follow up with the vendor vision net 25/04: We continue to follow up vision net on the RCA and other actions | Vision Net |  | NA | 14/06/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 905 | >60 | June | 2023 | #VALUE!
Customer Channels | Selling Experience | 89249625 | 2023-04-11 | Payment settlement for Customer Your School Uniform website orders not processed | Root cause for Payment Type field having empty value from 7th of Feb | Root cause | Arthi Suriyanarayanan | 02/05:The root cause has to come from Microsoft given it’s a system bug. If this is a mandatory and a pivotal field, the system should not allow the form to be saved without a value in it. The actions are closed as agreed with service manager 25/04: We continue to follow up vision net on the RCA and other actions | Vision Net |  | NA | 14/06/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 905 | >60 | June | 2023 | #VALUE!
Customer Channels | Selling Experience | 89249625 | 2023-04-11 | Payment settlement for Customer Your School Uniform website orders not processed | General review of application for peak readiness | Problem avoidance | Colin, Arthi | 02/05: Actions have been agreed to reviewed as part of peak readiness | Service Owner |  | NA | 2023-02-05 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 905 | >60 | May | 2023 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89241000 | 2023-03-28 | HHT connectivity issues across Foods and C&H sites | Checklist to be created at WMS end to capture appropriate information required for further investigation during such issues | Problem identification & Alerting | Deepali Parekh | 14/04: Discussions are in progress to tweak certain attributes in the checklist to ensure appropriate and detailed information are captured during such issues. This has been completed | Service Lead |  | NA | 20/05/23 | Closed | NA |  |  | Saloni | 2025-02-10 | 919 | >60 | May | 2023 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89241000 | 2023-03-28 | HHT connectivity issues across Foods and C&H sites | Visibility on the HHT availability dashboard to understand the scale of impact | Impact analysis | Deeplai Parekh & Joey Ocansey | 14/04: Discussions are in progress to understand the fundamentals before providing visibility to the dashboard. There is no HHT Dashboard for the DCs so this actions is obsolete | Service Leads |  | NA | 20/05/23 | Closed | NA |  |  | Saloni | 2025-02-10 | 919 | >60 | May | 2023 | #VALUE!
Supply Chain | Foods Supply Chain | 89241000 | 2023-03-28 | HHT connectivity issues across Foods and C&H sites | Is there a feasibility to ensure respective Service Leads are updating the Customer stakeholders during DC issues to ensure accuracy of the issue and impact statement. | Business & IT Communication | Deeplai Parekh & Joey Ocansey | For C&H sites, it has been agreed that either Deepali or Martin will be accountable to send comms. For Foods sites, Saloni to speak to Joey once he is back from holidays to confirm if he will be accountable to send stakeholder comms during any days in the week. 20/04: Awaiting updates from Joey 30/04: This is under discussion. 28/05: As there is a oncall rota, we will have to follow the same for Foods DC call outs. | Service Leads |  | NA | 26/05/23 | Closed | NA |  |  | Saloni | 2025-02-10 | 919 | >60 | May | 2023 | #VALUE!
GTS | Digital Workplace Services | 89241000 | 2023-03-28 | HHT connectivity issues across Foods and C&H sites | There was a slight confusion while trying to understand the process of manually authenticating the CA service, which caused further delays to the resolution of the issue. Runbook to be created detailing the architecture of the service. | Solution & Recovery | MuthuNagappan Subramanian | Since this is the first occurrence of the issue, there was a confusion between the root CRL and subCA CRL, it has been agreed to create a SOP detailing the steps for timely issue identification. | Active Directory |  | NA | 2023-03-04 | Closed | NA |  |  | Saloni | 2025-02-10 | 919 | >60 | April | 2023 | #VALUE!
GTS | Digital Workplace Services | 89241000 | 2023-03-28 | HHT connectivity issues across Foods and C&H sites | At what time does the auto renewal of the CRL happen? Did we receive an alert indicating the auto renewal failure on 25/03? | Problem identification & Alerting | MuthuNagappan Subramanian | Auto renewal of the CRL happens every Friday at 18:00. An event id 911 has been created to notify during auto renewal failure. Tech is now working with tools team to enable an alert at the back of the event. 05/04: Alerting has been created, | Active Directory |  | NA | 2023-05-04 | Closed | NA |  |  | Saloni | 2025-02-10 | 919 | >60 | April | 2023 | #VALUE!
GTS | Digital Workplace Services | 89241000 | 2023-03-28 | HHT connectivity issues across Foods and C&H sites | Is there an alert in place to notify when the CA services goes into inactive state? If yes, did we receive that alert of 25/03? | Problem identification & Alerting | MuthuNagappan Subramanian | There is an existing alert to notify when the CA service is down, however in this case, the service was running, but went into a hung state. There is no feasibility to configure an alert for hung service due to design restrictions. This has been addressed i | Active Directory |  | NA | 28/03/23 | Closed | NA |  |  | Saloni | 2025-02-10 | 919 | >60 | March | 2023 | #VALUE!
GTS | Digital Workplace Services | 89241000 | 2023-03-28 | HHT connectivity issues across Foods and C&H sites | Devise a plan to reboot the CA service every 30 days to ensure stability. This will require manual intervention as every time the service is rebooted, a password needs to be keyed in to authenticate the service | Permanent Fix | MuthuNagappan Subramanian | A decision has been taken to perform monthly reboot of the CA service, once the team identified the interval upon monitoring the event id 911 which will trigger an alert on the auto renewal failure. | Active Directory |  | NA | 28/03/23 | Closed | NA |  |  | Saloni | 2025-02-10 | 919 | >60 | March | 2023 | #VALUE!
GTS | Digital Workplace Services | 89241000 | 2023-03-28 | HHT connectivity issues across Foods and C&H sites | What caused the windows certificate authentication service to go into hung state? | Root cause | MuthuNagappan Subramanian | It has now been confirmed that as the CA service was not rebooted/patched for the last 90 days due to issues with the CATE environment, it went into “hung” state. To address this, discussions are ongoing to perform monthly service reboot of the CA service. | Active Directory |  | NA | 28/03/23 | Closed | NA |  |  | Saloni | 2025-02-10 | 919 | >60 | March | 2023 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89241000 | 2023-03-28 | HHT connectivity issues across Foods and C&H sites | Improve the quality of the comms sent to the DCs during such issues detailing the issue (non-technical). Also, provide timely updates every 30 mins to the DC on the progress towards resolution. | Business & IT Communication | Nandakumar Sivalingam | The sites were communicated on the issue, however, with minimal information. Therefore, we have now advised WMS team to ensure updates are sent to the sites, every 30 mins with proper non-technical summary of the issue. MIM team and service leads to ensure that appropriate communication is being sent to the sites during a MIM call. | WMS Product team |  | NA | 28/03/23 | Closed | NA |  |  | Saloni | 2025-02-10 | 919 | >60 | March | 2023 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89241000 | 2023-03-28 | HHT connectivity issues across Foods and C&H sites | There were multiple sev1s reported by each DCs between 06:30 and 07:00. What caused the delay in MIM engagement? | Supplier and support involvement | Nandakumar Sivalingam | We have reviewed each incident during the PIR call, and it has been communicated that during any HHT issue, it takes some time to perform the initial checks at WMS end. We have agreed actions like SOP, checklist at WMS end to capture the necessary information for further triage. | WMS Product team |  | NA | 28/03/23 | Closed | NA |  |  | Saloni | 2025-02-10 | 919 | >60 | March | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89241000 | 2023-03-28 | HHT connectivity issues across Foods and C&H sites | SOP to be documented detailing end to end touch points during a HHT connectivity issue, ie, from WMS, network, OS, server, authentication etc | Problem avoidance | Nandakumar Sivalingam, Rajesh Kumar, Alexander Jiju Baldino, Jafar Sadiq, Ramakrishnan Adhiyaman | There should be separate SOP documents across each layer, and this needs to be validated by the SMEs. 14/04: This is a very detailed document being created by the SMEs, this needs validation. | TEM |  | NA | 2023-02-06 | Closed | NA |  |  | Saloni | 2025-02-10 | 919 | >60 | June | 2023 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89238115 | 2023-03-23 | Intermittent issues while accessing the SAP enterprise portal | Can alerting be introduced to proactively identify when the URL is inaccessible? | Problem identification & Alerting | Balaji Rajendran | There is no feasibility to configure an alert however, proactive communication will be sent across the support teams during future changes | Network |  | NA | 23/03/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 924 | >60 | March | 2023 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89238115 | 2023-03-23 | Intermittent issues while accessing the SAP enterprise portal | Did we observe the DNS resolution failure while testing the change in non-prod? What post checks were performed after implementing the change in production? | Problem avoidance | Balaji Rajendran | No issues were identified in non-prod testing. During the testing post checks confirmed no issues, as the application cache takes some time to get triggered. Going forward, as a part of validations, additional hypercare monitoring has been agreed to proactively identify any such issues. | Network |  | NA | 23/03/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 924 | >60 | March | 2023 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89238115 | 2023-03-23 | Intermittent issues while accessing the SAP enterprise portal | The change was deployed on 20/03, however why did the issue occur only on 23/03? | Problem avoidance | Balaji Rajendran | DNS cache refresh takes time to reflect therefore we did not encounter the issue with the existing cache before 23/03. To address this, it has been agreed to be on hypercare for next 24/48 hours after the change. | Network |  | NA | 23/03/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 924 | >60 | March | 2023 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89238115 | 2023-03-23 | Intermittent issues while accessing the SAP enterprise portal | Is the Runbook in place to resolve such issue at the earliest? Is it being updated often? | Solution & Recovery | Balaji Rajendran | 7/4: Updated the run book and have uploaded in the sharepoint The run book is already in place and it needs to be updated as and when such changes are deployed to a set of applications. | Network |  | NA | 2023-07-04 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 924 | >60 | April | 2023 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89238115 | 2023-03-23 | Intermittent issues while accessing the SAP enterprise portal | Determine the root cause behind the DNS resolution failure. | Root cause | Mohan Pachiyappan | RCA: After the Zscaler CName change for SAP BPM application, the user's authentication requests are getting processed via zscaler(But the expectation is that it should be processed via global protect), since the users are not mapped/provided access in zscaler, the connectivity is dropped at zscaler and the authentication is failed. | Network |  | NA | 25/04/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 924 | >60 | April | 2023 | #VALUE!
GTS | Digital Workplace Services | 89238115 | 2023-03-23 | Intermittent issues while accessing the SAP enterprise portal | After the change was reverted the URL’s were accessible in Google Chrome however, it was still inaccessible in Edge. What caused the DNS flush to not work in Edge browser? | Problem avoidance | Promode Gnanaguru | As per policy cache clear will happen after restarting the browser but during the issue few users required a manual Cache clear. WPT team has informed that only if they can replicate the issue they will be able to check on the issue. (Note: for only very few users it needed a manual intervention) | WPT |  | NA | 2023-07-04 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 924 | >60 | April | 2023 | #VALUE!
Customer Channels | Platform & Store Ops | 89228347 | 2023-03-22 | Some applications were inaccessible on store workstations. | Alerting to be introduced to identify any authentication errors/ events in Domain controller | Problem identification & Alerting | Farid Arab | There were no specific error/event that was observed in the domain controller. Hence, alerting is not feasible | Active Directory |  | NA | 22/03/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 925 | >60 | March | 2023 | #VALUE!
Customer Channels | Platform & Store Ops | 89228347 | 2023-03-22 | Some applications were inaccessible on store workstations. | What post implementation checks were performed? How can we improve the testing/validation to avoid the impact to production? | Problem avoidance | Farid Arab | Once the patching has been implemented in DEV and CATE, AD team will get approval from Infrastructure device platform and then apply in production. Once the patches are implemented in production, validation checks will be performed again. | Active Directory |  | NA | 23/03/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 925 | >60 | March | 2023 | #VALUE!
GTS | Digital Workplace Services | 89228347 | 2023-03-22 | Some applications were inaccessible on store workstations. | Changes need to be communicated to all the relevant stakeholder and impacted applications/services | Problem avoidance | Farid Arab | This has been agreed. | Active Directory |  | NA | 23/03/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 925 | >60 | March | 2023 | #VALUE!
GTS | Digital Workplace Services | 89228347 | 2023-03-22 | Some applications were inaccessible on store workstations. | Peer review to be performed during change implementation and reversion. | Problem avoidance | Farid Arab | The has been agreed until it has been automated | Active Directory |  | NA | 23/03/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 925 | >60 | March | 2023 | #VALUE!
GTS | Digital Workplace Services | 89228347 | 2023-03-22 | Some applications were inaccessible on store workstations. | Automate the patch deployment to domain controllers | Problem avoidance | Farid Arab | A backlog is already available to develop a script to deploy the patches automatically in Q1 | Active Directory |  | NA | 23/03/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 925 | >60 | March | 2023 | #VALUE!
GTS | Digital Workplace Services | 89228347 | 2023-03-22 | Some applications were inaccessible on store workstations. | Track the progress of changes that spans for many days. | Problem avoidance | Farid Arab | It has been agreed to keep the change worklog to be updated on the progress. | Active Directory |  | NA | 23/03/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 925 | >60 | March | 2023 | #VALUE!
GTS | Operations | 89228347 | 2023-03-22 | Some applications were inaccessible on store workstations. | Major incident management to team to review all the changes during the incident | Solution & Recovery | MIM | Change management dashboard is being built to review the changes | Service Management |  | NA | 23/03/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 925 | >60 | March | 2023 | #VALUE!
GTS | Digital Workplace Services | 89228347 | 2023-03-22 | Some applications were inaccessible on store workstations. | What is the plan for re-applying the reverted patches to the domain controllers? | Permanent Fix | Muthunagappan Subramaniam | 29/08: Patches were deployed on 25th and no issues observed till now, hence closing the action 21/08: Further patching to be done by end of the week 12/08: No issues reported and teams to get change approval for further implementation by 15th 07/08: May patch implemented for 1st Batch by 4th and is in monitoring for a week to proceed further. Once no issues are reported, this actions will be closed by 11th 01/08: May patch to be implemented between (02/08) and (04/08) 24/07: Due to POS incident 89449493 - Tills offline estate wide, patching has been postponed, ETA is yet to be aware 10/07: Patch will be scheduled to be deployed starting 18th July for 6 days 03/07: manikandan solaimalai has asked Shyam to complete within this week 23/6: Still AD team is waiting for Syam's approval to go ahead 12/06: Waiting for Syam's confirmation to move to prod 6/6: Patches have been applied to Customer stores Dev and Cate without any issues, waiting for update from Syam V 26/5:Escalated to Deepak 23/5:Scheduled a call on 24/5 to understand the plan for reverting the patch 16/05: Waiting for the plan to redploy 09/05: Patch is reverted in the CATE, waiting for plan for patch to be reapplied 6/5: team is still working on this 28/04: CATE environment had issues with the patches applied and Rolling back the patches in CATE Store Domain, waiting for approval from Cyber team 19/04: Call rescheduled to 24th 14/04: Patch deployed in Dev, but unable to test, For CATE deployment and testing call is scheduled on 18th AD to liaise with cybersecurity and Infra device platform to perform risk assessment and devise a plan for reapplying the patch. | Active Directory |  | NA | 29/08/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 925 | >60 | August | 2023 | #VALUE!
GTS | Operations | 89228347 | 2023-03-22 | Some applications were inaccessible on store workstations. | Re-educate the SD Teams to ensure that each incident is handled separately and revalidated before mapping as child incident | Impact analysis | Rehan/Jaya | SD Team was educated to ensure that each incident is handled separately and revalidated before mapping as child incident | Service Desk |  | NA | 2023-05-04 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 925 | >60 | April | 2023 | #VALUE!
Customer Channels | Platform & Store Ops | 89228347 | 2023-03-22 | Some applications were inaccessible on store workstations. | Alerting to be introduced to identify any authentication errors/ events in store proxy server | Problem identification & Alerting | Subhasish | 27/04: No, It is not possible as the proxy servers will have only logs. They were rather authentication request which is normal. It may be possible at the domain controller level. but, AD Team also confirmed that it is not feasible. Hence closing the action 14/04: Call rescheduled to 27th based on Shyam's availability 09/04:Have a call with Subhasish by 11th April on open action updates | Infrastructure device platform |  | NA | 28/04/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 925 | >60 | April | 2023 | #VALUE!
Customer Channels | Platform & Store Ops | 89228347 | 2023-03-22 | Some applications were inaccessible on store workstations. | Alerting to be introduced to identify any authentication errors/ events in workstations. | Problem identification & Alerting | Subhasish | Alerting is not feasible for this scenario as there is no specific error to configure an alert. | Infrastructure device platform |  | NA | 23/03/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 925 | >60 | March | 2023 | #VALUE!
Customer Channels | Platform & Store Ops | 89228347 | 2023-03-22 | Some applications were inaccessible on store workstations. | Create a SOP documenting the resolution steps to resolve issue in future. | Solution & Recovery | Subhasish | 10/07: SOP Document shared and closing the action based on it, post confirmation from Solaimalai, Manikandan 03/07: manikandan solaimalai has asked Shyam to complete within this week 23/6: Followed up on the ETA for the SOP 6/6: Escalated to Vijay Arunprasath 26/5:Escalated to Deepak 23/5:Scheduled a call on 24/5 to understand status on SOP and Runbook 16/5: Followed up on the runbook 4/5: Followed up for the run book 27/04: To share the draft run book by 4th May 14/04: Call rescheduled to 27th based on Shyam's availability 09/04:Have a call with Subhasish by 11th April on open action updates | Infrastructure device platform |  | NA | 2023-10-07 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 925 | >60 | July | 2023 | #VALUE!
Customer Channels | Platform & Store Ops | 89228347 | 2023-03-22 | Some applications were inaccessible on store workstations. | Create a run book to understand and triage the incident for similar issues in future. | Solution & Recovery | Subhasish | 10/07: SOP Document shared and closing the action based on it, post confirmation from Solaimalai, Manikandan 03/07: manikandan solaimalai has asked Shyam to complete within this week 23/6: Followed up on the ETA for the SOP 6/6: Escalated to Vijay Arunprasath 26/5:Escalated to Deepak 23/5:Scheduled a call on 24/5 to understand status on SOP and Runbook 4/5: Followed up for the run book 27/04: To share the draft run book by 4th May 14/04: Call rescheduled to 27th based on Shyam's availability 09/04:Have a call with Subhasish by 11th April on open action updates The latest architectural diagram is already available. However, creating a SOP to resolve the issue is being tracked as part of action 4 | Infrastructure device platform |  | NA | 2023-10-07 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 925 | >60 | July | 2023 | #VALUE!
Customer Channels | Platform & Store Ops | 89228347 | 2023-03-22 | Some applications were inaccessible on store workstations. | How do we identify the impacted applications without the stores reporting to us? | Impact analysis | Subhasish | 12/09: Based on the backlog ID RPOS-10047 shared by Subhasish, closing the action 04/09:Followed up with Subhasish on the progress 29/08: May patching completed on 25/08 and no issues reported, as domain controllers are in 2003 still we won't be able to setup any alerts. Exploring further options on this 21/08: Further patching to be done by end of the week 12/08: No issues reported and teams to get change approval for further implementation by 15th 07/08: May patch implemented for 1st Batch by 4th and is in monitoring for a week to proceed further 01/08: May patch to be implemented between (02/08) and (04/08) 24/07: Shyam suggested to check if we can setup alerts at the Domain Controller end with Justification and it is being discussed with AD Team 11/07: Have requested Syam to update on this action 03/07: manikandan solaimalai has asked Shyam to complete within this week 6/6: Escalated to Vijay Arunprasath 26/5:Escalated to Deepak 23/5:Scheduled a call on 24/5 to understand status on SOP and Runbook 16/5: Followed up on the runbook 4/5: Followed up for the run book 27/04: To share the draft run book by 4th May 14/04: Call rescheduled to 27th based on Shyam's availability 09/04:Have a call with Subhasish by 11th April on open action updates All the application using the authentication will be impacted. Feasibility of consolidating the impacted application is being explored | Infrastructure device platform |  | NA | 2023-12-09 | Closed | NA | RPOS-10047 | Cancelled | Saloni | 2025-02-10 | 925 | >60 | September | 2023 | #VALUE!
Customer Channels | Platform & Store Ops | 89228347 | 2023-03-22 | Some applications were inaccessible on store workstations. | Create an SOP for failing over the services from store proxy to central server. | Solution & Recovery | Subhasish | 10/07: SOP Document shared and closing the action based on it, post confirmation from Solaimalai, Manikandan 03/07: manikandan solaimalai has asked Shyam to complete within this week 23/6: Followed up on the ETA for the SOP 6/6: Escalated to Vijay Arunprasath 26/5:Escalated to Deepak 23/5:Scheduled a call on 24/5 to understand status on SOP and Runbook 16/5: Followed up on the runbook 4/5: Followed up for the run book 27/04: Shyam to share the SOP by 3rd May 14/04: Call rescheduled to 27th based on Shyam's availability 09/04:Have a call with Subhasish by 11th April on open action updates | Infrastructure device platform |  | NA | 2023-10-07 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 925 | >60 | July | 2023 | #VALUE!
Customer Channels | Platform & Store Ops | 89228347 | 2023-03-22 | Some applications were inaccessible on store workstations. | SD template to be reviewed to capture the details for store incidents | Impact analysis | Valli | 28/04: Valli had validated the SD templates 24/04: Valli to connect with SD Leads 14/04: Followed up with Valli on the status | Service Owner |  | NA | 28/04/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 925 | >60 | April | 2023 | #VALUE!
Customer Channels | Selling Experience | 89207562 | 2023-03-14 | Onyx is down impacting Home Page, some PLPs and PDPs | Rollback strategy for content changes to be established. There is no ‘out of the box’ way of rolling back content. However, in order to have a defined rollback point scheduled backups can be taken (number and timings TBC ) of content to ensure a defined rollback point. | Solution & Recovery | Antony Del Beato | Contentful does provide a process for rolling back individual content entries within Contentful. We also have a ticket (https://jira.marksandspencer.app/browse/OCP-350) to investigate performing large scale rollbacks (for entire releases with many content changes). Closing with a backlog | Content Creation team |  | NA | 14/04/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 933 | >60 | April | 2023 | #VALUE!
Customer Channels | Selling Experience | 89207562 | 2023-03-14 | Onyx is down impacting Home Page, some PLPs and PDPs | The incident was not caused by any issues with Contentful itself. However, as part of rolling out Contentful and establishing the Digital Content domain, the team will establish clear SLIs/SLOs, Observability and Alerting, including alerts for API outages, increased latency, increased error rates, etc | Problem identification & Alerting | Antony Del Beato | Raised during incident discussion but would not have prevented this incident. Retaining this action for visibility - Teams has agreed on the same | Content Creation team |  | NA | 14/04/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 933 | >60 | April | 2023 | #VALUE!
Customer Channels | Selling Experience | 89207562 | 2023-03-14 | Onyx is down impacting Home Page, some PLPs and PDPs | Process for making changes within Contentful to be reviewed e.g. include safeguards to prevent the unintentional release of draft changes into the master branch. Contentful does have some safeguards but want to move into workflows so that users | Problem avoidance | Antony Del Beato | Contentful "Workflows" relies on Customer moving to a new subscription plan - Chris Pearce has taken over the negotiations Also in the process of POC-ing an extension to Contentful's UI that could potentially be used to indicate to Contentful users when a release contains references to "draft" content. We still need to valid whether this is going to work to some degree, but the work has begun. | Content Creation team |  | NA | 14/04/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 933 | >60 | April | 2023 | #VALUE!
Customer Channels | Selling Experience | 89207562 | 2023-03-14 | Onyx is down impacting Home Page, some PLPs and PDPs | Alerting: · GraphQL alerts need to be changed. A ticket has been created with high priority so that if an issue occurs in New Relic, an alert will be triggered · Improve alerting on GraphQL mesh to highlight any issues, (This is the first link in the chain so issues need to be identified here first) | Problem identification & Alerting | Hao Dong | A ticket has been created with high priority so that if an issue occurs in New Relic, an alert will be triggered. And any similar issues will be captured on the link provided : https://github.com/DigitalInnovation/gql-mesh/issues/3079 | Content Creation team |  | NA | 14/04/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 933 | >60 | April | 2023 | #VALUE!
Customer Channels | Selling Experience | 89207562 | 2023-03-14 | Onyx is down impacting Home Page, some PLPs and PDPs | Onyx to create a fall-back scenario for Header and Footer. | Problem avoidance | James Cross | There is a fallback header and footer now in place. If the content from CMS is not formed correctly, the fallback will be used. | Onyx team |  | NA | 20/03/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 933 | >60 | March | 2023 | #VALUE!
Customer Channels | Selling Experience | 89207562 | 2023-03-14 | Onyx is down impacting Home Page, some PLPs and PDPs | Onyx page for unexpected errors to be made more customer friendly. The page that was displayed to customers was blank with the message ‘internal server error’ on it. The generic error page used in FESK should be used as a template e.g. “Sorry Something went wrong” with an appropriate Customer image (approved by the business) | Problem avoidance | James Cross | There is now a more friendly error page shown to the user in the event of application failure | Onyx team |  | NA | 20/03/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 933 | >60 | March | 2023 | #VALUE!
Customer Channels | Selling Experience | 89207562 | 2023-03-14 | Onyx is down impacting Home Page, some PLPs and PDPs | Error handling within Onyx needs to be improved. Users should be able to make content changes without breaking the application e.g. introducing fall back content if any content is missing etc, graceful handing of errors | Problem avoidance | James Cross | There is a fallback header and footer now in place. If the content from CMS is not formed correctly, the fallback will be used. | Content Creation team |  | NA | 14/04/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 933 | >60 | April | 2023 | #VALUE!
Group Support | Finance | 89209183 | 2023-03-14 | Connectivity issue between cloud applications and SAP | Alerting to be introduced to identify continuous and regular connectivity issues to notify the impacted consumers | Problem identification & Alerting | Dhanvanttri Parameswaran | 28/03: OSS note has been raised to get suggection from SAP on congifuring an alert for this authentication issue. This will be priortorised in Q1 backlogs. SPM-19306 has been raised to track the alerting configuration | SAP CPI |  | NA | 2023-12-04 | Closed | NA | SPM-19306 |  | Saloni | 2025-02-10 | 933 | >60 | April | 2023 | #VALUE!
Group Support | Finance | 89209183 | 2023-03-14 | Connectivity issue between cloud applications and SAP | Is resilience in place during such global issues? | Solution & Recovery | Dhanvanttri Parameswaran | 13/04: Availability zones (AZ) are single failure domains within a single geographical region and are separate physical locations with independent power, network, and cooling. Multiple AZs exist in one region and are connected with each other through a low-latency network. SAP BTP services run on this Multi-AZ concept of the underlying hyperscalers thereby offering High Availability. Hence, if there is an outage in one of the AZ’s, the service/application will self-heal and will continue to be serviced with the other AZs in the region. 11/04: SAP product team is awaiting for a slot with vendor SAP to discuss 03/04: A call is being with Product teams to discuss further on the resileince 27/03: Awaiting further updates. | SAP CPI |  | NA | 13/04/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 933 | >60 | April | 2023 | #VALUE!
Group Support | Finance | 89209183 | 2023-03-14 | Connectivity issue between cloud applications and SAP | There was a delay in notifying the impacted stakeholders of the connectivity issue. | Problem identification & Alerting | Jothineela Thiagarajan | Going forward SAP CPI team will notify all the consumers | SAP CPI |  | NA | 23/03/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 933 | >60 | March | 2023 | #VALUE!
Group Support | Finance | 89209183 | 2023-03-14 | Connectivity issue between cloud applications and SAP | What is the root cause of the issue? | Root cause | Jothineela Thiagarajan | 29/03: A intermediate certificate was not renewed before its expiry as the certificate expiration monitor had an issue to detect the expiry of the ceritificate 27/03: Awaiting further updates. | SAP Vendor |  | NA | 29/03/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 933 | >60 | March | 2023 | #VALUE!
Customer Channels | Service Experience | 89196956 | 2023-03-07 | Some stores reporting incorrect prices on tills | Discuss and review the best time to send a full cache to tills – ask for Flooid’s assistance with this. | Problem avoidance | Seeva Sivasurath / Manikandan Solaimalai | 13/03: Currently team is gathering the caching applying data and will share it with Flooid. POS Dev will raise a Jira and will share. Team will be gathering data(Q4.S5) and Flooid to tune it(Q1.S2) - RPOS - 7728 | POS team |  | NA | 13/03/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 940 | >60 | March | 2023 | #VALUE!
Customer Channels | Service Experience | 89196955 | 2023-03-06 | Some stores reporting incorrect prices on tills | Review the audience for the respective dashboards and alerting to ensure all relevant stakeholders are aware of issues in a timely manner | Business & IT Communication | Laura Whittle | Laura has completed the action and had acknowledged the same | Service Owner |  | NA | 24/03/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 941 | >60 | March | 2023 | #VALUE!
Customer Channels | Service Experience | 89196955 | 2023-03-06 | Some stores reporting incorrect prices on tills | Identify the root cause: Identify the entire end to end steps of renumbering tills and identify the manual steps which could cause human error – find the opportunities for automation | Problem avoidance | Problem Management to lead this call to understand the cause | 07/03: To complete DN sco roll-out by end of month, new support technicians were introduced as a part of team expansion for doing the till re-numbering. Due to a manual error/process gap the new tech person has renumbered the till twice which had resulted in corrupted cache. Usually the Till renumbering will be done by Dave and Andy. Going forward it would be only the senior team doing the till re-numbering and the SOP is updated. | Problem management team |  | NA | 2023-07-03 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 941 | >60 | March | 2023 | #VALUE!
Customer Channels | Service Experience | 89196955 | 2023-03-06 | Some stores reporting incorrect prices on tills | Visibility of current roll out plans to ensure everyone is aware of the process and validation checks. | Business & IT Communication | Seeva Sivasurath | 07/03: Going forward Stuart Stale will inform the relevant teams/will send out the plan if the update(renumbering) is planned for the day. Likewise, the hypercare will be planned accordingly. | POS team |  | NA | 2023-07-03 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 941 | >60 | March | 2023 | #VALUE!
Customer Channels | Service Experience | 89196955 | 2023-03-06 | Some stores reporting incorrect prices on tills | The cache corruption finding tool only identifies a max of 50 tills (due to performance) and then corrects the cache. Look at building alerts to identify and report all tills in the estate with corrupt cache – agree a threshold when an alert will be triggered for the number of tills with corrupt cache. | Problem identification & Alerting | Seeva Sivasurath | 13/03: Increase the number of cached in the morning to be more and will have alert to support team. POS Dev will raise a Jira and will share. IT is expected to completed in Q1.sprint2 - RPOS - 7726 | POS team |  | NA | 13/03/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 941 | >60 | March | 2023 | #VALUE!
Customer Channels | Service Experience | 89196955 | 2023-03-06 | Some stores reporting incorrect prices on tills | Post Implementation checks after any change to cache (delta & cache processing) and corrective actions on issues | Problem avoidance | Seeva Sivasurath | 13/03: Seeva confirmed that SIT team have started doing the post implementation checks | POS team |  | NA | 13/03/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 941 | >60 | March | 2023 | #VALUE!
Customer Channels | Service Experience | 89196955 | 2023-03-06 | Some stores reporting incorrect prices on tills | Interim – Review and recover cache issues in BAU checks, until automated script corrective action is completed. Prioritise the stores not picked up in the max 50 check – create and document the process | Problem avoidance | Suresh/Sindhu | 13/03: To be informed to Suresh/Sindhu that POS Dev team will share in Q1.S2, till then hypercare to be in place - RPOS - 7727 | POS team |  | NA | 13/03/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 941 | >60 | March | 2023 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89171650 | 2023-03-03 | Cheshunt-0097- Store Offline | Can we get the 4G router process slicker for Vodafone stores | Solution & Recovery | Kamal | 20/07: Backlog id - NPD-2634 has been created for the VF 4G setup build 17/07: VF 4G setup build is prioritized as part of peak preparation, however waiting for a backlog id to close the action 09/07: Network team is waiting for a spare Junior SRX router stock for VF 4G setup build and is expected to be completed by end of Q2 as the spare should come from SDWAN migrated stores. However he will raise a backlog id with which this can be closed 03/07:Followed up with Rajesh latest on configuration 26/06: PM has spoken to Rajesh to understand the progress on the availability of the SRX300 router configuration. 6/6: Laura has scheduled a call by 7th June to discuss on engaging DN process for vodafone 4G deployment 26/5: Followed up with Rajesh on status 16/5:Still working with Darren (NW Architect) on this 6/5: NOC team to provide further updates on these 24/04: Laura has call with Customer and NOC on 28th 14/04: Few more actions were added, update ETA 18/04 09/04: Rajesh to provide the latest update by 12th April Kamal & team are working with Darren Coughlan and the RIT team to handle the configuration of the SRX300 remotely and not needing it to come from the Hangar | Network |  | NA | 20/07/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 944 | >60 | July | 2023 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89171650 | 2023-03-03 | Cheshunt-0097- Store Offline | Why did the alert not happen at Vodafone? | Root cause | Kamal/ Rajesh/ VF | 16/5: VF updated that there was a equipment fault at their end due to which alert was not triggered 6/5: NOC team to provide further updates on these 24/04: Laura has call with Customer and NOC on 28th 14/04: Few more actions were added, update ETA 18/04 09/04: Rajesh to provide the latest update by 12th April It was identified that a historic event meant that Vodafone had muted their alerts for their ADVA’s going offline. This is the reason this wasn’t alerted to them. Rajesh is working with Vodafone to ensure these are enabled for the remaining stores left on the Vodafone network | Network |  | NA | 16/05/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 944 | >60 | May | 2023 | #VALUE!
Customer Channels | Platform & Store Ops | 89171650 | 2023-03-03 | Cheshunt-0097- Store Offline | After reviewing what was done to resolve the issue is there anything different we would ask a store to do to help recover the situation? | Problem avoidance | Laura | 6/6: The process has been reiterated to follow the store user manual 26/5: Followed up with Rajesh on status 16/5: safety compliance of the stores colleagues to be reiterated 6/5: NOC team to provide further updates on these 24/04: Laura has call with Customer and NOC on 28th Laura needs to check with the FHSO team to make sure what we can and cant ask the stores to do in regards to power and electrical issues. And Review with DN knowing what we know now to ensure the engineers are aware of additional actions to take | Service Owner |  | NA |  | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 944 | >60 | January | 1900 | #VALUE!
Customer Channels | Platform & Store Ops | 89171650 | 2023-03-03 | Cheshunt-0097- Store Offline | Can the NOC team have access to the City Call out stores list to enable them to be able to be proactive when contacting stores on their network being down | Permanent Fix | Laura | 27/06: Laura mentioned that POC mentioned on the Incident Text will be used to keep updated on the progress of the ticket. Until such a time where a portal/tool will be in place where stores can log, and receive updates on issues that have been identified in their store- which is in discovery phase at the moment 26/5: Followed up with Laura on the status 16/5: The call out list isnt the right contacts to have and so still working through when a store is identified as offline, what should NOC do proactively. ongoing 6/5: NOC team to provide further updates on these 24/04: Laura has call with Customer and NOC on 25th 09/04: Have reached out to Valli as Laura is OOO Laura needs to speak to City and Business Continuity on this | Service Owner |  | NA | 27/06/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 944 | >60 | June | 2023 | #VALUE!
Customer Channels | Platform & Store Ops | 89171650 | 2023-03-03 | Cheshunt-0097- Store Offline | Circuit breaker failure/health status monitoring. | Problem identification & Alerting | Laura/CityFM | 16/5: NOC/Laura will highlight this is monthly connect 6/5: NOC team to provide further updates on these 24/04: Laura has call with Customer and NOC on 28th We have Cityfm weekly connect, will check for feasibility | Service Owner |  | NA | 18/05/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 944 | >60 | May | 2023 | #VALUE!
Customer Channels | Platform & Store Ops | 89171650 | 2023-03-03 | Cheshunt-0097- Store Offline | The response to a network issue is 4 hours, however Dn work 7am until 10pm. Is there anything that can be done to review those support hours? | Supplier and support involvement | Laura/Dave T | 18/5: There is no Business appetite to change the 4 hour SLA from overnight as store colleagues wont be available anyway to allow the engineer in most times. SLA to remain the same. 6/5: NOC team to provide further updates on these 24/04: Laura has call with Customer and NOC on 28th 14/04: Valli has no updates, Laura will be back by 20th Apr 09/04: Have reached out to Valli as Laura is OOO Laura will speak to Dave Tomling about this as it will be a cost addition to the contract but it also relies on there being someone in the store to allow the engineer in so its not as straight forward as this | Service Owner |  | NA |  | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 944 | >60 | January | 1900 | #VALUE!
Customer Channels | Platform & Store Ops | 89171650 | 2023-03-03 | Cheshunt-0097- Store Offline | Is there anything more the engineer should have done on that first visit? | Root cause | Laura/DN | 16/5: When engaging DN Engg or store user at the site for the physical check, NOC will be additionally requesting them to share the picture of the Network comms racks 6/5: NOC team to provide further updates on these 24/04: Laura has call with Customer and NOC on 28th 14/04: Valli has no updates, Laura will be back by 20th Apr 09/04: Have reached out to Valli as Laura is OOO DN are reviewing what it was the engineer did on that first visit and working with the NOC team to understand what other additional checks/actions could we pick up going forward to prevent this issue happening again- for example taking the PDU area into account | Service Owner |  | NA |  | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 944 | >60 | January | 1900 | #VALUE!
Customer Channels | Platform & Store Ops | 89171650 | 2023-03-03 | Cheshunt-0097- Store Offline | Process to ensure that DN talk to NOC on arrivals at site and agree with NOC to leave the site. | Problem avoidance | Laura/DN | 18/5:DN should be talking to NOC when the reach site for any network issues. Where this isn't happening NOC should feedback to Valli/Laura to raise with DN 6/5: NOC team to provide further updates on these 24/04: Laura has call with Customer and NOC on 28th The process to be reviewed with DN to confirm the call outs. | Service Owner |  | NA | 18/05/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 944 | >60 | May | 2023 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89171650 | 2023-03-03 | Cheshunt-0097- Store Offline | Is there anything that can be done remotely to identify at what point the failure occurred? | Problem avoidance | NOC | 16/5: When engaging DN Engg or store user at the site for the physical check, NOC will be additionally requesting them to share the picture of the Network comms racks 6/5: NOC team to provide further updates on these 24/04: Laura has call with Customer and NOC on 28th 14/04: Few more actions were added, update ETA 18/04 09/04: Rajesh to provide the latest update by 12th April It was advised on the call there isn’t anything that can be done. Once we lose visibility of the stores network we are reliant on hands and eyes on the ground to identify why. However the above alert would help in understanding what triggered offline first and give us a clue as to where to start investigating | Network |  | NA | 16/05/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 944 | >60 | May | 2023 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89171650 | 2023-03-03 | Cheshunt-0097- Store Offline | Why was the 4G router process not invoked to bring the store back online whilst the RCA was being investigated? | Impact analysis | NOC | The 4G router process for Vodafone stores required not only a 4G cradle but also a configured SRX300 router. At the moment these can only be configured by the RIT Hangar which is only open Monday-Friday, and hence this wasn’t requested and asked by the NOC team | Network |  | NA | 2023-03-03 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 944 | >60 | March | 2023 | #VALUE!
Customer Channels | Platform & Store Ops | 89171650 | 2023-03-03 | Cheshunt-0097- Store Offline | OOB(out of Band) management solution for critical stores | Problem avoidance | NOC | 16/5: 4G/5G solution will be deployed once SDWan rollout completes 6/5: NOC team to provide further updates on these 24/04: Laura has call with Customer and NOC on 28th Need to check for the best practice and solutions | Network |  | NA | 16/05/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 944 | >60 | May | 2023 | #VALUE!
Customer Channels | Platform & Store Ops | 89197087 | 2023-03-02 | Stores unable to perform waste reduction | Alerting to identify the indexing issue at RI before it was highlighted by Customer? | Problem identification & Alerting | Beth Kirby/Retail Insight | 07/03: AN alert has been configured at RI end and it has been agreed to notify Customer during such events in future. | Retail Insight Vendor |  | NA | 2023-07-03 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 945 | >60 | March | 2023 | #VALUE!
Customer Channels | Platform & Store Ops | 89197087 | 2023-03-02 | Stores unable to perform waste reduction | What caused the table indexing and data sync issue in the RI DB? What was the fix implemented? | Root cause | Beth Kirby/Retail Insight | 07/03: The nightly database maintenance indexing and maintenance job at RI had been failing for a few days. After the failure was identified, RI reran the job at 10:30 and at approximately 11am the indexing job started working on the very large table used by the markdown solution. The index rebuilds were set to be done offline, which unfortunately caused a block and ultimately the timeouts experienced for markdown 16/03: We have asked RI for further details on the index rebuilds been set offline, awaiting updates. 30/03: PM has spoken to Valli to get the following questions answered by RI.: What caused the rebuilds to be set offline? WHat caused the database maintenance job to fail? Valli will now initiate an internal technical call with Customer product team and RI and provide updates 14/4: Valli to chase up with RI for an update. 25/04: This needs discussion with Valli 28/05: THis has been closed | Retail Insight |  | NA | 28/05/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 945 | >60 | May | 2023 | #VALUE!
Customer Channels | Platform & Store Ops | 89197087 | 2023-03-02 | Stores unable to perform waste reduction | Issue was identified by 11:00 and it was not communicated to stores until the incident was raised and MIM was engaged around 14:00. How can we improve the communication to stores? | Business & IT Communication | Valliammai Ramasamy | Tech have been made aware of the process and this will be followed hereafter. | Service Owner |  | NA | 2023-06-03 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 945 | >60 | March | 2023 | #VALUE!
Customer Channels | Platform & Store Ops | 89197087 | 2023-03-02 | Stores unable to perform waste reduction | Proactive communication to be sent across by RI to Customer if they come across such issues in future? | Problem avoidance | Valliammai Ramasamy | This action has been completed. | Service Owner |  | NA | 2023-09-03 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 945 | >60 | March | 2023 | #VALUE!
Customer Channels | Platform & Store Ops | 89197087 | 2023-03-02 | Stores unable to perform waste reduction | Is there an option to handle such timeout scenarios within the application to mitigate impact at Customer Infrastructure? | Problem avoidance | Velrajan Chelliah | Tech will check the feasibility if default price reduction can be used as a workaround. This will be picked up in the next sprint dated 04/04 under the backlog CSSM-9037 | CSSM Devops |  | NA | 2023-06-03 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 945 | >60 | March | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89193627 | 2023-02-28 | Unplanned Power Outage at Castle Donington DC | The ASM was unable to recognise the Quorum voting disk in both the app cluster and DB – therefore there is lack of resilience. Oracle team is working the vendor to resolve. | Solution & Recovery | Boopathi Palanisamy | 18/03: A Quorom disk was added to resolve the issue. Monitoring continues. 10/04: Monitoring confirmed that the issue was fixed. | Oracle Team |  | NA | 2023-10-04 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 947 | >60 | April | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89193627 | 2023-02-28 | Unplanned Power Outage at Castle Donington DC | SCS should be running on two app servers however it was running only on one server after the power outage. Exploring the feasibility of alerting to be setup and review health checks | Problem identification & Alerting | Jafar Sadiq | Ideally, there should be no performance issues with SCS running on one server, we need to understand the reason behind the performance issues with WCS and SSI IT. Awaiting risk id | Unix Support |  | NA | 20/04/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 947 | >60 | April | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89193627 | 2023-02-28 | Unplanned Power Outage at Castle Donington DC | WCS should be running on two app servers however it was running only on one server after the power outage | Problem avoidance | Jafar/Sally/Toyin | Assess whether we have enough capacaity and capability to run on one WCS server – what is the status of high availability testing? 20/03: Sally has advised that the discussion is ongoing and will be completed by EOD today. 20/04: As one of the interface was restarted to bring up the WCS application, it triggered the application to run on one server after the outage. Discussions to be held with SSI on the high availability testing of the application on one server. | C&H PM, Unix and SSI |  | NA | 2023-12-05 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 947 | >60 | May | 2023 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89193627 | 2023-02-28 | Unplanned Power Outage at Castle Donington DC | SSI team available for most of the time, however in some instance they were jumping in and out of the calls | Supplier and support involvement | Marie Hicks/Toyin | Agree with SSI for continuous availability in MIM calls for Sev 1 incidents. Can this be improved for future incidents. Marie to have discussion with Toyin and feedback. 30/04: Awaiting updates from Murali Nasapu. Considering the number of incidents at Donington, it is taking time. 09/05: We plan to make an addendum to the SSI contract to ensure we have clarity on ownership of support. Completed | SSI Vendor |  | NA | 26/06/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 947 | >60 | June | 2023 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89193627 | 2023-02-28 | Unplanned Power Outage at Castle Donington DC | UPS supplies to the servers expected to last for few hours, however lasted for appx 30 to 45 mins | Root cause | Mark Davies | UPS maintenance carried out and showing 2 hours – we need to assess if the draw on power is more than expected and is this the reason it lasted for a much shorter period? Is it fit for purpose – provide clarity on ownership. 10/04: On the day the reading stated there was 2 hrs of battery life but it failed after 1hr 40. There is a plan to move servers from Stockley next year at which point the central Infra team (Elizabeth Golder) will be looking into increasing UPS supply accordingly. | Castle Donington IT support |  | NA | 2023-10-04 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 947 | >60 | April | 2023 | #VALUE!
GTS | Operations | 89193627 | 2023-02-28 | Unplanned Power Outage at Castle Donington DC | Controls are unable to communicate with DFT PLCs – resolved after re-starting one of the interface | Solution & Recovery | MIM | Analyse (deep dive) what was actually done and mentioned relating specifically to this issue and then work with the product teams to work on the accurate ownership - Arrange a meeting with the stakeholders on the call on the night to clarify what actually happened. 4/04: A meeting was scheduled to discuss on the actions, we will get an update by Friday, 19/04. 20/04: A clean restart of the app servers was required to establish complete control on the DFT PLCs. As this is the first instance of an unplanned outage, it was belived to be feasible to go for a component restart instead of a complete outage required for the graceful restart of the app servers. A document has been built to capture the steps required in future. | MIM |  | NA | 20/04/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 947 | >60 | April | 2023 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89193627 | 2023-02-28 | Unplanned Power Outage at Castle Donington DC | Documentation required explaining steps to be followed for shutting down re-starting servers/services gracefully | Solution & Recovery | Murali Nasapu | Sri-balaji has the shutdown document as it was used on 02/03 - review this document to ensure it covers the end to end and all related teams.. 10/04: The TPM has reviewed and updated the actions. | WMS |  | NA | 2023-11-04 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 947 | >60 | April | 2023 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89193627 | 2023-02-28 | Unplanned Power Outage at Castle Donington DC | As part of recovery it was seen that on two switches one supervisor module remains down – this recovery needs to be planned | Solution & Recovery | Murali Srinivasan | 08/04: A document has been created for the document. | Castle Donington IT support |  | NA | 2023-10-04 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 947 | >60 | April | 2023 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89193627 | 2023-02-28 | Unplanned Power Outage at Castle Donington DC | Labelling of App servers was confusion | Solution & Recovery | Murali Srinivasan | In progress. 4/04: A meeting was scheduled to discuss on the actions, we will get an update by Friday, 14/04: CDIT verified all the labels, and corrected them | Castle Donington IT support |  | NA | 14/04/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 947 | >60 | April | 2023 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89193627 | 2023-02-28 | Unplanned Power Outage at Castle Donington DC | Root cause report pending from City FM | Root cause | NA | We won’t get any further than we already have as confirmed by Paul Robson (Project Engineer) | NA |  | NA | 2023-03-03 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 947 | >60 | March | 2023 | #VALUE!
GTS | Operations | 89193627 | 2023-02-28 | Unplanned Power Outage at Castle Donington DC | MIM engaged within 10 to 15 mins of the issue. Initial engagement and comms are good Recommendation is to have two people from Tech to support Sev1 for communication and technical guidance with clearly defined roles and responsibilities | Solution & Recovery | Rehan Siddiqui | Road show sev 0 process to relevant teams This action has been closed. | MIM |  | NA | 2023-05-04 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 947 | >60 | April | 2023 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89193627 | 2023-02-28 | Unplanned Power Outage at Castle Donington DC | Didn't get enough support from DFT team and this impacted the resolution time of hanging operations | Supplier and support involvement | Sally Woodward | Clarify the support responsibilities for the different aspects of the DFT infrastructure at CD 20/03: Sally has advised that the discussion is ongoing and will be completed by EOD today. 30/04: Awaiting updates from Murali Nasapu. Considering the number of incidents at Donington, it is taking time. 25/04: Currently no established relationship between Tech and DFT, build relations and clarify roles. Awaiting backlog id. 18/07: As the discussion to improve the agreement between Customer and DFT is taking longer. Murali Nasapu has agreed to include the action in the exisitng JIRA id. | C&H PM |  | NA | 18/07/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 947 | >60 | July | 2023 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89193627 | 2023-02-28 | Unplanned Power Outage at Castle Donington DC | Database support moved from SSI to Customer Tech support. Co-ordination between SSI, Customer and DFT (Duerkopp) is a challenge | Supplier and support involvement | Sally Woodward | Clarify ownership and clarity on who owns what. Review and agree on next steps to improve seamless support and communication. 20/03: Sally has advised that the discussion is ongoing and will be completed by April end 30/04: Awaiting updates from Murali Nasapu. Considering the number of incidents at Donington, it is taking time. 09/05: We plan to make an addendum to the SSI contract to ensure we have clarity on ownership of support. Completed | C&H PM |  | NA | 26/06/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 947 | >60 | June | 2023 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89193627 | 2023-02-28 | Unplanned Power Outage at Castle Donington DC | SSI first line support should have more in depth knowledge of Donington so that they have to rely less on their second line. | Supplier and support involvement | Sally Woodward/Toyin | Sally and Toyin to have a discussion to ensure SSI have the appropriate contextual understanding of Castle Donington 20/03: Sally has advised that the discussion is ongoing and will be completed by EOD today. 30/04: Awaiting updates from Murali Nasapu. Considering the number of incidents at Donington, it is taking time. Completed | C&H PM & SSI |  | NA | 26/06/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 947 | >60 | June | 2023 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89193627 | 2023-02-28 | Unplanned Power Outage at Castle Donington DC | WCS Business continuity plan/ARP document required covering all Castle Donington operations and applications | Solution & Recovery | Sally Woodward/Ugne Sukaityte | This document is required in the event in a total failure – use WMS DR document and start working on an overall WCS DR doc. 20/03: Sally has advised that the discussion is ongoing and will be completed by EOD today. 30/04: Awaiting updates from Murali Nasapu. Considering the number of incidents at Donington, it is taking time. Completed | C&H PM |  | NA | 26/06/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 947 | >60 | June | 2023 | #VALUE!
Group Support | HR | 89171700 | 2023-02-26 | Issues in viewing payslips and claiming additonal payments in Peoplesystem | We need to expedite the Colleague Services Tech Major Incident process so that issues like these can be managed and communicated in a timely manner. This issue started six days before the MIM process was invoked to assist in a timely resolution | Supplier and support involvement | Gary Edwards/ Kirsten Walker | Gary had informed the team on the incident management process (how quickly we can get the MIM process invoked) and he had acknowleged the same | HR |  | NA | 14/03/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 949 | >60 | March | 2023 | #VALUE!
Group Support | HR | 89171700 | 2023-02-26 | Issues in viewing payslips and claiming additonal payments in Peoplesystem | Why were some SD Worx URL’s missed out of having the work around applied by Product teams once we knew SD Worx would not be adapting | Solution & Recovery | Jason Stiff | Some older urls were mistakenly being used. Jasonn and team has notified the users of the correct URLs and they could then access them. | HR |  | NA | 14/03/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 949 | >60 | March | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89179544 | 2023-02-24 | Label printing issues at Castle Donington and Ollerton DCs | Introduce a VIP which will allow the server to connect to the working domain controller whenever any domain controller goes down | Permanent Fix | Jafar Sadiq | 15/05: Team has validated validated and confirmed that configuring VIP is not feasible as there are not via Loadbalancer VLAN. Team will raise a risk to mitiagte this. 02/05: Spoke to Elizabeth on this pending action for traction. 12/04: Escalated further to get traction on this action 28/03: Follow up has been made, awaiting further updates. 14/03: Unix team is laising with Network and AD team to configure the VIP for DNS acrros the unix estate. 13/03: The discussion is still in progress to device a plan to configure VIP. 24/02: The feasibility is currently being discussed. Once the VIP has been configured, thorough testing will be performed. | Unix Support |  | NA | 15/05/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 951 | >60 | May | 2023 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89179544 | 2023-02-24 | Label printing issues at Castle Donington and Ollerton DCs | Configure alerting for Brands DC where there are no orders incoming for more than 15 mins. Tech is also working to configure additional alerts. | Problem identification & Alerting | Nandakumar Shivalingam | 09/03: The alerts have been configured in WMS for Brands DC 24/02: In progress | WMS |  | NA | 2023-09-03 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 951 | >60 | March | 2023 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89179544 | 2023-02-24 | Label printing issues at Castle Donington and Ollerton DCs | Thorncliffe had raised below log at 4.30 PM. What actions were taken for the log? There were no new orders in WMS for 2 hours - Did WMS receive an alert and manage the backlog and comms effectively? What checks were done at 4.30 pm and who was informed? Are the right people on the Incident DL? | Problem identification & Alerting | Nandakumar Shivalingam | 24/02: Multiple logs were raised for different issues. Alerts were received at Middleware at 15:30 indicating a connection issue with the WMS database. There were no alerts configured at WMS, hence there was a gap in resolving the issue. This has been addressed in the next action | WMS |  | NA | 24/02/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 951 | >60 | February | 2023 | #VALUE!
GTS | Digital Workplace Services | 89179544 | 2023-02-24 | Label printing issues at Castle Donington and Ollerton DCs | What caused the data replication issue in the domain controller? | Root cause | Ramakrishnan Adhiyaman | 13/03: Database was corrupted in one of the domain controller and hence the domain controller was rebuild to fix the issue. We are unable to indentify why the DB was corrupted. 24/02: case has been raised with Microsoft. | Active Directory Team |  | NA | 13/03/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 951 | >60 | March | 2023 | #VALUE!
GTS | Digital Workplace Services | 89179544 | 2023-02-24 | Label printing issues at Castle Donington and Ollerton DCs | It has been agreed to highlight in Teams Support channel during any issues observed in the domain controller or any maintenance activity performed hereafter for visibility and proactive notification. | Business & IT Communication | Ramakrishnan Adhiyaman/Farid Arab | 24/02: This has been agreed to been done going forward in the PIR call | Active Directory Team |  | NA | 24/02/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 951 | >60 | February | 2023 | #VALUE!
Group Support | Finance | 89160374 | 2023-02-15 | Delay to the GMOR critical batches | Communication between GMOR and RPA to provide information on the amended PO line-items with a breakdown of the POs with goods receipt information | Problem avoidance | Nithya Ponnusamy & Rhammya Somassoudirame | 13/04: number of GRed PO's to be <15K to avoid Overnight GMOR issues, it is taken care part of JIRA ID - RPA-77 31/03: This could take time as there are other priorities 27/03: Rhammya to escalate to Remko on this 21/3: Rhammya has escalated the RPA team to understand the status 3/3:Followed up with Rhammya on status 15/02: The feasibility to automate a report is currently being explored. | SAP BW & RPA |  | NA | 13/04/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 960 | >60 | April | 2023 | #VALUE!
C&H and Intl | C&H Commercial Trading | 89160374 | 2023-02-15 | Delay to the GMOR critical batches | Why was a change in delivery date performed for bulk number POs with goods receipt information? | Root cause | Rhammya Somassoudirame | 23/02: As per Business confirmation, the increase in Delivery date amendment for the Goods Receipted POs are due to the delivery of PO's beyond their delivery date. 20/02: SAP BW team is working with Business on this 15/02: Tech will liaise with colleagues to understand the reason behind bulk PO amendment | SAP BW team |  | NA | 23/02/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 960 | >60 | February | 2023 | #VALUE!
C&H and Intl | C&H Commercial Trading | 89160374 | 2023-02-15 | Delay to the GMOR critical batches | The average run time of the back posting job is 40 mins, the overrunning alert was triggered after 2 hours. Amend the configuration of the overrunning alert to 1 hour to facilitate early identification of the issue | Problem identification & Alerting | Rhammya Somassoudirame | 17/02: Alert configuration done 15/02: Team will analyse the statistics of the run times of the job and configure the alert accordingly. | SAP BW team |  | NA | 17/02/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 960 | >60 | February | 2023 | #VALUE!
C&H and Intl | C&H Commercial Trading | 89160374 | 2023-02-15 | Delay to the GMOR critical batches | Analyse the job performance in terms of data processing and explore ways to improve the job performance. | Permanent fix | Rhammya Somassoudirame | 21/02: SAP-GMORBW-00056 is backlog id 20/02: SAP BW team to share a backlog id 15/2: This is a long-term action. Tech have identified ways and are currently analysing. Backlog to be created | SAP BW team |  | NA | 21/02/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 960 | >60 | February | 2023 | #VALUE!
C&H and Intl | C&H Commercial Trading | 89160374 | 2023-02-15 | Delay to the GMOR critical batches | Analyse the alerting configuration for all the GMOR jobs in the landscape | Problem identification & Alerting | Rhammya Somassoudirame | 23/02: Alert configurations revisit for all GMOR jobs is completed and done the changes in Control M as well 15/02: This action was performed before peak. Tech will analyse the usual run times of the jobs and redo the alert configurations. | SAP BW team |  | NA | 23/02/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 960 | >60 | February | 2023 | #VALUE!
Group Support | Finance | 89160374 | 2023-02-15 | Delay to the GMOR critical batches | In case of bulk PO amendments, it was agreed between GMOR and RPA to amend 40k PO line items daily. Feasibility of setting up a threshold of 5k POs with good receipt information to prevent job overrun. This will then be coordinated with the business. | Problem avoidance | Rhammya Somassoudirame & Sanjoy Dev | 13/04: number of GRed PO's to be <15K to avoid Overnight GMOR issues, it is taken care part of JIRA ID - RPA-77 31/03: Currently RPA team is manually validating the count daily, Feasibility is still being explored 27/03: Rhammya to escalate to Remko on this 13/3: Rhammya has escalated the RPA team on the status 3/3:Followed up with Rhammya on status 25/02: Expecting RPA team to revert by 27th or 28th 15/02: Tech will check the run time of the job with 5k records before setting up a threshold. | SAP BW & RPA |  | NA | 13/04/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 960 | >60 | April | 2023 | #VALUE!
C&H and Intl | C&H Commercial Trading | 89160374 | 2023-02-15 | Delay to the GMOR critical batches | SOP to document the steps involved in triaging the process and validated. | Solution & Recovery | Rhammya Somassoudirame & Sasikala | 6/3: Rhammya confirmed that they have got the SOP from SAP B&M 3/3:Followed up with Rhammya on status 17/02: SOP is being created involving 2 teams, they will share it with us by 22nd | SAP BW team & B&M team |  | NA | 2023-06-03 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 960 | >60 | March | 2023 | #VALUE!
Customer Channels | Customer Engagement | 89146854 | 2023-02-10 | Sparks unavailable for iOS App | Loggly to new relic migration to improve alerting | Problem identification & Alerting | Aadil Kasmani | 2/05: Divakar confirmed that is done 24/04: Aadil is still OOO, checking with Hisham 09/04: Aadil is OOO, 3/4: Followed up with Aadil on the status 3/3: Loggly contract ends by 1st April and within that it is expected to be completed | Service lead |  | NA | 2023-02-05 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 965 | >60 | May | 2023 | #VALUE!
Customer Channels | Customer Engagement | 89146854 | 2023-02-10 | Sparks unavailable for iOS App | Review of existing alerts/thresholds on iOS and Android app | Problem identification & Alerting | Greame/Tim | 2/3: Divakar confirmed that the alerting has been configured 24/02: Revised target date is by 3rd March 17/02: Service owner told that, he will get us further updates by 23rd | iOS & Android |  | NA | 2023-02-03 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 965 | >60 | March | 2023 | #VALUE!
Customer Channels | Customer Engagement | 89146854 | 2023-02-10 | Sparks unavailable for iOS App | Alerting to be implemented in iOS and Android app | Problem identification & Alerting | Greame/Tim | 2/3: Divakar confirmed that the alerting has been configured 24/02: Revised target date is by 3rd March 17/02: Service owner told that, he will get us further updates by 23rd | iOS & Android |  | NA | 2023-02-03 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 965 | >60 | March | 2023 | #VALUE!
Customer Channels | Customer Engagement | 89146854 | 2023-02-10 | Sparks unavailable for iOS App | Corporate services to have alerts for drop in traffic | Problem identification & Alerting | Manoj | 2/3: Divakar confirmed that it is deployed in prod 24/02: Alerts have been deployed in lower env. It will be implemented in prod on 27th Feb 17/02: Service owner told that, he will get us further updates by 23rd | Corporate services |  | NA | 2023-02-03 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 965 | >60 | March | 2023 | #VALUE!
Customer Channels | Customer Engagement | 89146854 | 2023-02-10 | Sparks unavailable for iOS App | Ensure that End to end testing coverage is being performed | Problem avoidance | Manoj | 10/02: This actions have been agreed to an ongoing one as a best practice to be followed for any change implementations | Corporate services |  | NA | 2023-10-02 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 965 | >60 | February | 2023 | #VALUE!
Customer Channels | Customer Engagement | 89146854 | 2023-02-10 | Sparks unavailable for iOS App | Align with upstream and downstream systems (communication and approval required from all relevant teams) | Problem avoidance | Manoj | 10/02: This actions have been agreed to an ongoing one as a best practice to be followed for any change implementations | Corporate services |  | NA | 2023-10-02 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 965 | >60 | February | 2023 | #VALUE!
Customer Channels | Customer Engagement | 89146854 | 2023-02-10 | Sparks unavailable for iOS App | Explore ways to Improve impact assessment | Impact analysis | Manoj | 10/02: This actions have been agreed to an ongoing one as a best practice to be followed for any change implementations | Corporate services |  | NA | 2023-10-02 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 965 | >60 | February | 2023 | #VALUE!
Group Support | HR | 89116617 | 2023-02-10 | Sickness absences entered into the system were missing. | To ensure end to end impact analysis of defect fixes | Problem avoidance | Avinash S | 27/02: George confirmed that SDWorx have intoduced all new processes to ensure changes are fully tested and that their other teams are aware in case of related incident. Closing action baseed on this | SDWorx |  | NA | 27/02/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 965 | >60 | February | 2023 | #VALUE!
Group Support | HR | 89116617 | 2023-02-10 | Sickness absences entered into the system were missing. | To engage with the RFC team / implementation during initial stages of investigation, to confirm the status of recent changes deployed to Customer production | Problem identification & Alerting | Avinash S | 27/02: George confirmed that SDWorx have intoduced all new processes to ensure changes are fully tested and that their other teams are aware in case of related incident. Closing action baseed on this | SDWorx |  | NA | 27/02/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 965 | >60 | February | 2023 | #VALUE!
Group Support | HR | 89116617 | 2023-02-10 | Sickness absences entered into the system were missing. | To ensure that system testing process and UAT for defect fixes are followed. | Problem avoidance | Kathryn Crook | 27/02: George confirmed that SDWorx have intoduced all new processes to ensure changes are fully tested and that their other teams are aware in case of related incident. Closing action baseed on this | SDWorx |  | NA | 27/02/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 965 | >60 | February | 2023 | #VALUE!
GTS | Operations | 89125592 | 2023-02-06 | Multiple network devices in Swindon data centre were unreachable | Improvement in VF SIM engagement process – Saloni to provide feedback as to the experience from this issue | Issue handling/Management | Clair Magee/Jan/MIM | 15/02: Awaiting updates 15/03: Saloni has spoken to Jan to ensure that the VF SIM is aware of the process end to end inorder to ensure no confusion during a Major Incident call. VF has confirmed to redo their Incident management training and has provided assurance that this will induce improvement | Vodafone/ MIM |  | NA | 15/03/23 | Closed | NA |  |  | Saloni | 2025-02-10 | 969 | >60 | March | 2023 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89125592 | 2023-02-06 | Multiple network devices in Swindon data centre were unreachable | Claire to advise why the STP2 change was done without a change record or notification to Customer and if it’s a miss how can we prevent any future oversights. | Problem identification & Alerting | Claire Magee | 15/02: Awaiting updates. 19/03: Vodafone wouldn’t raise a change request for removing cabling. However they have put a process in place where they will inform us if they are doing any decommissioning work in our area. | Vodafone |  | NA | 17/03/23 | Closed | NA |  |  | Saloni | 2025-02-10 | 969 | >60 | March | 2023 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89125592 | 2023-02-06 | Multiple network devices in Swindon data centre were unreachable | The Secondary vMotion path that was disabled on 29/01 was enabled on 01/01, however, issues were encountered. What is causing the issue with replication cluster once the Secondary vMotion path is enabled? Carry out troubleshoot to ascertain the cause – plan an agreed outage. | Solution & Recovery | Ganesh Athivilli | 15/02: Awaiting updates 17/03: Saloni had a call with Rajesh and team are still working on troubleshooting the cause. 25/03: An outage hs been agreed on 05/04. 05/04: The issue has been fixed. | Network |  | NA | 2023-10-04 | Closed | NA |  |  | Saloni | 2025-02-10 | 969 | >60 | April | 2023 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89125592 | 2023-02-06 | Multiple network devices in Swindon data centre were unreachable | There are four links between the VF Nexus and the Customer LAN. One link is bypassing the Palo Alto – This bypass needs to be addressed. Three remain V-Wires remain connected and need to be analysed and decide whether they need to be bypassed – discuss with Cyber Sec for any approval required. Carry out the investigation and then plan the actions. | Solution & Recovery | Ganesh Athivilli | 15/02: Awaiting updates 17/03: Saloni had a call with Rajesh and team are still working on troubleshooting the cause. 10/04: This is still being investigated.. 25/04: A call will be scheduled this week to close these actions 29/05: This will be tracked under a backlog in Q2. | Network |  | NA | 30/05/23 | Closed | NA |  |  | Saloni | 2025-02-10 | 969 | >60 | May | 2023 | #VALUE!
Supply Chain | Foods Supply Chain | 89125592 | 2023-02-06 | Multiple network devices in Swindon data centre were unreachable | Collate an impact assessment of the impact if Swindon is unreachable – we have agreed to start with Foods portfolio as a test | Impact analysis | Joey Ocansey/Boopathy/Melissa | 15/02: Awaiting updates 17/03: Saloni had a call with Joey and they are going to pick up in the next sprint, ie., April 2023. 28/05: This has been completed. | Foods Service lead |  | NA | 28/05/23 | Closed | NA |  |  | Saloni | 2025-02-10 | 969 | >60 | May | 2023 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89125592 | 2023-02-06 | Multiple network devices in Swindon data centre were unreachable | What can be done in future to ensure a quicker process to recover in case of human error e.g. labelling cables, unplugging cables but leaving them in place, taking photographs | Solution & Recovery | Mark Sellick | 15/02: Awaiting updates 17/03: Vodafone reiterated that if the process is followed there will not be issues. | Vodafone |  | NA | 17/03/23 | Closed |  |  |  | Saloni | 2025-02-10 | 969 | >60 | March | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89125592 | 2023-02-06 | Multiple network devices in Swindon data centre were unreachable | Customer/TCS to be informed on decommissioning work happening in the Swindon datacentre. This won’t have exact timings but will have details of where is being done | Problem identification & Alerting | Mark Sellick (DC Manager) / Claire Magee (Service Manager) | 15/02: Awaiting updates 19/03: Emails sent to requested people as per the new process | Vodafone |  | NA | 17/03/23 | Closed |  |  |  | Saloni | 2025-02-10 | 969 | >60 | March | 2023 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89125592 | 2023-02-06 | Multiple network devices in Swindon data centre were unreachable | Tickets currently need to be raised by circuit number. In this case it was all circuits in one datacentre. We shouldn’t have to raise multiple tickets for individual circuits. •Vodafone to look at whether we can raise one master ticket via Site ID and the rest be added from the CMDB •Vodafone to look at training sessions for Service Desk and SIM | Problem identification & Alerting | Nicola Adair Claire Magee Jan Goodson | 15/02: Awaiting updates 19/03: Tickets still have to be raised by circuit however if we raise one ticket Vodafone will raise the rest | Vodafone |  | NA | 17/03/23 | Closed |  | NA | N/A | Saloni | 2025-02-10 | 969 | >60 | March | 2023 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89125592 | 2023-02-06 | Multiple network devices in Swindon data centre were unreachable | Introduce a mechanism to trace any devices in the Swindon datacentre internally and to Customer. VF to analyse and create a document which will narrate every details in order to ensure the process is known to other parts of the Vodafone organisation | Problem identification & Alerting | Nicola Adair Claire Magee Jan Goodson | 15/02: Awaiting updates 19/03: Elizabeth continues to followup with VF further to provide an update. 05/04: After a teams conversation, a reminder email has been sent. Awaiting update. The alerts on the circuits were raised and linked to the major incident. | Vodafone |  | NA | 2023-02-05 | Closed |  | NA | N/A | Saloni | 2025-02-10 | 969 | >60 | May | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89125592 | 2023-02-06 | Multiple network devices in Swindon data centre were unreachable | There were issues when the SIM tried to raise a ticket to get Hands and Feet support in Swindon. The Glasgow service desk hadn’t heard of the datacentre. Customer have encountered problems in the past in getting this support. Vodafone to review the process and how it can be improved. This is vital if we are to run more production services from Swindon | Issue handling/Management | Nicola Adair Claire Magee Jan Goodson | 15/02: Awaiting updates 19/03: Still following up on this as the answer from the Vodafone RCA document is not good enough. 05/04: After a teams conversation, a reminder email has been sent. Awaiting update. 02/05: Vodafone retrained the help desk staff for raising hands and eyes support. | Vodafone |  | NA | 2023-02-05 | Closed |  | NA | N/A | Saloni | 2025-02-10 | 969 | >60 | May | 2023 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89125592 | 2023-02-06 | Multiple network devices in Swindon data centre were unreachable | Vodafone have confirmed that there are processes where cables should all be traced end to end during decommissioning. If there is even a suspicion on a cable still in use, the detail should be logged for review and those cables left in place. These processes weren’t followed. Why weren’t they followed? Can all engineers be re-trained and KT given? | Problem identification & Alerting | Nicola Adair Claire Magee Jan Goodson | 15/02: Awaiting updates 17/03: Vodafone has re-trained their engineers in the process | Vodafone |  | NA | 17/03/23 | Closed |  | NA | N/A | Saloni | 2025-02-10 | 969 | >60 | March | 2023 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89125592 | 2023-02-06 | Multiple network devices in Swindon data centre were unreachable | Update a brief synopsis of the impact of Swindon being unreachable in the AIM tool | Impact analysis | Rajesh/Kamal | 15/02: Awaiting updates 19/03: Rajesh confirmed that this is a time talking activity and will update by Friday. 27/03: PM has spoken to Elizabeth to collate the impact to be updated in the AIM tool. 05/04: After a teams conversation, a reminder email has been sent. Awaiting update. This is a long procedure. the impact analysis in underway. This has been completed | Network |  | NA | 20/05/23 | Closed |  | NA | N/A | Saloni | 2025-02-10 | 969 | >60 | May | 2023 | #VALUE!
C&H and Intl | C&H Commercial Trading | 89119732 | 2023-02-06 | Issues in processing the 3rd Party wholesale Brands PO’s | A log was raised on 14/1 to say BU ID 100 was causing an issue however the issue was not fixed until 01/02 – why was there so much confusion on the problem statement, impact and hence why was the resolution prolonged? Once product teams believe they have fixed an issue they need to get the agreement of the customer that the issue is fixed before they stand down. If the raiser is not available, then the raiser should identify a suitably able person to handover to. All attendees have been advised of the “technical manager” role that should be assigned by the service lead. | Solution & Recovery | All/Ashok | 28/03: The fix was delayed due to the complextity of the issue as there was no BU changes in past 10 years. Hence going forward any new BU to OT will be sent via the exisiting BU ID as the new BU ID creation to Open text will need a design change. The design change to OT is not considered as it in the decommission scope. 17/03: Awaiting further updates as the team is busy in recovering another issue 13/02: Yet to understand the delay in recovering the issue as the incident resolver is on annual leave. Once he is back, further discussion will made to understand the gaps and address the same going forward. 10/02: Followed up with the action owner, awaiting further updates | Brands Team |  | NA | 28/03/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 969 | >60 | March | 2023 | #VALUE!
C&H and Intl | C&H Commercial Trading | 89119732 | 2023-02-06 | Issues in processing the 3rd Party wholesale Brands PO’s | What was missing in the end to end testing for Brands and how can this gap be address for next time? Provide an overall statement of the gaps and how they need to be addressed. | Root cause | Ashok/Farooq/Editrack | 13/02: If any new BU is introduced in Customer systems, this needs to be validated whether any new BU ID needs to sent to Editrack or through the exisiting BU ID's which is successfully getting processed in Editrack. The BU changes needs to performed in middleware system to process the message from SAP to Editrack. 10/02: Followed up with the action owner, awaiting further updates | Brands Team |  | NA | 13/02/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 969 | >60 | February | 2023 | #VALUE!
Group Support | Finance | 89119732 | 2023-02-06 | Issues in processing the 3rd Party wholesale Brands PO’s | Why were the shadow tables being used for the end to end flow rather than the primary? If it was supposed to be the primary then why was this missed and how can it be prevented in future? | Root cause | Kathickeyan Mariappan | 24?04: Team is working implementing a oss note to avoid the table synch issue. A SAP-MOV-00232 back log has been being to configure a alert irrepesctive of the scenario 13/03: Team is working on configure an alerting if the shadow table and primary table are not in synch 10/02: Followed up with the action owner, awaiting further updates. Karthick is on annual, have to laisie with the TDM for the latest. | SAP B&M |  | NA | 24/04/23 | Closed | NA | SAP-MOV-00232 |  | Saloni | 2025-02-10 | 969 | >60 | April | 2023 | #VALUE!
C&H and Intl | C&H Commercial Trading | 89119732 | 2023-02-06 | Issues in processing the 3rd Party wholesale Brands PO’s | There is currently no Brands product team – this is a risk. Currently the teams are cross functional. | Solution & Recovery | Matthew Wood | 14/02: Risk '1810 ' has been raised and it will be accepted with the HoTPM 'Halford Fagon' 13/02: The C&H Product structure is under review, but until HoTPMs and CTO agree to change it then Brands will continue to run as a Programme and does not have any engineers assigned. Hence risk has been asked to raise and accept it with the respective HoTPMs. 10/02: Followed up with the action owner, awaiting further updates | Brands Team |  | NA | 14/02/23 | Closed | 1810 | NA | N/A | Saloni | 2025-02-10 | 969 | >60 | February | 2023 | #VALUE!
Infosec & Tech Risk | Infosec & Tech Risk | 89134640 | 2023-02-03 | Customer.com - Drop in mobile orders | InfoSec Operations will input every IP into the Azure Portal search as another way of checking whether or not the IP is part of Customer infrastructure | Problem avoidance | Nikolay Dachev | 13/02: The action has been completed, the IP addresses are now keyed in Azure portal | Info Security |  | NA | 13/02/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 972 | >60 | February | 2023 | #VALUE!
Infosec & Tech Risk | Infosec & Tech Risk | 89134640 | 2023-02-03 | Customer.com - Drop in mobile orders | InfoSec Operations to validate if IPs are part of Customer infrastructure. A list of IPs that should never be blocked will be maintained and referred to before blocking any Ips | Problem avoidance | Nikolay Dachev | 28/02: Documentation has been updated to reflect all additional checks while implementation is done(Azure search and a list of never-to-be-blocked IPs) 27/02: The actions is still being worked upon and it couldn't priortised because of other incidents. Nikolay is aiming to close this on 27/02, EOD 13/02: The action is still in progress and expected to completed for EOD, 14/02 | Info Security |  | NA | 28/02/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 972 | >60 | February | 2023 | #VALUE!
Customer Channels | Customer Engagement | 89134640 | 2023-02-03 | Customer.com - Drop in mobile orders | Support team to ensure that they review which URLs are causing the spike in 404s. | Solution & Recovery | Sumitro Chakravarty | 03/02: The agreed actions has been closed | Mobile Apps |  | NA | 2023-03-02 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 972 | >60 | February | 2023 | #VALUE!
Customer Channels | Customer Engagement | 89134640 | 2023-02-03 | Customer.com - Drop in mobile orders | Support team to ensure that they compare the volume of invalid hits to previous days/weeks to ascertain trend. They should not assume that if the 404 alert is triggered there is a problem. | Problem identification & Alerting | Sumitro Chakravarty | 03/02: Alerting has been configured | Mobile Apps |  | NA | 2023-03-02 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 972 | >60 | February | 2023 | #VALUE!
Commercial Trading | Foods Commercial Trading | 89116913 | 2023-02-01 | FIND application was inaccessible | Was there any alerting to identify the issue with the Network hardware PA4 ? If not can a alerting be configure? | Problem identification & Alerting | Joey | 11/04:This issue was detected by TraceOne internal monitoring and managed, TraceOne are reviewing their monitoring to ensure they have the right severities configured and will share details in subsequent service Reviews. TraceOne are working to address, as part of their internal continual improvement approach, the external communications to customers when issues of this kind occur. They have taken feedback from PO, SL and HoTs and are working on these improvements actively. 28/03: Awaiting updates from TraceOne | TraceOne |  | NA | 2023-11-05 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 974 | >60 | May | 2023 | #VALUE!
Commercial Trading | Foods Commercial Trading | 89116913 | 2023-02-01 | FIND application was inaccessible | Why the issue was not communicated to Customer? | Supplier and support involvement | Joey | 11/04: We have agreed with TraceOne to improve communication channels. a new comms DL is now being used for outage and incident comms. the dl will be updated every 1hr for P0/P1 scenarios 28/03: Awaiting updates from TraceOne | TraceOne |  | NA | 2023-12-04 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 974 | >60 | April | 2023 | #VALUE!
Commercial Trading | Foods Commercial Trading | 89116913 | 2023-02-01 | FIND application was inaccessible | How the impacted to SQL cluster can be mitigated in future? | Problem avoidance | Joey | 11/05: TraceOne architects and internal team reviewing any efficiencies that could be added to their backlog for future releases. Any progress or opportunities of these will be shared in Service Reviews with PO/HoTs /SL In the meantime, an updated internal SOP/Process efficiency has been introduced and shared with internal TraceOne teams. As a result of this, this issue can now be addressed at speed (expectation is within 15mins of alert - up to 30mins max) if it ever re-occurs 11/04: Follow up made, still awaiting an update. 28/03: Awaiting updates from TraceOne | TraceOne |  | NA | 2023-11-05 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 974 | >60 | May | 2023 | #VALUE!
GTS | Digital Workplace Services | 89118309 | 2023-02-01 | Colleagues were unable to access multiple applications hosted on Microsoft o365 and Azure services | Customer Tech to propose and develop backup facilities for the use of the Major Incident teams to be able to send text and mail comms in the event of a full Microsoft O365 outage | Issue handling/Management | David Bruce | David Bruce to discuss with Andy Neilson/Stephen Bolton. 02/02: David had a conversation with Stephen Bolton, Andy etc and Customer are not planning resilience for Teams etc going down as the cost would be astronomical. The likelihood of MS services going down for an extended period is slim according to Customer and it would impact more than just Teams so multiple impact across applications if MS Azure fails. Duane said this is only the second blip in all the years he has been with Customer. That said, Jane Gilmore has mentioned exploring Multi Cloud and I have left this with Andy to come back on. We could raise as a risk if this is not already in place. Awaiting risk id | WPT |  | NA | 2023-10-02 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 974 | >60 | February | 2023 | #VALUE!
GTS | Digital Workplace Services | 89118309 | 2023-02-01 | Colleagues were unable to access multiple applications hosted on Microsoft o365 and Azure services | In the even of a total O365 outage can Microsoft provide a level of service which had resilience e.g.: can Customer move to a multi-cloud service? | Solution & Recovery | David Bruce | David Bruce/Andy Neilson/Stephen Bolton/Jane Gilmour to discuss – however as this is a discussion about a change in the level of service provision, this action will be dealt with outside the remit of this PIR | WPT |  | NA | 2023-02-01 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 974 | >60 | January | 2023 | #VALUE!
Group Support | Finance | 89114796 | 2023-01-26 | The stock at Hemel to the international partners was not present in WMS | In the incident it was highlighted that the change cannot be reverted immediately as its having dependencies for another code in dev region for a Feb release. Was there no ‘reversion plan’ planned for the change? If not, why? | Problem avoidance | John Burrett | 26/01: Reversion plan would have been to use the PST track (mirrors production) to revert code however it has not been possible in the case due to the SAP upgrade. In future the entire change needs to be reviewed and the appropriate deployment method needs to be agreed and signed off by product owners before deployment. | International Team |  | NA | 26/01/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 980 | >60 | January | 2023 | #VALUE!
Group Support | Finance | 89114796 | 2023-01-26 | The stock at Hemel to the international partners was not present in WMS | Downstream systems were not aware of the change. What was the change process followed? Was all the approval secured and downstream systems were made aware of the change? How can this be mitigated in future? | Impact analysis | John Burrett | 26/01:As was deemed a 4 wall change to align ref numbers on Hemel crossdock SO's to that of Hemel Hub SO's nodownstream systems were informed. In future any change that could affect integration flows will be communicated and impact assessed with all potentially impacted consumers | International Team |  | NA | 26/01/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 980 | >60 | January | 2023 | #VALUE!
Group Support | Finance | 89114796 | 2023-01-26 | The stock at Hemel to the international partners was not present in WMS |  | Impact analysis | John Burrett | 26/01: No. Due to the field already being populated on order and OBD documents flowing to Hemel Hub and downstream consumers it was not seen as necessary to complete full SIT and it was agreed by the International product owner to have only the standard 4 wall testing. Going forward if an integration or interface is affected, the other teams will be involved and SIT will be done. John Burrett has had the discussion with relevant teams. | International Team |  | NA | 26/01/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 980 | >60 | January | 2023 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89114796 | 2023-01-26 | The stock at Hemel to the international partners was not present in WMS | The trailer dashboard alert was received on 23/01 what actions were taken after that? If the issue was picked and investigation was started why wasn’t the issue addressed on 23rd? | Solution & Recovery | Karthick Girichandramohan | 13/02: WMS team should have followed up with middleware team, however this was missed. Team has been advised to address this gap and enagage middleware when an issue is encoutered with trailers. 10/02: The details are still being gathered awaiting an update from the action owner. 26/01:The delay was due to investigation carried out via emails and simple retriggers – the team now knows to escalate and communicate 24/07 via leads etc. Karthick to share the 23/1 timeline and steps taken | WMS |  | NA | 13/02/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 980 | >60 | February | 2023 | #VALUE!
GTS | Enterprise Integration | 89114796 | 2023-01-26 | The stock at Hemel to the international partners was not present in WMS | A permanent fix: small logic change is required in MULE to only look for the 002 segment rather than look across the whole array. | Solution & Recovery | Viswesvaran Ramakrishnan | 14/02: The logic change has been implemeted on 14/02 under the CR#174045. 10/02: The testing is expected to completed by 11/02, if the testing is successfull team will plan deployment before end of WE 19,after securing all the approvals 02/02: Logic changes have been delivered to Testing team to perform test in SIT. Awaiting further updates on the ETA on testing completion and deployment plan. 26/01: In the meantime, hypercare is in place and Deepali has confirmed with the DC that it is working. | Intergration devops |  | NA | 14/02/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 980 | >60 | February | 2023 | #VALUE!
Group Support | Finance | 89110869 | 2023-01-25 | Intermittent performance issues in SAP after SAP upgrade | Ben Dewitt has agreed that no further actions are required as ECC is now end of life and will be replaced with S4 Hana which will be deployed after business cases have been approved. This system will be entirely new and as such the learnings from a SAP ECC release are redundant. | Problem avoidance | Ben Dewitt | How can we make sure that Upgrade outage duration is estimated better (if possible)? Comment: Based on the earlier exp of the upgrade we assumed that a 1-hour buffer would suffice as it would be faster in the production environment. Production has more capacity in terms of CPU and memory and we have already added additional parallel jobs compared to Pre-prod environment. Action: 1 hour buffer is not sufficient for an activity with this complexity, and additional contingency will be added for future significant SAP outages. COMPLETE Could the DB performance issue have been picked up in testing? Comment: since no further upgrades will be done in SAP ECC, the SAP S/HANA (new product, cloud based) will have new processes for automated testing and outage management. Action: None. COMPLETE For the 640K missing sales (caused by upgrade defect), could this have been picked up in testing? Comment: 21K sales messages were stuck in PO due upgrade defect around 3 decimals issue; issue rapidly fixed and data reprocessed by Sunday for SAP and EDW. Test Coverage: Team has tested a scenario with 2 digits and it was rounded off successfully through SAP PO successfully and scenarios were passed. However, the issue happens when more than 2 decimal digits are flown in for WH_SMITH through A9 interface and thus the issue wasn’t identified. Subset of scenario with more than 2 digits wasn’t covered due to risk based test approach. Action: To prevent this, a new scenario is added in Core Regression suite for considering more than two digits in amount field of A9 and WH_SMITH interfaces while posting in SAP PO. COMPLETE For the 15% late GMOR sales, how could this have been avoided during Batch Catchup after outage? Action: confirmed with Sales and BW teams that after an outage the GMOR sales jobs should only be started once all inbound sales transactsions have been processed; it is better for the reporting data to be late than incomplete. COMPLETE | SAP Product team |  | NA | 2023-03-02 | Closed | NA |  |  | Saloni | 2025-02-10 | 981 | >60 | February | 2023 | #VALUE!
Group Support | Finance | 89110869 | 2023-01-25 | Intermittent performance issues in SAP after SAP upgrade | SAP teams to provide a full statement of the events with descriptions of each factor that led to the delay | Root cause | Gopi Kishan | The Agreed outage was extended by two hours due to several reasons: BW queue clearing prerequisite(1 hour): delayed since messages kept flowing into queue whilst BW team were clearing the previous messages Action: Ensure inbound jobs are stopped and the messages in PO are all drained before commencing the BW queue clearance to avoid delays due to trickling in of additional messages. Queue Clearing Process agreed with team. COMPLETE During version upgrade in production, the SLT triggers had to be dropped and tables regenerated in new EHP8. This consumed additional efforts eating into the buffer time (1 hour). Couldn't plan this as it didn't happen during non-prod upgrades(shadow). Comment: As part of the upgrade process, as it's a live system upgrade process continuously try to create the triggers on the tables. As part of the pre-process activities, we have moved around 16K tables to the new tablespace to avoid the issue as we performed the same in our PT (DR system). But during the Downtime phase, it created more tables and created issues. For this, we had to move around 600 tables temporarily to the new tablespace created. After moving the tables to new tablespaces issue didn't occur. Action: For this version upgrade we already started the pre-req and pre-upgrade process very early. As Prod is a live system this impacted on the upgrade execution. In the future maybe we need to start the activities based on the PT runtime with an addition of 4 days to avoid delays and not impact on a production system. COMPLETE | SAP Product team |  | NA | 2023-03-02 | Closed | NA |  |  | Saloni | 2025-02-10 | 981 | >60 | February | 2023 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89110302 | 2023-01-25 | Castle Donington WCS unable to process retail orders. | WA Product team to check whether we should/could cease WMS telegraphs relating to orders which have already been confirmed as in progress from WCS. | Problem avoidance | Murali Nasapu | 10/2: Anand clarified that "No mods are allowed in dispatcher product, so the change cannot be achieved , and more over it is an user operational error which should be handled by process", closing based on this 8/2: Anand told that "Not possible as it requires change to Dispatcher product" and have asked if there is any plan to upgrade the dispatcher 6/2: Murali is OOO till 27th, reached out to Anand Asokan and he will discuss with team and update 2/2: Murali is reviewing with team and update us | WMS |  | NA | 2023-10-02 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 981 | >60 | February | 2023 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89110302 | 2023-01-25 | Castle Donington WCS unable to process retail orders. | What prevention can be put in place to avoid unplanned change in ordertargettype/modularity. | Problem avoidance | Murali Nasapu | 25/01: This actions depends on the RCA actions | WMS |  | NA | 25/01/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 981 | >60 | January | 2023 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89110302 | 2023-01-25 | Castle Donington WCS unable to process retail orders. | Was there any alerting to notify there was change in Order target type/modularity ? | Problem identification & Alerting | Murali Nasapu | 10/2: Anand reconfirmed that "No alert setup is possible as it is manual error", closing the action based on it 8/2: Anand told that "No alerting setup available" and have asked to setup the alerts 6/2: Murali is OOO till 27th, reached out to Anand Asokan and he will discuss with team and update 2/2: Murali is reviewing with team and update us 25/01: Alerting is not feasible as we do have planned modularity changes | WMS |  | NA | 2023-10-02 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 981 | >60 | February | 2023 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89110302 | 2023-01-25 | Castle Donington WCS unable to process retail orders. | How did the ‘ordertargettype’ field changed to boxed instead of hanging? | Root cause | Murali Nasapu | 10/2: Anand clarified that "Users having SOP for processing SKU modularity change , and we will re-iterate to follow the process, system wise restriction no possible", based on that closing the action. 8/2: Anand told that "It was due to SKU Modularity changed by ICQA user, following an erroneous request from Flow Room The request was after the route was released so broke the batching of hanging items." and have asked "how can this be avoided in future or is there any possibility to setup any restriction to avoid in future" 6/2: Murali is OOO till 27th, reached out to Anand Asokan and he will discuss with team and update 2/2: Murali is reviewing with team and update us 25/01: Replicate the issue and identify the reason | WMS |  | NA | 2023-10-02 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 981 | >60 | February | 2023 | #VALUE!
GTS | Operations | 89110302 | 2023-01-25 | Castle Donington WCS unable to process retail orders. | Incident management /Problem management roadshow to be arranged for C&H supply chain team | Supplier and support involvement | Rehan Siddiqui | 10/2: Rehan has scheduled roadshow by 22nd Feb, hence closing the action 3/2: Rehan will do and update | MIM |  | NA | 2023-10-02 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 981 | >60 | February | 2023 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89110302 | 2023-01-25 | Castle Donington WCS unable to process retail orders. | The investigation and recovery took longer time, what could have been done differently to fix the issue sooner | Solution & Recovery | Toyin-SSI | 25/01: Involve all the upstream (WMS) and downstream (WCS) systems in the flow for investigation. SOP | WCS |  | NA | 25/01/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 981 | >60 | January | 2023 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89110302 | 2023-01-25 | Castle Donington WCS unable to process retail orders. | Was there any alerting to identify that order batches are not getting created in WCS until DC engaged SSI? | Problem identification & Alerting | Toyin-SSI | 25/01:No alerting cannot be set up as team doesn’t monitor the application. | WCS |  | NA | 25/01/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 981 | >60 | January | 2023 | #VALUE!
Customer Channels | Service Experience | 89111954 | 2023-01-24 | Tills are slow across few stores due to full cache refresh | The full cache refresh was triggered in error - can any prevention/recovery method be implemented to avoid/stop run of the job once it is triggered? | Problem avoidance | Bala | 13/02: A backlog (RPOS-7551) has been created to add additional dependcy outside Control-M to run the job , even if its triggered in advertently from Control-M. 30/01: Back log has been created to priortize to find a solution and implement the same. Awaiting back log details from Bala 24/01: Full cache runs in batches and different jobs in control-m, by the time POS new about it, it was 7am and the refresh was 90% complete. Is there any way of controlling a refresh whilst it flows to stop/start so that transactions are not impacted? | POS |  | NA | 13/02/23 | Closed | NA | RPOS-7550 |  | Saloni | 2025-02-10 | 982 | >60 | February | 2023 | #VALUE!
Customer Channels | Service Experience | 89111954 | 2023-01-24 | Tills are slow across few stores due to full cache refresh | Can we move the full cache refresh job in a place on its own. The full cache refresh should not belong in any folder with other jobs. | Problem avoidance | Bala/Siva | 10/02: Back log RPOS-7550 has been raised - The job will be moved out of c93 folder new folder with priorty 30/01: Back log has been created to priortize to find a solution and implement the same. Awaiting back log details from Bala 24/01: It is already in a folder of its own but a wildcard search brought up all user released jobs. It is felt that the job should be removed from Control M as it is an adhoc job and should only be run when needed. Bala and Siva to propose the best solution and present to Laura and Suresh to approve. Can an alert be created to notify if the full cache has been started? | POS |  | NA | 13/02/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 982 | >60 | February | 2023 | #VALUE!
Customer Channels | Service Experience | 89111954 | 2023-01-24 | Tills are slow across few stores due to full cache refresh | Comms to retail – we need to have a skeleton template so that it can be quickly filled in and sent in a timely manner | Business & IT Communication | Laura | 27/02: Agreement has been made with the Business teams around when a comms should be sent. Laura will communite with OOH service leads to ensure 24/7 is covered 14/02: The service lead is on annual leave, will follow up once she is back 10/02: Action owner is on sick leave. Will follow up once she is back 30/01: Actions is worked upon to create a template for any further issue such the communication is made quicker to buisness. ETA 04/02 24/01: ETA to beconfirmed for the action agreed on the call | POS |  | NA | 23/02/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 982 | >60 | February | 2023 | #VALUE!
Customer Channels | Service Experience | 89111954 | 2023-01-24 | Tills are slow across few stores due to full cache refresh | POS team was aware of the issue, why was the impact not called out and how can this gap be addressed? | Supplier and support involvement | POS | 24/01: POS team have been advised to update service leads and post an update in the support channel proactively – irrespective of the anticipated completion time. | POS |  | NA | 24/01/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 982 | >60 | January | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89111954 | 2023-01-24 | Tills are slow across few stores due to full cache refresh | Can the job owner details be made mandatory while scheduling the job in Control-M ? | Problem avoidance | Santhosh | 24/01: Santosh will implement this going forward after any deployments | SMT tools |  | NA | 24/01/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 982 | >60 | January | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89111954 | 2023-01-24 | Tills are slow across few stores due to full cache refresh | Can the details of the adhoc user confirmation jobs in control-m be validated so that they don’t need to be ordered daily – are there any other jobs that are ordered like this? | Problem avoidance | Sathya | 12/04: Team will be tracking this under 'SMT-7' going forward 3/04: There are no responses from other job owners, hence team will create a backlog id and share 20/03: SMT team has informed appln telog id ams and moved the user confirmation to disable state to avoid loading everyday. From 1100+ jobs, have reduced to 500+ jobs.and are still are working on it 27/02: 300+ jobs are removed and 800+ job are awaiting confirmation from the job owners 14/02: Control-M team is escalating furthers to get the updates from job owners. 03/02: 63 jobs have been disabled so far. Control-m team is chasing up with othe job owner to complete this activity. 01/02: Sathya is has list of user hold jobs to the owners to validate whether the job needs to order to schedule daily. Chasing upwith support team. 30/01: Followed up with action owner awaiting an update. 24/01: ETA to beconfirmed for the action agreed on the call | SMT tools |  | NA | 2023-12-04 | Closed | NA | SMT-7 |  | Saloni | 2025-02-10 | 982 | >60 | April | 2023 | #VALUE!
GTS | Operations | 89111954 | 2023-01-24 | Tills are slow across few stores due to full cache refresh | Support teams to provide the full details of the jobs that need to run and to be aware of the job names they need to see the list in Control M. | Problem avoidance | Suganya | 3/5: Templates have been validated by SAP and the corrected template will be sent today. this actions will be tracked under 89293860 incident. 25/4: Call scheduled with foods team on 26th 7/4: PCM waiting for details from Foods portfolio to share the template 3/04: There are no responses from all portfolios, however PCM to share the template by 4th April 20/03: A template is being prepared to consolidate the details of the job that needs to be actioned during a change 27/02:Yet to received an update on the latest progress. Follow up has been maded 13/02: SAP team has been advised and steps have been intiated to gain access for SAP. Discussion to be made with C&H team to gain read read to control-m jobs 24/01:Suganya to get control M read access for relevant support team members | PCM |  | NA | 2023-03-05 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 982 | >60 | May | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89111954 | 2023-01-24 | Tills are slow across few stores due to full cache refresh | Design a repository/report of control m jobs, names, owners, portfolios and possible impact if the job is run | Impact analysis | Suganya /Santhosh | 01/02: SMT-4 has been raised as agreed in PIR call. 30/01: Followed up with action owner awaiting an update. 24/01: Backlog to be raised. | SMT tools |  | NA | 2023-01-02 | Closed | NA | SMT-4 |  | Saloni | 2025-02-10 | 982 | >60 | February | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89111954 | 2023-01-24 | Tills are slow across few stores due to full cache refresh | PCM highlighted those 50 jobs that was triggered on 22/01 in error did not have job owner details to reach out to understand the impact. How many such jobs are there and how will we notify and address the issue if any of this job are critical? What is the mitigation plan? If we were aware of this scenario was this risk raised earlier | Problem identification & Alerting | Suganya /Santhosh | 03/02: Job owners have been updated for will 107 jobs. 02/02: Job owner for 68 jobs out of 107. Control-M team is following with team for an update 01/02: Sathya is has list of user hold jobs to the owners to validate whether the job needs to order to schedule daily. Chasing upwith support team. 30/01: Followed up with action owner awaiting an update. 24/01: A full review needs to be conducted of the list of user confirmation job to see which ones don’t have owner details. | PCM/SMT tools |  | NA | 2022-03-03 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 982 | >60 | March | 2022 | #VALUE!
GTS | Enterprise Technology Platform | 89111954 | 2023-01-24 | Tills are slow across few stores due to full cache refresh | When PCM realised that multiple jobs from folders was released why was the issue was not called out? How can this gap be addressed? | Problem identification & Alerting | Suganya /Santhosh | 27/04: Admin access cannot be provided, so After any major activity is completed - may be the change team can raise a task to CNTL M to get a report and validate 03/04: Followedup on the status of the testing 27/02: Testing is still inprogress 14/02: Team is still exploring the options 24/01: PCM were only aware of the error when stores called in. POS team made PCM aware. The alerts were hidden amongst all the alerts from the SAP and DS releases How can we supress the not started or started late alerts so that PCM are left with only genuine alerts. Suganya and Santosh to devise a solution and propose. | PCM/SMT tools |  | NA | 2023-03-05 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 982 | >60 | May | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89111954 | 2023-01-24 | Tills are slow across few stores due to full cache refresh | How can we prevent the inadvertent release of multiple jobs in error? | Problem avoidance | Suganya/ Santosh | 09/02: Team has confirmed that the IDOM list not being used for application team changes and its being followed only for platform changes. Hence PCM cannot get the list of job to release. 24/01: Suganya to share the job release steps with Santhosh and they both review the process. Look at whether further peer review is included or needs to be added. Is there an IODM checklist with full job names and full folder name? | SMT tools |  | NA | 2023-09-02 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 982 | >60 | February | 2023 | #VALUE!
Customer Channels | Customer Engagement | 89106250 | 2023-01-23 | Drop in Android App Orders | Alerting - Add the mobile app teams adobe Analytics and tweak the threshold to reduce the false alert | Problem identification & Alerting | Alison Villazon | 23/01: The actions is agreed to close on 30/01/2023 01/02: Alison stated"Alerts will now be sent to Tom Moat and Andreas Christophides on the Android team if Android order levels go beyond the expected hourly volume by more than a threshold amount. I've notified them both that these emails will start to be sent to them." | Adobe Analytics |  | NA | 2023-01-02 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 983 | >60 | February | 2023 | #VALUE!
Customer Channels | Customer Engagement | 89106250 | 2023-01-23 | Drop in Android App Orders | Test the broken version of Tealium UTag on Sit2 Android App to understand cause of breaking behaviour on App | Root cause | Florian Lamotte/Alison Villazon | 01/03: Alison confirmed that it is deployed and testing was successful 27/02: Alison confirmed that the final testing will happen on wednesday 22/02: Followed up for the update 15/02: Testing didn't go well and Alison will be testing it again on tuesday and providing the updates 12/02: Alison updated that" Due to a bug in the Tealium tool, we've been delayed in this work but have time scheduled in to do the testing on Tues 14th" 23/01: The actions is agreed to close on 15/02/2023 | Adobe Analytics |  | NA | 2023-01-03 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 983 | >60 | March | 2023 | #VALUE!
Customer Channels | Customer Engagement | 89106250 | 2023-01-23 | Drop in Android App Orders | Explore whether it is feasible to create automated SDK Journey Monitor for Android | Problem identification & Alerting | Florian Lamotte/Alison Villazon | 15/02: Alison will work with Observerpoint contact with the backlog ID AATR-112, hence closing the action 12/02: Alison updated that "The Observepoint tool, which would provide this audit does not currently provide the feature for Apps, but it is going to be re-launched soon and our Observepoint contact will provide me with further information once the feature is ready (no ETA)." 23/01: The actions is agreed to close on 15/02/2023 | Adobe Analytics |  | NA | 15/02/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 983 | >60 | February | 2023 | #VALUE!
Customer Channels | Customer Engagement | 89106250 | 2023-01-23 | Drop in Android App Orders | Explore real time Alerting options through technology tools | Problem identification & Alerting | Sam Barnes/Matthew Magee | 16/05: eComm Platform Support created an alert for a drop in Android and iOS Mobile Apps. 2/05: Trying finally this week if alerts can be set for Android in frontend 24/04: Followed up with Magee 14/04: Alerts have been setup for iOS, for Android team is working on. Followed up for the updates 09/04:Followed up with Magee 3/04: Team is still exploring 27/03: Alerts are still being explored 11/3: Followed up with MAtthew for the latest update on this 28/02: Matthew updated that " setup a New Relic query that checks for ambient checkout events over a period of several hours. We are going to do some further investigation to validate that 1) the query works as expected, and 2) doesn't impact performance of other queries, and then 3) setup alerts into Teams and - depending on the severity - PagerDuty in the event of a dramatic checkout activity dropoff." and confirm once deployed by 7th 22/02: Followed up for the update 15/02:Magee told that "they have explored New Relic queries that might help here, but nothing concrete has come out of that. Our feeling is that this should/could be at the API level - ambient transaction levels, etc." and they wanted time to explore it. 23/01: The actions is agreed to close on 15/02/2023 | Adobe Analytics |  | NA | 16/05/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 983 | >60 | May | 2023 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89104009 | 2023-01-20 | Multiple stores hard down due to BT Data Centre power outage | BT to investigate and report the detailed root cause of the issue | Root cause | BT/ Elizabeth Golder | 16/2: The issue was caused by a human error where multiple cables were removed from the Customer racks as part of STP2 decommissioning. 7/2: The RCA document shared by BT does not actually cover on what went wrong, how we can get resilince etc.. Elizabeth will follow-up again with BT on the weekly review meeting. 31/01: Followed up with Elizabteh and Network team to get the latest update, awaiting response. 20/01: Actions agreed and ETA is 27th Jan | Network |  | NA | 16/02/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 986 | >60 | February | 2022 | #VALUE!
GTS | ETP- Connectivity,service & solution | 89104009 | 2023-01-20 | Multiple stores hard down due to BT Data Centre power outage | There was a delay in incident communications from BT. How can be this be improved? | Business & IT Communication | BT/ Elizabeth Golder | 25/4: BT provided a new portal, where we can look for any outage communication and also raise a new tickets 11/4: BT is yet to come back on this and is being discussed in their weekly review meeting 3/3: Elizabeth is OOO till 7th March 27/2: Followed up with Elizabeth on the updates from BT 16/2: BT is still working on this 7/2: The RCA document shared by BT does not actually cover on what went wrong, how we can get resilience etc.. Elizabeth will follow-up again with BT on the weekly review meeting. 31/01: Followed up with Elizabeth and Network team to get the latest update, awaiting response. 20/01: Actions agreed and ETA is 27th Jan | Network |  | NA | 25/4/2023 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 986 | >60 | 25/4/2023 | #VALUE! | #VALUE!
GTS | ETP- Connectivity,service & solution | 89104009 | 2023-01-20 | Multiple stores hard down due to BT Data Centre power outage | If the primary and secondary links are both hosted in the BT data centre and there is a fault, then what resilience is in place or needs to be put in place to prevent future impact? | Problem avoidance | BT/ Elizabeth Golder | 17/5: BT is working on the multi customer impacting resilience as a permanent fix, hence closing the action. They will intimate us once this is addressed 25/4: BT is yet to come back on this and is being discussed in their weekly review meeting 11/4: BT is yet to come back on this and is being discussed in their weekly review meeting 3/3: Elizabeth is OOO till 7th March 27/2: Followed up with Elizabeth on the updates from BT 16/2: BT is still working on this 7/2: The RCA document shared by BT does not actually cover on what went wrong, how we can get resilience etc.. Elizabeth will follow-up again with BT on the weekly review meeting. 31/01: Followed up with Elizabeth and Network team to get the latest update, awaiting response. 20/01: Actions agreed and ETA is 27th Jan | Network |  | NA | 17/05/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 986 | >60 | May | 2023 | #VALUE!
Customer Channels | Platform & Store Ops | 89082631 | 2023-01-19 | Issues in performing counting for F19a Grocery and F20a Wine stock at stores | How do we identify whether this SDK bug impacts other applications that were built using SDK on android other than CSSM count? | Solution & Recovery | Anees Ahmed | Alerts configured for other applications build on this target SDK and it can be addressed during an issue. | Honeywell Andriod App |  | NA | 19/01/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 987 | >60 | January | 2023 | #VALUE!
Customer Channels | Platform & Store Ops | 89082631 | 2023-01-19 | Issues in performing counting for F19a Grocery and F20a Wine stock at stores | The comment was made during the MI that this issue cannot be replicated in testing environments - why? Is a lower environment available and if so is it suitable for testing? Does it closely reflect production? | Problem avoidance | Anees Ahmed | There is a testing environment available, however, as there was no version activity performed after Nov 2022, the data set up was no like production. Once the version was downgraded on 09/01, the issue was replicated in testing environment. | Honeywell Andriod App |  | NA | 19/01/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 987 | >60 | January | 2023 | #VALUE!
Customer Channels | Platform & Store Ops | 89082631 | 2023-01-19 | Issues in performing counting for F19a Grocery and F20a Wine stock at stores | The investigation of the issue during the incident took a significantly long time - what improvements can be systemically made to highlight issues better to allow for quicker recover? | Problem avoidance | Anees Ahmed | The error logs captured did not highlight the issue initially, a thorough analysis had to be performed on the configuration change to identify the issue. This has been addressed in action 2. | Honeywell Andriod App |  | NA | 19/01/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 987 | >60 | January | 2023 | #VALUE!
Customer Channels | Platform & Store Ops | 89082631 | 2023-01-19 | Issues in performing counting for F19a Grocery and F20a Wine stock at stores | Were there any alerts or logs that indicated that the count app had stopped responding? If not, how can we identify multiple counts failing before the store reports the issue? | Problem identification & Alerting | Anees Ahmed | A new relic alert was triggered at 17:09 and the issue was addressed on time. There are separate alerts for other counts performed across the estate. No additional alerts required | Honeywell Andriod App |  | NA | 19/01/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 987 | >60 | January | 2023 | #VALUE!
Customer Channels | Platform & Store Ops | 89082631 | 2023-01-19 | Issues in performing counting for F19a Grocery and F20a Wine stock at stores | In Nov 2022 as part of the Count app release the SDK was also upgraded from 23 to 26. Were we aware of the bug during the deployment? If yes, why did we proceed? If not, then was the correct level of testing done to identify such bugs - if not how can we carry out testing that reflects production load - giving us the best chance of finding any issues? | Problem avoidance | Anees Ahmed | The non-prod test case did not involve this target sdk configuration change. Tech will now include this test case in their deployment SOP to address this issue in future | Honeywell Andriod App |  | NA | 19/02/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 987 | >60 | February | 2023 | #VALUE!
Customer Channels | Platform & Store Ops | 89082631 | 2023-01-19 | Issues in performing counting for F19a Grocery and F20a Wine stock at stores | What was the root cause of the issue? | Root cause | Anees Ahmed | A bug in the target SDK version 26 (software development kit used to build applications in Android) in CSSM count app released in the Nov 2022 had caused the issue. As per Android developer document, if the target Sdk Version >= 24 and the saved state goes beyond a certain size, it will cause a runtime exception crash. The volume of counts performed across F15a and F20a products were significantly higher on 08/01, thus causing the issue. Note: These departments were last counted on July 2022 when the sdk version was 23, hence no issues were reported | Honeywell Andriod App |  | NA | 19/01/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 987 | >60 | January | 2023 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89070787 | 2023-01-05 | WMS performance issues at Castle Donington DC | Why was the WMS response time slow on 02/1/2023 overnight? | Root cause | Murali/ WMS | 1/5: Root cause is attributed to an user error, locking stock for PPM in HBW crane caused excess of WMS messages slowing down the server. Root cause identified to user error, locking stock for PPM in HBW crane caused excess of WMS messages slowing down the server | WMS |  | NA | 2023-05-01 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1001 | >60 | January | 2023 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 89070787 | 2023-01-05 | WMS performance issues at Castle Donington DC | Was there any alerts to notify that the response time was slow? | Problem identification & Alerting | Murali/ WMS | 1/5: a netcool alert was triggered around 00:29 | WMS |  | NA | 2023-05-01 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1001 | >60 | January | 2023 | #VALUE!
Supply Chain | Foods Supply Chain | 89054239 | 2022-12-29 | Stores reporting issues with scanning CFTO QR codes in the tills. | Review the CFTo capacity plan for customers per hour vs the actual collections per hour. Create a dashboard to showcase the same. | Impact analysis | Biju George | Completed | CFTO team |  | NA | 20/01/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1008 | >60 | January | 2023 | #VALUE!
Customer Channels | Service Experience | 89054239 | 2022-12-29 | Stores reporting issues with scanning CFTO QR codes in the tills. | Flooid to look at their key metrics and check for any additional metrics to be introduced - do the application teams have access and knowledge of these | Problem identification & Alerting | Manikandan Solaimalai | 20/01: Awaiting updates. Escalations have been made. Rishi Deva is currently coordinating this. In addition, he reckons we have made good progress with Flooid in identifying the solution which is currently in its testing phase, tracked under RSS-2609 | Collague Efficiency |  | NA | 20/01/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1008 | >60 | January | 2023 | #VALUE!
Customer Channels | Service Experience | 89054239 | 2022-12-29 | Stores reporting issues with scanning CFTO QR codes in the tills. | Revisit the performance testing scenarios and review the draft plan in the next follow up meeting | Problem avoidance | Rajan Kasturi | 20/01: Awaiting updates. Escalations have been made. Rishi Deva is currently coordinating this. In addition, he reckons we have made good progress with Flooid in identifying the solution which is currently in its testing phase, tracked under RSS-2609 | VOD |  | NA | 20/01/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1008 | >60 | January | 2023 | #VALUE!
Customer Channels | Service Experience | 89054239 | 2022-12-29 | Stores reporting issues with scanning CFTO QR codes in the tills. | Carry out a deep dive into the VOD application and look for further opportunities for tuning where it is necessary | Problem avoidance | Rajan Kasturi | 20/01: Awaiting updates. Escalations have been made. Rishi Deva is currently coordinating this. In addition, he reckons we have made good progress with Flooid in identifying the solution which is currently in its testing phase, tracked under RSS-2609 | VOD |  | NA | 20/01/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1008 | >60 | January | 2023 | #VALUE!
Customer Channels | Service Experience | 89054239 | 2022-12-29 | Stores reporting issues with scanning CFTO QR codes in the tills. | Not all transactions are stored as logs especially with regards to response times. Review the logging mechanism and enable additional if required. | Problem identification & Alerting | Rajan Kasturi | 20/01: Awaiting updates. Escalations have been made. Rishi Deva is currently coordinating this. In addition, he reckons we have made good progress with Flooid in identifying the solution which is currently in its testing phase, tracked under RSS-2609 | VOD |  | NA | 20/01/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1008 | >60 | January | 2023 | #VALUE!
Customer Channels | Service Experience | 89054239 | 2022-12-29 | Stores reporting issues with scanning CFTO QR codes in the tills. | VOD to liaise with Flooid & Mongo and extract the logs to identify the reason behind the ghost transactions. | Root cause | Rajan Kasturi | 20/01: Awaiting updates. Escalations have been made. Rishi Deva is currently coordinating this. In addition, he reckons we have made good progress with Flooid in identifying the solution which is currently in its testing phase, tracked under RSS-2609 | VOD |  | NA | 20/01/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1008 | >60 | January | 2023 | #VALUE!
Customer Channels | Service Experience | 89054239 | 2022-12-29 | Stores reporting issues with scanning CFTO QR codes in the tills. | Analyse the calls made by the app and produce a dashboard reflecting the metrics to proactively identify any failures or slower response times. Enable new relic traces to identify the slower transactions at VOD | Problem identification & Alerting | Rajan Kasturi | 20/01: Awaiting updates. Escalations have been made. Rishi Deva is currently coordinating this. In addition, he reckons we have made good progress with Flooid in identifying the solution which is currently in its testing phase, tracked under RSS-2609 | VOD |  | NA | 20/01/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1008 | >60 | January | 2023 | #VALUE!
Customer Channels | Service Experience | 89054239 | 2022-12-29 | Stores reporting issues with scanning CFTO QR codes in the tills. | Is there alerting to indicate the pod restarts and delay in VOD response times. | Problem identification & Alerting | Rajan Kasturi | VOD team received a alert indicating pod restart at 08:38. The feasibility to configure an alert for delay in response times is being explored. | VOD |  | NA | 20/01/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1008 | >60 | January | 2023 | #VALUE!
Customer Channels | Service Experience | 89054239 | 2022-12-29 | Stores reporting issues with scanning CFTO QR codes in the tills. | Identify if the pods were able to successfully carry out their liveliness and readiness checks and if not where was the point of failure in these checks and why? Document the steps taken in this action in a SOP | Root Cause | Rajan Kasturi/ Emmanuel George | 20/01: Awaiting updates. Escalations have been made. Rishi Deva is currently coordinating this. In addition, he reckons we have made good progress with Flooid in identifying the solution which is currently in its testing phase, tracked under RSS-2609 | VOD & Cloud exponence |  | NA | 20/01/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1008 | >60 | January | 2023 | #VALUE!
Customer Channels | Service Experience | 89054239 | 2022-12-29 | Stores reporting issues with scanning CFTO QR codes in the tills. | Create an Incident runbook - In the MI it took time to ascertain the flow of the CFTO application end to end - include application/infrastructure triage checks for each hop in the chain so that these can be completed in a timely manner | Solution & Recovery | Rishi Deva | 20/01: Awaiting updates. Escalations have been made. Rishi Deva is currently coordinating this. In addition, he reckons we have made good progress with Flooid in identifying the solution which is currently in its testing phase, tracked under RSS-2609 | VOD |  | NA | 20/01/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1008 | >60 | January | 2023 | #VALUE!
Customer Channels | Platform & Store Ops | 89054239 | 2022-12-29 | Stores reporting issues with scanning CFTO QR codes in the tills. | Re-analyse the retry timeouts on the tills if they are set to optimum levels for this application. Enables traces through the systems: from the tills to VOD into Mongo Is the error handling on the device accurate for the customer? | Problem identification & Alerting | Seevaratnam Sivasurath | 20/01: Awaiting updates. Escalations have been made. Rishi Deva is currently coordinating this. In addition, he reckons we have made good progress with Flooid in identifying the solution which is currently in its testing phase, tracked under RSS-2609 | POS dev |  | NA | 20/01/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1008 | >60 | January | 2023 | #VALUE!
Supply Chain | Foods Supply Chain | 89034867 | 2022-12-15 | Foods DCs reporting issues in GR (goods receipts) flow | The following updates will be made in the relevant SOPS for communication when alerts are observed ASO team will update teams support channel if they get an alert | Solution & Recovery | Mehra, Vivek | 29/12: SOP has been created and updated on the Remedy 28/12: Awaiting further updates from Vivek. 21/12: Followed up with the action owner awaiting updates | ASO |  | NA | 29/12/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1022 | >60 | December | 2022 | #VALUE!
GTS | Enterprise Integration | 89034867 | 2022-12-15 | Foods DCs reporting issues in GR (goods receipts) flow | Where was the testing lacking – The following flows such as oms to bigdata, oms to orca were all tested individually not together. Raise a risk of the testing process | Problem avoidance | Rajagopalan, Mukundan | 30/12: Risk ID 1801 has been raised to mitigate the issue 29/12: Performance testing will be done only within the landscape. End-to-end and cross-functionality testing will not be done. as this is the PT standard across most of the applications in Customer. A design change is required to remove the clould flow going through On-prem. A risk will be raised to address this. Awaiting risk ID for the same. 28/12: Awaiting further updates from Mukundan. 21/12: Followed up with the action owner awaiting updates | Integration Services |  | NA | 30/12/22 | Closed | 1801 | NA | N/A | Saloni | 2025-02-10 | 1022 | >60 | December | 2022 | #VALUE!
GTS | Enterprise Integration | 89034867 | 2022-12-15 | Foods DCs reporting issues in GR (goods receipts) flow | Can we uplift capacity in middleware | Problem avoidance | Rajagopalan, Mukundan | 29/12:Uplift is not possible in middleware since its just a simple queue to queue transfer across the Express Route network 28/12: Awaiting further updates from Mukundan 21/12: Followed up with the action owner awaiting updates | Integration Services |  | NA | 29/12/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1022 | >60 | December | 2022 | #VALUE!
GTS | Enterprise Integration | 89034867 | 2022-12-15 | Foods DCs reporting issues in GR (goods receipts) flow | The following updates will be made in the relevant SOPS for communication when alerts are observed Messaging team will update teams support channel if they get an alert They will call foods/aso to check if GR’s are coming through in a timely manner If not, then call SO/TEM/Boopathy and arrange for MIM to be engaged | Solution & Recovery | Rajagopalan, Mukundan | 13/01: SOP has been created and published under the KBA article KBA00025005 11/01: Team is in progress of creating the SOP and will complete by tomorrow, EOD 29/12: Mukundan is yet to provide an update on the SOP. 22/12: Middleware team have been advised give callout to ASO team everytime we see pile up in the common transmission queue along with usual email thread. 21/12: Followed up with the action owner awaiting updates | Integration Services |  | NA | 13/01/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1022 | >60 | January | 2023 | #VALUE!
GTS | Enterprise Integration | 89034867 | 2022-12-15 | Foods DCs reporting issues in GR (goods receipts) flow | A change to route the Order Events messages through a dedicated High NFR queue needs to be implemented. | Permanent Fix | Rajagopalan, Mukundan | 30/12:The routing change to High NFR channel has been deployed 28/12: The routing change to High NFR channel will be done on 29/12 at 9 PM GMT 21/12: Followed up with the action owner awaiting updates | Integration Services |  | NA | 30/12/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1022 | >60 | December | 2022 | #VALUE!
Customer Channels | Service Experience | 89007834 | 2022-12-15 | Contactless and Chip & pin payments were declined at stores | Replacement of faulty disk | Permanent fix | Gary Allenby | 7/2: Gary confirmed that the disk replacement is completed 23/12: Gary informed that team is still working on this 19/12: In Progress, ETA - 21/12/2022 | Worldline |  | NA | 2022-07-02 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1022 | >60 | February | 2022 | #VALUE!
Customer Channels | Service Experience | 89007834 | 2022-12-15 | Contactless and Chip & pin payments were declined at stores | Review with provider on improvements in alerting for this type of issue | Problem identification & Alerting | Gary Allenby | 13/06: Alerting improved will be tracked under the back log RPOS-9047 26/05: Followed up on the status 16/5: Followed up with Gary and Bala on their open actions 3/05: Bala is OOO, followed up with Gary 28/04:Followed up on the latest status with GAry and Bala 22/03: The changes are in Preprod and to be deployed in End of April, followed up on latest status 6/3: Followed-up with Gary and waiting for an update 18/01: Followed-up with Gary and awaiting for an update 23/12: Customer and Worldline had initial meeting on 22nd Dec and gathered the logs to configure the alerts. A follow-up call will be arranged on early January to go through the progress 19/12: In Progress | Worldline |  | NA |  | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1022 | >60 | January | 1900 | #VALUE!
GTS | Enterprise Technology Platform | 89026544 | 2022-12-12 | Stores reporting issues with Accuracy Checker when doing target counts | If the issue happens again then the relevant teams to capture: -SQL server CPU, memory, disk utilisation, i/o -Capture all the long running queries in a screenshot during the issue with their CPU utilisation -Capture any obvious deadlocks -Capture what started first - CPU spike or the long running query | Root Cause | Haritha Karri | 28/12: No further issues reported. Teams are requested to capture the required information incase of issue re-occurs 16/12: Followed-up, awaiting response | SQL Team |  | NA | 28/12/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1025 | >60 | December | 2022 | #VALUE!
GTS | Enterprise Technology Platform | 89026544 | 2022-12-12 | Stores reporting issues with Accuracy Checker when doing target counts | Long running and deadlock scenarios have an email alert which goes to product teams – we need to explore options for triggering a sev 1 via Remedy and Netcool. | Problem identification & Alerting | Haritha Karri | 6/2: Alerting has been enabled 31/01: Team is enabling the alerting on 2nd Feb'23 18/01: Haritha informed that prod deployment will be done in week's time 13/01: Haritha informed that the testing is completed and will be deployed into production on 18th Jan 5/01:The alerting for long running queries is being done with script customization to write events to Windows eventviewer so that SCOM can pick the alerts 28/12: Team tried to add the deadlock sessions to the event viewer and it was not feasibile so other options are being explored 16/12: Followed-up, awaiting response | SQL Team |  | NA | 2023-06-02 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1025 | >60 | February | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89026544 | 2022-12-12 | Stores reporting issues with Accuracy Checker when doing target counts | Follow up root cause via the case logged with Microsoft - Microsoft case raised. | Root Cause | Saravanan | 30/12: The accuracy checker was enabled on 27th Dec and teams monitored the system during issue window and no issues were identified. Team will capture the required logs if the issue re-occurs 22/12: Microsoft could not identify the cause of the issue from the logs provided and requested to capture the additional logs if the issue re-occurs. As part of business request to support peak trading, the accuracy checker is disabled and it will be enabled on 27th Dec. Teams will be on hypercare call and capture the additional logs during problematic window and the same will be provided it to Microsoft. 16/12: Followed-up, awaiting response | SQL Team |  | NA | 30/12/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1025 | >60 | December | 2022 | #VALUE!
GTS | Enterprise Technology Platform | 89026544 | 2022-12-12 | Stores reporting issues with Accuracy Checker when doing target counts | A custom CPU alert to be created for the SQL team at a threshold of 80% for ten mins | Problem identification & Alerting | Saravanan | 12/12: Alerts have been set-up if CPU remains more than 80% | SQL Team |  | NA | 2022-12-12 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1025 | >60 | December | 2022 | #VALUE!
Customer Channels | Platform & Store Ops | 89026544 | 2022-12-12 | Stores reporting issues with Accuracy Checker when doing target counts | For this application, Swindon and Stockley are operated on a replicated cluster – that’s why we were unable to failover as the problem would have replicated – investigate other possible failover options. | Solution & Recovery | Velrajan C | 30/12: Requested vel to create a risk 28/12: Vel informed that he will discuss with infra archetict after new year 16/12: Followed-up, awaiting response | CSSM team |  | NA | 2023-04-01 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1025 | >60 | January | 2023 | #VALUE!
Customer Channels | Platform & Store Ops | 89026544 | 2022-12-12 | Stores reporting issues with Accuracy Checker when doing target counts | Ascertain if there is an incident runbook to handle CSSM issues – review if any changes are needed | Solution & Recovery | Velrajan C | 28/12: Vel confirmed that all scenarios are covered in CSSM runbook 16/12: Followed-up, awaiting response | CSSM team |  | NA | 28/12/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1025 | >60 | December | 2022 | #VALUE!
Customer Channels | Selling Experience | 89001060 | 2022-12-12 | Stock mismatch between PDPs and checkout for free gift promotional product | In the scenario where a stock mismatch occurs, there are 2 options to prevent a broken customer journey: •Delete both main item and free gift from basket and move both to Saved basket OR •Allow customer to remove free gift item. | Problem avoidance | Hemant Goyal | 12/12: This actions is being tracked under CD-3707 | WCS |  | NA | 2022-12-12 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1025 | >60 | December | 2022 | #VALUE!
Customer Channels | Selling Experience | 89001060 | 2022-12-12 | Stock mismatch between PDPs and checkout for free gift promotional product | To fix the immediate issue the promotion and product were removed from the website. The stock picture was aligned for the impacted product | Solution & Recovery | Hemant Goyal | 12/12: Completed as part of incident | WCS |  | NA | 2022-12-12 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1025 | >60 | December | 2022 | #VALUE!
Customer Channels | Service Experience | 89001060 | 2022-12-12 | Stock mismatch between PDPs and checkout for free gift promotional product | Reconciliation between inventory levels in SS and OMS. 3 times a day a reconciliation is run between the 2 systems and any stock mismatch is highlighted which is then adjusted and corrected | Problem avoidance | Jackson Solomon | 03/01: Jackson confirmed that the action is completed 29/12: Still OOO, waiting for him to revert 22/12: OOO with no return date 12/12: Yet to get an updated from the action owner on the status | Sterling |  | NA | 2023-03-01 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1025 | >60 | January | 2023 | #VALUE!
Customer Channels | Service Experience | 89001060 | 2022-12-12 | Stock mismatch between PDPs and checkout for free gift promotional product | A change is required to update all negative quantities to zero (OMRS-532) | Solution & Recovery | Jackson Solomon | 12/12: This actions is being tracked under OMRS-532 | Sterling |  | NA | 2022-12-12 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1025 | >60 | December | 2022 | #VALUE!
Customer Channels | Service Experience | 89001060 | 2022-12-12 | Stock mismatch between PDPs and checkout for free gift promotional product | Given that the problem occurred because of negative demand, a new report will be created to identify products having a negative quantity (Refer to Jira OMR-535) | Problem identification & Alerting | Jackson Solomon | 12/12: This actions is being tracked under OMR-535 | Sterling |  | NA | 2022-12-12 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1025 | >60 | December | 2022 | #VALUE!
Customer Channels | Customer Engagement | 89008298 | 2022-12-09 | 12 Days of Sparks - broken customer journey and incorrect number of offers | Review regression test scenarios for Sparks Advent Calendar and include cross product test cases (e.g. delivery pass, Sparksplus, Digi rewards .) | Problem avoidance | Antony Narcissot | 19/12: The test cases has been agreed to added to the regression test scenarios of Sparks advent Calendar and it will be reviewes by Antony Narcissot while performing the test next year. This cannot be tracked as any back log items as it has been taken lesson learnt 15/12: Followed up with Divakar for an update on ETA 07/12: Actions has be agreed, awaiting further updates | Sparks |  | NA | 19/12/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1028 | >60 | December | 2022 | #VALUE!
Customer Channels | Customer Engagement | 89008298 | 2022-12-09 | 12 Days of Sparks - broken customer journey and incorrect number of offers | Sparks plus customers were getting the “Snowman” offer . This was a mistake from Planning Inc’s side. Need better governance and check alerting to be introduced to avoid such issues in future | Problem avoidance | Mark Anderson | anning Inc (PI) have confirmed that they will improve their reviews and checks | Planning PI team |  | NA | 2022-07-12 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1028 | >60 | December | 2022 | #VALUE!
Customer Channels | Customer Engagement | 89008298 | 2022-12-09 | 12 Days of Sparks - broken customer journey and incorrect number of offers | Alerting for CMS/Bullseye overlap of offers | Problem identification & Alerting | Moutusi Layek/Antony Narcissot | 19/12: There are scenarios where we have overlap of offer is valid, hence alerting is not feasible for this feasible. 15/12: Followed up with Divakar for an update on ETA 07/12: Actions has be agreed, awaiting further updates | Sparks |  | NA | 19/12/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1028 | >60 | December | 2022 | #VALUE!
Customer Channels | Customer Engagement | 89008298 | 2022-12-09 | 12 Days of Sparks - broken customer journey and incorrect number of offers | Verify offer type for all upcoming offers of 12 Days of Sparks and ensure they are setup as Advent calendar | Solution & Recovery | Nikki Widman/ Gillian O’Connor | All offers for 12 DOS have been cross verified and changed from Bonus to advent | Loyalty team |  | NA | 2022-07-12 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1028 | >60 | December | 2022 | #VALUE!
C&H and Intl | C&H Commercial Trading | 89016407 | 2022-12-06 | Delay to the GMOR critical batches | Communication between RPA and SAP teams to notify on higher volume of SAP amendments until action#1 is in place | Business & IT communication | Rhammya Somassoudirame | 09/12: RPA Team confirmed that they will manually check the total PO line items count for the input data received and then proceed with starting the Bot process to perform PO amends until this is automated. Hence closing | SAP BW team |  | NA | 2022-09-12 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1031 | >60 | December | 2022 | #VALUE!
Group Support | Finance | 89016407 | 2022-12-06 | Delay to the GMOR critical batches | Discussion with RPA Team to conclude on the data restriction | Permanent fix | Rhammya Somassoudirame | 19/12: RPA-77 is created and development is planned to be taken up in Q4'22 15/12: Rhammya has followed up with the BOT team 09/12: RPA Team confirmed that they could do restriction at their end and it would take Jan 2023 to do it, waiting for Jira/Backlog ID | SAP BW team |  | NA | 19/12/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1031 | >60 | December | 2022 | #VALUE!
Supply Chain | Foods Supply Chain | 89011800 | 2022-12-05 | Issues with customer FTO orders | In the event of future changes of deliveries to depots - supplier PO's need to be changed, confirm and validate the correct the process for this and communicate to relevant stake holders. | Business & IT Communication | Andrew Goslin/ Dan Maddox | 6/12: Andrew discussed with Dan Maddox on the process | SCRD |  | NA | 2022-06-12 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1032 | >60 | December | 2022 | #VALUE!
Supply Chain | Foods Supply Chain | 89011800 | 2022-12-05 | Issues with customer FTO orders | Apply a daily manual check between SCRD and ORCA to confirm if the data is inline. | Solution & Recovery | Harihanuman | 5/12:The checks are currently in place, once action #6 is completed, this will be halted. 12/12: Since the automatic pod restart is in place, this has been halted now, hence marking it as completed | ORCA |  | NA | 2022-12-12 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1032 | >60 | December | 2022 | #VALUE!
Supply Chain | Foods Supply Chain | 89011800 | 2022-12-05 | Issues with customer FTO orders | Clear communication between Tech and Customer stakeholders during such changes in future | Business & IT Communication | Joey Ocansey/ Andrew Goslin | 5/12: Joey and Andrew to arrange a session with Foods tech exploring way to improve communication. 20/12: Dan agreed to reiterate the correct procedures as part of ongoing comms internally in Customer and between Customer & suppliers. | Service Owner |  | NA | 20/12/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1032 | >60 | December | 2022 | #VALUE!
Supply Chain | Foods Supply Chain | 89011800 | 2022-12-05 | Issues with customer FTO orders | Create an automated test case to validate the cache refresh | Problem avoidance | Pushparaj | 5/12: Development is in progress. Deployment TBC. 12/12: This activity is completed | SCRD |  | NA | 2022-12-12 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1032 | >60 | December | 2022 | #VALUE!
Supply Chain | Foods Supply Chain | 89011800 | 2022-12-05 | Issues with customer FTO orders | Automate the manual pod restarts at 20:00 until action 3 is in place | Solution & Recovery | Pushparaj | 5/12: The pods are currently being restarted manually, this will be automated to avoid manual intervention. 12/12: Completed | SCRD |  | NA | 2022-12-12 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1032 | >60 | December | 2022 | #VALUE!
Supply Chain | Foods Supply Chain | 89011800 | 2022-12-05 | Issues with customer FTO orders | Analyse and propose a robust solution to ensure that the correct data is coming into ORCA from SCRD. | Permanent fix | Pushparaj | 5/12: This is a long-term solution and needs further discussion. 16/12: The activity Is still ongoing 20/12: Andrew wil liaise with Pushpa to get an update. 21/12: Discussions are ongoing internally for the recon approach but it is paused due to CFTO and NY-FTO activities . Next update by 2nd week of Jan.\ 30/01: SCLT2-4053 - Recon between ORCA and SCRD for store moves SCLT2-4054 - Recon between ORCA SAP and FITS for FCO POs | SCRD |  | NA | 30/01/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1032 | >60 | January | 2023 | #VALUE!
Supply Chain | Foods Supply Chain | 89011800 | 2022-12-05 | Issues with customer FTO orders | Configure an alert to validate if the cache is refreshed or not across the environment in all scenarios. | Problem identification & Alerting | Vinoth purushothaman | 5/12: This action will be performed for SCRD cache, followed by analysing the other application caches 20/12: Andrew wil liaise with Vinoth to get an update 21/12: Verified the Cache across other application PODs and no issues found. | SCRD |  | NA | 21/12/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1032 | >60 | December | 2022 | #VALUE!
Supply Chain | Foods Supply Chain | 89011800 | 2022-12-05 | Issues with customer FTO orders | Fix the code to ensure the cache clear logic is functioning as expected. | Permanent Fix | Vinoth purushothaman | 12/12: Code fix and testing completed. Deployment will be planned post peak 30/01: SCLT2-4053 - Recon between ORCA and SCRD for store moves SCLT2-4054 - Recon between ORCA SAP and FITS for FCO Pos | SCRD |  | NA | 30/01/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1032 | >60 | January | 2023 | #VALUE!
Customer Channels | Service Experience | 89007834 | 2022-12-05 | Contactless and Chip & pin payments were declined at stores | Worldline to investigate and report on the root cause of the hardware issue | Root Cause | Gary Allenby | 19/12: Root Cause has been identified and the same has been updated in the other tab 12/12: Tried to reach Gary over the phone but no luck. Therefore sent an email to Gary on the RCA | Worldline |  | NA | 15/12/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1032 | >60 | December | 2022 | #VALUE!
Customer Channels | Service Experience | 89007834 | 2022-12-05 | Contactless and Chip & pin payments were declined at stores | There was a delay in incident communications from Worldline. How can be this be improved? | Business & IT Communication | Gary Allenby | 4/12: Gary informed that there was NO delayfrom their end since they sent the communication as per sev2 process from their end. 23/12: Followed-up with Gary again to share an update on this action 12/12: Tried to reach Gary over the phone but no luck. Therefore sent an email to Gary to update the status | Worldline |  | NA | 2023-04-01 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1032 | >60 | January | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 89007834 | 2022-12-05 | Contactless and Chip & pin payments were declined at stores | Analyse the feasibility to configure the alerts where the payments weren’t going through and did not fall to offline payment. | Problem identification & Alerting | Noc | 23/12: Additional alerting has been configured from NOC 12/12: Followed up, awaiting response | NOC |  | NA | 23/12/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1032 | >60 | December | 2022 | #VALUE!
Customer Channels | Service Experience | 89007834 | 2022-12-05 | Contactless and Chip & pin payments were declined at stores | Analyse the feasibility to configure the alerts where the payments weren’t going through and did not fall to offline payment. | Problem identification & Alerting | POS | 18/01: I have spoken to Bala who informed that team is still working on this 23/12: Bala informed that this will be picked in 2nd week of january since team is busy in peak trading period 12/12: Followed up, awaiting response | POS |  | NA | 26/01/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1032 | >60 | January | 2022 | #VALUE!
Digital & Data | Digital & Data | 89006243 | 2022-11-30 | Retail dashboard sales flow was delayed | Analytical comms: SOP to document the impacted service/reports/database to send proper communication to the stakeholders. | Solution & Recovery | Arup Neogy | 09/12: This was not for retail sales flow directly. It was a food report that got imapcted in exadata due to it. We had a call yesterday and going forward from upcoming week, we will drop comms to the below dl in case of any issue in EDW SWAT flow that has been informed to our team by EDW and if it delays/may delay FAP table loads. food.analytics@marks-and-spencer.com 07/12: Arup will schedule a call with Joey, Sandipan and team to come to an agreement. A SOP to be created documenting the reports and comms | EDW Support |  | NA | 2022-09-12 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1037 | >60 | December | 2022 | #VALUE!
Digital & Data | Digital & Data | 89006243 | 2022-11-30 | Retail dashboard sales flow was delayed | Can we do a proactive check on all the surrogate key value (current vs threshold) across EDW landscape. | Problem avoidance | Gaurav Kothari | 30/12: Deployment completed, PBI000000063718 created to do the fix for all EDW tables 29/12: Got approval to implement on 29th due to long Christmas weekend 22/12: Deployment is rescheduled to 28th Dec. Due to long weekend and peak we are preferring for any changes to be done post this long weekend only. 15/12: Once the solution is deployed for the affected table(alert creation), we need to check the feasibility for all tables and accordingly we can provide ETA | EDW Support |  | NA | 30/12/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1037 | >60 | December | 2022 | #VALUE!
Digital & Data | Digital & Data | 89006243 | 2022-11-30 | Retail dashboard sales flow was delayed | How can we ensure that the primary key value will not breach its threshold limit in future? | Problem avoidance | Gaurav Kothari | This requires a design change – long term solution. Temporary fix is to create an alert to identify the issue proactively. Action#2 | EDW Support |  | NA | 2022-01-12 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1037 | >60 | December | 2022 | #VALUE!
Digital & Data | Digital & Data | 89006243 | 2022-11-30 | Retail dashboard sales flow was delayed | Was there an alert for the Surrogate key threshold? Was the surrogate key threshold gradual or sudden? Were we aware of reaching the limit before 30/11? Feasibility of creating an alert to identify the surrogate key is nearing its threshold? | Problem identification & Alerting | Gaurav Kothari | 30/12: Deployment completed yesterday, closing the action 29/12: Got approval to implement on 29th due to long Christmas weekend, waiting for confirmation to close the action 22/12: Deployment is rescheduled to 28th Dec. Due to long weekend and peak we are preferring for any changes to be done post this long weekend only. 15/12: We have identified the solution for this alert check and expecting to deploy the same by 23rd Dec. It is for the impacted tables we had on that day. 09/12: No alert was there for Surrogate key threshold. Surrogate key threshold was gradual as transactions are flowing into this table from last 10 years. We were not aware of reching the limit before 30/11. We are checking the feasibility of creating an alert to identify the surrogate key when it is nearing its threshold. 07/12: There were no alerts configured previously for this threshold, as this is the first occurrence of the issue. The threshold reached its limit gradually. The feasibility of creating an alert are being explored. | EDW Support |  | NA | 30/12/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1037 | >60 | December | 2022 | #VALUE!
Digital & Data | Digital & Data | 89006243 | 2022-11-30 | Retail dashboard sales flow was delayed | Considering the variance alert triggered at 20:18, why was it highlighted after a 75 mins delay at 21:05? | Problem identification & Alerting | Gaurav Kothari | Initial analysis was being performed to identify the issue, however, MIM process was invoked when it was identified to be a critical problem. It has been agreed to proactive inform MIM within the first 30 mins of an issue. | EDW Support |  | NA | 2022-01-12 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1037 | >60 | December | 2022 | #VALUE!
Digital & Data | Digital & Data | 89006243 | 2022-11-30 | Retail dashboard sales flow was delayed | Why did it take 4 hours to identify that the Datamart table had invalid records due to the overnight surrogate key issue? A SOP document to be created | Solution & Recovery | Gaurav Kothari/ Samik Ray | 08/12: Gaurav confimred that SOP has been created Since this is the first occurrence of the issue, it took a while for the team to understand the issue with invalid records. SOP creation is in progress | EDW Support |  | NA | 2022-08-12 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1037 | >60 | December | 2022 | #VALUE!
Digital & Data | Digital & Data | 89006243 | 2022-11-30 | Retail dashboard sales flow was delayed | A temp table was manually created to reset the primary key, what can be put in place to remove the manual intervention if the issue occurs again? | Solution & Recovery | Gaurav Kothari/ Samik Ray | 29/12: Got approval to implement on 29th due to long Christmas weekend, waiting for confirmation to close the action 22/12: Deployment is rescheduled to 28th Dec. Due to long weekend and peak we are preferring for any changes to be done post this long weekend only. 15/12: With the alert being created for the affected table, this action will be addressed 09/12: Tech are discussing the feasibility of revisiting the surrogate key threshold value to increase to highest possible available, however, this needs thorough analysis and investigations | EDW Support |  | NA | 30/12/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1037 | >60 | December | 2022 | #VALUE!
Digital & Data | Digital & Data | 89006243 | 2022-11-30 | Retail dashboard sales flow was delayed | Retail Dashboard comms | Business & IT Communication | George Louizou | 30/12: George has sent the contacts(Damien.x.Stephenson@marks-and-spencer.com; Tom.AguBenson@marks-and-spencer.com; Sarbjit.Thethi@marks-and-spencer.com; :Philippa.Knipe@marks-and-spencer.com; ) to all On Call BSP's 09/12: George has the contact details for OOO in the business team to amend the message. They do want TCS to do it though which makes sense. He will speak to Sandipan/Ankita so that, it can be arranged 06/12: George will now speak to the colleagues to understand how to take this forward during on call hours and share the contacts with the oncall BSPs. | Service Owner |  | NA | 30/12/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1037 | >60 | December | 2022 | #VALUE!
GTS | Enterprise Technology Platform | 88971977 | 2022-11-25 | Orders being placed offline & Sterling COM & DOM Unavailable | Document manual failover process and include the need to bring down application first, complete manual failover, stop start old primary DB & bring application back up | Solution & Recovery | Jishin Jacob | 19/12: Document has been review and published 15/12: Document has been prepared however SME review is expected to be completed by 16/12 05/12: Followed up with Jishin for an ETA 29/11: Followed up with action owner for an ETA | Unix Support |  | NA | 19/12/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1042 | >60 | December | 2022 | #VALUE!
GTS | ETP- Cloud operations / Frameworks | 88971977 | 2022-11-25 | Orders being placed offline & Sterling COM & DOM Unavailable | Root cause analysis to continue for the post web server restart issue (server is responsive but OMS is not working properly) | Root Cause | Prathyush MakkaparambilRamachandran/ Vijay Sekar | 11/01: The rootcaus is inconclusive 29/12: Spoke Anurag, awaiting more information on IBM, however there is backlog id DNCTA-7099 with the development team to track the root cause. 19/12: Followed up with Vijay for an update on the case with IBM 05/12: Root cause analysis from the application side is still in progress and have created a case with IBM # TS011288854. Few observations from replication process are being reviewed. 29/11: Followed with action owner for an ETA | Cloud Operation |  | NA | 2023-11-01 | Closed | NA | DNCTA-7099 |  | Saloni | 2025-02-10 | 1042 | >60 | January | 2023 | #VALUE!
GTS | ETP- Cloud operations / Frameworks | 88971977 | 2022-11-25 | Orders being placed offline & Sterling COM & DOM Unavailable | Follow up with Microsoft via ticket on feedback from Sterling IBM PMR | Root Cause | Prathyush MakkaparambilRamachandran/Anurag Sharma | 29/12: Team is still working on capturing the log and sharing it with Microsoft and this is being tracked under a back log ID - DNCTA-7099 19/12: Followed up with Anurag for further updates 13/12: Team is able to replicate ClassNotFound exception error. But still continue to investigate on the issue with application went to stale state after server restart. Below are the two ongoing action as part of this investigation. 1. We were able to bring down few of the application pods. However, despite readiness probe failure, the pods were able to serve the requests. A case will be raised with Microsoft. 2. While above happened, we see an increase in number of active DB connections. However, it did not bring down the DB which can cause application hung state. Need to understand more from DBA to replicate this scenario. 05/11:The issues was not reproduced in Production. Awaiting for the issue to be reproduced in VNP(non prod env) by app teams . We can bring the MS teams on call to check further.Awaiting an ETA. 29/11: Followed with action owner for an ETA | Cloud Operation |  | NA | 2023-11-01 | Closed | NA | DNCTA-7099 |  | Saloni | 2025-02-10 | 1042 | >60 | January | 2023 | #VALUE!
Customer Channels | Service Experience | 88971977 | 2022-11-25 | Orders being placed offline & Sterling COM & DOM Unavailable | Add to the Fulfilment backlog changes to the PayPal settlement & refund processes to prevent a delay in sending OF following service disruption | Problem avoidance | Vijayakumar Sekar | 30/11: The actions has been added to fulfillment backlog under DNCTA-6941 29/11: Followed with action owner for an ETA | Sterling |  | NA | 30/11/22 | Closed | NA | DNCTA-6941 |  | Saloni | 2025-02-10 | 1042 | >60 | November | 2022 | #VALUE!
Customer Channels | Service Experience | 88971977 | 2022-11-25 | Orders being placed offline & Sterling COM & DOM Unavailable | Add to Fulfilment backlog segregation within Sterling API infrastructure – 1. My Account/Mobile Apps services 2. Fulfilment services | Problem avoidance | Vijayakumar Sekar & Loganathan Kalyanasundaram | 30/11: The actions has been added to fulfillment backlog under FULRE-851 29/11: Followed with action owner for an ETA | Sterling |  | NA | 30/11/22 | Closed | NA | FULRE-851 |  | Saloni | 2025-02-10 | 1042 | >60 | November | 2022 | #VALUE!
Customer Channels | Service Experience | 88971977 | 2022-11-25 | Orders being placed offline & Sterling COM & DOM Unavailable | Add to the Fulfilment backlog the facility so if the secondary DB is not available Sterling API servers are automatically pointed to primary DB to prevent further impact to these services | Problem avoidance | Vijayakumar Sekar & Loganathan Kalyanasundaram | 30/11: The actions has been added to fulfillment backlog under DNCTA-6943 29/11: Followed with action owner for an ETA | Sterling |  | NA | 30/11/22 | Closed | NA | DNCTA-6943 |  | Saloni | 2025-02-10 | 1042 | >60 | November | 2022 | #VALUE!
Customer Channels | Service Experience | 88971977 | 2022-11-25 | Orders being placed offline & Sterling COM & DOM Unavailable | Once DBA recommendations are reviewed, plan changes accordingly (build, test, deploy) | Solution & Recovery | Vivekananda Gaikwad | 17/01: MCIP-3379 has raised to track the implementation of DBA parameter 17/01: Testing is still inprogress and planned to deploy in production before end of Jan 2023. 2022 19/12: Outage date needs to be finalised, probaly after peak 05/12: Followed with Vivekananda Gaikwad for an ETA 29/11: Followed with action owner for an ETA | Sterling |  | NA | 26/01/23 | Closed | NA | MCIP-3379 |  | Saloni | 2025-02-10 | 1042 | >60 | January | 2023 | #VALUE!
Customer Channels | Service Experience | 88971977 | 2022-11-25 | Orders being placed offline & Sterling COM & DOM Unavailable | App DBA to review recommendations from Oracle | Solution & Recovery | Vivekananda Gaikwad | 13/12: DBA recommendations has reviewed and implementation is yet to be planned which is tracked as separate action. 05/12: Followed with Vivekananda Gaikwad for an ETA 29/11: Followed with action owner for an ETA | Sterling |  | NA | 13/12/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1042 | >60 | December | 2022 | #VALUE!
GTS | Enterprise Technology Platform | 88980082 | 2022-11-24 | cSAP BW and BPC was unavailable | Investigate the root cause further to find why the ethernet adaptor was switching continually from primary VIOS to secondary VIOS (flapping). | Root Cause | Jafar/Sathish | 26/11: Root Cause was provided by IBM and the same has been updated in PR tab | Unix Support |  | NA | 26/11/22 | Closed | NA |  |  | Saloni | 2025-02-10 | 1043 | >60 | November | 2022 | #VALUE!
GTS | Enterprise Technology Platform | 88980082 | 2022-11-24 | cSAP BW and BPC was unavailable | Disable the ITM monitoring as IBM suggested we disable it due to the memory leak – however we are waiting until the iFIX (24/11 emergency CR) | Problem identification & Alerting | Jafar/Sathish | 29/11: The fix has been appllied to fix the memory leak 26/11: IBM provided an iFIX and agent upgrade to fix the memory leak on ITM agent which is planned(CRQ00000017290)9 to deploy on 27/11/2022. | Unix Support |  | NA | 29/11/22 | Closed | NA |  |  | Saloni | 2025-02-10 | 1043 | >60 | November | 2022 | #VALUE!
GTS | Enterprise Technology Platform | 88980082 | 2022-11-24 | cSAP BW and BPC was unavailable | Alerting to be introduced for VIOS (Virtual I/O Server) flapping on the UNIX | Problem identification & Alerting | Jafar/Sathish | 29/11: The alerts are in place now. 26/11: Team is inprocess of configuring the alerts | Unix Support |  | NA | 29/11/22 | Closed | NA |  |  | Saloni | 2025-02-10 | 1043 | >60 | November | 2022 | #VALUE!
GTS | Enterprise Technology Platform | 88980082 | 2022-11-24 | cSAP BW and BPC was unavailable | Quantum and SAP services are running on the primary VIOS, so why were only a few SAP servers not reachable when we shut down the primary VIOS? | Problem identification & Alerting | Jafar/Sathish | 29/11: IBM confirmed that they could not determine the cause of why only a few servers were impacted. This is believed to be a bug on the respective servers which triggered and a fix needs to be applied on these servers which will be planned as part of the patching activity. 26/11: Team is inprocess of understanding the cause of this | Unix Support |  | NA | 2022-05-12 | Closed | NA |  |  | Saloni | 2025-02-10 | 1043 | >60 | December | 2022 | #VALUE!
GTS | ETP- Connectivity,service & solution | 88980082 | 2022-11-24 | cSAP BW and BPC was unavailable | Alerting to be introduced for VIOS (Virtual I/O Server) flapping on the Network. | Problem identification & Alerting | Rajesh S | 29/11: The alerts are in place now. 26/11: Team is inprocess of configuring the alerts | Network |  | NA | 29/11/22 | Closed | NA |  |  | Saloni | 2025-02-10 | 1043 | >60 | November | 2022 | #VALUE!
Customer Channels | Service Experience | 88963304 | 2022-11-23 | Click and Collect orders are incorrectly showing as overdue after 7 days | Is it possible to set up an alert on the Collection App for early overdue date? | Problem identification & Alerting | Lokesh Kumar Sukumar | 29/11: Application is on AWS. It is not possible to setup alert on AWS. We had plan to move application on azure V2 then the alerts will be setup. The migration plan will tracked under EG-5419 23/11: PIR has been published actions to be tracked | BOSS Support |  | NA | 29/11/22 | Closed | NA | EG-5419 |  | Saloni | 2025-02-10 | 1044 | >60 | November | 2022 | #VALUE!
Customer Channels | Service Experience | 88963304 | 2022-11-23 | Click and Collect orders are incorrectly showing as overdue after 7 days | How was this issue on ready to collect emails not picked up within SIT testing? We know now this issue started in production between 30th Aug to 10th Sep. Had a Sterling Release on 5th Sep. | Problem identification & Alerting | Rajammal Subramania Pillai | 29/11:Regression pack contain validation point to check whether email is getting triggered or not but mail content validation will be added only when there is change for email is included in release scope. As discussed with Emma, considering the criticality of project, Ready to collect email content validation point is added in to the regression suite 23/11: PIR has been published actions to be tracked | Sterling |  | NA | 29/11/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1044 | >60 | November | 2022 | #VALUE!
Customer Channels | Service Experience | 88963304 | 2022-11-23 | Click and Collect orders are incorrectly showing as overdue after 7 days | Is it possible to set up an alert on Sterling for a change in last collection day dates in SYW 1, 2, 3 & 4? | Problem identification & Alerting | Rajeev Ekambaram | 25/11: Alerts have been configured, to notify if there is an "Incorrect collection expiry in OMS" 23/11: PIR has been published actions to be tracked | Sterling |  | NA | 25/11/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1044 | >60 | November | 2022 | #VALUE!
Customer Channels | Service Experience | 88965488 | 2022-11-22 | Orders picked not moving to pack screen in SPPD application | Capture the audit status updates in SPPD application | Problem identification & Alerting | Arthi Suriyanarayanan | 30/01: The production deployment is completed 17/01: The prod deployment is expected to complete on next week 22/12: The development of this is completed and the testing and prod deployment is in production 14/12: Followed up with the team and awaiting response 25/11: Spoke to Saswati Sinha (TPM) who informed that this will be actioned in Sprint 5 which will start on 26th Nvember and end on 12th December 22/11: PIR has been published actions to be tracked | Web Engg Team |  | NA | 30/01/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1045 | >60 | January | 2023 | #VALUE!
Customer Channels | Service Experience | 88965488 | 2022-11-22 | Orders picked not moving to pack screen in SPPD application | Capture the audit status updates in DRL job | Problem identification & Alerting | Arthi Suriyanarayanan | 25/11: This action is completed now 22/11: PIR has been published actions to be tracked | Web Engg Team |  | NA | 25/11/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1045 | >60 | November | 2022 | #VALUE!
Customer Channels | Service Experience | 88965488 | 2022-11-22 | Orders picked not moving to pack screen in SPPD application | Configure Ageing alert (e.g.: status change like awaiting pick in more than 2 hours) | Problem identification & Alerting | Lokesh Kumar Sukumar | 30/01: Team confirmed alerts cannot be generated due to integration unavailability between MongoDB and New relic. 17/01: Saswati Sinha informed that this will be completed 22/12: Lokesh confirmed that this action is dependant on the above action i.e. Capture the audit status updates in SPPD app 14/12: Followed up with the team and awaiting response 25/11: Spoke to Lokesh who informed that Webengg team needs to Capture the audit status updates in SPPD application after which an alerting can be introduced. Currently, webengg team is trying to action in Sprint5. 22/11: PIR has been published actions to be tracked | BOSS Support |  | NA | 30/01/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1045 | >60 | January | 2023 | #VALUE!
Customer Channels | Service Experience | 88965488 | 2022-11-22 | Orders picked not moving to pack screen in SPPD application | Code revamping requried to change job as event driven updates | Problem avoidance | Steve | 29/11: Backlog has been raised to track this 25/11: Requested Arthi to get the backlog ID, awaiting response 22/11: Backlog to raised | Web Engg Team |  | NA | 29/11/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1045 | >60 | November | 2022 | #VALUE!
Customer Channels | Service Experience | 88965488 | 2022-11-22 | Orders picked not moving to pack screen in SPPD application | A tool to be developed for the DevOps / Ops team to process the referenceIDs status change / DRL processing. | Solution & Recovery | Steve | 29/11: Backlog has been raised to track this 25/11: Requested Arthi to get the backlog ID, awaiting response 22/11: Backlog to raised | Web Engg Team |  | NA | 29/11/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1045 | >60 | November | 2022 | #VALUE!
GTS | Enterprise Technology Platform | 88964193 | 2022-11-21 | Non Customer or unregistered devices unable to login to Microsoft applications | These type of policy changes are carried out by InfoSec on a very regular basis, similar to AD, so can be outside the change process – however what type of internal communication process can be implemented so that wider stakeholders are aware of the work - so that fault finding can be much easier in the event of an incident. | Problem avoidance | Ian Banks/Jason Stiff | 21/11: Initial PIR conducted and actions have been agreed 25/11: Followed up with Cyber Sec. Awaiting an update. 02/12: Discussions are ongoing, awaiting an update. 20/12: Ian Banks, Simon Harrish and Ian Kirk to handle it internally | Cyber Security |  | NA | 21/12/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1046 | >60 | December | 2022 | #VALUE!
GTS | Enterprise Technology Platform | 88964193 | 2022-11-21 | Non Customer or unregistered devices unable to login to Microsoft applications | Is there a central place where the errors are logged for colleagues not being able to log in – if we do, then a threshold alert could be set and this would help quicker fault finding. | Problem identification & Alerting | Jason Stiff/Promode | 21/11: Initial PIR conducted and actions have been agreed 23/11: Additional discussions are in place before configuring an alert. Next update on 30/11 02/12: Discussions are ongoing, awaiting an update 20/12: Owing to peak activities, Ian will meet with Jason Stiffe and conclude the same in Jan 5th 31/01: This is not feasible | Cyber Security |  | NA | 31/01/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1046 | >60 | January | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 88964193 | 2022-11-21 | Non Customer or unregistered devices unable to login to Microsoft applications | Obtain a formal root cause statement from Microsoft | Root Cause | Vinish/Adrian | 21/11: Initial PIR conducted and actions have been agreed 27/11: Awaiting updates from Vinish 01/12: Dropped an email to Vinish, will wait until 08/12 and then speak to David and Stephen 20/12: A bug in Microsoft end was identified after a change on 14/11 which was reverted to fix the issue permanently. Microsoft advise their change was “There was a problem introduced in the latest build on the Grant control configuration pane.” No further updates from Microsoft can be procured. | 3rd Party |  | NA | 20/12/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1046 | >60 | December | 2022 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 88961520 | 2022-11-15 | Carrier label print failures across Bradford C&H and Donington | Bradford raised multiple logs on this issue – Attari to reiterate the appropriate log raising approach to site | Supplier and support involvement | Attari Ghulam/Vinoth | 18/11: The process has been re-iterated to the operations team 15/11: Initial PIR conducted and actions agreed | Service Owners |  | NA | 18/11/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1052 | >60 | November | 2022 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 88961520 | 2022-11-15 | Carrier label print failures across Bradford C&H and Donington | Murali to provide exact timelines to Tim Cox of when the Sorted desk was called and what the response was, so that Tim can see if the Sorted desk responded appropriately. | Supplier and support involvement | Murali Srinivasan | 18/11: Murali shared the timelines when CD reached Sorted Service Desk. Tim Cox advised Customer to call out the sorted helpdesk once an incident was raised to get an engineer assigned. In this instance, CD IT called sorted after 30 minutes of emailing sorted which resulted in the delay. 15/11: Initial PIR conducted and actions agreed | Service Owners |  | NA | 18/11/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1052 | >60 | November | 2022 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 88961520 | 2022-11-15 | Carrier label print failures across Bradford C&H and Donington | Complete planned Azure API Management logs output to monitoring/alerting platform. This enhances agility to diagnose failure scenario for customers. | Problem identification & Alerting | Tim Cox | 4/01: Tim confirmed that this action is completed now 19/12: Tim Cox is OOO and will be return on 3rd January 2023 7/12: Tim confirmed this is in-progress and ETA would be 16th Dec 5/12: Reminder email sent to Tim, however Tim is OOO and will be return on 6th Dec 25/11: Tim Cox is OOO until 29th Nov. This will be followedup with Tim upon his return 15/11: Initial PIR conducted and actions agreed | 3rd Party |  | NA | 2023-04-01 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1052 | >60 | January | 2023 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 88961520 | 2022-11-15 | Carrier label print failures across Bradford C&H and Donington | Investigate root cause further to find why the instances failed in the first place | Root Cause | Tim Cox | 22/11: Root cause has been obtained and updated in PR tab 18/11: Tim Cox advised that team is investigating on the RCA 15/11: Initial PIR conducted and actions agreed | 3rd Party |  | NA | 22/11/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1052 | >60 | November | 2022 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 88961520 | 2022-11-15 | Carrier label print failures across Bradford C&H and Donington | Complete planned work to increase the Auth service to three instances, increasing redundancy. | Problem avoidance | Tim Cox | Complete | 3rd Party |  | NA | 16/11/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1052 | >60 | November | 2022 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 88961520 | 2022-11-15 | Carrier label print failures across Bradford C&H and Donington | Implement monitors to detect Kubernetes pod restarts. This would have detected this failure scenario. | Problem identification & Alerting | Tim Cox | Complete | 3rd Party |  | NA | 16/11/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1052 | >60 | November | 2022 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 88961520 | 2022-11-15 | Carrier label print failures across Bradford C&H and Donington | Implement monitors to ensure expected instance counts are running. This would have detected running with single instance for an extended period. | Problem identification & Alerting | Tim Cox | 18/11: Alerting and monitoring is in place 17/11 MC agreed with Sorted that they come back with cause before the weekend | 3rd Party |  | NA | 18/11/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1052 | >60 | November | 2022 | #VALUE!
Customer Channels | Service Experience | 88949337 | 2022-11-14 | Store colleagues unable to print ISF labels via SPPD | Rootcause to be indentifed. | Root Cause | Arthi Suriyanarayanan | 22/11: Root caused has been identified and actions are tracked under 88965488 18/11: The follow-up PIR meeting has been postponed to next week due to ongoing incidents in customer channels area | Service Owner |  | NA | 22/11/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1053 | >60 | November | 2022 | #VALUE!
Customer Channels | Service Experience | 88949337 | 2022-11-14 | Store colleagues unable to print ISF labels via SPPD | Ensure regression testing to be performed and end to end impact analysis to be carried out before we roll-out any changes into production | Problem avoidance | Jeevan Pattanaik | 14/11: Re-iterated to product teams to perform end to end impact analysis and testing before implementing the changed to production | Web Engg Team |  | NA | 14/11/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1053 | >60 | November | 2022 | #VALUE!
Customer Channels | Customer Engagement | 88950014 | 2022-11-11 | Some customers facing order tracking issues | Review deployment process for Parcel Lab POD. To prevent previous changes being overridden when changes are deployed (Moving POD to read only mode) | Problem avoidance | Abhishek z kumar | 15/11: This will be picked up in Sprint 5. Please find JIRA Ref: 6836 | Devops |  | NA | 15/11/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1056 | >60 | November | 2022 | #VALUE!
Customer Channels | Customer Engagement | 88950014 | 2022-11-11 | Some customers facing order tracking issues | This solution is an interim solution, full solution should be Sorted Pro updates Sorted React of the shipments. When is this planned in the road map to be delivered | Permanent fix | Clare Peririra | This is unlikely to change during this contract time, whilst we review future partnerships and solution. This method of communicating the order details isn’t going to change in the next 1 year 11/22: This is not possible at the moment. | Product Owner |  | NA | 20/11/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1056 | >60 | November | 2022 | #VALUE!
Customer Channels | Customer Engagement | 88950014 | 2022-11-11 | Some customers facing order tracking issues | Check the possibility of setting up an alert to cover this scenario | Problem identification & Alerting | Rajeev Ekambaram/Vipin x Kumar | 15/11: Creating an alert for this scenario is not technically feasible | Devops |  | NA | 15/11/2022 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1056 | >60 | 15/11/2022 | #VALUE! | #VALUE!
Customer Channels | Service Experience | 88953113 | 2022-11-10 | Store colleagues unable to find parcels via the Collection App | Standard is Akamai is used for load balancing across Customer not Apigee. Need a review to happen should Apigee be standard as well and if so look at the Whitelisting model (should we whitelist Apigee prod & DR as standard?) | Problem avoidance | Aravind Rajaveeraswamy | 30/11: Jira ID is 5380 28/11: waiting for the Jira to be shared 23/11: ETA for the redployment in a store is by 29th, however for all stores it will deployed post peak 18/11: change was reverted as part of the incident. Part of redeployment we will address this | Sterling Support |  | NA | 30/11/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1057 | >60 | November | 2022 | #VALUE!
Customer Channels | Service Experience | 88953113 | 2022-11-10 | Store colleagues unable to find parcels via the Collection App | Service Desk to follow an existing process to call Service Owner for all severity 1 & 2 incidents they raise | Business & IT Communication | Emma Rotheram | 29/11: Now it is agreed that SO will be called during on call 22/11: Emma will connect with Rehan and update us 18/11: Followed up on the status | Service Owner |  | NA | 29/11/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1057 | >60 | November | 2022 | #VALUE!
Customer Channels | Selling Experience | 88953113 | 2022-11-10 | Store colleagues unable to find parcels via the Collection App | Retail Ops to follow the existing process when they are facing issues in store, contact Customer Ops Hub/Service Owners | Business & IT Communication | Hisham Khalid | Retail Ops have been advised to follow the exisiting process during an instore issue to contact service leads, | Service Owner |  | NA | 15/11/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1057 | >60 | November | 2022 | #VALUE!
Customer Channels | Selling Experience | 88953113 | 2022-11-10 | Store colleagues unable to find parcels via the Collection App | Whitelist Collection App DR IP’s | Permanent fix | Jeevan Pattnaik/Arun Kumar | Tech team has whitelistd the application DR Ips. | TPM |  | NA | 14/11/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1057 | >60 | November | 2022 | #VALUE!
Customer Channels | Service Experience | 88953113 | 2022-11-10 | Store colleagues unable to find parcels via the Collection App | Add New Relic alert to cover when an origin is not serving traffic – Prod & DR | Problem identification & Alerting | Jeevan Pattnaik/Arun Kumar | 22/11: Alert added confirmed by Arun 18/11: Followed up on the status 15/11: In progress in non prod | Web Engg Team |  | NA | 22/11/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1057 | >60 | November | 2022 | #VALUE!
Customer Channels | Service Experience | 88953113 | 2022-11-10 | Store colleagues unable to find parcels via the Collection App | Create a dashboard to cover monitoring of message processing between Sterling & Collection App | Problem identification & Alerting | Jeevan Pattnaik/Arun Kumar | 25/11: Dashboard created, confirmed by Arun 22/11: In Progress confirmed by Arun 18/11: Followed up on the status | Web Engg Team |  | NA | 25/11/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1057 | >60 | November | 2022 | #VALUE!
Customer Channels | Service Experience | 88953113 | 2022-11-10 | Store colleagues unable to find parcels via the Collection App | Whitelisting process, need to validate our whitelisting before traffic is pushed for a migration/new service go live | Permanent fix | Jeevan Pattnaik/Arun Kumar | 29/11: Got the Jira ID from Arun 28/11: Followed up with Saswati Sinha, the replacement of Jeevan 22/11: In Progress confirmed by Arun 18/11: Followed up on the status 15/11: For current change validation is in progress | Web Engg Team |  | NA | 29/11/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1057 | >60 | November | 2022 | #VALUE!
Customer Channels | Service Experience | 88953113 | 2022-11-10 | Store colleagues unable to find parcels via the Collection App | Set up alerting to cover degraded performance on the Collection App API’s | Problem identification & Alerting | Jeevan Pattnaik/Arun Kumar | 29/11: Got the Jira ID from Arun 28/11: Followed up with Saswati Sinha, the replacement of Jeevan 22/11: In Progress confirmed by Arun 18/11: Followed up on the status 15/11: This action is in progress. | Web Engg Team |  | NA | 29/11/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1057 | >60 | November | 2022 | #VALUE!
Customer Channels | Service Experience | 88953113 | 2022-11-10 | Store colleagues unable to find parcels via the Collection App | Post implementation validation checks need to be carried out at the right time e.g. post change deployment, time period when service will be used | Problem avoidance | Jeevan Pattnaik/Arun Kumar | 29/11: Got the Jira ID from Arun 28/11: Followed up with Saswati Sinha, the replacement of Jeevan 22/11: In Progress confirmed by Arun 18/11: Followed up on the status | Web Engg Team |  | NA | 29/11/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1057 | >60 | November | 2022 | #VALUE!
Customer Channels | Service Experience | 88953113 | 2022-11-10 | Store colleagues unable to find parcels via the Collection App | Post implementation validation checks need to include where applicable API performance monitoring within Apigee & New Relic | Problem avoidance | Jeevan Pattnaik/Arun Kumar | 29/11: Got the Jira ID from Arun 28/11: Followed up with Saswati Sinha, the replacement of Jeevan 22/11: In Progress confirmed by Arun 18/11: Followed up on the status | Web Engg Team |  | NA | 29/11/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1057 | >60 | November | 2022 | #VALUE!
Customer Channels | Service Experience | 88953113 | 2022-11-10 | Store colleagues unable to find parcels via the Collection App | Add configuration to Apigee to route traffic to Prod when DR is not reachable | Permanent fix | Jeevan Pattnaik/Arun Kumar | 25/11: Done, confirmed by Arun 22/11: In Progress confirmed by Arun 18/11: Followed up on the status 15/11: Dev, Stage , PT configuration in Progress | TPM |  | NA | 25/11/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1057 | >60 | November | 2022 | #VALUE!
Customer Channels | Service Experience | 88953113 | 2022-11-10 | Store colleagues unable to find parcels via the Collection App | Reemphasise process to engage Service Owner’s for business/customer impacting alerts – Process is Integration Team will engage Application Teams and its Application Teams responsibility to engage SO. | Business & IT Communication | Rajasekar Subramanian/ Lokesh Kumar | 18/11: This action has been completed by Rajasekar S | Integration Services |  | NA | 18/11/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1057 | >60 | November | 2022 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 88947892 | 2022-11-10 | Carrier label print failures observed in Bradford (C&H and Foods) and Castle Donington | Sorted are trying to find out the cause from their sub domain hosts, BRANDIT vendor actions are below Ensure APIM logs are surfaced in Datadog to improve speed of diagnosis, Further improve alarms around unusual request patterns and Review DNS setup and redundancy to reduce single points of failure | Root Cause | Gemma/Tim Cox | BRANDIT has done •A post project audit of configuration files has been completed •The continuous monitoring of DNS service operation, security and availability has been reinforced •The configuration file issue has been rectified and further audit will be implemented | 3rd Party |  | NA | 22/11/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1057 | >60 | November | 2022 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 88947892 | 2022-11-10 | Carrier label print failures observed in Bradford (C&H and Foods) and Castle Donington | Did Sorted have the adequate alerting to notify them of this issue? | Problem identification & Alerting | Peter Ennis | Peter has confirmed that all possible alerting to capture this type of issue is live and does not need changing. | 3rd Party |  | NA | 2022-10-11 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1057 | >60 | November | 2022 | #VALUE!
Customer Channels | Platform & Store Ops | 88938344 | 2022-11-04 | Issue in printing tickets for 116 Foods UPCs in ECS | Raise an issue with ECS that when ringing their service desk number it went through to someone’s voicemail and it took time to get a resource until someone manually pulled in Chris Bell. | Supplier and support involvement | Chris Thomas | 15/11: Being followed up wih Chris 20/11: Chris Bell has now spoken to the team at ECS to follow a proper escalation process in times of a critical incident. In addition, we have all possible contacts to escalate to ECS during an incident. | 3rd Party |  | NA | 20/11/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1063 | >60 | November | 2022 | #VALUE!
Customer Channels | Platform & Store Ops | 88938344 | 2022-11-04 | Issue in printing tickets for 116 Foods UPCs in ECS | Create an incident run book for the most commonly reported incidents. Vel to verify that the run book is technically correct. | Solution & Recovery | Hima Varghese | This action has been completed. | ECS Team(TCS) |  | NA | 2022-09-11 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1063 | >60 | November | 2022 | #VALUE!
Customer Channels | Platform & Store Ops | 88938344 | 2022-11-04 | Issue in printing tickets for 116 Foods UPCs in ECS | Hima to ensure that the contact repository will be updated for the ECS SME within TCS | Supplier and support involvement | Hima Varghese | This action has been completed. | ECS Team(TCS) |  | NA | 2022-08-11 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1063 | >60 | November | 2022 | #VALUE!
Customer Channels | Platform & Store Ops | 88938344 | 2022-11-04 | Issue in printing tickets for 116 Foods UPCs in ECS | Mark to send a mail to MIM team with the keys roles within Tech and the Business for ECS | Business & IT Communication | Mark Charlwood | 15/11: Being followed up with Mark 17/11: Mark has sent the details. Hence this action is closed | Product Owner |  | NA | 20/11/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1063 | >60 | November | 2022 | #VALUE!
GTS | Enterprise Technology Platform | 88938344 | 2022-11-04 | Issue in printing tickets for 116 Foods UPCs in ECS | Add Mark to MI Notification DL | Business & IT Communication | Sravan Kumar Garjala | 7/11: Mark C has been added to PO DL 4/11: WO 1260621 has been created to add Mark C into Product owner DL so that Mark will get MIM notifications | Service Management |  | NA | 2022-07-11 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1063 | >60 | November | 2022 | #VALUE!
Supply Chain | Foods Supply Chain | 88940631 | 2022-11-03 | Delay in sending UPT "units per tray" Extract File to 27 foods suppliers | The file-watcher alert was not triggered yesterday due to a bug in the alerting logic, hence there was further delay to understand the issue and generate the extract. This alert will be fixed by today (03/11). | Problem identification & Alerting | Gopinath Shanmugam | 03/11: Alerts have been configured | Foods SCL |  | NA | 2022-03-11 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1064 | >60 | November | 2022 | #VALUE!
Supply Chain | Foods Supply Chain | 88940631 | 2022-11-03 | Delay in sending UPT "units per tray" Extract File to 27 foods suppliers | Joey to review the business communication process | Business & IT Communication | Joey Ocansey | 04/11: Discussion took place with Antonia due to a communication gap into Q Business from Tech - And it has been agreed that Q Business will be looped in all Q related issues, for visibility (and input where necessary), going forward. Joey has also stipulated that the Q Tech team will also highlight issues in the Q Hypercare chat so Q Business are up to date on progress/updates on any given issue. Boopathy and Team will be making sure they highlight issues in the central support teams channel for quicker/better visibility of issues as soon as we are aware of them. This will allow us to engage MIM and wider teams more efficiently | Service Owner |  | NA | 2022-04-11 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1064 | >60 | November | 2022 | #VALUE!
Supply Chain | Foods Supply Chain | 88940631 | 2022-11-03 | Delay in sending UPT "units per tray" Extract File to 27 foods suppliers | Ensure that if support teams are working on an incident, they need to post it in the Teams support channel and anywhere else to make other key stakeholders aware. | Problem identification & Alerting | NOTE TO ALL | 03/11: It has been agreed in the PIR call that, team will notify the key stakeholders in case of any ongoing issues. | Foods SCL |  | NA | 2022-03-11 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1064 | >60 | November | 2022 | #VALUE!
Supply Chain | Foods Supply Chain | 88940631 | 2022-11-03 | Delay in sending UPT "units per tray" Extract File to 27 foods suppliers | Foods team to suggest improvements on how to get the impacted UPC’s, suppliers and quantities affected in a timelier manner | Impact Analysis | Preethi Rajaram | 07/11: SOP has been created with table names and SQLs to extract required information based on the ask from business to understand the impact soon. | Foods SCL |  | NA | 2022-07-11 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1064 | >60 | November | 2022 | #VALUE!
Supply Chain | Foods Supply Chain | 88940631 | 2022-11-03 | Delay in sending UPT "units per tray" Extract File to 27 foods suppliers | Ensure appropriate hypercare is maintained during peak periods, | Problem avoidance | Santhosh Veeraraghavan | 07/11: Hypercare is in place. In addition, a plan is in place to have a MoD for all critical flows in Foods portfolio. | Foods SCL |  | NA | 2022-07-11 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1064 | >60 | November | 2022 | #VALUE!
Supply Chain | Foods Supply Chain | 88940631 | 2022-11-03 | Delay in sending UPT "units per tray" Extract File to 27 foods suppliers | Create a SOP for how to recover from such issues with the constraint UPT job in future | Solution & Recovery | Santhosh Veeraraghavan | 08/11:SOP has been created in SCRD 04/11: Followed up with actions owner for the latest | Foods SCL |  | NA | 2022-08-11 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1064 | >60 | November | 2022 | #VALUE!
Supply Chain | Foods Supply Chain | 88940631 | 2022-11-03 | Delay in sending UPT "units per tray" Extract File to 27 foods suppliers | How will Quantum handle these kind of issues in future such as file incorrect/corrupt data – check for thresholds. | Permanent fix | Shravan MK | 07/11: Quantum already has threshold and corruption checks for all the interfaces. We have one for UOD data as well, but the threshold check was not triggered because the job itself was not triggered as the file was delayed and job was skipped as it wasn't a mandatory job. This is now permanently fixed. The job is made a mandatory job. https://jira.marksandspencer.app/browse/FSORP-19643 | Quantum |  | NA | 2022-07-11 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1064 | >60 | November | 2022 | #VALUE!
Supply Chain | Foods Supply Chain | 88940631 | 2022-11-03 | Delay in sending UPT "units per tray" Extract File to 27 foods suppliers | The Quantum batch skipped the UPT extract file as it was not set to be a “mandatory” file – Action to make the job mandatory. | Problem avoidance | Shravan MK | 03/11: This has now been rectified to prevent the issue. | Quantum |  | NA | 2022-03-11 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1064 | >60 | November | 2022 | #VALUE!
Customer Channels | Platform & Store Ops | 88938344 | 2022-11-02 | Issue in printing tickets for 116 Foods UPCs in ECS | Foods pricing & promotions have confirmed that colleagues were making changes for the past few weeks in ECS as there was an issue with the changes being done in SAP – which should be the normal way. This issue has now been fixed by ECS as of three weeks ago and Foods pricing and promotions will tell all relevant colleagues that they can now go back to the normal process of making any changes in SAP. | Solution & Recovery | Jonathan Philbey | This has been closed | Food pricing Operations |  | NA | 2022-02-11 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1065 | >60 | November | 2022 | #VALUE!
Customer Channels | Platform & Store Ops | 88938344 | 2022-11-02 | Issue in printing tickets for 116 Foods UPCs in ECS | Foods pricing and promotions will enquire with ECS if they can remove the functionality to make changes. All implications of this are to be analysed before any actions are taken. | Permanent Fix | Jonathan Philbey/Chris Bell (ECS) | This action has been completed. | Food pricing Operations |  | NA | 2022-02-11 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1065 | >60 | November | 2022 | #VALUE!
Customer Channels | Platform & Store Ops | 88938344 | 2022-11-02 | Issue in printing tickets for 116 Foods UPCs in ECS | If the above functionality cannot be taken away from ECS due to genuine requirements, then what prompts can be put into the ECS GUI to warn the colleague of the action about to take place? | Permanent Fix | Jonathan Philbey/Chris Bell (ECS) | The functionality has been removed as of 02/11 | Food pricing Operations |  | NA | 2022-02-11 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1065 | >60 | November | 2022 | #VALUE!
Customer Channels | Platform & Store Ops | 88938344 | 2022-11-02 | Issue in printing tickets for 116 Foods UPCs in ECS | Verify and confirm all the relevant contact numbers for ECS including Service Desk 24/7 and out of hours | Supplier and support involvement | Velrajan C | This has been closed | ECS Team(TCS) |  | NA | 2022-02-11 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1065 | >60 | November | 2022 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 88928761 | 2022-11-01 | Issue in processing ecom orders at CD | How can the script be modified to handle such issues during clock change activity? | Permanent Fix | Anand Ashokan | 08/11: Tech debt is raised for the same and will be picked up in later sprints of Q3 or early in Q4. This has been closed now. | WMS Product team |  | NA | 2022-09-11 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1066 | >60 | November | 2022 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 88928761 | 2022-11-01 | Issue in processing ecom orders at CD | How can we systemically identify the issue in future? | Problem identification & Alerting | Anand Ashokan | 08/11: It is not possible unless alert monitoring is placed for the same. Since this issue is specific to clock change , we will improve the hypercare process during the clock changes. | WMS Product team |  | NA | 2022-09-11 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1066 | >60 | November | 2022 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 88928761 | 2022-11-01 | Issue in processing ecom orders at CD | Considering the issue started at 00:00, why was the issue reported with a delay of 9 hours? | Problem identification & Alerting | CD flow room/Murali Srinivasan | 08/11: CD has an internal meeting with the team who confirmed lack of resourcing which delayed the proactiveness in reporting the issue. This has now been addressed | CD flow room |  | NA | 2022-09-11 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1066 | >60 | November | 2022 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 88928761 | 2022-11-01 | Issue in processing ecom orders at CD | What can be the ideal solution to this issue considering the script cannot be tweaked? | Permanent Fix | Murali Nasapu | 08/11: This has been confirmed to be long term. A backlog has to be raised. 14/11: Anand advised this has been added as a Tech debt in the CD backlog, hence closing it off. | WMS Product team |  | NA | 15/11/2022 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1066 | >60 | 15/11/2022 | #VALUE! | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 88928761 | 2022-11-01 | Issue in processing ecom orders at CD | Improve the hypercare in place during clock change activities. | Problem avoidance | Murali Srinivasan | 08/11: This has been reitetrated to the team | WMS support |  | NA | 2022-11-09 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1066 | >60 | September | 2022 | #VALUE!
Customer Channels | Platform & Store Ops | 88933293 | 2022-11-01 | ECS application was inaccessible | ECS are requesting full details of the enlargement change in writing | Problem avoidance | Anees Ahamed | 1/11: Anees to lead and own this and take ECS through the change verbally via a call and afterwards in writing by EOD 02/11 2/11: The App walk through given via Teams call. App workflow is shared to ECS[Chris Bell] via email. | ECS Team |  | NA | 2022-02-11 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1066 | >60 | November | 2022 | #VALUE!
Customer Channels | Platform & Store Ops | 88933293 | 2022-11-01 | ECS application was inaccessible | Did ECS get an alert on their infrastructure and if so, when did the alert come in at the ECS end for memory breach? | Problem identification & Alerting | Chris (ECS) | 07/11 : Chrish to come back with updates 11/11: Email follow up sent 15/11: Spoken to Chris to send us an update on all the pending actions 16/11: ECS received an alert at 7:13 and started investigating the issue. | 3rd Party |  | NA | 20/11/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1066 | >60 | November | 2022 | #VALUE!
Customer Channels | Platform & Store Ops | 88933293 | 2022-11-01 | ECS application was inaccessible | ECS have added two additional TOMCAT instances on top of the existing two – this will give us more CPU and more capacity. | Solution & Recovery | Chris (ECS) | 07/11 : Chrish to come back with updates 11/11: Email follow up sent 15/11: Spoken to Chris to send us an update on all the pending actions 16/11: This action was completed. | 3rd Party |  | NA | 16/11/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1066 | >60 | November | 2022 | #VALUE!
Customer Channels | Platform & Store Ops | 88933293 | 2022-11-01 | ECS application was inaccessible | Based on action 4 do ECS feel that the enlargement change has been deployed correctly or would they suggest further changes. | Problem avoidance | Chris (ECS) | 07/11 : Chrish to come back with updates 11/11: Email follow up sent 15/11: Spoken to Chris to send us an update on all the pending actions 17/11: the initial enlargement change was implemented using duplicated web service calls to fetch the same data as opposed to caching the data and reusing which would be more efficient. The Customer application team has already made changes to the app to implement caching and this has been implemented in a small number of stores with a view to rolling this out store wide on November 23rd. 23/11: This action has been completed as the change has been rolled out across estate. | 3rd Party |  | NA | 23/11/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1066 | >60 | November | 2022 | #VALUE!
Customer Channels | Platform & Store Ops | 88933293 | 2022-11-01 | ECS application was inaccessible | The priority is to get the testing environment up and running as quickly as possible and work with ECS to raise the necessary changes. Provide ECS with our volumes so that load can be replicated in testing. | Problem avoidance | Hima/Mark Charlwood | 1/11: Mark, Hima, technical teams and ECS to meet on 02/11. Provide a plan going forward day by day of how this test environment will be created with the test plan. 9/11: Perf test environment set up by ECS team - Customer has to raise this as CR. Since CR process takes time- a plan has been agreed to implement Honeywell optimised code solution in phases and ECS to provide a volume stats. CR to be raised on 14/11 15/11: ECS is expecting a change request for setting up Perf infra set up whic involved budget. This is currently being discussed 19/11: A backlog- EP-1145 has been raised as PT execution for ECS. this will be taken into sprint- once Andy and Chris Bell has agreement on infra set up | ECS Team |  | NA | 19/11/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1066 | >60 | November | 2022 | #VALUE!
Customer Channels | Platform & Store Ops | 88933293 | 2022-11-01 | ECS application was inaccessible | The volume of search and print prior to 09:00 on 01/11 was a lot higher than usual. | Solution & Recovery | Velrajan C | Closed | ECS Team(TCS) |  | NA | 2022-01-11 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1066 | >60 | November | 2022 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 88928760 | 2022-10-31 | Issue in processing ecom orders at CD | Can the delivery date timestamp be changed in OMS from 23:00? | Problem avoidance | Anand Ashokan | 08/11: This is not feasible. | WMS Product team |  | NA | 2022-11-09 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1067 | >60 | September | 2022 | #VALUE!
Customer Channels | Service Experience | 88907857 | 2022-10-26 | Drop in Brands availability picture | Is it possible to alert from the availability dashboard used by the business | Problem identification & Alerting | Emma Rotheram | 16/11: The requirement is no longer need as the team have configured an alerting in WCS to notify when their is a 20% drop to number of products showing out of stock on the website compared to previous day ( out of stock alert). 31/10 : The dashboards are supported by Customer Adobe team. Emma is awaiting for their response. | Service Owners |  | NA | 16/11/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1072 | >60 | November | 2022 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 88907857 | 2022-10-26 | Drop in Brands availability picture | Potentially a way to correct items to 0 qty in the future is to add this to the existing SOD process | Problem avoidance | Kunal Chichkar | 31/10:This is action is no longer needed as the OMS sterling updates '0 Qty' to SKU's which are not part of SOD full refresh automatically. | WMS Devops |  | NA | 31/10/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1072 | >60 | October | 2022 | #VALUE!
Customer Channels | Service Experience | 88907857 | 2022-10-26 | Drop in Brands availability picture | Set up alert in OMS which compares SOD to previous run, more than X% difference on either item or qty level | Problem identification & Alerting | Rajeev Ekambaram | 27/10: The alerts have been setup. 26/10: Team will configure alert before EOD, 27/10 | Sterling |  | NA | 27/10/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1072 | >60 | October | 2022 | #VALUE!
Customer Channels | Service Experience | 88907857 | 2022-10-26 | Drop in Brands availability picture | Set up alert in OMS when SOD runs outside of standard window 6am to midnight | Problem identification & Alerting | Rajeev Ekambaram | 27/10: The alerts have been setup. 26/10: Team will configure alert before EOD, 27/10 | Sterling |  | NA | 27/10/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1072 | >60 | October | 2022 | #VALUE!
Customer Channels | Service Experience | 88907857 | 2022-10-26 | Drop in Brands availability picture | Sterling product team to take SO approval when re-triggering SOD in day | Problem avoidance | Rajeev Ekambaram | 24/10: Sterling team has agreed to secure SO approval when re-triggering SOD in day | Sterling |  | NA | 24/10/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1072 | >60 | October | 2022 | #VALUE!
Customer Channels | Service Experience | 88907857 | 2022-10-26 | Drop in Brands availability picture | Correct understanding of how SOD process works for Brands/8604 | Problem avoidance | Rajeev Ekambaram Raja Vasupalli Ab Sharimili Priyas | 21/10: Sterling team now has a correct understanding of how the SOD process works for Brand DC - 8604 | Sterling |  | NA | 21/10/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1072 | >60 | October | 2022 | #VALUE!
Customer Channels | Service Experience | 88907857 | 2022-10-26 | Drop in Brands availability picture | Update repository to reflect the correct SOD process for Brands/8604 | Problem avoidance | Rajeev Ekambaram Abhishek z Kumar | 27/10: The repository hads been updated with correct process for SOD for Brands DC in Sterling | Sterling |  | NA | 27/10/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1072 | >60 | October | 2022 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 88907857 | 2022-10-26 | Drop in Brands availability picture | Set up alert in WMS for incomplete SOD trigger | Problem identification & Alerting | Sharimili Priyas | 31/10: Alerting is not techically feasible as they cant set a specific file size to trigger the alert. Also this scenario will occur when there is no stock in the DC which will happen only during DC decommission. Hence there no further actions need. | WMS Devops |  | NA | 31/10/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1072 | >60 | October | 2022 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 88907857 | 2022-10-26 | Drop in Brands availability picture | WMS product team to take SO approval when re-triggering SOD in day | Problem avoidance | Sharimili Priyas | 24/10: WMS team has agreed to secure SO approval when re-triggering SOD in day | WMS Devops |  | NA | 24/10/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1072 | >60 | October | 2022 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 88907857 | 2022-10-26 | Drop in Brands availability picture | Correct understanding of how SOD process works for Brands/8604 | Problem avoidance | Sharimili Priyas | 21/10: WMS team now has a correct understanding of how the SOD process works for Brand DC - 8604 | WMS Devops |  | NA | 21/10/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1072 | >60 | October | 2022 | #VALUE!
Customer Channels | Service Experience | 88907857 | 2022-10-26 | Drop in Brands availability picture | Review this incident with Stock Service Team to confirm if any further development should be added/planned to help prevent this | Problem avoidance | Emma Rotheram | 31/10: No further development needed in Stock Service as they work on a delta refresh model not full refresh model like OMS. If this issue occurred when we are fully live on Stock Service that service would have updated the sku's the team were trying to align not the full Brands catalogue of items. This has been validated and confirmed by Stock Service Team as well | Service Owners |  | NA | 31/10/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1072 | >60 | October | 2022 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 88914810 | 2022-10-25 | Issues with Bradford C&H DC operations | Knapp have set three CR’s which will need to be implemented to protect Users & System: 1) We have an automated kill switch for any large queries on KISOFT, this is set to 60seconds. This kill switch is not implemented for any Exports into Excel as CSV. A CR will be written up for KNAPP to implement this change functionality to the export function. 2) Data & reporting will be looked at with GXO site operations & Customer Tech to ensure we have the right level of reporting available on KISOFT, to safeguard from any large extracts. 3) KNAPP to see if Alerting can be implemented to capture this and save time on RC analysis | Problem avoidance | Attari Ghulam | 22/3: Closing with CR backlogs R64 and R65 - tentative date of completion is by 30th June 3/3: Vinoth confirmed that 2nd and 3rd actions are completed in Jan'23, while for the 1st "KNAPP have found that they need to perform the command server upgrade to enable this feature, considering the current CR backlog, aiming to upgrade command server in Q2." Have asked for a reference with which this can be closed 27/2: Vinoth would be providing the ETA for this change 18/01: Spoke to Vinoth, who informed that the CR will be planned by end of Q4'23. 25/11: Knapp had raised a CR and awaiting deployment date from Knapp. Hopefully, the change will be deployed by mid of january 9/11: Knapp is still working on this and requested to update by 22nd Nov 8/11: Followed up with Vinoth and Attari, awaiting response | Service Owners |  | NA | 28/03/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1073 | >60 | March | 2023 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 88914810 | 2022-10-25 | Issues with Bradford C&H DC operations | GXO to brief Team Leader – about using filters when doing data extracts. | Problem avoidance | GXO Ops Manger | 26/10: GXO team has briefed their team Leads on how to use the filters when doing data extracts. | 3rd Party |  | NA | 26/10/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1073 | >60 | October | 2022 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 88914810 | 2022-10-25 | Issues with Bradford C&H DC operations | Customer Tech to work with GXO operations to analyse where any other reports have been missed and implement the required reports for operations. | Problem avoidance | Mick Williams | 9/11: GXO team analysed the reports and taken the appropirate actions 8/11: Followed up with Vinoth and Attari, awaiting response | 3rd Party |  | NA | 2022-09-11 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1073 | >60 | November | 2022 | #VALUE!
Customer Channels | Selling Experience | 88904516 | 2022-10-25 | Checkout issues on International Flagship sites | Improve the database failover mechanism to reduce the overall recovery time | Solution & Recovery | Hisham Khalid | 29/11: Vendor has confirmed that the action has been closed. Yet to get more information on the same. 29/11: Followed up with Hisham awaiting an update 31/10: This a long term solution to be worked with non-technology contract based thirdparty Vendors. It cannot be tracked with our internal backlog. | Service Owner |  | NA | 29/11/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1073 | >60 | November | 2022 | #VALUE!
Customer Channels | Selling Experience | 88904516 | 2022-10-25 | Checkout issues on International Flagship sites | Implement a new fix to eliminate the possibility of unexpected errors in the future | Problem avoidance | Hisham Khalid | 29/11: Vendor has confirmed that the action has been closed. Yet to get more information on the same. 29/11: Followed up with Hisham awaiting an update 31/10: This a long term solution to be worked with non-technology contract based thirdparty Vendors. It cannot be tracked with our internal backlog. | Service Owner |  | NA | 29/11/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1073 | >60 | November | 2022 | #VALUE!
GTS | Enterprise Technology Platform | 88888766 | 2022-10-21 | Control M services were unavailable | Follow up with Microsoft to understand the root cause | Root Cause | Elizabeth Golder | 07/11: The severity of the case has been raised and awaiting a response. 9/11: Still awaiting updates from Microsoft 11/11: Spoke to Elizabeth to escalate to Microsoft 15/11: Microsoft confirmed no issue in the database. There is no feasibility to configure alerting for long running sessions. Hence, SOP has been created documenting the restoration steps and updated in Control M SOM | System tools management |  | NA | 15/11/2022 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1077 | >60 | 15/11/2022 | #VALUE! | #VALUE!
GTS | Enterprise Technology Platform | 88888766 | 2022-10-21 | Control M services were unavailable | In the past a DR exercise has been carried out but without failing over the Db server to Swindon, this needs to be planned | Problem avoidance | Elizabeth Golder | 28/10: Database failover testing was performed on 19th March 2022 In 2019 the entire stack DR testing was done. The Control-m server ran from secondary successfully during this issue. Full stack DR test to be planned post peak. A backlog SMT-1 has been raised to address this. | System tools management |  | NA | 28/10/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1077 | >60 | October | 2022 | #VALUE!
GTS | Enterprise Technology Platform | 88888766 | 2022-10-21 | Control M services were unavailable | Update SOM with steps from BMC from this investigation | Solution & Recovery | Santhosh G | The steps have been updated in sharepoint | System tools management |  | NA | 21/10/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1077 | >60 | October | 2022 | #VALUE!
GTS | Enterprise Technology Platform | 88888766 | 2022-10-21 | Control M services were unavailable | How can the architecture be improved to help with quicker recovery? Is there a secondary db we could have failed over to and would the long running transaction have been on there too? | Solution & Recovery | Santhosh G | 21/10: There is a secondary database however the transaction would have failed over to that database. So DR could not be invoked. The transaction was required to be terminated and cleaned up. | System tools management |  | NA | 21/10/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1077 | >60 | October | 2022 | #VALUE!
GTS | Enterprise Technology Platform | 88888766 | 2022-10-21 | Control M services were unavailable | Alerting was 21 mins late - why and what can be done to improving the same | Problem identification & Alerting | Santhosh G | 21/10: The alert was received within 12 minutes of the new day process not being successful. Job failure alerting has been changed from 30 to 15 minutes. More servers to be added to this for resilience Contrlol-m down will continue to be alerted after 15 minutes | System tools management |  | NA | 22/10/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1077 | >60 | October | 2022 | #VALUE!
GTS | Enterprise Technology Platform | 88888766 | 2022-10-21 | Control M services were unavailable | BMC to update the root cause behind the issue | Root Cause | Santhosh G | 21/10: BMC initially pointed towards an error indicating space crunch in the database, however this was ruled out after analysing with the database team. Further analysis are being performed. In addition, a case has been raised with Microsoft. See action 7. 28/10: No actions are pending with BMC. We await an update from Microsoft | System tools management |  | NA | 28/10/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1077 | >60 | October | 2022 | #VALUE!
GTS | Enterprise Technology Platform | 88888766 | 2022-10-21 | Control M services were unavailable | We need to store the base line impact assessment for a control m outage in a central location so we can access it quickly - is AIM a possibility or some other tool? | Impact Analysis | Service Owners | 21/10: The impact will be different for each application dependant on the time of day. This is not something that can be done from the systems management team. This will be an action for the SO. | Service Owners |  | NA | 21/10/2022 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1077 | >60 | 21/10/2022 | #VALUE! | #VALUE!
GTS | Enterprise Integration | 88897530 | 2022-10-18 | Delay to the GMOR critical batches | Update the SOP with the recovery steps | Solution & Recovery | Murali Irrniki | 18/10: SOP has been updated with recovery steps | Middleware Admin |  | NA | 18/10/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1080 | >60 | October | 2022 | #VALUE!
Group Support | Finance | 88897530 | 2022-10-18 | Delay to the GMOR critical batches | What caused the selective deletion to not work causing the predecessor step to overrun on 16/10. Fix the resolve this problem. Can we configure an alert? | Root Cause | Rhammya Somassoudirame | 19/10: Team identified that on certain weeks, the selective deletion program has not deleted the expected data with successful completion of the program leading with no alerts. The program has not deleted data as expected since the Stock reporting table has been locked in a parallel load to a different table. Whenever such locks are in the table, deletion cannot happen. But the Program is currently designed in such a way that the program completes for such locks without deleting the data. Workaround: As a workaround, we would re-design the job in Production to allow the Selective deletion program to run on an ideal window and make the parallel loading step to be in sequence to the deletion program. By doing so, the locking issue can be eradicated. Fix: As a permanent fix, we will re-design the program in order to throw an error whenever lock occurs to the table and causing deletion not to occur. Backlog ID SAP-GMORBW-00051 has been created for the same. | SAP BW team |  | NA | 19/10/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1080 | >60 | October | 2022 | #VALUE!
Group Support | Finance | 88897530 | 2022-10-18 | Delay to the GMOR critical batches | Proper hypercare to be put in place during any such activities in future. | Problem avoidance | Rhammya Somassoudirame | 18/10: hypercare will be be put in place during any such activities in future | SAP BW team |  | NA | 18/10/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1080 | >60 | October | 2022 | #VALUE!
Group Support | Finance | 88897530 | 2022-10-18 | Delay to the GMOR critical batches | Re-iterate the urgency of the impact to the team. MIM needs to be aware of any such activities being performed during the critical batch window | Supplier and support involvement | Rhammya Somassoudirame | 18/10: Teams had agreed to Re-iterate the urgency of the impact to the team. | SAP BW team |  | NA | 18/10/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1080 | >60 | October | 2022 | #VALUE!
Group Support | Finance | 88897530 | 2022-10-18 | Delay to the GMOR critical batches | Devise a way to reduce the run time of the predecessor step by splitting the data load in parallel phases. | Problem avoidance | Rhammya Somassoudirame | 18/10: This has been planned in Jan 23 release. Backlog documented. | SAP BW team |  | NA | 18/10/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1080 | >60 | October | 2022 | #VALUE!
Group Support | Finance | 88897530 | 2022-10-18 | Delay to the GMOR critical batches | Review of all the accesses that are currently not present with the SAP functional teams which requires additional assistance from other teams in SAP. How can this be improved? | Problem avoidance | Rhammya Somassoudirame | 18/10: We had a chat with Remko and have jointly agreed that all required accesses should be provided to the SMEs of the support teams to avoid any dependency on other teams. In progress | SAP BW team |  | NA | 21/10/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1080 | >60 | October | 2022 | #VALUE!
Customer Channels | Platform & Store Ops | 88850486 | 2022-10-16 | Printer access issues on the Windows 10 workstations | Phill Gooriah to go through the CR in detail and ascertain the cause | Root Cause | Phill Gooriah | Phil is unable to ascertain any definitive RCA for this inability to remap printers at the few stores alerting this issue. He couldn't pinpoint a patch being applied, network anomaly, AD or DNS issue that could cause this and can see no other route to investigate. | SSI |  | NA | 2022-06-10 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1082 | >60 | October | 2022 | #VALUE!
Customer Channels | Platform & Store Ops | 88850486 | 2022-10-16 | Printer access issues on the Windows 10 workstations | SIT team to be readvised of the ways of working and what is expected of product teams during a major incidents e.g.: remain on the bridge, actively update the team, assist in creating the recovery plan. | Supplier and support involvement | Rosemary Flynn | 20/10: SIT team assured Rosie that they will adhere to MIM process | Service Owner |  | NA | 20/10/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1082 | >60 | October | 2022 | #VALUE!
GTS | Operations | 88861805 | 2022-10-10 | Issue with e-SAP operating from DR environment | Review which other on-prem applications will need configuring to ensure a future DR exercise will be successful especially considering Azure? E.g.: CSAP | Problem avoidance | Priyadharshini Somasundaram | Priya as governance for business continuity to ensure that technical teams are thorough in their step by step planning. Rehan and Sravan spoke with Priya. | Service Management |  | NA | 2022-10-10 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1088 | >60 | October | 2022 | #VALUE!
GTS | Operations | 88861805 | 2022-10-10 | Issue with e-SAP operating from DR environment | Going forward all relevant SME’s should be involved in all planning and implementation discussions for a future DR exercises. Relevant SME’s and architects should sign off that the DR environment is ready to be tested otherwise the change will not be approved. | Problem avoidance | Priyadharshini Somasundaram | Rehan and Sravan spoke with Priya. | Service Management |  | NA | 2022-10-10 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1088 | >60 | October | 2022 | #VALUE!
GTS | Operations | 88861805 | 2022-10-10 | Issue with e-SAP operating from DR environment | We have to replan this DR test in 2023 | Problem avoidance | Priyadharshini Somasundaram | Rehan and Sravan spoke with Priya. | Service Management |  | NA | 2022-10-10 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1088 | >60 | October | 2022 | #VALUE!
Customer Channels | Selling Experience | 88876687 | 2022-10-09 | Customers reported that they were unable to log in to the website via mobile web | Identify synthetic alerting around alerting for Mobile apps | Problem identification & Alerting | John Davis | 20/10: The action was agreed upon for mobile application instead of the mobile web during PIR. Considering, we already agreed on synthetic alerts for the mobile web. This action can be closed 18/10: Requested Elaine Hawthorn for an update and awaiting response | MCP |  | NA | 20/10/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1089 | >60 | October | 2022 | #VALUE!
Customer Channels | Selling Experience | 88876687 | 2022-10-09 | Customers reported that they were unable to log in to the website via mobile web | Set up alerts for order drop based on guest/logged in user | Problem identification & Alerting | Manikandan Selvaraj | 12/10: Alerts are in place now | WCS |  | NA | 2022-12-10 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1089 | >60 | October | 2022 | #VALUE!
Customer Channels | Selling Experience | 88876687 | 2022-10-09 | Customers reported that they were unable to log in to the website via mobile web | Make backend order rate monitors more granular differentiating desktop, mobile web, android app, iOS app, instore assisted and contact centre assisted | Problem identification & Alerting | Pulkit Goyal | 14/10: Pulkit advised that this action has been completed | MCP |  | NA | 14/10/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1089 | >60 | October | 2022 | #VALUE!
Customer Channels | Selling Experience | 88876687 | 2022-10-09 | Customers reported that they were unable to log in to the website via mobile web | Document a comprehensive list of all business specific rate-monitoring alerts. Validate this with Business Operations. | Problem identification & Alerting | Pulkit Goyal | 14/10: Barani Vijayan confirmed that additional alerting has been configured and the list of alerts has been shared with Command Centre | MCP |  | NA | 14/10/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1089 | >60 | October | 2022 | #VALUE!
Customer Channels | Selling Experience | 88876687 | 2022-10-09 | Customers reported that they were unable to log in to the website via mobile web | Fix synthetic alerts in New Relic for mobile web | Problem identification & Alerting | Pulkit Goyal | 16/11: New-relic vendor confirmed that exact implementation or mimicking the mobile journey explicitly is not feasible. However, we can configure a mobile journey can be by resizing the browser which we have already been implemented in Customer. 14/11: As requested by new relic vendor, team had shared the additional information and awaiting response 4/11: The synthetic alerts were already in place for mobile web journeys but they did not pick up the issue. Therefore, the team is working with the New relic vendor to fine-tune the alerts. 24/10: A case has been raised with New relic to configure the alert for specific user agent 20/10: Team need some more time to brainstorm this scenario to introduce the synthetic alerting 14/10: Team is working on this and provided the revised ETA | MCP |  | NA | 16/11/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1089 | >60 | November | 2022 | #VALUE!
Customer Channels | Selling Experience | 88876687 | 2022-10-09 | Customers reported that they were unable to log in to the website via mobile web | Plan decommissioning of MCP as the FEAR are responsive. (Provide backlog number) | Problem avoidance | Ramsankar Ramaswamy | 13/01: A backlog has been raised to track this 4/01: Spoke to Ramsankar who informed that he did not got a chance to talk to Steve and he will try to speak to Steve tomorrow on who will own this action. 30/12: Ramsankar will talk to Steve Warren on 3rd january and will update the progress of it. 28/12: Vadi requested Ramsankar to talk to Hisham and get the updates from Steve 5/12: Followed up with Vadi and Ram, awaiting response 25/11: Spoke to Vadi and Ramasamy who will be setting-up a meeting with David and Steve next week to get the latest on this. 21/11: An follow-up email sent to Vadi & team, awaiting response 16/11: Followed up for a latest updated, awaiting response 7/11: Vadi informed that the action is pending with Steve W. This will be followed-up with Steve again 31/10: A decision is being pending with Steve Warren(Customer Enginering Head). Vadi and Ram will follow-up and share an update by end of this week 20/10: Impact analysis is being carried out by David Raine before proceeding with the decommissioning. Awaiting revised ETA for this activity 13/10: Discussed with Ram and Vadi who advised that this needs to be further discussed with Steve W and update us back. | MCP |  | NA | 13/01/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1089 | >60 | January | 2023 | #VALUE!
Customer Channels | Selling Experience | 88876687 | 2022-10-09 | Customers reported that they were unable to log in to the website via mobile web | Agree an approach for MCP in lower environment (to test or not in one or both regions, SIT2 and SIT3) | Problem avoidance | Ramsankar Ramaswamy | 20/10: Its been agreed that we are not going to get in SIT2, SIT3 13/10: Discussed with Ram and Vadi who advised that this needs to be further discussed with Steve W and update us back. | MCP |  | NA | 20/10/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1089 | >60 | October | 2022 | #VALUE!
Customer Channels | Selling Experience | 88876687 | 2022-10-09 | Customers reported that they were unable to log in to the website via mobile web | Fix the defect in MCP and deploy in production. Even though login pages are not impacted because of the work around, there might be pages impacted by this change | Solution & Recovery | Skand Mishra | 20/10: The fix was deployed to production on 19/10 11/10: The code fix has been deployed into lower environment(Sit1, Sit2 and Stage). Once it is proven successful, the fix will be deployed into production | MCP |  | NA | 20/10/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1089 | >60 | October | 2022 | #VALUE!
Customer Channels | Selling Experience | 88851924 | 2022-10-03 | Intermittent Errors on Homepage, DLP, SRP & PLP Pages | Implementers of dotcom related Certificate renewals should validate that a certificate renewal has successfully been installed following implementation using openssl. | Problem avoidance | Aadil Kasmani | 06/10: Going forward, product teams should ensure to validate the renewed certificate end to end. | Service Owner |  | NA | 2022-06-10 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1095 | >60 | October | 2022 | #VALUE!
Customer Channels | Selling Experience | 88851924 | 2022-10-03 | Intermittent Errors on Homepage, DLP, SRP & PLP Pages | Product teams for Homepage/DLP to setup alerting to monitor Traffic Drops on New Relic for their Applications | Problem identification & Alerting | Aadil Kasmani | 11/10: Aadil confirmed that teams implemented the required alerting | Service Owner |  | NA | 2022-11-10 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1095 | >60 | October | 2022 | #VALUE!
Customer Channels | Selling Experience | 88851924 | 2022-10-03 | Intermittent Errors on Homepage, DLP, SRP & PLP Pages | SRP/PLP/DLP clusters to be migrated to V2 (Currently on a hosted AKS environment which is not supported well) | Permanent Fix | Aadil Kasmani | Jira Backlog FINDPDP – 116 is created to track this action | Service Owner |  | NA | 2022-03-10 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1095 | >60 | October | 2022 | #VALUE!
Customer Channels | Selling Experience | 88851924 | 2022-10-03 | Intermittent Errors on Homepage, DLP, SRP & PLP Pages | Test of Automated Cert Renewal process using (Cert Manager) in a controlled manner on NEU cluster for SRP/PLP/DLP | Problem avoidance | Aadil Kasmani | Completed | Service Owner |  | NA | 2022-05-10 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1095 | >60 | October | 2022 | #VALUE!
Customer Channels | Customer Engagement | 88857202 | 2022-10-03 | Customers are unable to redeem Loyalty Reward Vouchers online | LRS application is hosted in Azure and there was an issue in reaching the application in N. Europe (not an application issue). It was not failing over to W. Europe through Stockley Park due to missing setup – this missing setup needs to be investigated. | Root Cause | Divakar Hariraju | 27/02: Testing has been completed. Awaiting the reference details 14/02: DR has been planned in Q2, awaiting a back log ID from product team to track the same 13/02: Followed up again no further updates. 10/02: Follow up made no further updates 19/01: Divakar has advised that team will have discussion and provide an update on 30/01 17/01: Team had a discussion on finalising the DR date, Expecting a date to be confirmed by today or tomorrow. 07/12: Spoke to Vadi for an update on the plan for DR, still awaiting the action plan 05/12: Followed up with Divakar for an updated, yet to receive an update 29/11: Vadi will be discussing with product to devise a plan. Awaiting an ETA 24/11: Followed up with Divakar, awaiting an update. 22/11: Followed up with Divakar, awaiting an update. 17/11:Discussion on rising a risk is going between the prouct team and the service owner awaiting further response from Divakar. 16/11: Followed on the plan for DR activity, awaiting further response from Divakar 09/11: Aged-out and reset were observed in the server logs during that issue, however there was no connection breaks on Network layer. The only issue from network end was the health monitor mapping and it has been configured in both North and West Europe regions. Advised team to perform a DR test. 07/11: Awaiting further updates from Network team 31/10: LRS and Network team continues the missing setup issue. No major updates yet. Awaiting an ETA for the same. 11/10: Divakar is awaiting for an ETA for the open action | Service Owner |  | NA | 14/02/23 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1095 | >60 | February | 2023 | #VALUE!
Customer Channels | Customer Engagement | 88857202 | 2022-10-03 | Customers are unable to redeem Loyalty Reward Vouchers online | Monitoring identified that the number of orders where Loyalty Reward Vouchers is used for payment is very low. The issue started at 00:20 but was escalated to a sev 2 at 16:20 which is 16 hours later. We need to address why it took this period of time to identify that this was a significant issue. Could the potential impact have been better assessed? | Problem identification & Alerting | Divakar Hariraju | 04/11: The alerting has been configured and reviewed with Business. 31/10: The alerting was not available for all the flows. Now alerting has been configured on 18/10, however the alerting thresholds are being reveiwed with the business 11/10: Divakar is awaiting for an ETA for the open action | Service Owner |  | NA | 2022-04-11 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1095 | >60 | November | 2022 | #VALUE!
Customer Channels | Customer Engagement | 88857202 | 2022-10-03 | Customers are unable to redeem Loyalty Reward Vouchers online | What was the exact issue because of which we could not reach the application in North Europe – this is a Microsoft issue and we need to follow up on the cause. | Root Cause | Divakar Hariraju | 09/11: There is no evidence that there is an issue from Network end. Aged-out and reset were observed in the server logs during that issue, however there was no connection breaks on Network layer. The only issue from network end was the health monitor mapping and it has been configured in both North and West Europe regions. NU further invesitigations are pending to determine the root cause, hence RCA is unknown 07/11: Awaiting further updates from Network team 31/10: We believe that its not a Microsoft issue, however network team is checking further. 11/10: Divakar is awaiting for an ETA for the open actionn | Service Owner |  | NA | 2022-09-11 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1095 | >60 | November | 2022 | #VALUE!
Customer Channels | Selling Experience | 88846160 | 2022-10-03 | Collection slots not showing intermittently on CFTO App | Why did this issue not happen last year when TCS/Customer did not make any changes. | Root Cause | Aadil Kasmani | 8/11: Apigee confirmed that both the headers (Request & Response) are valid and that its not an issue from Apigee end. 03/10 - Last year browsers began to request multiple compression types. We believe that that an update has changed the types and quantity of compression in the cache. We use a mechanism (vary header) that we use to deliver the correct type of content. This header works fine for Akamai but not Apigee. Log raised with Apigee on 03/10 12pm | .com Service Owner |  | NA | 2022-08-11 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1095 | >60 | November | 2022 | #VALUE!
Customer Channels | Selling Experience | 88846160 | 2022-10-03 | Collection slots not showing intermittently on CFTO App | Add fortify on demand into the CFTO build pipeline | Problem avoidance | Bernie Bird | 10/11: Backlogs have been created to track this 8/11: Follow-up email sent, awaiting response Raise a log for this and add to backlog for next year | CFTO team |  | NA | 2022-10-11 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1095 | >60 | November | 2022 | #VALUE!
Customer Channels | Selling Experience | 88846160 | 2022-10-03 | Collection slots not showing intermittently on CFTO App | Make sure that that the libraries used by CFTO specifically are still in support and have no warning conditions | Problem avoidance | Jamie Leven | 14/11: The responsibility for ensuring that libraries used as part of any initiative or product sit within those respective teams. Customer as a collective should have a minimum technical spec that ensures libraries used are supported.This action will be added as part of the ‘Lessons Learned / Suggested Actions’ for 2023. 8/11: Follow-up email sent, awaiting response | CFTO team |  | NA | 14/11/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1095 | >60 | November | 2022 | #VALUE!
Customer Channels | Selling Experience | 88846160 | 2022-10-03 | Collection slots not showing intermittently on CFTO App | A new test plan needs to be created for Xmas 2023 to cater for the new library and the combination of scenarios – the replication of production traffic is a challenge however a proposal needs to be provided. Highlight this as a risk as no end to end owner. | Problem avoidance | Jamie Leven | 17/11: Burke, Tony’s team should document this in their Confluence pages for the CFTO App to pickup next year. 8/11: Follow-up email sent, awaiting response | CFTO team |  | NA | 18/11/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1095 | >60 | November | 2022 | #VALUE!
Customer Channels | Selling Experience | 88846160 | 2022-10-03 | Collection slots not showing intermittently on CFTO App | If there is another future change then how do we know about it and how do we get our systems to handle the change? | Problem avoidance | NOTE TO ALL | All applications have a header logic which advertise what types of data the application can support, the updates will then cater for that type of data. In this case there is looks to be an issue with Apigee and its acceptance of compressed data. | CFTO team |  | NA | 2022-07-10 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1095 | >60 | October | 2022 | #VALUE!
GTS | Operations | 88846160 | 2022-10-03 | Collection slots not showing intermittently on CFTO App | Which other applications are potentially vulnerable to this type of issue? Review what other request libraries are in use for applications that have public web access (outbound requests) – this is for all Product teams. | Problem avoidance | Rehan Siddiqui | 17/11: Aadil had advised that this actions cannot be completed as the scope of the requirement is so big. Hence we have agreed to close the action. Aadil and David to ascertain the scope of the review – which other applications use this request library. Rehan to ascertain who can own a large scale action like this and then speak to proposed owner. | Service Management |  | NA | 17/11/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1095 | >60 | November | 2022 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 88848166 | 2022-10-01 | Issues with Bradford C&H DC operations | Closed down the ticket so that the root cause can be provided 24 hours after the closure Time | Root Cause | Attari Ghulam | Complete | Service Owner |  | NA | 2022-07-10 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1097 | >60 | October | 2022 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 88848166 | 2022-10-01 | Issues with Bradford C&H DC operations | When we have any WMS down time, Sterling have to take Bradford out of fulfilment as there is no buffering/exception queue – there is a change due for release 61 (end of Oct) – update required. | Solution & Recovery | Attari/ Michael Williams | 18/11: A dedicated queue has been set-up for bradford to take the orders offline 8/11: The release is postponned to 18th November 31/10: The release is planned on 15th November 07/10: There is a release (61) going in at the end of November that will deploy queues so that the messages can be better managed and Bradford will not have to be taken out of fulfilment. Attari to provide the exact release data by 31/10. | Service Owner |  | NA | 18/11/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1097 | >60 | November | 2022 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 88848166 | 2022-10-01 | Issues with Bradford C&H DC operations | Customer Tech and Knapp working in collaboration during major incidents – we need to review the process and improve it and align it between the two stakeholders | Supplier and support involvement | Attari/Martin | 25/11: Process has been agreed with logistics, knapp, GXO for major incidents 18/11: Attari advised that meeting was postponed to 25th Nov 8/11: The sign-off date for the new severity matrix for IM process is 16th Nov 20/10: The first meeting happened between GXO and Knapp to align on the incident management process and the same will be discussed and reviewed with Customer logistics to agree on the same. 07/10: Spoken with Attari and agreed revised date | Service Owner |  | NA | 25/11/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1097 | >60 | November | 2022 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 88848166 | 2022-10-01 | Issues with Bradford C&H DC operations | Site cannot be kept down to investigate the root cause and this is what happened in this instance. We need to document and formalise the agreed recovery process between Customer Engineering/Customer Tech and Knapp – who will take the lead and take the decisions? | Solution & Recovery | Attari/Martin/Luke | 8/11: Knapp agreed not to investigate the root cause of the issue by keeping the site down instead they need to provide a fix ASAP. 31/10: The service call has been rescheduled to next week. We will await updates from attari on 8/11 07/10: This will be picked up in the service call with Knapp on 28/10 | Service Owner |  | NA | 2022-08-11 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1097 | >60 | November | 2022 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 88848166 | 2022-10-01 | Issues with Bradford C&H DC operations | We await the actual root cause from JBOSS | Root Cause | Luke Goddard (Knapp) | 07/10: Root cause obtained and updated in the main tracker | Knapp |  | NA | 2022-04-10 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1097 | >60 | October | 2022 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 88848166 | 2022-10-01 | Issues with Bradford C&H DC operations | There should have been alerting for the fact that messages were not flowing – Knapp to advise if alerting is in place and if not what can be configured | Problem identification & Alerting | Luke Goddard (Knapp) | 8/11: Alerts have been configured now. 31/10: This is still being looked upon by Knapp Austria team. Attari is following up on the same 07/10: Spoken with Attari and agreed revised date | Knapp |  | NA | 2022-08-11 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1097 | >60 | November | 2022 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 88848166 | 2022-10-01 | Issues with Bradford C&H DC operations | In this instance command centre came to us to ask about impact and recovery when in fact they need to go GXO directly. | Solution & Recovery | Martin/Jonathan (Logistics) | 20/10: Bradford Control room will add Dot com and MIM team to their incident communication from where the impact can be taken 11/10: The business impact for .com should be obtained by the site and the service owner. GXO have taken some actions away and will report back next wednesday(19th Oct) with some action plan to raise incidents and communication 07/10: Jonathan Hutchinson has sent up a call on Monday 10/10 at 10am | Service Owner |  | NA | 20/10/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1097 | >60 | October | 2022 | #VALUE!
Customer Channels | Service Experience | 88841443 | 2022-09-28 | Issues in packing ISF orders via SPPD | Configuration of an alert to proactively identify whenever the job stops responding in future. | Problem identification & Alerting | Lokesh Kumar | 12/10:Initially, there was a miss from tech to configure an alert for this job. However, a sev1 alert has now been configured based on the count of messages picked up by the job to be sent to Sterling. For eg: If the message count is 0 between 7am to 7pm for 5 mins, the alert will get triggered. This will be monitored to confirm the effectiveness of the alert. | BOSS Support |  | NA | 2022-12-10 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1100 | >60 | October | 2022 | #VALUE!
Customer Channels | Service Experience | 88841443 | 2022-09-28 | Issues in packing ISF orders via SPPD | Why did the job stop responding? | Root Cause | Lokesh Kumar | 31/10: Team performed a detailed investigation along with the development team and could not find the reason why the job had stopped picking messages. Support also monitored the job performance and the issue did not re-occur. 28/09: A catchup call is scheduled today with the tech teams (only) to perform detailed analysis. | BOSS Support |  | NA | 31/10/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1100 | >60 | October | 2022 | #VALUE!
Customer Channels | Service Experience | 88841443 | 2022-09-28 | Issues in packing ISF orders via SPPD | Considering the SPPD application has been recently migrated to Azure V2, teams to create SOP document for new scenarios. | Solution & Recovery | Lokesh Kumar | 31/10: A SOP has been created to cover all incident scenarios Further follow-up needs to be done | BOSS Support |  | NA | 31/10/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1100 | >60 | October | 2022 | #VALUE!
Supply Chain | Foods Supply Chain | 88838928 | 2022-09-28 | Issue with frozen delivery messages interfacing into CSSM | If there are any changes to the schedule for frozen deliveries, Foods teams need to advise the CSSM team so that they can amend their alerts accordingly | Problem identification & Alerting | Joey Ocansey | As agreed in PIR call, Joey will advise Foods teams and downstream teams incase of changes to the changes to the schedule for frozen deliveries | Service Owner |  | NA | 2022-07-10 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1100 | >60 | October | 2022 | #VALUE!
Customer Channels | Platform & Store Ops | 88838928 | 2022-09-28 | Issue with frozen delivery messages interfacing into CSSM | Was there a delay in stores comms because the entire impact was not realised in a timely manner? | Business & IT Communication | Joey/Laura/Rosie | 09/11: This action is no longer needed. As there was no issues in the communications sent | Service Owners |  | NA | 2022-09-11 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1100 | >60 | November | 2022 | #VALUE!
Supply Chain | Foods Supply Chain | 88838928 | 2022-09-28 | Issue with frozen delivery messages interfacing into CSSM | What went wrong with the change and were there any E2E checks after implementation of the change | Root Cause | Richard Readshaw(GIST) | 09/11: GIST has shared the plan with Joey and Andrew Goslin 28/09: The change was impacted by a human error when naming the new directory. GXO have advised that they should have monitored the outbound messages as hypercare after the change.Another level of verification is to be implemented during and after the change – Richard to speak to his team and provide us with a plan of improvements. This plan will go to GIST and to Joey/Andrew Goslin | GXO IT/GIST |  | NA | 2022-09-11 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1100 | >60 | November | 2022 | #VALUE!
Supply Chain | Foods Supply Chain | 88838928 | 2022-09-28 | Issue with frozen delivery messages interfacing into CSSM | Was Customer made aware of the change? | Root Cause | Richard Readshaw(GIST) | Customer/GIST were not made aware of the change and Richard has advised that going forward they will be notified and proof of notification will be provided. This improvement initiative will be included as part of the improvement plan mentioned in action 1 | GXO IT/GIST |  | NA | 2022-09-11 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1100 | >60 | November | 2022 | #VALUE!
Supply Chain | Foods Supply Chain | 88838928 | 2022-09-28 | Issue with frozen delivery messages interfacing into CSSM | Why was the connection issue between OpenText and Ultima was not highlighted before as it was ongoing from the morning? | Supplier and support involvement | Richard Readshaw(GIST) | 09/11: This has been closed as part of improvement plan GXO believe that as connection was no longer required as the route had been changed it was no longer being checked. End to end checks initiative will be included as part of the improvement plan mentioned in action 1. Note: alerting for the new route is already in place. | GXO IT |  | NA | 2022-09-11 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1100 | >60 | November | 2022 | #VALUE!
Supply Chain | Foods Supply Chain | 88838928 | 2022-09-28 | Issue with frozen delivery messages interfacing into CSSM | Was there any alerting in Ultima to notify message pile up from 20/09 before the issue was highlighted by Customer on 22/09? | Problem identification & Alerting | Richard Readshaw(GIST) | 17/11: The alerting has been configured in Ultima if the files are not processed for more than an hour. 09/11: GIST is still working on testing the outbound transfer to configure the alerts. There is no alerting and this will be configured to notify for pileups and gaps in messages flowing. The metrics of these alerts will need to be agreed. | GXO IT |  | NA | 17/11/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1100 | >60 | November | 2022 | #VALUE!
Supply Chain | Foods Supply Chain | 88838928 | 2022-09-28 | Issue with frozen delivery messages interfacing into CSSM | We had overallocation in ASO as the stock was understated in CSSM. Is there a way to highlight this in ASO/Quantum? | Problem identification & Alerting | Vinoth/Santhosh/Lakshman | 09/11: Its not feasible to find the stock (over / under) in ASO and Quantum. Hence no actions is pending from the ASO/ Quantum team 08/11: Followed up with action owner awaiting a response Is there anyway to highlight/alert for over allocations | ASO, Quantum |  | NA | 2022-09-11 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1100 | >60 | November | 2022 | #VALUE!
Customer Channels | Selling Experience | 88837724 | 2022-09-28 | Issue with DTC services on Infoblox | Why were the response failures in carrier gateway not addressed or highlighted earlier to relevant teams? | Problem identification & Alerting | Jeevan | 23/09: An alert is already available in pager duty, but failure didn't reach the threshold level. | Carrier gateway |  | NA | 23/09/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1100 | >60 | September | 2022 | #VALUE!
Customer Channels | Selling Experience | 88837724 | 2022-09-28 | Issue with DTC services on Infoblox | Can any alerting be put in place if there is a failure in carrier gateway to notify Castle Donington DC? | Problem identification & Alerting | Jeevan | PagerDuty alerting is already configured, however on the day of the incident the failure didn't reach the threshold level for a critical alert to be triggered. | Carrier gateway |  | NA | 23/09/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1100 | >60 | September | 2022 | #VALUE!
GTS | ETP- Connectivity,service & solution | 88837724 | 2022-09-28 | Issue with DTC services on Infoblox | Are there any alerts configured for DTC service restart? | Problem identification & Alerting | Rajesh | 04/11: The pagerduty alert cannot be configured for service, it can configured its a cloud component. Hence closing this actions 18/10: The feasibility of configuring the pager duty alert since the alert is triggering from infoblox devices as a service based. The priority of the email alerting has been increased to Sev1. The feasibility of configuring a pager duty alert is being explored. | Network |  | NA | 2022-04-11 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1100 | >60 | November | 2022 | #VALUE!
GTS | ETP- Connectivity,service & solution | 88837724 | 2022-09-28 | Issue with DTC services on Infoblox | The list of applications which uses DTC services needs to be documented and they will be engaged to assess the impact incase of any issues with the services | Impact Analysis | Rajesh | 18/10: The details of all DTC services which are running in infoblox has been collected and network team will liaise with platform team to document the list of applications which uses DTC services. The application detail has been partially collected and remaining will be completed by 28/10 Network team will liaise with platform team to document the list of applications which uses DTC services. Team have agreed in the PIR call to engage the relevant teams in case of any issues with DTC service. | Network |  | NA | 18/10/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1100 | >60 | October | 2022 | #VALUE!
GTS | ETP- Connectivity,service & solution | 88837724 | 2022-09-28 | Issue with DTC services on Infoblox | Why did the change in non-prod impact production service? | Root Cause | Rajesh | 20/10:Due to the bug in current NIOS version 8.5.4, its impacted the production also while run the script in Non Prod. This is addressed and fixed in NIOS 9.0. and the Infoblox upgrade will be planned after peak and this will tracked under the risk 1780 Below is technical RCA shared by Infoblox The reason for this behavior is as in the words of engineering team, When named_control sends SIGTERM to the named process while doing forceful restart then the idns threads will not exit immediately, when they are actively receiving the health updates. The threads which are not exiting wont return immediately until the timeout is expired or there is no more data to be received from the other end. Hence we need to forcefully exit the receiving sockets before another thread join / instantiation. 28/09: A case has been raised with Infoblox to understand why it impacted production services. Network is following up with Infoblox to understand the RC. Infoblox has advised that the similar issue has been observed for the customers and they are continuing to investigate Network team to chase up with Infoblox for the RCA. | Network |  | NA | 20/10/22 | Closed | 1780 | NA | N/A | Saloni | 2025-02-10 | 1100 | >60 | October | 2022 | #VALUE!
GTS | ETP- Connectivity,service & solution | 88837724 | 2022-09-28 | Issue with DTC services on Infoblox | Production change process to be followed for components which share both Production and Non-Prod services | Problem avoidance | Rajesh | 20/10: Network and framework teams have agreed that the any automation go live in non prod will follow change process followed for production 28/09: Review the existing non-prod change process and agree the way forward. | Network |  | NA | 20/10/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1100 | >60 | October | 2022 | #VALUE!
GTS | ETP- Connectivity,service & solution | 88837724 | 2022-09-28 | Issue with DTC services on Infoblox | Review all the existing shared (prod and non-prod) network components and services in both Cloud and On-prem | Problem avoidance | Rajesh | 20/10: A risk has been raised and in Open state, will be moved to accepted once agreed with Product owners. | Network |  | NA | 20/10/22 | Closed | 1780 | NA | N/A | Saloni | 2025-02-10 | 1100 | >60 | October | 2022 | #VALUE!
GTS | Operations | 88886973 | 2022-09-28 | Goods Receipt messages from Bedworth’s WMS system, Ultima, had not reached Customer/SAP | The actions are populated and tracked on 88838928 | Issue handling/Management | Saloni | The actions are tracked on 88838928 | Service Management |  | NA | 2022-07-10 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1100 | >60 | October | 2022 | #VALUE!
Customer Channels | Service Experience | 88835977 | 2022-09-27 | Entire orders getting cancelled instead of the out of stock lines | To resolve slowness in SIT testing environment, increase Infrastructure (number of pods) this will reduce offline orders | Problem avoidance | Ambalavanan Chockalingam | 31/10: Team monitored and confirmed that they did not encounter the slownessin SIT after increasing the PODs 06/10: The number of PODs has been increassed and will be monitored until next release which is planned on end of October | Fulfilment Product |  | NA | 31/10/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1101 | >60 | October | 2022 | #VALUE!
Customer Channels | Platform & Store Ops | 88835977 | 2022-09-27 | Entire orders getting cancelled instead of the out of stock lines | Review WCS offline order alerts and update | Problem identification & Alerting | Pulkit Goyal | Alerts are in place | WCS |  | NA | 27/09/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1101 | >60 | September | 2022 | #VALUE!
Customer Channels | Service Experience | 88835977 | 2022-09-27 | Entire orders getting cancelled instead of the out of stock lines | Agree threshold and set up alerts in EM for OMS Unreachable orders | Problem identification & Alerting | Rajeev Ekambaram | Alerts are in place | Sterling |  | NA | 27/09/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1101 | >60 | September | 2022 | #VALUE!
Customer Channels | Platform & Store Ops | 88861216 | 2022-09-27 | Drop in Orders on UK & IE Customer.com Website | What alerts were configured for the webserver that was down in the second hall? | Problem identification & Alerting | Elaine H | Completed. New alerts have been set up | Service Owner |  | NA | 2022-10-11 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1101 | >60 | November | 2022 | #VALUE!
Customer Channels | Platform & Store Ops | 88861216 | 2022-09-27 | Drop in Orders on UK & IE Customer.com Website | Checks to be performed if it is feasible to divert a small percentage of traffic to the hall and see if the infrastructure is working as expected. | Problem avoidance | Elaine H & Business | It has been decided that during webserver reboot, only 50% of the traffic will be routed to it to prevent such scenarios. | Service Owner |  | NA | 14/10/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1101 | >60 | October | 2022 | #VALUE!
Customer Channels | Platform & Store Ops | 88861216 | 2022-09-27 | Drop in Orders on UK & IE Customer.com Website | Were these alerts triggered BEFORE traffic was failed over to the other hall in readiness for the change? If they were then why did we proceed with the fail over? | Problem identification & Alerting | Sumitro | Issue would not have been obvious during sanity testing because the no customer-facing/front end errors appeared. The alerts will only trigger when there is some traffic on the servers. Ideally, some percentage of traffic should have been diverted to check the server status, but in this case, 100% was diverted at one go. This needs to be picked up. Refer to point 3 | WCS |  | NA | 2022-10-11 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1101 | >60 | November | 2022 | #VALUE!
Customer Channels | Platform & Store Ops | 88861216 | 2022-09-27 | Drop in Orders on UK & IE Customer.com Website | What was the root cause for the webserver being down? | Root Cause | Sumitro | Completed. The webserver was up but unable to connect to the application server because a plug-in file was not loaded correctly. | WCS |  | NA | 14/10/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1101 | >60 | October | 2022 | #VALUE!
Customer Channels | Platform & Store Ops | 88861216 | 2022-09-27 | Drop in Orders on UK & IE Customer.com Website | Were there alerts for the plug-in file not being loaded correctly. If yes, did it get triggered, If not, can we configure an alert? | Problem identification & Alerting | Sumitro | An additional step has been introduced to the deployment plan to perform health checks on the webservers and the plug in files. | WCS |  | NA | 14/10/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1101 | >60 | October | 2022 | #VALUE!
Customer Channels | Platform & Store Ops | 88833884 | 2022-09-22 | Spike in offline and failed card transactions for stores | Include a sanity check directly in the automation layer prior to any DNS record creation ensuring that no record of the same name but of a different type is already present in the public zone | Problem avoidance | Gary Allenby | 7/11: This action is closed now 4/11: Follow-up email sent to Gary, awaiting response | 3rd Party |  | NA | 2022-07-11 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1106 | >60 | November | 2022 | #VALUE!
Customer Channels | Platform & Store Ops | 88833884 | 2022-09-22 | Spike in offline and failed card transactions for stores | Amend the coding review guidelines in order to mandate a four eyes principle on ANY other new provider on the sanity checks | Problem avoidance | Gary Allenby | 7/11: This action is closed now 4/11: Follow-up email sent to Gary, awaiting response | 3rd Party |  | NA | 2022-07-11 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1106 | >60 | November | 2022 | #VALUE!
Customer Channels | Platform & Store Ops | 88833884 | 2022-09-22 | Spike in offline and failed card transactions for stores | Management actions are being discussed in order to ensure that the situational awareness of the SRE team in charge of the DNS is increased at all time. | Problem avoidance | Gary Allenby | 7/11: This action is closed now 4/11: Follow-up email sent to Gary, awaiting response | 3rd Party |  | NA | 2022-07-11 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1106 | >60 | November | 2022 | #VALUE!
Customer Channels | Customer Engagement | 88826158 | 2022-09-21 | Issues in accessing Sparks hub | What preventive measure can be put in place from Sparks application perspective to avoid the impact if there is a spike in apple wallet database request? | Problem avoidance | Divakar Hariraju | 14/10: loyalty team have removed the webservice URL to avoid the increase in traffic, in addition to blocking traffic at akamai. This service is not used by the CDP and the issue will not reoccur again | Loyalty team |  | NA | 14/10/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1107 | >60 | October | 2022 | #VALUE!
Customer Channels | Customer Engagement | 88826158 | 2022-09-21 | Issues in accessing Sparks hub | What caused the spike in database request related to Apple wallet | Root Cause | Divakar Hariraju | 14/10: The issue believed to caused by either of the below scenario due to an fault at application end. 1. More people might have be added causing a spike. 2. Apple have change some logic increasing the traffic, but the funcationality is disabled. Hence to avoid the traffice we should remove the web service url | Loyalty team |  | NA | 14/10/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1107 | >60 | October | 2022 | #VALUE!
Supply Chain | Foods Supply Chain | 88830426 | 2022-09-21 | Delay in supplier order generation for Relex products | Detailed root cause analysis by Relex | Root Cause | Promoth/Tamil | Certificate renewal activity encountered an error | Relex Support |  | NA | 2022-10-10 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1107 | >60 | October | 2022 | #VALUE!
Supply Chain | Foods Supply Chain | 88830426 | 2022-09-21 | Delay in supplier order generation for Relex products | If there is an existing issue with the Relex tool, what measures are being taken to resolve it? | Root Cause | Promoth/Tamil | The peak file was generated on the wrong date as the support activity to correct this has not been made for this year. This is due to a gap between the RELEX support function and project function over the ownership of supporting Customer specific configuration. An item was in the backlog to make this change but incorrect analysis from the RELEX scrum team was performed suggesting this file should not generated until the week after and therefore the change could be made later. Mitigation and fix plan: A fix was made via hotfix to mitigate for this year. However no long term solution was created. | Relex Support |  | NA | 2022-10-10 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1107 | >60 | October | 2022 | #VALUE!
Supply Chain | Foods Supply Chain | 88830426 | 2022-09-21 | Delay in supplier order generation for Relex products | Improvement in communication at Relex | Problem identification & Alerting | Promoth/Tamil | This action has been completed. | Relex Support |  | NA | 2022-10-10 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1107 | >60 | October | 2022 | #VALUE!
Supply Chain | Foods Supply Chain | 88830426 | 2022-09-21 | Delay in supplier order generation for Relex products | Decision to implement the workaround was delayed. Can that be addressed as well with the supply chain to save the SLA | Solution & Recovery | Promoth/Tamil | This action has been completed. | Relex Support |  | NA | 2022-10-10 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1107 | >60 | October | 2022 | #VALUE!
Customer Channels | Service Experience | 88833884 | 2022-09-19 | Spike in offline and failed card transactions for stores | Awaiting RCA from worldline | Root Cause | Worldline | On 15th September 2022 Worldline's Advanced Infrastructure Services (AIS) deployed an automated change applied to the ahub.global.ingenico.com DNS record. AHUB is a shared service so this resulted in failures of payment platforms depending on it (including the AXIS platform for customers that rely on AHUB(authorization flow). The change was erroneously executed not in "test" mode but in “execute”, effectively creating a new DNS subzone for each tenant that held the name of the tenant(ahub.global.ingenico.com). As the tenant already had an Address record pointing to the same name (ahub.global.ingenico.com). The new subzone effectively masked the visibility of the original Address record. | 3rd Party |  | NA | 2022-04-11 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1109 | >60 | November | 2022 | #VALUE!
GTS | Digital Workplace Services | 88887235 | 2022-09-16 | Issues with Tasks | Can any dedicated queue be created for handling publishing list to avoid the issue with internal queues? | Problem avoidance | Saran Rajkumar | 18/10: The issue was escalated with Customer and no further response from Microsoft. Business are looking for an alternatives. Hence Rosie has advised close it off from the tracker 11/10: Followed with Saran for the update, waiting for an update This will make sure publishing will never be blocked for customers and will always succeed because this will be a priority queue. Microsoft is in the process of looking into design | Messaging Team |  | NA | 18/10/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1112 | >60 | October | 2022 | #VALUE!
GTS | Enterprise Technology Platform | 88887235 | 2022-09-16 | Issues with Tasks | Multiple issue occurred from 31/08. Was the previous occurrence of the issue and the issue on 05/09 related? If not, what was the cause for previous instances? | Root Cause | Saran Rajkumar | 18/10: The issue was escalated with Customer and no further response from Microsoft. Business are looking for an alternatives. Hence Rosie has advised close it off from the tracker 11/10: Followed with Saran for the update, waiting for an update | Messaging Team |  | NA | 18/10/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1112 | >60 | October | 2022 | #VALUE!
GTS | Enterprise Technology Platform | 88887235 | 2022-09-16 | Issues with Tasks | Hypercare monitoring to be in place on 12th and 19th Sep 2022 as these are the heavy load days before peak. | Problem identification & Alerting | Saran Rajkumar | 11/10: Followed with Saran for the update, waiting for an update Issues were experienced on 12/09, however it got resolved without any intervention. No issue in 19/09 run | Messaging Team |  | NA | 2022-11-10 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1112 | >60 | October | 2022 | #VALUE!
GTS | Enterprise Integration | 88828574 | 2022-09-15 | No BP Sales received into CSSM | Why did the agent not come up automatically | Root Cause | Aarthy Rajaram | We have checked the logs and found the agent went to hung state since there are many number of transfers queued. So we have to clean up the transfers and start the agents again. This is a usual behaviour in MQFTE, the agents will go to hung state due to more number of transfers. This will be addressed as part of step 2 – healthcheck script. Need to understand what caused higher number of transfers? | Integration Services |  | NA | 21/09/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1113 | >60 | September | 2022 | #VALUE!
GTS | Enterprise Integration | 88828574 | 2022-09-15 | No BP Sales received into CSSM | Health checks to be prioritised on the agents across the portfolios after a cluster refresh activity. | Problem avoidance | Aarthy Rajaram/Swathika V | This action has been completed. | Integration Services |  | NA | 21/09/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1113 | >60 | September | 2022 | #VALUE!
GTS | Enterprise Integration | 88828574 | 2022-09-15 | No BP Sales received into CSSM | Analyse the impact that might incur before the next migration activity is planned. | Impact Analysis | Aarthy Rajaram/Swathika V | This action has been completed. | Integration Services |  | NA | 21/09/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1113 | >60 | September | 2022 | #VALUE!
Customer Channels | Selling Experience | 88821404 | 2022-09-15 | Issues in the Bespoke School uniform microsite | Need to check with Microsoft whether any new properties are added as part of every upgrade. | Problem avoidance | Tapas | 2/11: Microsoft recommended to run the commerce scheduler in HQ so that the new properties (if any) will be auto populated in HQ side(Head Quarter - Backend of schoolwear site) | Schoolwear Support |  | NA | 2022-02-11 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1113 | >60 | November | 2022 | #VALUE!
Customer Channels | Selling Experience | 88821404 | 2022-09-15 | Issues in the Bespoke School uniform microsite | Need to set the commerce initialization auto feature to run automatically after dynamics upgrade. | Problem avoidance | Tapas | 2/11: The commerce scheduler has now been auto enabled to run after every upgrade | Schoolwear Support |  | NA | 2022-02-11 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1113 | >60 | November | 2022 | #VALUE!
Customer Channels | Platform & Store Ops | 88810002 | 2022-09-14 | Store colleagues are unable to print ISF labels | SOP to document the testing and package building process to be deployed across the stores. | Problem avoidance | Colin/Phil | This action has been completed. | SSI |  | NA | 21/09/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1114 | >60 | September | 2022 | #VALUE!
Customer Channels | Platform & Store Ops | 88810002 | 2022-09-14 | Store colleagues are unable to print ISF labels | Workshop for knowledge transfer for modifying the script, package building and deployment | Problem avoidance | Colin/Phil | 09/11: We are awaiting for the TPMs to talk to Steve explaining him the technical details which concluded SPPD print service has to be owned by him Next update on 15/11 22/11: Once the ownership is confirmed, this actions will be taken care, hence will track it as part of the ownership action | SSI |  | NA | 22/11/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1114 | >60 | November | 2022 | #VALUE!
GTS | Digital Workplace Services | 88810002 | 2022-09-14 | Store colleagues are unable to print ISF labels | SOP for certificate renewal | Problem avoidance | Ramkrishnan Adhiyaman | This action has been completed. | Active Directory Team |  | NA | 2022-10-10 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1114 | >60 | October | 2022 | #VALUE!
Customer Channels | Platform & Store Ops | 88810002 | 2022-09-14 | Store colleagues are unable to print ISF labels | Engaging SSI team during non business hours | Supplier and support involvement | Renjith Nair | This has been closed | TPM |  | NA | 31/10/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1114 | >60 | October | 2022 | #VALUE!
Customer Channels | Service Experience | 88810002 | 2022-09-14 | Store colleagues are unable to print ISF labels | Deployment stats to be shared to track | Problem avoidance | Shyam Vadgama | 09/11: We are awaiting for the TPMs to talk to Steve explaining him the technical details which concluded SPPD print service has to be owned by him Next update on 15/11 22/11: Once the ownership is confirmed, this actions will be taken care, hence will track it as part of the ownership action | SSI |  | NA | 22/11/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1114 | >60 | November | 2022 | #VALUE!
Customer Channels | Platform & Store Ops | 88810002 | 2022-09-14 | Store colleagues are unable to print ISF labels | Retail and Dot com to discuss on the app ownership and support wrap combined with adding more SMEs to reduce the reliance on Colin | Supplier and support involvement | Vijay/Steve | 14/9: The problem identification and certificate renewal to be owned by the product team. The testing and deployment bit will be owned by the SSI team. Agree to circulate the contacts of the SMEs, shift rota of the team. Emergency contact details during major incidents. 28/09 - 31/10: Multiple conversations to take a decision who should own SPPD. or ISF labels 09/11: 09/11: We are awaiting for the TPMs to talk to Steve to talk through him the technical details which concluded SPPD print service has to be owned by him Next update on 15/11. 22/11: Spoken to Shankar, who will now speak to the team on the ownership 28/11: An email has been sent to the required POC along with the Delivery head to come to a conclusion on the ownership. 05/12: All the senior leaders in TCS met on a call on 02/12 to decide on the ownership. I am awaiting updates. Saswati Sinha (TEM) to follow up. 21/12: Tech had a technical session with Colin and his team. For the time being, it has been agreed to retain this support with the existing team as this skill can’t be transitioned over immediately. Web engg product would own to raise the requests against the print service team to extend the certificates. Tech would also raise this as a risk in the risk register for the Product to mitigate. In parallel, there is a spike being carried out by the product to replace the print service with an in-house solution to remove this dependency. Backlog id: EG 5457 | TPM |  | NA | 21/12/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1114 | >60 | December | 2022 | #VALUE!
Customer Channels | Platform & Store Ops | 88810002 | 2022-09-14 | Store colleagues are unable to print ISF labels | Ownership of the certificate extension along with knowledge transfer | Problem avoidance | Vijay/Steve | 09/11: We are awaiting for the TPMs to talk to Steve to talk through him the technical details which concluded SPPD print service has to be owned by him Next update on 15/11 22/11: Once the ownership is confirmed, this actions will be taken care, hence will track it as part of the ownership action | TPM |  | NA | 22/11/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1114 | >60 | November | 2022 | #VALUE!
Customer Channels | Platform & Store Ops | 88810002 | 2022-09-14 | Store colleagues are unable to print ISF labels | Can the certificate renewal process be automated? Work around the alerting mechanism to notify the self signed certificate expiry well before to avoid such issue? | Problem avoidance | Vijay/Steve | AD team can help in confirming if there is a solution for auto- renewal. But the packaging and deployment process should still happen to make the end to end solution to work. Alert implementation is the other option with a window of 1 month in advance. 09/11: Jeevan is yet to speak to Steve on the ownership. Next update on 15/11 22/11: Once the ownership is confirmed, this actions will be taken care, hence will track it as part of the ownership action | TPM |  | NA | 22/11/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1114 | >60 | November | 2022 | #VALUE!
Group Support | Finance | 88822742 | 2022-09-14 | Issues in processing retail sales data in SAP | Detailed understanding on the inconsistent QRFC T id | Root Cause | Murali/Rhammya | SAP mentioned they cannot identify the rootcause unless a parameter as suggested by them is maintanged. Hence team are awaiting ehp8 upgrade, where the suggested prevention notes are available post which if the issue reoccurs, the RC can be ascertained. | SAP BW team |  | NA | 2022-10-10 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1114 | >60 | October | 2022 | #VALUE!
Group Support | Finance | 88822742 | 2022-09-14 | Issues in processing retail sales data in SAP | SOP to identify the problematic id and perform the deletion | Solution & Recovery | Murali/Rhammya | Documenting is completed. Validation is in progress. | SAP BW team |  | NA | 2022-10-02 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1114 | >60 | February | 2022 | #VALUE!
Group Support | Finance | 88822742 | 2022-09-14 | Issues in processing retail sales data in SAP | Vendor SAP engagement to be improved | Supplier and support involvement | Remko/Krishna R | 23/09: Next steps being reviewed by Remko & team after a meeting with SAP vendor | SAP BW team |  | NA | 2022-10-02 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1114 | >60 | February | 2022 | #VALUE!
Customer Channels | Platform & Store Ops | 88813770 | 2022-09-12 | Issue with ECS application | The scrum master is accountable for the overall change – what due diligence and checks were put in place for this change on 30/09 and how will any gaps be urgently addressed. | Problem avoidance | Hima Varghese | 07/10: Following up with action owner to share the latest progress 11/10: Prior to any release/deployment, scrum master will ensure to review the implementation plan end to end before sign-off | ECS Team |  | NA | 2022-07-10 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1116 | >60 | October | 2022 | #VALUE!
Customer Channels | Platform & Store Ops | 88813770 | 2022-09-12 | Issue with ECS application | In future any ECS application change has to have mandatory performance testing and should involve vendor ECS so that they can assist with testing and also be aware of the change. | Problem avoidance | NOTE TO ALL | 07/10: Following up with action owner to share the latest progress 11/10: Closing this action since its an information to everyone | ECS Team |  | NA | 2022-07-10 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1116 | >60 | October | 2022 | #VALUE!
Customer Channels | Platform & Store Ops | 88813770 | 2022-09-12 | Issue with ECS application | How could we have identified the issue before stores reported it? | Problem identification & Alerting | Vijay/Hima | 10/10: The team have been advised to monitor and act on the incidents assigned to their queue. Vel says a critical new relic alert was received 08:40 stating the slowness of the API however it wasn’t picked up until later. All relevant team members need to be included into the ECS Remedy queue and need to reiterate the incident process to the ECS internal team. | ECS Team |  | NA | 2022-10-10 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1116 | >60 | October | 2022 | #VALUE!
Customer Channels | Platform & Store Ops | 88813770 | 2022-09-12 | Issue with ECS application | A ECS major incident run book is being prioritised to document the triage that needs to be done in a timely manner to ascertain the problem statement, the impact and what checks need to be initially done. | Solution & Recovery | Vijay/Hima | 10/10: ECS team shared the ECS runbook 07/10: Following up with action owner to share the latest progress | ECS Team |  | NA | 2022-10-10 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1116 | >60 | October | 2022 | #VALUE!
GTS | ETP- Cloud operations / Frameworks | 88801699 | 2022-08-31 | Microsoft central issue impacting the deployment and recreation of new pods in AKS | If Microsoft place something their health portal, who in our support teams are responsible for monitoring the portal and advising the relevant stakeholders? There is potential for improvement with the alerting here | Problem identification & Alerting | Asok Sreedharan | 15/10: Cloud operations and respective application service teams will get automated alerts if Microsoft place any outage notification on their "Service Health" page. In addition, there is also a global communication page by region which can be referred to. 14/10: Spoke to Aso who informed that this needs to be monitored manually. However, he will check and confirm back 12/10: Asok is OOO, checking with Prasanth Rowlo | Cloud Operation |  | NA | 15/10/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1128 | >60 | October | 2022 | #VALUE!
GTS | Enterprise Technology Platform | 88801699 | 2022-08-31 | Microsoft central issue impacting the deployment and recreation of new pods in AKS | If this type of issue was to reoccur, we should place all application team on hypercare to ensure that any further impact can be proactively captured | Problem identification & Alerting | NOTE TO ALL | No pending actions | All |  | NA | 31/08/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1128 | >60 | August | 2022 | #VALUE!
GTS | ETP- Cloud operations / Frameworks | 88801699 | 2022-08-31 | Microsoft central issue impacting the deployment and recreation of new pods in AKS | How can we get a list of applications hosted in the various cloud types – Azure, PaaS, AKS etc. | Impact Analysis | Raguram | 28/10: A backlog ID has been created to track this action 26/10: Followed up with Raghu to share the backlog reference number, awaiting response 18/10: Requested Ragu to raise a backlog and awaiting for the same 12/10: Considering, number of services we use within cloud. Ragu advised that this need to be taken as POC(Proof Of Concept) which is in-progress now and this needs time till end of Q3 31/08: There is a backlog with the cloud team who are working on an app service inventory report. Also, Ragu to extract a current AKS app list so we can review. | Cloud Operation |  | NA | 28/10/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1128 | >60 | October | 2022 | #VALUE!
Customer Channels | Selling Experience | 88801699 | 2022-08-31 | Microsoft central issue impacting the deployment and recreation of new pods in AKS | When OMS pods went down on day 2 – did they get any alerts | Problem identification & Alerting | Rajeev Ekambaram | 11/10: Rajeev confirmed that the newrelic alerts were configured now | Sterling |  | NA | 2022-11-10 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1128 | >60 | October | 2022 | #VALUE!
GTS | Enterprise Technology Platform | 88801699 | 2022-08-31 | Microsoft central issue impacting the deployment and recreation of new pods in AKS | Could Microsoft have alerted us nearer to 7am when their issue actually started | Problem identification & Alerting | Rehan Siddiqui | 3/3: In MS review meeting it was agreed for early comms 17/01: We are still awaiting for an update from Microsoft on this 30/12: Spoke to Sathish who informed that he will follow-up with Microsoft on the pending actions and update us back. 18/11: Sathish informed that we are expecting an update from Vineesh in the next monthly meeting 9/11: Vineesh from Microsoft is looking into this and will update back at the earliest 26/10: A reminder has been sent to Adrian from Microsoft 18/10: Rehan to send out an remainder email to Microsoft 12/10: Rehan sent an email and awaiting response back from Microsoft 31/08: Rehan to email Adrian and Vineesh | Service Management |  | NA | 2023-03-03 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1128 | >60 | March | 2023 | #VALUE!
GTS | Operations | 88801699 | 2022-08-31 | Microsoft central issue impacting the deployment and recreation of new pods in AKS | The Microsoft MIM did not seem aware of the global issue that Microsoft were running | Supplier and support involvement | Rehan Siddiqui | 12/10: Rehan emailed the feedback to Adrian Neagu 31/08: Rehan to feedback to Microsoft | Service Management |  | NA | 2022-12-10 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1128 | >60 | October | 2022 | #VALUE!
Customer Channels | Service Experience | 88801699 | 2022-08-31 | Microsoft central issue impacting the deployment and recreation of new pods in AKS | Why at 14:00 did multiple pods restart for digital café? Why did the alerting not inform us of the issue rather than the stores? | Problem identification & Alerting | Sreejith Purushothaman | 12/10:As per the design, the PODs will be auto scaled based on the incoming traffic. Since the new PODs were not able to auto scale due to Microsoft central issue, the existing PODs could not handle the traffic and went to unresponsive status. The alert did not trigger due to a variable mismatch and this has been corrected now. | VOD |  | NA | 2022-12-10 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1128 | >60 | October | 2022 | #VALUE!
GTS | Enterprise Technology Platform | 88801699 | 2022-08-31 | Microsoft central issue impacting the deployment and recreation of new pods in AKS | Microsoft reviewing their release process to ensure that future changes are not deployed on their primary and DR environments simultaneously | Problem avoidance | Vineesh | 3/3: In MS review meeting, it was agreed that MS will be reviewing the central process 17/01: We are still awaiting for an update from Microsoft on this 30/12: Spoke to Sathish who informed that he will follow-up with Microsoft on the pending actions and update us back. 18/11: Sathish informed that we are expecting an update from Vineesh in the next monthly meeting 9/11: Vineesh from Microsoft is looking into this and will update back at the earliest Following up with Microsoft | Service Management |  | NA | 2023-03-03 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1128 | >60 | March | 2023 | #VALUE!
GTS | Enterprise Technology Platform | 88785880 | 2022-08-23 | Issue with WCS primary database | Revisit alerting/monitoring setup in cloud Azure DB servers | Problem identification & Alerting | Jishin | Alerting has been configured | Oracle Team |  | NA | 23/08/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1136 | >60 | August | 2022 | #VALUE!
Customer Channels | Platform & Store Ops | 88785880 | 2022-08-23 | Issue with WCS primary database | Deadlock scenario troubleshooting | Solution & Recovery | Sumitro | It is a default scenario and have not caused issues in the past, the issue was caused due to the housekeeping job not functioning as expected at Infra | WCS |  | NA | 23/08/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1136 | >60 | August | 2022 | #VALUE!
Group Support | Finance | 88786139 | 2022-08-19 | Delay to the overnight critical batches | Feasibility to configure a data level alert at SAP to identify such issues proactively | Problem identification & Alerting | Kevin E | Not feasible | SAP B&M |  | NA | 2022-08-11 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1140 | >60 | November | 2022 | #VALUE!
GTS | Enterprise Technology Platform | 88786139 | 2022-08-19 | Delay to the overnight critical batches | A case has been raised with BMC to understand the reason behind the blockage | Root Cause | Santhosh G | 19/08: As per the Control M logs, the jobs were stuck in execution state, as the Control M ports were blocked which hindered the communication between application and Control M. | Control M team |  | NA | 2022-08-11 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1140 | >60 | November | 2022 | #VALUE!
GTS | Enterprise Technology Platform | 88786139 | 2022-08-19 | Delay to the overnight critical batches | Alerting to be configured/ Checks to be put in place if the agent becomes unresponsive, not processing the jobs | Problem identification & Alerting | Santhosh G | This action has been completed. | Control M team |  | NA | 2022-08-11 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1140 | >60 | November | 2022 | #VALUE!
GTS | ETP- Connectivity,service & solution | 88784091 | 2022-08-18 | Spike in card payment transaction failures between 10:44 and 10:56 | Aged out alerts are configured which highlights if there are any timeouts in transactions between network and worldline. However further analysis needs to be done to understand where the timeout is happening? | Root Cause | Rajesh | 31/10: Network team investigated and could not find any timeout in the components with Customer Networks purview. However, they suspect that there is possibility that these timeouts might have happen outside Customer network and Worldline. Hence they no further actions pending. 11/10: Followed up on actions for an update/ETA, awaiting response | Network |  | NA | 31/10/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1141 | >60 | October | 2022 | #VALUE!
Customer Channels | Service Experience | 88784091 | 2022-08-18 | Spike in card payment transaction failures between 10:44 and 10:56 | 25/10:No action was taken to resolve the issue during period of spikes. The root cause was implementation of a technical change in combination with an undiscovered dormant bug in Ahub. Fixes have been applied for the bug, meaning a similar change implementation would not result in the same problem. The root cause and recovery actions for the issue to be confirmed | Root Cause | Worldline | 11/10: An consolidated email has been sent to Gary to track all the open actions and pending RCA from Worldline | 3rd Party |  | NA | 2022-11-10 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1141 | >60 | October | 2022 | #VALUE!
Customer Channels | Platform & Store Ops | 88763682 | 2022-08-17 | Issues in Foods pricing and promotion flow | Automate the recon of promotion feeds between the following sytems - SAP, ES, RET and ECS" | Problem avoidance | Velraj | 20/10: Recon between SAP and ECS is not feasible as ECS is taken care by third party. A recon between RET and SAP is tracked under EP-1076 05/10: Followed up with Joey for an update | ECS Team |  | NA | 20/10/22 | Closed | NA | EP-1076 |  | Saloni | 2025-02-10 | 1142 | >60 | October | 2022 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 88782583 | 2022-08-17 | Bradford C&H replenishment not being communicated to WCS | What was the root cause of the issue in detail? | Root Cause | Mick Williams | 20/10: The issue was caused due to an incorrect sequence of job schedule within KiSoft after migrated to new hardware. This has now been corrected to fix the issue permanently 18/10: Rehan is following up with Mick Williams 24/08, Mick to speak with Knapp and get a written root cause report outlining the cause, resolution steps and any learnings/actions from their side. | Bradford DC |  | NA | 20/10/22 | Closed | NA |  |  | Saloni | 2025-02-10 | 1142 | >60 | October | 2022 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 88782583 | 2022-08-17 | Bradford C&H replenishment not being communicated to WCS | What post deployment testing was carried out and why was the fact that new replenishment orders were not flowing to WCS missed? | Problem identification & Alerting | Mick Williams/Shankar Govindan | 20/10: 18/10: Rehan is following up with Mick Williams 24/08, The test environment did not replicate production in terms of hardware and volume. Mick/Shankar to meet with Knapp to ensure that the test environment matches production closely. Study the test plan and identify where the gaps were in this case and how testing plans can be improved. | Bradford DC |  | NA | 20/10/22 | Closed | NA |  |  | Saloni | 2025-02-10 | 1142 | >60 | October | 2022 | #VALUE!
Customer Channels | Platform & Store Ops | 88805217 | 2022-08-16 | Sparks mobile application inaccessible in both android and iOS devices | Review the email distribution list used for communicating akamai changes and ensure relevant teams are included on the DL. This should be reviewed at portfolio level | Problem avoidance | David Raine | This action has been completed. | Akamai |  | NA | 14/11/2022 | Closed |  |  |  | Saloni | 2025-02-10 | 1143 | >60 | 14/11/2022 | #VALUE! | #VALUE!
Customer Channels | Customer Engagement | 88805217 | 2022-08-16 | Sparks mobile application inaccessible in both android and iOS devices | Automating the process of updating IP ranges at Akamai end. David to own 50% of automating the process rest 50% to be owned by teams from relevant portfolio | Permanent Fix | David Raine | 18/10 : David started work on the automation development and have also been helping the brightcloud team use the api calls to retreive current IP addresses. I will check the status of that work. 07/11: Divakar to update on 11/11/2022 after having a detailed discussion with the business. Else a backlog to be raised. 14/11: Akamai will publish a documented API endpoint for the consumers to allow visibility of these addresses, so that they can point all teams at a reliable source of truth. This will be done post peak as it is reviewed and confirmed not a peak risk. | Service Owner |  | NA | 14/11/2022 | Closed |  |  |  | Saloni | 2025-02-10 | 1143 | >60 | 14/11/2022 | #VALUE! | #VALUE!
Customer Channels | Customer Engagement | 88805217 | 2022-08-16 | Sparks mobile application inaccessible in both android and iOS devices | Setup alerting for high error rates in all loyalty API's consumed in mobile apps. | Problem identification & Alerting | Ryan Mason-Davies | 01/09: Alerting is configured for unexpected significant drops in offer activation on iOS or Android apps. This is a proxy effect as the real error was in retrieving offers data but Android does not have reliable tracking for this at present. Will review a better longer term solution but this will give us visibility for now. | Mobile Apps |  | NA | 2022-01-09 | Closed |  |  |  | Saloni | 2025-02-10 | 1143 | >60 | September | 2022 | #VALUE!
Customer Channels | Customer Engagement | 88805217 | 2022-08-16 | Sparks mobile application inaccessible in both android and iOS devices | Process of bringing up holding page on Apps should be quicker | Solution & Recovery | Ryan Mason-Davies | 26/08 : Cache purging is now included in the deployment scripts for iOS and Android configuration files, so once a holding page has been enabled by an app engineer customers will see it within a minute or two (rather than 25) | Mobile Apps |  | NA | 26/08/22 | Closed |  |  |  | Saloni | 2025-02-10 | 1143 | >60 | August | 2022 | #VALUE!
Customer Channels | Platform & Store Ops | 88775876 | 2022-08-16 | Sparks hub mobile app inaccessible on both Android and iOS | Review the email distribution list used for communicating akamai changes and ensure relevant teams are included on the DL. This should be reviewed at portfolio level. | Problem avoidance | David Raine | This action has been completed. | Akamai |  | NA | 25/08/2022 | Closed |  |  |  | Saloni | 2025-02-10 | 1143 | >60 | 25/08/2022 | #VALUE! | #VALUE!
Customer Channels | Customer Engagement | 88775876 | 2022-08-16 | Sparks hub mobile app inaccessible on both Android and iOS | Have a separate workshop with the teams to agree on the short-term solution and potentially get approximate timelines and come up with permanent solution | Problem avoidance | Divakar Hariraju | 03/10: This has been completed | Service Owner |  | NA | 2022-03-10 | Closed |  |  |  | Saloni | 2025-02-10 | 1143 | >60 | October | 2022 | #VALUE!
Customer Channels | Service Experience | 88774345 | 2022-08-15 | Contactless transactions getting declined at stores | Feasibility to check whether we can communicate the notification thorough Honeywell device (Similar to RED alerts) - This action is dependent on Customer to provide us a tool to publish the notifications | Problem identification & Alerting | Laura W | 16/12: A backlog has been created to track this 16/11: Laura informed that this needs to be moved to post peak and will continue with the way we currently message central issues until Peak is over and then we can review this. 14/11: This action has been discussed with Richard WrightWells (Solution Architect) who informed that introducing notification on Tills/Honeywells might result in fraudulent/security-related issues. 19/10: Laura is having a meeting with the business on Friday to ask them if they want to use this or set up something else to alert store users on an issue. In meantime, Laura is chasing Will Hanson for backlog ID. 14/10: Tried reaching Laura to get the backlog reference but no luck 06/10: Laura to share the backlog ID to cover this action. Customer to share us a tool/pltaform to publish the notifications | Service Owner |  | NA | 16/12/22 | Closed |  | RPOS-6712 |  | Saloni | 2025-02-10 | 1144 | >60 | December | 2022 | #VALUE!
GTS | ETP- Connectivity,service & solution | 88774345 | 2022-08-15 | Contactless transactions getting declined at stores | The Run Book to be updated with the detailed operation procedures for all the card payment issue scenarios faced so far for Netwrok | Solution & Recovery | Rajesh S | Network run book - Complete. | Network |  | NA | 20/08/22 | Closed |  |  |  | Saloni | 2025-02-10 | 1144 | >60 | August | 2022 | #VALUE!
Customer Channels | Service Experience | 88774345 | 2022-08-15 | Contactless transactions getting declined at stores | The Customer contact details in operations manual needs to be updated and share with Worldline to contact Customer in case of any card payment issues. | Supplier and support involvement | Balaguru | 20/10: The DL details has been reviewed 03/10: The DL details needs to be reviewed with Laura W 06/10: Laura W confirmed that the DLs have been reviewed and shared with Worldline. | POS |  | NA | 20/10/22 | Closed |  |  |  | Saloni | 2025-02-10 | 1144 | >60 | October | 2022 | #VALUE!
Customer Channels | Service Experience | 88774345 | 2022-08-15 | Contactless transactions getting declined at stores | The Run Book to be updated with the detailed operation procedures for all the card payment issue scenarios faced so far for POS | Solution & Recovery | Balaguru | 9/11: The initial runthrough with MIM, POS and NOC given. MIM advised few more updates to the runbook and this will be completed by 16th November. Closing the action here and will track under action#178 8/11: Team shared the runbook and the same will be discussed in tomorrow's call with all stakeholders 2/11: Team will have an internal review of runbook tomorrow and this will be circulated to wider audience by COP, 5th Nov 26/10: Spoke to Bala who informed that Laura did an initial review and gave feedback. Bala is incorporating the same into a run book 18/10: Runbook creation is complete and this will be reviewed with Laura. | POS |  | NA | 2022-10-11 | Closed |  |  |  | Saloni | 2025-02-10 | 1144 | >60 | November | 2022 | #VALUE!
Customer Channels | Service Experience | 88774345 | 2022-08-15 | Contactless transactions getting declined at stores | Run through the run book with all relevant stakeholders – MIM, SD, POS, NOC, Laura, Rosie | Solution & Recovery | Balaguru & Rajesh S | 25/11: We had a final runbook walkthrough today with POS, SD, NOC and MIM team 16/11: The feedback to add few more points into the run-book is being worked upon. This will be completed by 25th Nov and a follow-up call will be arranged for the same. 9/11: The initial runthrough with MIM, POS and NOC given. MIM advised few more updates to the runbook and this will be completed by 16th November 8/11: A call has been scheduled for tomorrow(9/11) to go through the POS and NOC runbook 18/10: Network and POS team will run through the runbook | POS & Network |  | NA | 25/11/22 | Closed |  |  |  | Saloni | 2025-02-10 | 1144 | >60 | November | 2022 | #VALUE!
Customer Channels | Service Experience | 88774345 | 2022-08-15 | Contactless transactions getting declined at stores | Use store self-portal to publish any central store issues - This action is dependant on Customer to provide us a tool to publish the notifications | Problem identification & Alerting | Will Hanson/ Laura W | 16/12: A backlog has been created to track this 16/11: Laura informed that this needs to be moved to post peak and will continue with the way we currently message central issues until Peak is over and then we can review this. 14/11: Being followed-up with Laura and awaiting her response 31/10: Laura informed that there is a Self help portal which can be used to broadcast the central store issues. Laura will liaise with SD on how to use this and then feedback to business to see if we can use it or not. 19/10: Laura is having a meeting with the business on Friday to ask them if they want to use this or set up something else to alert store users on an issue. In meantime, Laura is chasing Will Hanson for backlog ID. 14/10: Tried reaching Laura to get the backlog reference but no luck 06/10: Laura to share the backlog ID to cover this action. Customer to share us a tool/pltaform to publish the notifications | Service Owner |  | NA | 16/12/22 | Closed |  | RPOS-6712 |  | Saloni | 2025-02-10 | 1144 | >60 | December | 2022 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 88774563 | 2022-08-12 | Issue in processing new ECom orders in Castle Donington WMS | How to restrict the connection between one source application and MQ manager in production stack or can any alerting be configured if the queue is picked by two daemons? | Problem identification & Alerting | Asokan, Anand | 17/11: A risk- 1796 has been created to mitigate this as part of the Castle Donington upgrade plan 16/11: Followed up with Asokan, Anand for further updates on upgrade activity, awaiting further updates. 31/10: The plan for upgrading the components in CD stack is being discussed, the details of the project is yet to confirmed 18/10:SSL is used for application to Queue manager connection, but current CD stack is not compatible with SSL. Application team have confirmed that the future dispatcher upgrade will handle this connectivity when migrating to MULE 11/10: Followed up on actions for an update/ETA, awaiting response | WMS Devops |  | NA | 17/11/22 | Closed | 1796 | NA | N/A | Saloni | 2025-02-10 | 1147 | >60 | November | 2022 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 88774563 | 2022-08-12 | Issue in processing new ECom orders in Castle Donington WMS | Configure an alerting for to notify the ‘Unable to get message – error code (2033) | Problem identification & Alerting | Dean W | The action will be tracked under the backlog id JDATE-9108 and is aimed to close in Sprint 4 | CD WMS Devops |  | NA | 2022-12-08 | Closed | NA | JDATE-9108 |  | Saloni | 2025-02-10 | 1147 | >60 | August | 2022 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 88774563 | 2022-08-12 | Issue in processing new ECom orders in Castle Donington WMS | ‘Zero KB’ file was created in previous instance on 29th of Jun and 9th Jan. Further analysis to be made to understand the scenarios in which the file is getting created and is there any actual impact due to this? | Root Cause | Varun Challa | The action will be tracked under the backlog id JDATE-9084 and is aimed to close in Sprint 4 | WMS Devops |  | NA | 2022-12-08 | Closed | NA | JDATE-9084 |  | Saloni | 2025-02-10 | 1147 | >60 | August | 2022 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 88774563 | 2022-08-12 | Issue in processing new ECom orders in Castle Donington WMS | Create a SOP with detailed steps to recover the issue related to this specific error message – ‘2033’ | Solution & Recovery | Varun Challa | The action will be tracked under the backlog id JDATE-9132 and is aimed to close in Sprint 4 | WMS Devops |  | NA | 2022-12-08 | Closed | NA | JDATE-9132 |  | Saloni | 2025-02-10 | 1147 | >60 | August | 2022 | #VALUE!
Customer Channels | Service Experience | 88759635 | 2022-08-01 | Store colleagues unable to complete labelling compliance checks | Configure alerting or monitoring tool to proactively identify when and for which app, the secret key is about to expire | Problem identification & Alerting | Colin Wilson/James | This action has been completed. | In-Store Payments |  | NA | 21/09/22 | Closed | NA |  |  | Saloni | 2025-02-10 | 1158 | >60 | September | 2022 | #VALUE!
Customer Channels | Service Experience | 88759635 | 2022-08-01 | Store colleagues unable to complete labelling compliance checks | List the apps (3) using a secret key and ensure app owners know when the keys will expire and ensure they are responsible | Problem avoidance | Colin Wilson/James | 08/11: This has been taken care. Also , this will not be categorised a MI. So the respective Pos will take care going forward. | In-Store Payments |  | NA | 2022-07-11 | Closed | NA |  |  | Saloni | 2025-02-10 | 1158 | >60 | November | 2022 | #VALUE!
Customer Channels | Service Experience | 88759635 | 2022-08-01 | Store colleagues unable to complete labelling compliance checks | Confirm the ownership at an app level of the sharepoint client secret key for Label compliance | Solution & Recovery | James Harris | 08/11: This has been taken care. Also , this will not be categorised a MI. So the respective Pos will take care going forward. | In-Store Payments |  | NA | 2022-07-11 | Closed | NA |  |  | Saloni | 2025-02-10 | 1158 | >60 | November | 2022 | #VALUE!
GTS | Enterprise Technology Platform | 88714999 | 2022-07-02 | WMS application inaccessible | Investigate scripts to analyse hardcoding of DNS in every Unix and Linux server config in SP and SW. | Problem avoidance | Elzibeth Golder | 07/10: Going forward, team will run a script to analyse the traffic going through the DNS servers for few days, if any services are going through then it will be reconfigured before poweing off the DNS server. | Linux/Unix |  | NA | 2022-07-10 | Closed | NA |  |  | Saloni | 2025-02-10 | 1188 | >60 | October | 2022 | #VALUE!
Customer Channels | Service Experience | 88707710 | 2022-06-23 | Intermittent spikes were observed due to failed and rejected card payments at stores between 9:38 and 10:50 on 23/06 | Awaiting RCA from worldline | Root Cause | Laura/Worldline | 26/10: Worldline shared the root cause and the same has been updated in RCA tab in PR tracker 19/10: Laura has escalated this with Worldline in the service review meeting 06/10: Spoke to Laura and requested her to help in getting the document from Worldline. | Worldline |  | NA | 26/10/22 | Closed | NA |  |  | Saloni | 2025-02-10 | 1197 | >60 | October | 2022 | #VALUE!
Customer Channels | Service Experience | 88695094 | 2022-06-23 | A spike observed in failed/offline card transactions | Regroup to understand our Dashboards and what each element depicts - How can we better resolve “it’s your network issue” debates – Laura Whittle - Analyse the requirements for any new dashboard so it looks at the overall picture | Problem identification & Alerting | Balaguru | 27/10: A backlog ID has been created to track this action. 11/10: Bala is follwing-up with Worldline to understand on how the grafana board data can be obtained in e-portal 29/07: Few queries about Grafana dashboard is still pending with Ingenico and being tracked in weekly payments call. | POS |  | NA | 27/10/22 | Closed | NA | RPOS - 6958 |  | Saloni | 2025-02-10 | 1197 | >60 | October | 2022 | #VALUE!
GTS | Enterprise Technology Platform | 88517212 | 2022-02-15 | Multiple applications experiencing performance issues | The impact assessment was not comprehensive and attained in a timely manner – can we create a list of all the services that rely on replication through the two DWDM links and the new DEA – this can be used for the impact assessment if there is an issue with the DWDM links in future before we move to the new solution- DEA is direct Ethernet access - we have apps running with replication between SP and SW and this replication traffic goes via DEA - VMWare Team will have the list of applications - Dharma. | Impact Analysis | Dharma | 11/10: Server list have been consolidated and discussion are ongoing to maintain the server list AIM/SharePoint for accessing it easily. Rehan has spoken with Dharma on 05/10 and Dharma will provide a list of servers and their corresponding application which run through the new DEA links. MIM will then decide where to store this list and VM Ware team will also keep a copy | VM Ware Team |  | NA | 14/10/22 | Closed | NA | NA | N/A | Saloni | 2025-02-10 | 1325 | >60 | October | 2022 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 88422146 | 2021-12-08 | Ollerton Network Issue | Review business comms for Ollerton – why was there a lack of business comms for this issue. Who is supposed to on the comms | Business & IT Communication | Colin H | 11/10: Spoken to Murali Srinivasan and got a confirmation that the process is put in place now and this action can be closed | Service Owner |  | NA | 2022-11-10 | Closed |  |  |  | Saloni | 2025-02-10 | 1394 | >60 | October | 2022 | #VALUE!
C&H and Intl | C&H and Intl Supply Chain | 88422146 | 2021-12-08 | Ollerton Network Issue | The PC that was utilizing a lot of network bandwidth still needs investigating | Root Cause | Matt/Michael | 11/10: There were no issues identified with the PC and the issue re-occurred after the PC was disconnected. The issue was caused by users acidentally looping a LAN cable with both ends connected to a switch, causing a switch traffic storm. | CD WMS Devops |  | NA | 2022-11-10 | Closed |  |  |  | Saloni | 2025-02-10 | 1394 | >60 | October | 2022 | #VALUE!
GTS | ETP- Connectivity,service & solution | 88422146 | 2021-12-08 | Ollerton Network Issue | How can loops be prevented? If a cable was bridging two switches in a DC, the switches would detect this and automatically disable the port and trigger an alert – this feature is called Spanning Tree. | Problem avoidance | Paul B | 18/10: The issue will be tracked unders a black log - NPD-1725 14/10: 14/10: Rajesh advised this should go as project work. A backlog will be created for this and will share it with us on week commencing 17th Oct 11/10: This requirees a design change. Kamal has a meeting on Thursday where this will be added in the to do list 08/12/21:Paul to analyse if this can be turned on in Ollerton – Paul to liaise with Kamal – look at the design/costs and what is required. | Network |  | NA | 18/10/22 | Closed |  | NPD-1725 |  | Saloni | 2025-02-10 | 1394 | >60 | October | 2022 | #VALUE!
GTS | ETP- Connectivity,service & solution | 88422146 | 2021-12-08 | Ollerton Network Issue | Update NOC SOP’s to guide support to look for loops and network storms in case of any similar issue in the future | Problem identification & Alerting | Rajesh | 11/10: Kamal updated that the SOP is updated and can mark the action has closed | Network | Tactical | NA | 2022-11-10 | Closed |  |  |  | Saloni | 2025-02-10 | 1394 | >60 | October | 2022 | #VALUE!